## FactProjectMonthly
SnapshotKey | ReportingDateKey | ProjectKey | ProgrammeKey | BusinessUnitKey | ProjectManagerKey | SponsorKey | LocationKey | DeliveryModelKey | StrategicThemeKey | ProjectStatus | LifecycleStage | RAGStatus | PlannedProgressPct | ActualProgressPct | BaselineBudgetEUR | PlannedCostToDateEUR | ActualCostToDateEUR | ForecastTotalCostEUR | ScheduleVarianceEUR | CostVarianceEUR | SchedulePerformanceIndex | CostPerformanceIndex | BaselineCompletionDateKey | ForecastCompletionDateKey | ForecastDelayDays | TotalMilestones | MilestonesDue | MilestonesCompletedOnTime | OverdueMilestones | CriticalMilestonesOverdue | PlannedResourceHours | AvailableResourceHours | ActualResourceHours | ResourceCapacityGapHours | OpenRisks | CriticalRisks | RiskExposureScore | OverdueMitigationActions | PlannedBenefitEUR | PlannedBenefitToDateEUR | ForecastBenefitEUR | RealisedBenefitToDateEUR | BenefitRealisationPct | ApprovedScopeChanges | ApprovedChangeValueEUR | OpenQualityDefects | StakeholderConfidenceScore | PortfolioHealthScore
1 | 20250430 | 1 | 6 | 4 | 1 | 25 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.0667 | 0.0925 | 676402 | 41726 | 58110 | 680911 | -20841 | 4457 | 1.5 | 1.077 | 20260630 | 20260630 | 0 | 8 | 1 | 1 | 0 | 0 | 3663 | 3792 | 4034 | 129 | 1 | 0 | 10 | 0 | 1600000 | 0 | 1628090 | 0 |  | 0 | 0 | 2 | 96 | 100
2 | 20250531 | 1 | 6 | 4 | 1 | 25 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.1333 | 0.1497 | 676402 | 83934 | 95317 | 681362 | -17323 | 5940 | 1.207 | 1.063 | 20260630 | 20260630 | 0 | 8 | 1 | 1 | 0 | 0 | 4265 | 4435 | 4667 | 170 | 3 | 0 | 29 | 1 | 1600000 | 0 | 1603053 | 0 |  | 0 | 0 | 4 | 90 | 100
3 | 20250630 | 1 | 6 | 4 | 1 | 25 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.2 | 0.2074 | 676402 | 126622 | 125396 | 681813 | -13664 | 14890 | 1.108 | 1.119 | 20260630 | 20260630 | 0 | 8 | 2 | 2 | 0 | 0 | 4814 | 5097 | 5280 | 283 | 2 | 0 | 19 | 0 | 1600000 | 0 | 1599537 | 0 |  | 0 | 0 | 3 | 91 | 100
4 | 20250731 | 1 | 6 | 4 | 1 | 25 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.2667 | 0.2774 | 676402 | 169792 | 174572 | 682264 | -17842 | 13062 | 1.105 | 1.075 | 20260630 | 20260630 | 0 | 8 | 2 | 2 | 0 | 0 | 5285 | 5624 | 5456 | 339 | 2 | 0 | 19 | 0 | 1600000 | 0 | 1666415 | 0 |  | 0 | 0 | 1 | 93 | 100
5 | 20250831 | 1 | 6 | 4 | 1 | 25 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.3333 | 0.3127 | 676402 | 213442 | 195496 | 682715 | 1931 | 16015 | 0.991 | 1.082 | 20260630 | 20260630 | 10 | 8 | 3 | 2 | 0 | 0 | 5658 | 6068 | 5976 | 410 | 4 | 0 | 38 | 1 | 1600000 | 0 | 1655447 | 0 |  | 0 | 0 | 4 | 81 | 100
6 | 20250930 | 1 | 6 | 4 | 1 | 25 | 1 | 3 | 1 | Active | Deliver | Green | 0.4 | 0.4008 | 676402 | 257574 | 254333 | 683166 | -13528 | 16769 | 1.052 | 1.066 | 20260630 | 20260630 | 0 | 8 | 3 | 3 | 0 | 0 | 5916 | 6107 | 5871 | 191 | 3 | 0 | 29 | 1 | 1600000 | 0 | 1623395 | 0 |  | 0 | 0 | 4 | 86 | 100
7 | 20251031 | 1 | 6 | 4 | 1 | 25 | 1 | 3 | 1 | Active | Deliver | Green | 0.4667 | 0.4702 | 676402 | 302186 | 303203 | 683617 | -15858 | 14841 | 1.053 | 1.049 | 20260630 | 20260630 | 0 | 8 | 4 | 3 | 0 | 0 | 6048 | 6007 | 5760 | -41 | 3 | 0 | 29 | 1 | 1600000 | 0 | 1662289 | 0 |  | 0 | 0 | 1 | 86 | 100
8 | 20251130 | 1 | 6 | 4 | 1 | 25 | 1 | 3 | 1 | Active | Deliver | Green | 0.5333 | 0.5529 | 676402 | 347280 | 363312 | 684068 | -26703 | 10671 | 1.077 | 1.029 | 20260630 | 20260630 | 0 | 8 | 4 | 4 | 0 | 0 | 6048 | 5895 | 6216 | -153 | 4 | 0 | 38 | 1 | 1600000 | 0 | 1653781 | 0 |  | 0 | 0 | 5 | 87 | 100
9 | 20251231 | 1 | 6 | 4 | 1 | 25 | 1 | 3 | 1 | Active | Deliver | Green | 0.6 | 0.6163 | 676402 | 392854 | 403054 | 684519 | -24013 | 13813 | 1.061 | 1.034 | 20260630 | 20260630 | 0 | 8 | 5 | 5 | 0 | 0 | 5916 | 5749 | 5706 | -167 | 2 | 0 | 19 | 0 | 1600000 | 0 | 1605624 | 0 |  | 0 | 0 | 2 | 89 | 100
10 | 20260131 | 1 | 6 | 4 | 1 | 25 | 1 | 3 | 1 | Active | Deliver | Green | 0.6667 | 0.6857 | 676402 | 438910 | 458329 | 684970 | -24899 | 5480 | 1.057 | 1.012 | 20260630 | 20260630 | 0 | 8 | 5 | 5 | 0 | 0 | 5658 | 5438 | 5192 | -220 | 3 | 0 | 29 | 1 | 1600000 | 0 | 1598612 | 0 |  | 1 | 11000 | 4 | 83 | 100
11 | 20260228 | 1 | 6 | 4 | 1 | 25 | 1 | 3 | 1 | Active | Deliver | Green | 0.7333 | 0.7479 | 676402 | 485446 | 505075 | 685421 | -20435 | 806 | 1.042 | 1.002 | 20260630 | 20260630 | 0 | 8 | 6 | 5 | 0 | 0 | 5285 | 5323 | 5337 | 38 | 2 | 0 | 19 | 0 | 1600000 | 76190 | 1651657 | 0 | 0 | 1 | 10000 | 4 | 81 | 100
12 | 20260331 | 1 | 6 | 4 | 1 | 25 | 1 | 3 | 1 | Active | Deploy | Green | 0.8 | 0.823 | 676402 | 532464 | 562324 | 687367 | -24215 | -5645 | 1.045 | 0.99 | 20260630 | 20260630 | 0 | 8 | 6 | 5 | 0 | 0 | 4814 | 5051 | 5160 | 237 | 4 | 1 | 56 | 1 | 1600000 | 457143 | 1603821 | 93638 | 0.2048 | 1 | 8000 | 3 | 80 | 93.7
13 | 20260430 | 1 | 6 | 4 | 1 | 25 | 1 | 3 | 1 | Active | Deploy | Green | 0.8667 | 0.8689 | 676402 | 579962 | 595578 | 688276 | -7764 | -7852 | 1.013 | 0.987 | 20260630 | 20260630 | 0 | 8 | 7 | 6 | 0 | 0 | 4265 | 4282 | 4560 | 17 | 2 | 0 | 19 | 0 | 1600000 | 838095 | 1651453 | 476561 | 0.5686 | 1 | 6000 | 0 | 85 | 100
14 | 20260531 | 1 | 6 | 4 | 1 | 25 | 1 | 3 | 1 | Active | Deploy | Green | 0.9333 | 0.9305 | 676402 | 627942 | 647362 | 690900 | -1450 | -17970 | 1.002 | 0.972 | 20260630 | 20260630 | 1 | 8 | 7 | 6 | 0 | 0 | 3663 | 3812 | 3996 | 149 | 0 | 0 | 0 | 0 | 1600000 | 1219048 | 1622104 | 817123 | 0.6703 | 1 | 10000 | 0 | 84 | 99.1
15 | 20260630 | 1 | 6 | 4 | 1 | 25 | 1 | 3 | 1 | Completed | Completed | Green | 1 | 1 | 676402 | 676402 | 695667 | 695667 | 0 | -19265 | 1 | 0.972 | 20260630 | 20260630 | 0 | 8 | 8 | 7 | 0 | 0 | 3032 | 3055 | 3186 | 23 | 0 | 0 | 0 | 0 | 1600000 | 1600000 | 1631756 | 1152898 | 0.7206 | 1 | 7000 | 2 | 83 | 99
16 | 20250630 | 2 | 8 | 6 | 2 | 26 | 2 | 1 | 2 | Active | Initiate & Design | Green | 0.0417 | 0.0875 | 1443101 | 55519 | 112912 | 1470881 | -70752 | 13359 | 2.274 | 1.118 | 20270531 | 20270531 | 0 | 12 | 1 | 1 | 0 | 0 | 7313 | 7961 | 7868 | 648 | 0 | 0 | 0 | 0 | 2100000 | 0 | 2319514 | 0 |  | 1 | 22000 | 4 | 96 | 100
17 | 20250731 | 2 | 8 | 6 | 2 | 26 | 2 | 1 | 2 | Active | Initiate & Design | Green | 0.0833 | 0.1187 | 1443101 | 111439 | 162832 | 1472685 | -59857 | 8464 | 1.538 | 1.052 | 20270531 | 20270531 | 0 | 12 | 1 | 1 | 0 | 0 | 8143 | 9224 | 9243 | 1081 | 1 | 0 | 9 | 0 | 2100000 | 0 | 2314778 | 0 |  | 1 | 23000 | 3 | 96 | 100
18 | 20250831 | 2 | 8 | 6 | 2 | 26 | 2 | 1 | 2 | Active | Initiate & Design | Green | 0.125 | 0.1572 | 1443101 | 167760 | 217481 | 1474488 | -59095 | 9374 | 1.353 | 1.043 | 20270531 | 20270531 | 0 | 12 | 2 | 2 | 0 | 0 | 8945 | 9237 | 9542 | 292 | 0 | 0 | 0 | 0 | 2100000 | 0 | 2269589 | 0 |  | 1 | 21000 | 3 | 96 | 100
19 | 20250930 | 2 | 8 | 6 | 2 | 26 | 2 | 1 | 2 | Active | Initiate & Design | Green | 0.1667 | 0.1928 | 1443101 | 224482 | 254839 | 1476292 | -53748 | 23391 | 1.24 | 1.092 | 20270531 | 20270531 | 0 | 12 | 2 | 1 | 0 | 0 | 9704 | 10682 | 11178 | 978 | 0 | 0 | 0 | 0 | 2100000 | 0 | 2218387 | 0 |  | 1 | 20000 | 2 | 95 | 100
20 | 20251031 | 2 | 8 | 6 | 2 | 26 | 2 | 1 | 2 | Active | Initiate & Design | Green | 0.2083 | 0.2347 | 1443101 | 281605 | 320966 | 1478096 | -57091 | 17730 | 1.203 | 1.055 | 20270531 | 20270531 | 0 | 12 | 3 | 2 | 0 | 0 | 10407 | 11750 | 11591 | 1343 | 0 | 0 | 0 | 0 | 2100000 | 0 | 2215936 | 0 |  | 1 | 20000 | 2 | 96 | 100
21 | 20251130 | 2 | 8 | 6 | 2 | 26 | 2 | 1 | 2 | Active | Initiate & Design | Green | 0.25 | 0.2814 | 1443101 | 339129 | 376236 | 1479900 | -66960 | 29853 | 1.197 | 1.079 | 20270531 | 20270531 | 0 | 12 | 3 | 3 | 0 | 0 | 11043 | 12259 | 11609 | 1216 | 1 | 0 | 9 | 0 | 2100000 | 0 | 2294304 | 0 |  | 1 | 17000 | 1 | 92 | 100
22 | 20251231 | 2 | 8 | 6 | 2 | 26 | 2 | 1 | 2 | Active | Initiate & Design | Green | 0.2917 | 0.3285 | 1443101 | 397053 | 444593 | 1481704 | -77006 | 29466 | 1.194 | 1.066 | 20270531 | 20270531 | 0 | 12 | 4 | 3 | 0 | 0 | 11601 | 12160 | 11757 | 559 | 1 | 0 | 9 | 0 | 2100000 | 0 | 2276378 | 0 |  | 1 | 12000 | 1 | 94 | 100
23 | 20260131 | 2 | 8 | 6 | 2 | 26 | 2 | 1 | 2 | Active | Deliver | Green | 0.3333 | 0.3949 | 1443101 | 455379 | 542914 | 1483508 | -114502 | 26967 | 1.251 | 1.05 | 20270531 | 20270531 | 0 | 12 | 4 | 4 | 0 | 0 | 12071 | 13077 | 12697 | 1006 | 0 | 0 | 0 | 0 | 2100000 | 0 | 2251692 | 0 |  | 1 | 19000 | 2 | 96 | 100
24 | 20260228 | 2 | 8 | 6 | 2 | 26 | 2 | 1 | 2 | Active | Deliver | Green | 0.375 | 0.4329 | 1443101 | 514105 | 602206 | 1485312 | -110613 | 22512 | 1.215 | 1.037 | 20270531 | 20270531 | 0 | 12 | 5 | 5 | 0 | 0 | 12446 | 13939 | 14516 | 1493 | 1 | 0 | 9 | 0 | 2100000 | 0 | 2285699 | 0 |  | 1 | 14000 | 3 | 92 | 100
25 | 20260331 | 2 | 8 | 6 | 2 | 26 | 2 | 1 | 2 | Active | Deliver | Green | 0.4167 | 0.4745 | 1443101 | 573232 | 659552 | 1487116 | -111519 | 25199 | 1.194 | 1.038 | 20270531 | 20270531 | 0 | 12 | 5 | 4 | 0 | 0 | 12718 | 14267 | 14663 | 1549 | 2 | 0 | 18 | 0 | 2100000 | 0 | 2263917 | 0 |  | 1 | 12000 | 3 | 94 | 100
26 | 20260430 | 2 | 8 | 6 | 2 | 26 | 2 | 1 | 2 | Active | Deliver | Green | 0.4583 | 0.5181 | 1443101 | 632760 | 723824 | 1488919 | -114911 | 23847 | 1.182 | 1.033 | 20270531 | 20270531 | 0 | 12 | 6 | 5 | 0 | 0 | 12883 | 13615 | 14355 | 732 | 1 | 0 | 9 | 0 | 2100000 | 0 | 2287034 | 0 |  | 1 | 14000 | 5 | 89 | 100
27 | 20260531 | 2 | 8 | 6 | 2 | 26 | 2 | 1 | 2 | Active | Deliver | Green | 0.5 | 0.5454 | 1443101 | 692688 | 774346 | 1490723 | -94379 | 12721 | 1.136 | 1.017 | 20270531 | 20270531 | 0 | 12 | 6 | 6 | 0 | 0 | 12938 | 13638 | 14556 | 700 | 3 | 0 | 27 | 0 | 2100000 | 0 | 2247644 | 0 |  | 1 | 16000 | 1 | 93 | 100
28 | 20260630 | 2 | 8 | 6 | 2 | 26 | 2 | 1 | 2 | Active | Deliver | Green | 0.5417 | 0.6007 | 1443101 | 753018 | 839906 | 1492527 | -113853 | 26965 | 1.151 | 1.032 | 20270531 | 20270531 | 0 | 12 | 7 | 6 | 0 | 0 | 12883 | 13833 | 13262 | 950 | 2 | 0 | 18 | 0 | 2100000 | 0 | 2224845 | 0 |  | 1 | 13000 | 4 | 89 | 100
29 | 20260731 | 2 | 8 | 6 | 2 | 26 | 2 | 1 | 2 | Active | Deliver | Green | 0.5833 | 0.6314 | 1443101 | 813749 | 889456 | 1494331 | -97425 | 21718 | 1.12 | 1.024 | 20270531 | 20270531 | 0 | 12 | 7 | 6 | 0 | 0 | 12718 | 14441 | 13958 | 1723 | 1 | 0 | 9 | 0 | 2100000 | 0 | 2318172 | 0 |  | 1 | 15000 | 4 | 91 | 100
30 | 20260831 | 2 | 8 | 6 | 2 | 26 | 2 | 1 | 2 | Active | Deliver | Green | 0.625 | 0.6815 | 1443101 | 874880 | 971445 | 1496135 | -108593 | 12028 | 1.124 | 1.012 | 20270531 | 20270531 | 0 | 12 | 8 | 7 | 0 | 0 | 12446 | 13097 | 12789 | 651 | 3 | 0 | 27 | 0 | 2100000 | 0 | 2291086 | 0 |  | 1 | 23000 | 2 | 92 | 100
31 | 20260930 | 2 | 8 | 6 | 2 | 26 | 2 | 1 | 2 | Active | Deliver | Green | 0.6667 | 0.7294 | 1443101 | 936412 | 1054911 | 1498629 | -116186 | -2313 | 1.124 | 0.998 | 20270531 | 20270531 | 0 | 12 | 8 | 7 | 0 | 0 | 12071 | 13676 | 13330 | 1605 | 1 | 0 | 9 | 0 | 2100000 | 0 | 2284341 | 0 |  | 1 | 16000 | 3 | 91 | 100
32 | 20231031 | 3 | 10 | 7 | 3 | 27 | 3 | 2 | 3 | Active | Deliver | Green | 0.5238 | 0.4001 | 1230348 | 619917 | 478064 | 1299482 | 127655 | 14198 | 0.794 | 1.03 | 20240831 | 20241130 | 100 | 11 | 6 | 3 | 2 | 1 | 11015 | 8546 | 8530 | -2469 | 7 | 1 | 101 | 2 | 3500000 | 0 | 3368810 | 0 |  | 0 | 0 | 6 | 71 | 77.8
33 | 20231130 | 3 | 10 | 7 | 3 | 27 | 3 | 2 | 3 | Active | Deliver | Green | 0.5714 | 0.4343 | 1230348 | 678951 | 528524 | 1302411 | 144611 | 5816 | 0.787 | 1.011 | 20240831 | 20241231 | 111 | 11 | 6 | 4 | 2 | 1 | 10892 | 7921 | 8353 | -2971 | 6 | 1 | 89 | 2 | 3500000 | 0 | 3333279 | 0 |  | 0 | 0 | 3 | 68 | 75.5
34 | 20231231 | 3 | 10 | 7 | 3 | 27 | 3 | 2 | 3 | Active | Deliver | Green | 0.619 | 0.4926 | 1230348 | 738432 | 605401 | 1305341 | 132363 | 668 | 0.821 | 1.001 | 20240831 | 20241130 | 103 | 11 | 7 | 4 | 2 | 1 | 10649 | 7864 | 7624 | -2785 | 6 | 1 | 89 | 2 | 3500000 | 0 | 3220335 | 0 |  | 1 | 13000 | 6 | 68 | 76
35 | 20240131 | 3 | 10 | 7 | 3 | 27 | 3 | 2 | 3 | Active | Deliver | Green | 0.6667 | 0.5415 | 1230348 | 798359 | 680877 | 1314107 | 132126 | -14644 | 0.834 | 0.978 | 20240831 | 20241130 | 102 | 11 | 7 | 4 | 2 | 1 | 10292 | 8458 | 8254 | -1834 | 7 | 1 | 101 | 2 | 3500000 | 0 | 3234895 | 0 |  | 1 | 18000 | 5 | 69 | 77.8
36 | 20240229 | 3 | 10 | 7 | 3 | 27 | 3 | 2 | 3 | Active | Deliver | Green | 0.7143 | 0.5774 | 1230348 | 858733 | 727603 | 1317614 | 148330 | -17200 | 0.827 | 0.976 | 20240831 | 20241231 | 111 | 11 | 8 | 4 | 3 | 1 | 9827 | 7978 | 8046 | -1849 | 5 | 0 | 59 | 1 | 3500000 | 0 | 3218918 | 0 |  | 1 | 13000 | 3 | 73 | 85
37 | 20240331 | 3 | 10 | 7 | 3 | 27 | 3 | 2 | 3 | Active | Deliver | Green | 0.7619 | 0.6368 | 1230348 | 919553 | 805845 | 1321631 | 136067 | -22359 | 0.852 | 0.972 | 20240831 | 20241130 | 102 | 11 | 8 | 6 | 2 | 1 | 9267 | 7772 | 7668 | -1495 | 6 | 1 | 89 | 2 | 3500000 | 523810 | 3350323 | 0 | 0 | 1 | 11000 | 4 | 71 | 79.6
38 | 20240430 | 3 | 10 | 7 | 3 | 27 | 3 | 2 | 3 | Active | Deliver | Green | 0.8095 | 0.6894 | 1230348 | 980819 | 876892 | 1325919 | 132617 | -28690 | 0.865 | 0.967 | 20240831 | 20241130 | 98 | 11 | 9 | 6 | 2 | 1 | 8622 | 6436 | 6491 | -2186 | 4 | 0 | 47 | 1 | 3500000 | 1119048 | 3212186 | 282363 | 0.2523 | 2 | 30000 | 2 | 72 | 84.9
39 | 20240531 | 3 | 10 | 7 | 3 | 27 | 3 | 2 | 3 | Active | Deliver | Green | 0.8571 | 0.7356 | 1230348 | 1042532 | 942056 | 1330632 | 137488 | -37012 | 0.868 | 0.961 | 20240831 | 20241130 | 99 | 11 | 9 | 7 | 2 | 1 | 7908 | 5768 | 5830 | -2140 | 5 | 1 | 77 | 1 | 3500000 | 1714286 | 3220118 | 826237 | 0.482 | 2 | 29000 | 3 | 73 | 76.5
40 | 20240630 | 3 | 10 | 7 | 3 | 27 | 3 | 2 | 3 | Active | Deploy | Green | 0.9048 | 0.7751 | 1230348 | 1104691 | 1008705 | 1337704 | 151048 | -55062 | 0.863 | 0.945 | 20240831 | 20241231 | 106 | 11 | 10 | 6 | 3 | 1 | 7141 | 5840 | 5594 | -1301 | 6 | 1 | 89 | 2 | 3500000 | 2309524 | 3286760 | 1352648 | 0.5857 | 2 | 28000 | 1 | 70 | 78.2
41 | 20240731 | 3 | 10 | 7 | 3 | 27 | 3 | 2 | 3 | Active | Deploy | Green | 0.9524 | 0.8051 | 1230348 | 1167296 | 1048855 | 1340885 | 176743 | -58302 | 0.849 | 0.944 | 20240831 | 20241231 | 120 | 11 | 10 | 7 | 3 | 1 | 6337 | 4958 | 4998 | -1379 | 6 | 1 | 89 | 2 | 3500000 | 2904762 | 3358756 | 1813963 | 0.6245 | 2 | 22000 | 3 | 68 | 77.3
42 | 20240831 | 3 | 10 | 7 | 3 | 27 | 3 | 2 | 3 | Active | Deploy | Green | 1 | 0.8584 | 1230348 | 1230348 | 1140109 | 1348699 | 174217 | -83978 | 0.858 | 0.926 | 20240831 | 20241231 | 115 | 11 | 11 | 8 | 3 | 1 | 5515 | 4552 | 4464 | -963 | 5 | 1 | 77 | 1 | 3500000 | 3500000 | 3278525 | 2313952 | 0.6611 | 2 | 24000 | 4 | 69 | 77.4
43 | 20240930 | 3 | 10 | 7 | 3 | 27 | 3 | 2 | 3 | Active | Deploy | Green | 1 | 0.8642 | 1230348 | 1230348 | 1148094 | 1351707 | 167081 | -84827 | 0.864 | 0.926 | 20240831 | 20241231 | 111 | 11 | 11 | 7 | 3 | 1 | 5515 | 4289 | 4326 | -1226 | 4 | 1 | 65 | 1 | 3500000 | 3500000 | 3363643 | 2974410 | 0.8498 | 2 | 39000 | 4 | 65 | 77.3
44 | 20241031 | 3 | 10 | 7 | 3 | 27 | 3 | 2 | 3 | Active | Deploy | Green | 1 | 0.8651 | 1230348 | 1230348 | 1155825 | 1356064 | 165974 | -91451 | 0.865 | 0.921 | 20240831 | 20241231 | 109 | 11 | 11 | 8 | 3 | 1 | 5515 | 4035 | 4103 | -1480 | 5 | 0 | 59 | 1 | 3500000 | 3500000 | 3301190 | 3011702 | 0.8605 | 2 | 37000 | 2 | 74 | 83.7
45 | 20241130 | 3 | 10 | 7 | 3 | 27 | 3 | 2 | 3 | Active | Deploy | Green | 1 | 0.8753 | 1230348 | 1230348 | 1177702 | 1360730 | 153424 | -100778 | 0.875 | 0.914 | 20240831 | 20241130 | 102 | 11 | 11 | 7 | 3 | 1 | 5515 | 4224 | 4321 | -1291 | 3 | 0 | 36 | 1 | 3500000 | 3500000 | 3337560 | 3282054 | 0.9377 | 2 | 33000 | 0 | 71 | 84.9
46 | 20241231 | 3 | 10 | 7 | 3 | 27 | 3 | 2 | 3 | Active | Deploy | Green | 1 | 0.8785 | 1230348 | 1230348 | 1196757 | 1366719 | 149487 | -115896 | 0.878 | 0.903 | 20240831 | 20241130 | 99 | 11 | 11 | 7 | 3 | 1 | 5515 | 4403 | 4397 | -1112 | 5 | 1 | 77 | 1 | 3500000 | 3500000 | 3229518 | 2857901 | 0.8165 | 2 | 30000 | 1 | 69 | 76.5
47 | 20250131 | 3 | 10 | 7 | 3 | 27 | 3 | 2 | 3 | Active | Deploy | Green | 1 | 0.9006 | 1230348 | 1230348 | 1236566 | 1371542 | 122297 | -128515 | 0.901 | 0.896 | 20240831 | 20241130 | 81 | 11 | 11 | 8 | 2 | 1 | 5515 | 4358 | 4633 | -1157 | 4 | 1 | 65 | 1 | 3500000 | 3500000 | 3287385 | 2997747 | 0.8565 | 2 | 36000 | 1 | 70 | 77.6
48 | 20250228 | 3 | 10 | 7 | 3 | 27 | 3 | 2 | 3 | Active | Deploy | Green | 1 | 0.9006 | 1230348 | 1230348 | 1244858 | 1376087 | 122297 | -136807 | 0.901 | 0.89 | 20240831 | 20241130 | 81 | 11 | 11 | 9 | 2 | 1 | 5515 | 4589 | 4342 | -926 | 4 | 1 | 65 | 1 | 3500000 | 3500000 | 3257977 | 3212047 | 0.9177 | 2 | 36000 | 2 | 66 | 78.1
49 | 20250331 | 3 | 10 | 7 | 3 | 27 | 3 | 2 | 3 | Active | Deploy | Green | 1 | 0.9006 | 1230348 | 1230348 | 1253463 | 1380670 | 122297 | -145412 | 0.901 | 0.884 | 20240831 | 20241130 | 81 | 11 | 11 | 8 | 2 | 1 | 5515 | 4043 | 4085 | -1472 | 4 | 0 | 47 | 1 | 3500000 | 3500000 | 3258627 | 2988684 | 0.8539 | 2 | 20000 | 4 | 76 | 83.7
50 | 20250430 | 3 | 10 | 7 | 3 | 27 | 3 | 2 | 3 | Active | Deploy | Green | 1 | 0.9006 | 1230348 | 1230348 | 1253463 | 1381695 | 122297 | -145412 | 0.901 | 0.884 | 20240831 | 20241130 | 81 | 11 | 11 | 8 | 2 | 1 | 5515 | 4444 | 4592 | -1071 | 5 | 0 | 59 | 1 | 3500000 | 3500000 | 3315648 | 3272907 | 0.9351 | 2 | 37000 | 4 | 72 | 85.7
51 | 20250531 | 3 | 10 | 7 | 3 | 27 | 3 | 2 | 3 | Active | Deploy | Green | 1 | 0.9006 | 1230348 | 1230348 | 1256524 | 1382278 | 122297 | -148473 | 0.901 | 0.882 | 20240831 | 20241130 | 81 | 11 | 11 | 9 | 2 | 1 | 5515 | 4530 | 4727 | -985 | 3 | 0 | 36 | 1 | 3500000 | 3500000 | 3360178 | 3235439 | 0.9244 | 2 | 25000 | 4 | 75 | 86.3
52 | 20250630 | 3 | 10 | 7 | 3 | 27 | 3 | 2 | 3 | Active | Deploy | Green | 1 | 0.9006 | 1230348 | 1230348 | 1256524 | 1382278 | 122297 | -148473 | 0.901 | 0.882 | 20240831 | 20241130 | 81 | 11 | 11 | 9 | 2 | 1 | 5515 | 4197 | 4360 | -1318 | 5 | 1 | 77 | 1 | 3500000 | 3500000 | 3283522 | 3237153 | 0.9249 | 2 | 20000 | 2 | 66 | 76.4
53 | 20250331 | 4 | 2 | 4 | 4 | 28 | 4 | 2 | 4 | Active | Initiate & Design | Red | 0.0417 | 0.0068 | 777876 | 29927 | 9657 | 890217 | 24637 | -4367 | 0.177 | 0.548 | 20270228 | 20270331 | 33 | 12 | 1 | 0 | 1 | 0 | 3942 | 3755 | 4001 | -187 | 12 | 2 | 182 | 3 | 2000000 | 0 | 1918735 | 0 |  | 0 | 0 | 5 | 24 | 28.9
54 | 20250430 | 4 | 2 | 4 | 4 | 28 | 4 | 2 | 4 | Active | Initiate & Design | Amber | 0.0833 | 0.032 | 777876 | 60069 | 27681 | 832533 | 35177 | -2789 | 0.414 | 0.898 | 20270228 | 20270430 | 49 | 12 | 1 | 0 | 1 | 0 | 4390 | 4157 | 4292 | -233 | 9 | 1 | 127 | 2 | 2000000 | 0 | 1967465 | 0 |  | 0 | 0 | 3 | 47 | 60.4
55 | 20250531 | 4 | 2 | 4 | 4 | 28 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.125 | 0.069 | 777876 | 90428 | 52909 | 817353 | 36755 | 764 | 0.594 | 1.014 | 20270228 | 20270430 | 52 | 12 | 2 | 1 | 1 | 0 | 4821 | 4662 | 4502 | -159 | 9 | 1 | 127 | 2 | 2000000 | 0 | 1920811 | 0 |  | 0 | 0 | 4 | 63 | 72.4
56 | 20250630 | 4 | 2 | 4 | 4 | 28 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.1667 | 0.0972 | 777876 | 121003 | 75597 | 819681 | 45393 | 13 | 0.625 | 1 | 20270228 | 20270430 | 66 | 12 | 2 | 0 | 1 | 0 | 5231 | 5014 | 5288 | -217 | 7 | 1 | 103 | 2 | 2000000 | 0 | 1934210 | 0 |  | 0 | 0 | 5 | 58 | 73.3
57 | 20250731 | 4 | 2 | 4 | 4 | 28 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.2083 | 0.1464 | 777876 | 151794 | 109002 | 821891 | 37913 | 4879 | 0.75 | 1.045 | 20270228 | 20270430 | 59 | 12 | 3 | 1 | 1 | 0 | 5610 | 5454 | 5250 | -156 | 6 | 1 | 91 | 2 | 2000000 | 0 | 1932561 | 0 |  | 0 | 0 | 3 | 67 | 80.8
58 | 20250831 | 4 | 2 | 4 | 4 | 28 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.25 | 0.1968 | 777876 | 182801 | 139841 | 824160 | 29715 | 13245 | 0.837 | 1.094 | 20270228 | 20270430 | 50 | 12 | 3 | 1 | 1 | 0 | 5953 | 5140 | 5295 | -813 | 6 | 1 | 91 | 2 | 2000000 | 0 | 1920275 | 0 |  | 0 | 0 | 4 | 75 | 83.9
59 | 20250930 | 4 | 2 | 4 | 4 | 28 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.2917 | 0.2447 | 777876 | 214024 | 177765 | 826428 | 23678 | 12581 | 0.889 | 1.071 | 20270228 | 20270430 | 45 | 12 | 4 | 2 | 1 | 0 | 6253 | 5959 | 5936 | -294 | 6 | 1 | 91 | 2 | 2000000 | 0 | 1888593 | 0 |  | 1 | 11000 | 3 | 73 | 86.9
60 | 20251031 | 4 | 2 | 4 | 4 | 28 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.3333 | 0.2965 | 777876 | 245463 | 224888 | 828697 | 14823 | 5752 | 0.94 | 1.026 | 20270228 | 20270331 | 35 | 12 | 4 | 2 | 1 | 0 | 6507 | 5755 | 5892 | -752 | 5 | 1 | 79 | 1 | 2000000 | 0 | 1924978 | 0 |  | 1 | 7000 | 5 | 74 | 86.6
61 | 20251130 | 4 | 2 | 4 | 4 | 28 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.375 | 0.3117 | 777876 | 277118 | 230080 | 830966 | 34654 | 12384 | 0.875 | 1.054 | 20270228 | 20270430 | 60 | 12 | 5 | 4 | 1 | 0 | 6709 | 6110 | 6147 | -599 | 6 | 1 | 91 | 2 | 2000000 | 0 | 1959656 | 0 |  | 1 | 12000 | 3 | 70 | 85.7
62 | 20251231 | 4 | 2 | 4 | 4 | 28 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.4167 | 0.3492 | 777876 | 308990 | 265653 | 833235 | 37356 | 5981 | 0.879 | 1.022 | 20270228 | 20270430 | 64 | 12 | 5 | 3 | 1 | 0 | 6855 | 6274 | 6554 | -581 | 6 | 1 | 91 | 2 | 2000000 | 0 | 1895580 | 0 |  | 1 | 11000 | 6 | 68 | 84
63 | 20260131 | 4 | 2 | 4 | 4 | 28 | 4 | 2 | 4 | Active | Deliver | Green | 0.4583 | 0.3788 | 777876 | 341077 | 285117 | 835504 | 46418 | 9542 | 0.864 | 1.034 | 20270228 | 20270531 | 75 | 12 | 6 | 3 | 2 | 1 | 6944 | 6284 | 6590 | -660 | 6 | 1 | 91 | 2 | 2000000 | 0 | 1928553 | 0 |  | 1 | 8000 | 3 | 75 | 84
64 | 20260228 | 4 | 2 | 4 | 4 | 28 | 4 | 2 | 4 | Active | Deliver | Green | 0.5 | 0.4069 | 777876 | 373380 | 317515 | 838294 | 56862 | -997 | 0.848 | 0.997 | 20270228 | 20270531 | 88 | 12 | 6 | 3 | 2 | 1 | 6974 | 6808 | 7270 | -166 | 6 | 0 | 73 | 2 | 2000000 | 0 | 1900535 | 0 |  | 1 | 9000 | 6 | 76 | 91.1
65 | 20260331 | 4 | 2 | 4 | 4 | 28 | 4 | 2 | 4 | Active | Deliver | Green | 0.5417 | 0.4437 | 777876 | 405900 | 348847 | 841870 | 60756 | -3703 | 0.85 | 0.989 | 20270228 | 20270531 | 93 | 12 | 7 | 4 | 2 | 1 | 6944 | 6544 | 6616 | -400 | 6 | 1 | 91 | 2 | 2000000 | 0 | 1967467 | 0 |  | 1 | 8000 | 6 | 72 | 83.2
66 | 20260430 | 4 | 2 | 4 | 4 | 28 | 4 | 2 | 4 | Active | Deliver | Green | 0.5833 | 0.4967 | 777876 | 438636 | 391772 | 844677 | 52265 | -5401 | 0.881 | 0.986 | 20270228 | 20270531 | 81 | 12 | 7 | 5 | 2 | 1 | 6855 | 6106 | 6042 | -749 | 8 | 1 | 115 | 2 | 2000000 | 0 | 1906296 | 0 |  | 1 | 12000 | 5 | 75 | 82.4
67 | 20260531 | 4 | 2 | 4 | 4 | 28 | 4 | 2 | 4 | Active | Deliver | Green | 0.625 | 0.5597 | 777876 | 471587 | 447037 | 849036 | 36210 | -11660 | 0.923 | 0.974 | 20270228 | 20270430 | 62 | 12 | 8 | 7 | 1 | 0 | 6709 | 6136 | 6117 | -573 | 8 | 1 | 115 | 2 | 2000000 | 0 | 1881168 | 0 |  | 1 | 10000 | 3 | 76 | 84.1
68 | 20260630 | 4 | 2 | 4 | 4 | 28 | 4 | 2 | 4 | Active | Deliver | Green | 0.6667 | 0.6134 | 777876 | 504755 | 493270 | 852450 | 27606 | -16121 | 0.945 | 0.967 | 20270228 | 20270331 | 15 | 12 | 8 | 6 | 1 | 0 | 6507 | 6102 | 6499 | -405 | 5 | 1 | 79 | 1 | 2000000 | 0 | 1926785 | 0 |  | 1 | 12000 | 5 | 70 | 86
69 | 20260731 | 4 | 2 | 4 | 4 | 28 | 4 | 2 | 4 | Active | Deliver | Green | 0.7083 | 0.6613 | 777876 | 538139 | 535869 | 855980 | 23730 | -21460 | 0.956 | 0.96 | 20270228 | 20270228 | 10 | 12 | 9 | 8 | 1 | 0 | 6253 | 6048 | 6414 | -205 | 7 | 1 | 103 | 2 | 2000000 | 0 | 1921300 | 0 |  | 1 | 12000 | 7 | 70 | 86.8
70 | 20260831 | 4 | 2 | 4 | 4 | 28 | 4 | 2 | 4 | Active | Deliver | Green | 0.75 | 0.6929 | 777876 | 571739 | 560738 | 858025 | 32749 | -21748 | 0.943 | 0.961 | 20270228 | 20270331 | 19 | 12 | 9 | 8 | 1 | 0 | 5953 | 5737 | 5618 | -216 | 7 | 1 | 103 | 2 | 2000000 | 214286 | 1892467 | 0 | 0 | 1 | 10000 | 3 | 73 | 85.8
71 | 20260930 | 4 | 2 | 4 | 4 | 28 | 4 | 2 | 4 | Active | Deliver | Green | 0.7917 | 0.7158 | 777876 | 605555 | 587027 | 862455 | 48751 | -30223 | 0.92 | 0.949 | 20270228 | 20270331 | 37 | 12 | 10 | 8 | 2 | 1 | 5610 | 4863 | 4868 | -747 | 8 | 1 | 115 | 2 | 2000000 | 511905 | 1943417 | 70466 | 0.1377 | 1 | 12000 | 6 | 72 | 82.9
72 | 20231031 | 5 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.5833 | 0.61 | 1119418 | 631227 | 682160 | 1159157 | -51618 | 685 | 1.082 | 1.001 | 20240831 | 20240831 | 0 | 12 | 7 | 7 | 0 | 0 | 9865 | 9638 | 9728 | -227 | 3 | 0 | 31 | 1 | 800000 | 0 | 586578 | 0 |  | 1 | 16000 | 5 | 80 | 95.7
73 | 20231130 | 5 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.625 | 0.6437 | 1119418 | 678647 | 712123 | 1160557 | -41922 | 8446 | 1.062 | 1.012 | 20240831 | 20240831 | 0 | 12 | 8 | 8 | 0 | 0 | 9654 | 9226 | 8779 | -428 | 5 | 0 | 51 | 1 | 800000 | 0 | 582810 | 0 |  | 1 | 10000 | 5 | 73 | 94.6
74 | 20231231 | 5 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.6667 | 0.6832 | 1119418 | 726378 | 758417 | 1161956 | -38408 | 6369 | 1.053 | 1.008 | 20240831 | 20240831 | 0 | 12 | 8 | 7 | 0 | 0 | 9364 | 9635 | 9786 | 271 | 2 | 0 | 20 | 0 | 800000 | 0 | 591759 | 0 |  | 1 | 14000 | 2 | 73 | 95.4
75 | 20240131 | 5 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.7083 | 0.7317 | 1119418 | 774420 | 819555 | 1163501 | -44658 | -477 | 1.058 | 0.999 | 20240831 | 20240831 | 0 | 12 | 9 | 9 | 0 | 0 | 8999 | 8728 | 8368 | -271 | 2 | 0 | 20 | 0 | 800000 | 0 | 618256 | 0 |  | 1 | 13000 | 5 | 77 | 95.6
76 | 20240229 | 5 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deploy | Green | 0.75 | 0.766 | 1119418 | 822772 | 860535 | 1165638 | -34702 | -3061 | 1.042 | 0.996 | 20240831 | 20240831 | 0 | 12 | 9 | 9 | 0 | 0 | 8566 | 8823 | 8884 | 257 | 3 | 0 | 31 | 1 | 800000 | 85714 | 589893 | 0 | 0 | 1 | 15000 | 3 | 76 | 94.4
77 | 20240331 | 5 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deploy | Green | 0.7917 | 0.7893 | 1119418 | 871436 | 903339 | 1171558 | -12121 | -19782 | 1.014 | 0.978 | 20240831 | 20240831 | 2 | 12 | 10 | 9 | 0 | 0 | 8073 | 8359 | 8339 | 286 | 3 | 0 | 31 | 1 | 800000 | 204762 | 598114 | 22380 | 0.1093 | 1 | 14000 | 4 | 70 | 92.8
78 | 20240430 | 5 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deploy | Green | 0.8333 | 0.8265 | 1119418 | 920410 | 954685 | 1175158 | -4789 | -29486 | 1.005 | 0.969 | 20240831 | 20240831 | 6 | 12 | 10 | 9 | 0 | 0 | 7527 | 7886 | 8093 | 359 | 2 | 1 | 38 | 0 | 800000 | 323810 | 604510 | 97155 | 0.3 | 1 | 13000 | 2 | 70 | 84.3
79 | 20240531 | 5 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deploy | Green | 0.875 | 0.8877 | 1119418 | 969696 | 1026424 | 1176794 | -24011 | -32717 | 1.025 | 0.968 | 20240831 | 20240831 | 0 | 12 | 11 | 11 | 0 | 0 | 6938 | 7334 | 7239 | 396 | 3 | 0 | 31 | 1 | 800000 | 442857 | 600771 | 185099 | 0.418 | 1 | 17000 | 2 | 76 | 93
80 | 20240630 | 5 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deploy | Green | 0.9167 | 0.9229 | 1119418 | 1019292 | 1076659 | 1180312 | -13819 | -43548 | 1.014 | 0.96 | 20240831 | 20240831 | 0 | 12 | 11 | 11 | 0 | 0 | 6317 | 6734 | 7037 | 417 | 3 | 0 | 31 | 1 | 800000 | 561905 | 589775 | 237333 | 0.4224 | 1 | 15000 | 3 | 69 | 91.8
81 | 20240731 | 5 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deploy | Green | 0.9583 | 0.9898 | 1119418 | 1069200 | 1163576 | 1183513 | -38800 | -55576 | 1.036 | 0.952 | 20240831 | 20240831 | 0 | 12 | 12 | 12 | 0 | 0 | 5673 | 5511 | 5718 | -162 | 0 | 0 | 0 | 0 | 800000 | 680952 | 607011 | 352126 | 0.5171 | 1 | 13000 | 1 | 75 | 92.6
82 | 20240831 | 5 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Completed | Completed | Green | 1 | 1 | 1119418 | 1119418 | 1175430 | 1184886 | 0 | -56012 | 1 | 0.952 | 20240831 | 20240831 | 0 | 12 | 12 | 12 | 0 | 0 | 5018 | 5296 | 5047 | 278 | 1 | 0 | 10 | 0 | 800000 | 800000 | 599732 | 408679 | 0.5108 | 1 | 15000 | 3 | 71 | 91.3
83 | 20240630 | 6 | 5 | 5 | 6 | 30 | 6 | 1 | 6 | Active | Initiate & Design | Red | 0.0833 | 0 | 1477559 | 114100 | 8114 | 2004555 | 114100 | -8114 | 0 | 0 | 20250531 | 20250630 | 44 | 6 | 1 | 0 | 1 | 1 | 8338 | 6922 | 6680 | -1416 | 13 | 3 | 239 | 4 | 4300000 | 0 | 3046254 | 0 |  | 0 | 0 | 5 | 24 | 0
84 | 20240731 | 6 | 5 | 5 | 6 | 30 | 6 | 1 | 6 | Active | Initiate & Design | Red | 0.1667 | 0.0351 | 1477559 | 229843 | 44059 | 1704118 | 177981 | 7803 | 0.225 | 1.176 | 20250531 | 20250731 | 69 | 6 | 1 | 0 | 1 | 1 | 9935 | 7982 | 7742 | -1953 | 11 | 2 | 193 | 4 | 4300000 | 0 | 2928187 | 0 |  | 0 | 0 | 7 | 33 | 42.1
85 | 20240831 | 6 | 5 | 5 | 6 | 30 | 6 | 1 | 6 | Active | Initiate & Design | Amber | 0.25 | 0.1251 | 1477559 | 347226 | 173497 | 1728744 | 162383 | 11346 | 0.532 | 1.065 | 20250531 | 20250731 | 66 | 6 | 2 | 1 | 1 | 1 | 11307 | 8794 | 9080 | -2513 | 10 | 2 | 178 | 3 | 4300000 | 0 | 3115684 | 0 |  | 1 | 22000 | 6 | 41 | 52.6
86 | 20240930 | 6 | 5 | 5 | 6 | 30 | 6 | 1 | 6 | Active | Initiate & Design | Amber | 0.3333 | 0.2025 | 1477559 | 466252 | 311102 | 1765762 | 167046 | -11896 | 0.642 | 0.962 | 20250531 | 20250731 | 69 | 6 | 2 | 0 | 1 | 1 | 12360 | 10559 | 10753 | -1801 | 9 | 2 | 164 | 3 | 4300000 | 0 | 3114561 | 0 |  | 2 | 29000 | 5 | 44 | 55.6
87 | 20241031 | 6 | 5 | 5 | 6 | 30 | 6 | 1 | 6 | Active | Initiate & Design | Amber | 0.4167 | 0.2697 | 1477559 | 586919 | 417528 | 1792805 | 188421 | -19030 | 0.679 | 0.954 | 20250531 | 20250831 | 78 | 6 | 3 | 0 | 2 | 1 | 13021 | 10833 | 10643 | -2188 | 10 | 2 | 178 | 3 | 4300000 | 0 | 2916307 | 0 |  | 2 | 39000 | 8 | 49 | 55.3
88 | 20241130 | 6 | 5 | 5 | 6 | 30 | 6 | 1 | 6 | Active | Initiate & Design | Amber | 0.5 | 0.3251 | 1477559 | 709228 | 501581 | 1816419 | 228874 | -21227 | 0.677 | 0.958 | 20250531 | 20250831 | 92 | 6 | 3 | 0 | 2 | 1 | 13247 | 11001 | 11065 | -2246 | 9 | 2 | 164 | 3 | 4300000 | 0 | 3054740 | 0 |  | 2 | 46000 | 7 | 49 | 56.1
89 | 20241231 | 6 | 5 | 5 | 6 | 30 | 6 | 1 | 6 | Active | Deliver | Amber | 0.5833 | 0.3922 | 1477559 | 833179 | 632759 | 1854595 | 253680 | -53260 | 0.696 | 0.916 | 20250531 | 20250831 | 101 | 6 | 4 | 2 | 2 | 1 | 13021 | 10298 | 9728 | -2723 | 11 | 2 | 193 | 4 | 4300000 | 0 | 3053264 | 0 |  | 2 | 44000 | 4 | 46 | 54.6
90 | 20250131 | 6 | 5 | 5 | 6 | 30 | 6 | 1 | 6 | Active | Deliver | Amber | 0.6667 | 0.4301 | 1477559 | 958772 | 704946 | 1883922 | 323274 | -69448 | 0.663 | 0.901 | 20250531 | 20250930 | 125 | 6 | 4 | 2 | 2 | 1 | 12360 | 9884 | 10109 | -2476 | 10 | 2 | 178 | 3 | 4300000 | 0 | 2907965 | 0 |  | 2 | 40000 | 5 | 45 | 51.9
91 | 20250228 | 6 | 5 | 5 | 6 | 30 | 6 | 1 | 6 | Paused | Deliver | Amber | 0.75 | 0.4899 | 1477559 | 1086006 | 823424 | 1915811 | 362150 | -99568 | 0.667 | 0.879 | 20250531 | 20251031 | 138 | 6 | 5 | 1 | 3 | 2 | 11307 | 9496 | 9959 | -1811 | 9 | 2 | 164 | 3 | 4300000 | 460714 | 3044064 | 0 | 0 | 2 | 39000 | 6 | 46 | 53.1
92 | 20250331 | 6 | 5 | 5 | 6 | 30 | 6 | 1 | 6 | Paused | Deliver | Amber | 0.8333 | 0.5666 | 1477559 | 1214882 | 972999 | 1946478 | 377697 | -135814 | 0.689 | 0.86 | 20250531 | 20251031 | 141 | 6 | 5 | 1 | 3 | 2 | 9935 | 7951 | 7750 | -1984 | 8 | 2 | 150 | 3 | 4300000 | 1740476 | 2933363 | 501830 | 0.2883 | 3 | 53000 | 4 | 47 | 51.8
93 | 20250430 | 6 | 5 | 5 | 6 | 30 | 6 | 1 | 6 | Paused | Deliver | Amber | 0.9167 | 0.6252 | 1477559 | 1345400 | 1099651 | 1977730 | 421630 | -175881 | 0.687 | 0.84 | 20250531 | 20251031 | 154 | 6 | 6 | 3 | 3 | 2 | 8338 | 6367 | 6410 | -1971 | 9 | 2 | 164 | 3 | 4300000 | 3020238 | 3049326 | 1328077 | 0.4397 | 3 | 42000 | 5 | 46 | 51
94 | 20250531 | 6 | 5 | 5 | 6 | 30 | 6 | 1 | 6 | Terminated | Deliver | Amber | 1 | 0.7115 | 1477559 | 1477559 | 1296520 | 2011853 | 426276 | -245237 | 0.712 | 0.811 | 20250531 | 20251031 | 153 | 6 | 6 | 3 | 3 | 2 | 6624 | 5344 | 5039 | -1280 | 10 | 2 | 178 | 3 | 4300000 | 4300000 | 2986148 | 2146619 | 0.4992 | 4 | 82000 | 3 | 40 | 51.6
95 | 20231031 | 7 | 9 | 8 | 7 | 31 | 7 | 3 | 7 | Active | Deliver | Green | 0.4583 | 0.4171 | 113262 | 49662 | 47271 | 125266 | 2420 | -29 | 0.951 | 0.999 | 20241130 | 20241231 | 40 | 12 | 6 | 4 | 1 | 0 | 1011 | 908 | 963 | -103 | 8 | 2 | 137 | 2 | 200000 | 0 | 176229 | 0 |  | 1 | 1000 | 4 | 73 | 76.2
96 | 20231130 | 7 | 9 | 8 | 7 | 31 | 7 | 3 | 7 | Active | Deliver | Green | 0.5 | 0.4615 | 113262 | 54366 | 52397 | 125783 | 2096 | -127 | 0.961 | 0.997 | 20241130 | 20241231 | 38 | 12 | 6 | 5 | 1 | 0 | 1015 | 939 | 898 | -76 | 7 | 1 | 106 | 2 | 200000 | 0 | 181398 | 0 |  | 1 | 1000 | 7 | 79 | 85.9
97 | 20231231 | 7 | 9 | 8 | 7 | 31 | 7 | 3 | 7 | Active | Deliver | Green | 0.5417 | 0.505 | 113262 | 59101 | 57694 | 126408 | 1904 | -497 | 0.968 | 0.991 | 20241130 | 20241231 | 35 | 12 | 7 | 5 | 1 | 0 | 1011 | 909 | 954 | -102 | 8 | 1 | 119 | 2 | 200000 | 0 | 183584 | 0 |  | 2 | 3000 | 4 | 74 | 85.7
98 | 20240131 | 7 | 9 | 8 | 7 | 31 | 7 | 3 | 7 | Active | Deliver | Green | 0.5833 | 0.5597 | 113262 | 63867 | 64919 | 127252 | 474 | -1526 | 0.993 | 0.976 | 20241130 | 20241231 | 23 | 12 | 7 | 5 | 1 | 0 | 998 | 933 | 908 | -65 | 7 | 1 | 106 | 2 | 200000 | 0 | 183706 | 0 |  | 2 | 2000 | 3 | 76 | 87.1
99 | 20240229 | 7 | 9 | 8 | 7 | 31 | 7 | 3 | 7 | Active | Deliver | Green | 0.625 | 0.578 | 113262 | 68665 | 67983 | 128060 | 3200 | -2518 | 0.953 | 0.963 | 20241130 | 20250131 | 46 | 12 | 8 | 7 | 1 | 0 | 977 | 877 | 887 | -100 | 7 | 1 | 106 | 2 | 200000 | 0 | 181509 | 0 |  | 2 | 3000 | 5 | 74 | 83.8
100 | 20240331 | 7 | 9 | 8 | 7 | 31 | 7 | 3 | 7 | Active | Deliver | Green | 0.6667 | 0.5991 | 113262 | 73494 | 71001 | 128714 | 5639 | -3146 | 0.923 | 0.956 | 20241130 | 20250131 | 66 | 12 | 8 | 6 | 1 | 0 | 947 | 888 | 855 | -59 | 7 | 1 | 106 | 2 | 200000 | 0 | 176463 | 0 |  | 2 | 2000 | 4 | 68 | 82.3
101 | 20240430 | 7 | 9 | 8 | 7 | 31 | 7 | 3 | 7 | Active | Deliver | Green | 0.7083 | 0.6365 | 113262 | 78355 | 75779 | 129292 | 6264 | -3688 | 0.92 | 0.951 | 20241130 | 20250131 | 70 | 12 | 9 | 6 | 2 | 1 | 911 | 880 | 857 | -31 | 8 | 1 | 119 | 2 | 200000 | 0 | 175408 | 0 |  | 2 | 3000 | 5 | 74 | 82.5
102 | 20240531 | 7 | 9 | 8 | 7 | 31 | 7 | 3 | 7 | Active | Deliver | Green | 0.75 | 0.6825 | 113262 | 83248 | 81839 | 129935 | 5947 | -4538 | 0.929 | 0.945 | 20241130 | 20250131 | 66 | 12 | 9 | 6 | 2 | 1 | 867 | 846 | 850 | -21 | 6 | 1 | 94 | 2 | 200000 | 21429 | 177970 | 0 | 0 | 2 | 3000 | 6 | 76 | 83.2
103 | 20240630 | 7 | 9 | 8 | 7 | 31 | 7 | 3 | 7 | Active | Deliver | Green | 0.7917 | 0.7288 | 113262 | 88171 | 89001 | 130831 | 5626 | -6456 | 0.936 | 0.928 | 20241130 | 20250131 | 61 | 12 | 10 | 7 | 2 | 1 | 817 | 756 | 711 | -61 | 7 | 1 | 106 | 2 | 200000 | 51190 | 177143 | 6062 | 0.1184 | 2 | 3000 | 3 | 69 | 81.8
104 | 20240731 | 7 | 9 | 8 | 7 | 31 | 7 | 3 | 7 | Active | Deploy | Green | 0.8333 | 0.7702 | 113262 | 93127 | 94028 | 131296 | 5893 | -6794 | 0.937 | 0.928 | 20241130 | 20250131 | 61 | 12 | 10 | 7 | 2 | 1 | 762 | 698 | 695 | -64 | 5 | 1 | 81 | 1 | 200000 | 80952 | 181406 | 29516 | 0.3646 | 2 | 3000 | 3 | 70 | 82.2
105 | 20240831 | 7 | 9 | 8 | 7 | 31 | 7 | 3 | 7 | Active | Deploy | Green | 0.875 | 0.8375 | 113262 | 98113 | 103628 | 132077 | 3256 | -8771 | 0.967 | 0.915 | 20241130 | 20241231 | 36 | 12 | 11 | 10 | 1 | 0 | 702 | 686 | 658 | -16 | 5 | 1 | 81 | 1 | 200000 | 110714 | 183690 | 54508 | 0.4923 | 2 | 2000 | 4 | 69 | 84.8
106 | 20240930 | 7 | 9 | 8 | 7 | 31 | 7 | 3 | 7 | Active | Deploy | Green | 0.9167 | 0.8711 | 113262 | 103131 | 109271 | 132860 | 4468 | -10608 | 0.957 | 0.903 | 20241130 | 20241231 | 44 | 12 | 11 | 9 | 1 | 0 | 639 | 594 | 591 | -45 | 4 | 1 | 69 | 1 | 200000 | 140476 | 177864 | 79116 | 0.5632 | 2 | 3000 | 3 | 73 | 82
107 | 20241031 | 7 | 9 | 8 | 7 | 31 | 7 | 3 | 7 | Active | Deploy | Green | 0.9583 | 0.9094 | 113262 | 108181 | 114054 | 133328 | 5181 | -11054 | 0.952 | 0.903 | 20241130 | 20250131 | 47 | 12 | 12 | 9 | 2 | 1 | 574 | 519 | 553 | -55 | 4 | 1 | 69 | 1 | 200000 | 170238 | 181021 | 107600 | 0.6321 | 2 | 3000 | 4 | 72 | 81.7
108 | 20241130 | 7 | 9 | 8 | 7 | 31 | 7 | 3 | 7 | Active | Deploy | Green | 1 | 0.942 | 113262 | 113262 | 120233 | 134191 | 6569 | -13540 | 0.942 | 0.887 | 20241130 | 20250131 | 57 | 12 | 12 | 10 | 2 | 1 | 508 | 487 | 466 | -21 | 4 | 0 | 51 | 1 | 200000 | 200000 | 175740 | 119016 | 0.5951 | 2 | 2000 | 2 | 75 | 89.1
109 | 20241231 | 7 | 9 | 8 | 7 | 31 | 7 | 3 | 7 | Active | Deploy | Green | 1 | 0.942 | 113262 | 113262 | 120500 | 134712 | 6569 | -13807 | 0.942 | 0.885 | 20241130 | 20250131 | 57 | 12 | 12 | 10 | 2 | 1 | 508 | 490 | 479 | -18 | 4 | 0 | 51 | 1 | 200000 | 200000 | 182831 | 146962 | 0.7348 | 3 | 3000 | 5 | 78 | 90.2
110 | 20250131 | 7 | 9 | 8 | 7 | 31 | 7 | 3 | 7 | Active | Deploy | Green | 1 | 0.942 | 113262 | 113262 | 121969 | 135450 | 6569 | -15276 | 0.942 | 0.875 | 20241130 | 20250131 | 57 | 12 | 12 | 10 | 2 | 1 | 508 | 481 | 475 | -27 | 5 | 1 | 81 | 1 | 200000 | 200000 | 183863 | 166436 | 0.8322 | 3 | 5000 | 4 | 68 | 81.6
111 | 20250228 | 7 | 9 | 8 | 7 | 31 | 7 | 3 | 7 | Active | Deploy | Green | 1 | 0.942 | 113262 | 113262 | 122008 | 135929 | 6569 | -15315 | 0.942 | 0.874 | 20241130 | 20250131 | 57 | 12 | 12 | 9 | 2 | 1 | 508 | 511 | 513 | 3 | 4 | 0 | 51 | 1 | 200000 | 200000 | 183199 | 169621 | 0.8481 | 3 | 5000 | 4 | 75 | 90.6
112 | 20250331 | 7 | 9 | 8 | 7 | 31 | 7 | 3 | 7 | Active | Deploy | Green | 1 | 0.942 | 113262 | 113262 | 124304 | 136803 | 6569 | -17611 | 0.942 | 0.858 | 20241130 | 20250131 | 57 | 12 | 12 | 10 | 2 | 1 | 508 | 503 | 533 | -5 | 4 | 0 | 51 | 1 | 200000 | 200000 | 177367 | 166861 | 0.8343 | 3 | 4000 | 3 | 73 | 89
113 | 20250430 | 7 | 9 | 8 | 7 | 31 | 7 | 3 | 7 | Active | Deploy | Green | 1 | 0.942 | 113262 | 113262 | 124608 | 137327 | 6569 | -17915 | 0.942 | 0.856 | 20241130 | 20250131 | 57 | 12 | 12 | 10 | 2 | 1 | 508 | 470 | 467 | -38 | 5 | 1 | 81 | 1 | 200000 | 200000 | 177422 | 162845 | 0.8142 | 3 | 5000 | 2 | 73 | 79.5
114 | 20250531 | 7 | 9 | 8 | 7 | 31 | 7 | 3 | 7 | Active | Deploy | Green | 1 | 0.9439 | 113262 | 113262 | 126161 | 138017 | 6354 | -19253 | 0.944 | 0.847 | 20241130 | 20250131 | 54 | 12 | 12 | 9 | 2 | 1 | 508 | 470 | 476 | -38 | 6 | 1 | 94 | 2 | 200000 | 200000 | 179813 | 163974 | 0.8199 | 3 | 5000 | 2 | 73 | 79.7
115 | 20250630 | 7 | 9 | 8 | 7 | 31 | 7 | 3 | 7 | Active | Deploy | Green | 1 | 0.9439 | 113262 | 113262 | 127019 | 138632 | 6354 | -20111 | 0.944 | 0.842 | 20241130 | 20250131 | 54 | 12 | 12 | 9 | 2 | 1 | 508 | 479 | 454 | -29 | 6 | 1 | 94 | 2 | 200000 | 200000 | 181776 | 161777 | 0.8089 | 3 | 5000 | 3 | 67 | 80.1
116 | 20250731 | 7 | 9 | 8 | 7 | 31 | 7 | 3 | 7 | Active | Deploy | Green | 1 | 0.9439 | 113262 | 113262 | 128691 | 139376 | 6354 | -21783 | 0.944 | 0.831 | 20241130 | 20250131 | 54 | 12 | 12 | 9 | 2 | 1 | 508 | 480 | 465 | -28 | 6 | 1 | 94 | 2 | 200000 | 200000 | 175568 | 162208 | 0.811 | 3 | 3000 | 2 | 68 | 78.9
117 | 20250831 | 7 | 9 | 8 | 7 | 31 | 7 | 3 | 7 | Active | Deploy | Green | 1 | 0.9439 | 113262 | 113262 | 128691 | 139565 | 6354 | -21783 | 0.944 | 0.831 | 20241130 | 20250131 | 54 | 12 | 12 | 9 | 2 | 1 | 508 | 456 | 431 | -52 | 6 | 1 | 94 | 2 | 200000 | 200000 | 181387 | 171986 | 0.8599 | 3 | 3000 | 4 | 72 | 78.7
118 | 20250930 | 7 | 9 | 8 | 7 | 31 | 7 | 3 | 7 | Active | Deploy | Green | 1 | 0.9439 | 113262 | 113262 | 129374 | 139674 | 6354 | -22466 | 0.944 | 0.826 | 20241130 | 20250131 | 54 | 12 | 12 | 10 | 2 | 1 | 508 | 453 | 442 | -55 | 7 | 1 | 106 | 2 | 200000 | 200000 | 181130 | 161834 | 0.8092 | 3 | 5000 | 2 | 71 | 78.4
119 | 20231031 | 8 | 2 | 4 | 8 | 32 | 8 | 3 | 8 | Active | Deploy | Green | 0.8889 | 0.8953 | 117744 | 103731 | 107600 | 120022 | -1685 | -2184 | 1.016 | 0.98 | 20231130 | 20231130 | 0 | 6 | 5 | 4 | 0 | 0 | 708 | 722 | 731 | 14 | 1 | 0 | 10 | 0 | 100000 | 60317 | 102718 | 35503 | 0.5886 | 0 | 0 | 2 | 84 | 100
120 | 20231130 | 8 | 2 | 4 | 8 | 32 | 8 | 3 | 8 | Active | Deploy | Green | 1 | 0.9984 | 117744 | 117744 | 121126 | 121126 | 188 | -3570 | 0.998 | 0.97 | 20231130 | 20231130 | 0 | 6 | 6 | 6 | 0 | 0 | 528 | 552 | 552 | 24 | 0 | 0 | 0 | 0 | 100000 | 100000 | 100000 | 69848 | 0.6985 | 0 | 0 | 0 | 82 | 98.9
121 | 20231231 | 8 | 2 | 4 | 8 | 32 | 8 | 3 | 8 | Completed | Completed | Green | 1 | 1 | 117744 | 117744 | 123274 | 123274 | 0 | -5530 | 1 | 0.955 | 20231130 | 20231130 | 0 | 6 | 6 | 6 | 0 | 0 | 528 | 550 | 586 | 22 | 2 | 0 | 19 | 0 | 100000 | 100000 | 102562 | 96146 | 0.9615 | 0 | 0 | 2 | 77 | 98.4
122 | 20250228 | 9 | 2 | 4 | 9 | 33 | 1 | 2 | 1 | Active | Initiate & Design | Green | 0.0833 | 0.1281 | 397152 | 30669 | 48738 | 405294 | -20206 | 2137 | 1.659 | 1.044 | 20260131 | 20260131 | 0 | 6 | 1 | 1 | 0 | 0 | 2241 | 2484 | 2405 | 243 | 0 | 0 | 0 | 0 | 400000 | 0 | 434019 | 0 |  | 0 | 0 | 4 | 96 | 100
123 | 20250331 | 9 | 2 | 4 | 9 | 33 | 1 | 2 | 1 | Active | Initiate & Design | Green | 0.1667 | 0.2326 | 397152 | 61779 | 86595 | 406286 | -30599 | 5783 | 1.495 | 1.067 | 20260131 | 20260131 | 0 | 6 | 1 | 0 | 0 | 0 | 2671 | 2727 | 2847 | 56 | 0 | 0 | 0 | 0 | 400000 | 0 | 427872 | 0 |  | 0 | 0 | 4 | 96 | 100
124 | 20250430 | 9 | 2 | 4 | 9 | 33 | 1 | 2 | 1 | Active | Initiate & Design | Green | 0.25 | 0.3003 | 397152 | 93331 | 114728 | 407279 | -25934 | 4537 | 1.278 | 1.04 | 20260131 | 20260131 | 0 | 6 | 2 | 2 | 0 | 0 | 3039 | 3397 | 3555 | 358 | 1 | 0 | 9 | 0 | 400000 | 0 | 427709 | 0 |  | 0 | 0 | 4 | 96 | 100
125 | 20250531 | 9 | 2 | 4 | 9 | 33 | 1 | 2 | 1 | Active | Deliver | Green | 0.3333 | 0.398 | 397152 | 125324 | 150641 | 408272 | -32742 | 7425 | 1.261 | 1.049 | 20260131 | 20260131 | 0 | 6 | 2 | 2 | 0 | 0 | 3322 | 3586 | 3800 | 264 | 1 | 0 | 9 | 0 | 400000 | 0 | 436328 | 0 |  | 0 | 0 | 2 | 92 | 100
126 | 20250630 | 9 | 2 | 4 | 9 | 33 | 1 | 2 | 1 | Active | Deliver | Green | 0.4167 | 0.4656 | 397152 | 157758 | 175406 | 409265 | -27156 | 9508 | 1.172 | 1.054 | 20260131 | 20260131 | 0 | 6 | 3 | 2 | 0 | 0 | 3500 | 3588 | 3586 | 88 | 0 | 0 | 0 | 0 | 400000 | 0 | 424122 | 0 |  | 0 | 0 | 4 | 90 | 100
127 | 20250731 | 9 | 2 | 4 | 9 | 33 | 1 | 2 | 1 | Active | Deliver | Green | 0.5 | 0.5469 | 397152 | 190633 | 209540 | 410258 | -26569 | 7662 | 1.139 | 1.037 | 20260131 | 20260131 | 0 | 6 | 3 | 2 | 0 | 0 | 3561 | 3920 | 3736 | 359 | 1 | 0 | 9 | 0 | 400000 | 0 | 440666 | 0 |  | 0 | 0 | 5 | 88 | 100
128 | 20250831 | 9 | 2 | 4 | 9 | 33 | 1 | 2 | 1 | Active | Deliver | Green | 0.5833 | 0.6254 | 397152 | 223950 | 247688 | 411251 | -24429 | 691 | 1.109 | 1.003 | 20260131 | 20260131 | 0 | 6 | 4 | 4 | 0 | 0 | 3500 | 3810 | 4001 | 310 | 3 | 0 | 27 | 0 | 400000 | 0 | 423635 | 0 |  | 0 | 0 | 2 | 90 | 100
129 | 20250930 | 9 | 2 | 4 | 9 | 33 | 1 | 2 | 1 | Active | Deliver | Green | 0.6667 | 0.732 | 397152 | 257708 | 292201 | 412685 | -33007 | -1486 | 1.128 | 0.995 | 20260131 | 20260131 | 0 | 6 | 4 | 4 | 0 | 0 | 3322 | 3569 | 3357 | 247 | 3 | 0 | 27 | 0 | 400000 | 0 | 434788 | 0 |  | 1 | 3000 | 4 | 88 | 100
130 | 20251031 | 9 | 2 | 4 | 9 | 33 | 1 | 2 | 1 | Active | Deploy | Green | 0.75 | 0.831 | 397152 | 291907 | 332655 | 413921 | -38126 | -2622 | 1.131 | 0.992 | 20260131 | 20260131 | 0 | 6 | 5 | 4 | 0 | 0 | 3039 | 3462 | 3617 | 423 | 2 | 0 | 18 | 0 | 400000 | 42857 | 422548 | 0 | 0 | 1 | 5000 | 3 | 85 | 100
131 | 20251130 | 9 | 2 | 4 | 9 | 33 | 1 | 2 | 1 | Active | Deploy | Green | 0.8333 | 0.937 | 397152 | 326547 | 383201 | 416754 | -45584 | -11070 | 1.14 | 0.971 | 20260131 | 20260131 | 0 | 6 | 5 | 4 | 0 | 0 | 2671 | 2994 | 3163 | 323 | 0 | 0 | 0 | 0 | 400000 | 161905 | 426407 | 71269 | 0.4402 | 1 | 3000 | 3 | 88 | 100
132 | 20251231 | 9 | 2 | 4 | 9 | 33 | 1 | 2 | 1 | Completed | Completed | Green | 0.9167 | 1 | 397152 | 361629 | 414244 | 418827 | -35523 | -17092 | 1.098 | 0.959 | 20260131 | 20260131 | 0 | 6 | 6 | 6 | 0 | 0 | 2241 | 2445 | 2601 | 204 | 1 | 0 | 9 | 0 | 400000 | 280952 | 436029 | 178037 | 0.6337 | 1 | 4000 | 1 | 82 | 100
133 | 20250630 | 10 | 9 | 8 | 10 | 34 | 2 | 3 | 2 | Active | Initiate & Design | Green | 0.1111 | 0.062 | 725551 | 74884 | 39367 | 751348 | 29900 | 5617 | 0.601 | 1.144 | 20260228 | 20260331 | 17 | 6 | 1 | 0 | 1 | 0 | 4365 | 3184 | 3046 | -1181 | 9 | 1 | 125 | 2 | 800000 | 0 | 749457 | 0 |  | 0 | 0 | 3 | 66 | 71.4
134 | 20250731 | 10 | 9 | 8 | 10 | 34 | 2 | 3 | 2 | Active | Initiate & Design | Green | 0.2222 | 0.1744 | 725551 | 151201 | 122259 | 755379 | 24665 | 4277 | 0.837 | 1.035 | 20260228 | 20260331 | 17 | 6 | 1 | 1 | 0 | 0 | 5343 | 4020 | 3990 | -1323 | 5 | 0 | 59 | 1 | 800000 | 0 | 746884 | 0 |  | 0 | 0 | 4 | 78 | 86.6
135 | 20250831 | 10 | 9 | 8 | 10 | 34 | 2 | 3 | 2 | Active | Initiate & Design | Green | 0.3333 | 0.251 | 725551 | 228952 | 177792 | 759410 | 46839 | 4321 | 0.796 | 1.024 | 20260228 | 20260331 | 28 | 6 | 2 | 0 | 1 | 0 | 6069 | 5033 | 5022 | -1036 | 7 | 0 | 83 | 2 | 800000 | 0 | 766671 | 0 |  | 1 | 6000 | 5 | 73 | 86.7
136 | 20250930 | 10 | 9 | 8 | 10 | 34 | 2 | 3 | 2 | Active | Initiate & Design | Green | 0.4444 | 0.3326 | 725551 | 308135 | 239714 | 763441 | 66817 | 1604 | 0.783 | 1.007 | 20260228 | 20260331 | 39 | 6 | 3 | 2 | 1 | 0 | 6456 | 5106 | 5183 | -1350 | 7 | 1 | 101 | 2 | 800000 | 0 | 734302 | 0 |  | 1 | 9000 | 6 | 68 | 75.6
137 | 20251031 | 10 | 9 | 8 | 10 | 34 | 2 | 3 | 2 | Active | Deliver | Green | 0.5556 | 0.4269 | 725551 | 388752 | 311373 | 768297 | 79014 | -1635 | 0.797 | 0.995 | 20260228 | 20260430 | 45 | 6 | 3 | 1 | 1 | 0 | 6456 | 5222 | 5285 | -1234 | 6 | 0 | 71 | 2 | 800000 | 0 | 750855 | 0 |  | 1 | 7000 | 4 | 70 | 84.8
138 | 20251130 | 10 | 9 | 8 | 10 | 34 | 2 | 3 | 2 | Active | Deliver | Green | 0.6667 | 0.5315 | 725551 | 470802 | 386554 | 771869 | 85172 | -924 | 0.819 | 0.998 | 20260228 | 20260430 | 46 | 6 | 4 | 2 | 1 | 0 | 6069 | 4710 | 4942 | -1359 | 8 | 1 | 113 | 2 | 800000 | 0 | 771601 | 0 |  | 1 | 11000 | 3 | 68 | 77.9
139 | 20251231 | 10 | 9 | 8 | 10 | 34 | 2 | 3 | 2 | Active | Deliver | Green | 0.7778 | 0.6322 | 725551 | 554285 | 472672 | 780253 | 95592 | -13979 | 0.828 | 0.97 | 20260228 | 20260430 | 50 | 6 | 5 | 2 | 2 | 1 | 5343 | 4021 | 3807 | -1322 | 8 | 1 | 113 | 2 | 800000 | 165079 | 761925 | 0 | 0 | 1 | 9000 | 4 | 69 | 76.4
140 | 20260131 | 10 | 9 | 8 | 10 | 34 | 2 | 3 | 2 | Active | Deploy | Green | 0.8889 | 0.7535 | 725551 | 639201 | 576964 | 787930 | 92498 | -30261 | 0.855 | 0.948 | 20260228 | 20260430 | 48 | 6 | 5 | 4 | 1 | 0 | 4365 | 3214 | 3366 | -1151 | 4 | 0 | 47 | 1 | 800000 | 482540 | 751930 | 268864 | 0.5572 | 1 | 9000 | 4 | 70 | 84.2
141 | 20260228 | 10 | 9 | 8 | 10 | 34 | 2 | 3 | 2 | Active | Deploy | Green | 1 | 0.8855 | 725551 | 725551 | 691281 | 794865 | 83076 | -48806 | 0.885 | 0.929 | 20260228 | 20260331 | 40 | 6 | 6 | 4 | 1 | 0 | 3252 | 2639 | 2539 | -613 | 6 | 1 | 89 | 2 | 800000 | 800000 | 732995 | 487440 | 0.6093 | 1 | 10000 | 3 | 73 | 77.9
142 | 20260331 | 10 | 9 | 8 | 10 | 34 | 2 | 3 | 2 | Active | Deploy | Green | 1 | 0.9013 | 725551 | 725551 | 712822 | 800817 | 71612 | -58883 | 0.901 | 0.917 | 20260228 | 20260331 | 35 | 6 | 6 | 4 | 1 | 0 | 3252 | 2651 | 2561 | -601 | 5 | 1 | 77 | 1 | 800000 | 800000 | 744518 | 717799 | 0.8972 | 1 | 7000 | 4 | 69 | 78.7
143 | 20260430 | 10 | 9 | 8 | 10 | 34 | 2 | 3 | 2 | Active | Deploy | Green | 1 | 0.9013 | 725551 | 725551 | 727209 | 807744 | 71612 | -73270 | 0.901 | 0.899 | 20260228 | 20260331 | 35 | 6 | 6 | 5 | 1 | 0 | 3252 | 2731 | 2739 | -521 | 5 | 1 | 77 | 1 | 800000 | 800000 | 771918 | 733389 | 0.9167 | 1 | 8000 | 1 | 69 | 79.5
144 | 20260531 | 10 | 9 | 8 | 10 | 34 | 2 | 3 | 2 | Active | Deploy | Green | 1 | 0.9013 | 725551 | 725551 | 739973 | 814251 | 71612 | -86034 | 0.901 | 0.884 | 20260228 | 20260331 | 35 | 6 | 6 | 4 | 1 | 0 | 3252 | 2398 | 2427 | -854 | 3 | 1 | 54 | 1 | 800000 | 800000 | 755443 | 726147 | 0.9077 | 1 | 11000 | 4 | 65 | 76.1
145 | 20260630 | 10 | 9 | 8 | 10 | 34 | 2 | 3 | 2 | Active | Deploy | Green | 1 | 0.9013 | 725551 | 725551 | 739973 | 814856 | 71612 | -86034 | 0.901 | 0.884 | 20260228 | 20260331 | 35 | 6 | 6 | 4 | 1 | 0 | 3252 | 2433 | 2343 | -819 | 4 | 1 | 65 | 1 | 800000 | 800000 | 762806 | 732433 | 0.9155 | 1 | 9000 | 3 | 70 | 76.6
146 | 20260731 | 10 | 9 | 8 | 10 | 34 | 2 | 3 | 2 | Active | Deploy | Green | 1 | 0.9013 | 725551 | 725551 | 739973 | 814856 | 71612 | -86034 | 0.901 | 0.884 | 20260228 | 20260331 | 35 | 6 | 6 | 5 | 1 | 0 | 3252 | 2623 | 2732 | -629 | 5 | 1 | 77 | 1 | 800000 | 800000 | 751580 | 665215 | 0.8315 | 2 | 13000 | 3 | 66 | 77.5
147 | 20260831 | 10 | 9 | 8 | 10 | 34 | 2 | 3 | 2 | Active | Deploy | Green | 1 | 0.9013 | 725551 | 725551 | 744721 | 815755 | 71612 | -90782 | 0.901 | 0.878 | 20260228 | 20260331 | 35 | 6 | 6 | 4 | 1 | 0 | 3252 | 2626 | 2609 | -626 | 5 | 1 | 77 | 1 | 800000 | 800000 | 768633 | 765438 | 0.9568 | 2 | 19000 | 1 | 67 | 78
148 | 20260930 | 10 | 9 | 8 | 10 | 34 | 2 | 3 | 2 | Active | Deploy | Green | 1 | 0.9013 | 725551 | 725551 | 744721 | 815755 | 71612 | -90782 | 0.901 | 0.878 | 20260228 | 20260331 | 35 | 6 | 6 | 5 | 1 | 0 | 3252 | 2652 | 2615 | -600 | 5 | 0 | 59 | 1 | 800000 | 800000 | 749443 | 736051 | 0.9201 | 2 | 18000 | 4 | 72 | 85.5
149 | 20240831 | 11 | 1 | 1 | 11 | 35 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.0833 | 0.0596 | 828754 | 63998 | 49927 | 870473 | 14604 | -533 | 0.771 | 0.989 | 20250731 | 20250731 | 12 | 6 | 1 | 1 | 0 | 0 | 4677 | 4345 | 4232 | -332 | 8 | 2 | 133 | 2 | 1800000 | 0 | 1734313 | 0 |  | 0 | 0 | 4 | 63 | 70.7
150 | 20240930 | 11 | 1 | 1 | 11 | 35 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.1667 | 0.1265 | 828754 | 128917 | 100061 | 873230 | 24080 | 4776 | 0.813 | 1.048 | 20250731 | 20250831 | 18 | 6 | 1 | 0 | 0 | 0 | 5573 | 5013 | 4966 | -560 | 8 | 1 | 115 | 2 | 1800000 | 0 | 1733038 | 0 |  | 0 | 0 | 4 | 67 | 82
151 | 20241031 | 11 | 1 | 1 | 11 | 35 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.25 | 0.1773 | 828754 | 194757 | 134858 | 878065 | 47819 | 12080 | 0.754 | 1.09 | 20250731 | 20250831 | 34 | 6 | 2 | 0 | 1 | 0 | 6342 | 5794 | 5482 | -548 | 8 | 1 | 115 | 2 | 1800000 | 0 | 1752038 | 0 |  | 0 | 0 | 4 | 73 | 81.4
152 | 20241130 | 11 | 1 | 1 | 11 | 35 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.3333 | 0.2525 | 828754 | 261518 | 200825 | 882899 | 52258 | 8435 | 0.8 | 1.042 | 20250731 | 20250831 | 38 | 6 | 2 | 1 | 1 | 0 | 6932 | 6589 | 6992 | -343 | 6 | 1 | 91 | 2 | 1800000 | 0 | 1717167 | 0 |  | 1 | 13000 | 7 | 69 | 82.1
153 | 20241231 | 11 | 1 | 1 | 11 | 35 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.4167 | 0.3405 | 828754 | 329200 | 281085 | 887734 | 47009 | 1106 | 0.857 | 1.004 | 20250731 | 20250831 | 35 | 6 | 3 | 2 | 1 | 0 | 7304 | 6470 | 6504 | -834 | 7 | 1 | 103 | 2 | 1800000 | 0 | 1709930 | 0 |  | 1 | 11000 | 6 | 75 | 81.8
154 | 20250131 | 11 | 1 | 1 | 11 | 35 | 3 | 2 | 3 | Active | Deliver | Green | 0.5 | 0.4007 | 828754 | 397802 | 324141 | 892568 | 65720 | 7941 | 0.835 | 1.024 | 20250731 | 20250930 | 47 | 6 | 3 | 2 | 1 | 0 | 7430 | 6704 | 6697 | -726 | 8 | 1 | 115 | 2 | 1800000 | 0 | 1731077 | 0 |  | 1 | 9000 | 5 | 69 | 82.2
155 | 20250228 | 11 | 1 | 1 | 11 | 35 | 3 | 2 | 3 | Active | Deliver | Green | 0.5833 | 0.4962 | 828754 | 467325 | 414538 | 898859 | 56097 | -3310 | 0.88 | 0.992 | 20250731 | 20250831 | 41 | 6 | 4 | 3 | 1 | 0 | 7304 | 6384 | 6314 | -920 | 6 | 0 | 73 | 2 | 1800000 | 0 | 1755180 | 0 |  | 1 | 9000 | 5 | 76 | 90.9
156 | 20250331 | 11 | 1 | 1 | 11 | 35 | 3 | 2 | 3 | Active | Deliver | Green | 0.6667 | 0.5881 | 828754 | 537769 | 494961 | 905012 | 50379 | -7571 | 0.906 | 0.985 | 20250731 | 20250731 | 2 | 6 | 4 | 2 | 1 | 0 | 6932 | 6638 | 6889 | -294 | 7 | 1 | 103 | 2 | 1800000 | 0 | 1770196 | 0 |  | 2 | 25000 | 6 | 72 | 85.9
157 | 20250430 | 11 | 1 | 1 | 11 | 35 | 3 | 2 | 3 | Active | Deliver | Green | 0.75 | 0.7119 | 828754 | 609134 | 615818 | 914710 | 19144 | -25828 | 0.969 | 0.958 | 20250731 | 20250731 | -17 | 6 | 5 | 3 | 1 | 0 | 6342 | 6158 | 6194 | -184 | 8 | 1 | 115 | 2 | 1800000 | 192857 | 1740796 | 0 | 0 | 2 | 19000 | 3 | 75 | 87.6
158 | 20250531 | 11 | 1 | 1 | 11 | 35 | 3 | 2 | 3 | Active | Deploy | Green | 0.8333 | 0.8034 | 828754 | 681420 | 701021 | 921062 | 15599 | -35200 | 0.977 | 0.95 | 20250731 | 20250731 | -21 | 6 | 5 | 4 | 0 | 0 | 5573 | 4952 | 4913 | -621 | 4 | 1 | 67 | 1 | 1800000 | 728571 | 1736683 | 304872 | 0.4185 | 2 | 23000 | 3 | 74 | 85.8
159 | 20250630 | 11 | 1 | 1 | 11 | 35 | 3 | 2 | 3 | Active | Deploy | Green | 0.9167 | 0.8886 | 828754 | 754627 | 794039 | 929961 | 18196 | -57608 | 0.976 | 0.927 | 20250731 | 20250731 | -22 | 6 | 6 | 4 | 1 | 0 | 4677 | 4236 | 4314 | -441 | 6 | 1 | 91 | 2 | 1800000 | 1264286 | 1689578 | 716556 | 0.5668 | 2 | 19000 | 4 | 73 | 84.6
160 | 20250731 | 11 | 1 | 1 | 11 | 35 | 3 | 2 | 3 | Active | Deploy | Green | 1 | 0.9788 | 828754 | 828754 | 879564 | 935748 | 17570 | -68380 | 0.979 | 0.922 | 20250731 | 20250731 | -25 | 6 | 6 | 4 | 1 | 0 | 3715 | 3373 | 3609 | -342 | 4 | 1 | 67 | 1 | 1800000 | 1800000 | 1735864 | 1110627 | 0.617 | 2 | 19000 | 3 | 74 | 85.3
161 | 20250831 | 11 | 1 | 1 | 11 | 35 | 3 | 2 | 3 | Active | Deploy | Green | 1 | 0.9788 | 828754 | 828754 | 900294 | 944455 | 17570 | -89110 | 0.979 | 0.901 | 20250731 | 20250731 | -25 | 6 | 6 | 4 | 1 | 0 | 3715 | 3490 | 3543 | -225 | 5 | 0 | 61 | 1 | 1800000 | 1800000 | 1689672 | 1681289 | 0.934 | 2 | 26000 | 3 | 79 | 92.5
162 | 20250930 | 11 | 1 | 1 | 11 | 35 | 3 | 2 | 3 | Active | Deploy | Green | 1 | 0.9788 | 828754 | 828754 | 916205 | 952137 | 17570 | -105021 | 0.979 | 0.885 | 20250731 | 20250731 | -25 | 6 | 6 | 5 | 1 | 0 | 3715 | 3493 | 3733 | -222 | 5 | 0 | 61 | 1 | 1800000 | 1800000 | 1744998 | 1542793 | 0.8571 | 2 | 23000 | 1 | 80 | 92.9
163 | 20251031 | 11 | 1 | 1 | 11 | 35 | 3 | 2 | 3 | Completed | Completed | Green | 1 | 1 | 828754 | 828754 | 943269 | 958212 | 0 | -114515 | 1 | 0.879 | 20250731 | 20250731 | -35 | 6 | 6 | 6 | 0 | 0 | 3715 | 3528 | 3642 | -187 | 4 | 1 | 67 | 1 | 1800000 | 1800000 | 1762044 | 1585303 | 0.8807 | 2 | 26000 | 2 | 76 | 86.1
164 | 20251130 | 12 | 9 | 8 | 12 | 36 | 4 | 1 | 4 | Active | Initiate & Design | Green | 0.0476 | 0.0646 | 133266 | 5862 | 7646 | 135855 | -2747 | 963 | 1.468 | 1.126 | 20270731 | 20270731 | 0 | 11 | 1 | 0 | 0 | 0 | 686 | 695 | 672 | 9 | 1 | 0 | 10 | 0 | 300000 | 0 | 220254 | 0 |  | 0 | 0 | 2 | 96 | 100
165 | 20251231 | 12 | 9 | 8 | 12 | 36 | 4 | 1 | 4 | Active | Initiate & Design | Green | 0.0952 | 0.0964 | 133266 | 11773 | 11541 | 136046 | -1074 | 1306 | 1.091 | 1.113 | 20270731 | 20270731 | 0 | 11 | 1 | 0 | 0 | 0 | 773 | 827 | 874 | 54 | 2 | 0 | 20 | 0 | 300000 | 0 | 224611 | 0 |  | 0 | 0 | 4 | 83 | 100
166 | 20260131 | 12 | 9 | 8 | 12 | 36 | 4 | 1 | 4 | Active | Initiate & Design | Green | 0.1429 | 0.1443 | 133266 | 17733 | 17558 | 136236 | -1497 | 1672 | 1.084 | 1.095 | 20270731 | 20270731 | 0 | 11 | 2 | 1 | 0 | 0 | 857 | 853 | 863 | -4 | 3 | 0 | 31 | 1 | 300000 | 0 | 221292 | 0 |  | 0 | 0 | 2 | 81 | 99.7
167 | 20260228 | 12 | 9 | 8 | 12 | 36 | 4 | 1 | 4 | Active | Initiate & Design | Green | 0.1905 | 0.1873 | 133266 | 23740 | 24153 | 136426 | -1221 | 808 | 1.051 | 1.033 | 20270731 | 20270731 | 2 | 11 | 2 | 1 | 0 | 0 | 934 | 889 | 868 | -45 | 4 | 0 | 41 | 1 | 300000 | 0 | 231122 | 0 |  | 0 | 0 | 2 | 77 | 96
168 | 20260331 | 12 | 9 | 8 | 12 | 36 | 4 | 1 | 4 | Active | Initiate & Design | Green | 0.2381 | 0.2285 | 133266 | 29796 | 28420 | 136617 | -655 | 2031 | 1.022 | 1.071 | 20270731 | 20270731 | 7 | 11 | 3 | 2 | 0 | 0 | 1004 | 969 | 926 | -35 | 5 | 0 | 51 | 1 | 300000 | 0 | 230864 | 0 |  | 1 | 1000 | 2 | 75 | 96.3
169 | 20260430 | 12 | 9 | 8 | 12 | 36 | 4 | 1 | 4 | Active | Initiate & Design | Green | 0.2857 | 0.2981 | 133266 | 35900 | 38149 | 136807 | -3827 | 1578 | 1.107 | 1.041 | 20270731 | 20270731 | 0 | 11 | 3 | 2 | 0 | 0 | 1064 | 1065 | 1004 | 1 | 2 | 1 | 38 | 0 | 300000 | 0 | 218629 | 0 |  | 1 | 2000 | 3 | 74 | 90.6
170 | 20260531 | 12 | 9 | 8 | 12 | 36 | 4 | 1 | 4 | Active | Deliver | Green | 0.3333 | 0.3644 | 133266 | 42053 | 46754 | 136997 | -6509 | 1808 | 1.155 | 1.039 | 20270731 | 20270731 | 0 | 11 | 4 | 3 | 0 | 0 | 1115 | 1086 | 1073 | -29 | 3 | 0 | 31 | 1 | 300000 | 0 | 231542 | 0 |  | 1 | 1000 | 2 | 85 | 100
171 | 20260630 | 12 | 9 | 8 | 12 | 36 | 4 | 1 | 4 | Active | Deliver | Green | 0.381 | 0.3978 | 133266 | 48254 | 50930 | 137188 | -4759 | 2083 | 1.099 | 1.041 | 20270731 | 20270731 | 0 | 11 | 4 | 3 | 0 | 0 | 1154 | 1211 | 1290 | 57 | 3 | 0 | 31 | 1 | 300000 | 0 | 223881 | 0 |  | 1 | 1000 | 3 | 77 | 98.8
172 | 20260731 | 12 | 9 | 8 | 12 | 36 | 4 | 1 | 4 | Active | Deliver | Green | 0.4286 | 0.4484 | 133266 | 54503 | 58252 | 137378 | -5253 | 1504 | 1.096 | 1.026 | 20270731 | 20270731 | 0 | 11 | 5 | 4 | 0 | 0 | 1180 | 1246 | 1271 | 66 | 4 | 0 | 41 | 1 | 300000 | 0 | 225785 | 0 |  | 1 | 1000 | 2 | 78 | 98.3
173 | 20260831 | 12 | 9 | 8 | 12 | 36 | 4 | 1 | 4 | Active | Deliver | Green | 0.4762 | 0.4793 | 133266 | 60801 | 61560 | 137569 | -3073 | 2314 | 1.051 | 1.038 | 20270731 | 20270731 | 0 | 11 | 5 | 5 | 0 | 0 | 1193 | 1161 | 1114 | -32 | 3 | 0 | 31 | 1 | 300000 | 0 | 228091 | 0 |  | 1 | 2000 | 3 | 77 | 96.3
174 | 20260930 | 12 | 9 | 8 | 12 | 36 | 4 | 1 | 4 | Active | Deliver | Green | 0.5238 | 0.5156 | 133266 | 67147 | 67795 | 137759 | -1565 | 917 | 1.023 | 1.014 | 20270731 | 20270731 | 6 | 11 | 6 | 5 | 0 | 0 | 1193 | 1240 | 1263 | 47 | 4 | 0 | 41 | 1 | 300000 | 0 | 224009 | 0 |  | 1 | 2000 | 3 | 73 | 94.4
175 | 20251031 | 13 | 7 | 5 | 13 | 25 | 5 | 1 | 5 | Active | Initiate & Design | Red | 0.0556 | 0 | 871275 | 44747 | 5276 | 1177189 | 44747 | -5276 | 0 | 0 | 20270331 | 20270430 | 44 | 9 | 1 | 0 | 1 | 1 | 4584 | 3844 | 3716 | -740 | 15 | 3 | 268 | 5 | 1100000 | 0 | 745523 | 0 |  | 0 | 0 | 6 | 24 | 0
176 | 20251130 | 13 | 7 | 5 | 13 | 25 | 5 | 1 | 5 | Active | Initiate & Design | Red | 0.1111 | 0.0026 | 871275 | 89924 | 5276 | 1104823 | 87659 | -3011 | 0.025 | 0.428 | 20270331 | 20270630 | 87 | 9 | 1 | 0 | 1 | 1 | 5242 | 4592 | 4767 | -650 | 13 | 3 | 239 | 4 | 1100000 | 0 | 765202 | 0 |  | 1 | 8000 | 7 | 24 | 0.9
177 | 20251231 | 13 | 7 | 5 | 13 | 25 | 5 | 1 | 5 | Active | Initiate & Design | Red | 0.1667 | 0.0284 | 871275 | 135532 | 28407 | 1029831 | 110788 | -3663 | 0.182 | 0.87 | 20270331 | 20270731 | 110 | 9 | 2 | 0 | 1 | 1 | 5859 | 4755 | 4470 | -1104 | 12 | 3 | 225 | 4 | 1100000 | 0 | 771286 | 0 |  | 1 | 8000 | 5 | 24 | 22.1
178 | 20260131 | 13 | 7 | 5 | 13 | 25 | 5 | 1 | 5 | Active | Initiate & Design | Red | 0.2222 | 0.0802 | 871275 | 181569 | 62445 | 1014551 | 111693 | 7431 | 0.385 | 1.119 | 20270331 | 20270731 | 113 | 9 | 2 | 1 | 1 | 1 | 6416 | 4892 | 4922 | -1524 | 12 | 3 | 225 | 4 | 1100000 | 0 | 789257 | 0 |  | 1 | 13000 | 4 | 38 | 39.3
179 | 20260228 | 13 | 7 | 5 | 13 | 25 | 5 | 1 | 5 | Active | Initiate & Design | Red | 0.2778 | 0.1431 | 871275 | 228037 | 123399 | 1024232 | 103358 | 1280 | 0.547 | 1.01 | 20270331 | 20270731 | 107 | 9 | 3 | 0 | 2 | 1 | 6898 | 5676 | 5486 | -1222 | 12 | 3 | 225 | 4 | 1100000 | 0 | 743155 | 0 |  | 1 | 9000 | 6 | 41 | 43
180 | 20260331 | 13 | 7 | 5 | 13 | 25 | 5 | 1 | 5 | Active | Initiate & Design | Amber | 0.3333 | 0.1932 | 871275 | 274936 | 166392 | 1033913 | 106606 | 1938 | 0.612 | 1.012 | 20270331 | 20270731 | 112 | 9 | 3 | 1 | 2 | 1 | 7288 | 5788 | 5705 | -1500 | 10 | 2 | 178 | 3 | 1100000 | 0 | 769825 | 0 |  | 1 | 9000 | 5 | 46 | 54
181 | 20260430 | 13 | 7 | 5 | 13 | 25 | 5 | 1 | 5 | Active | Initiate & Design | Amber | 0.3889 | 0.2377 | 871275 | 322264 | 205687 | 1043594 | 115162 | 1415 | 0.643 | 1.007 | 20270331 | 20270731 | 120 | 9 | 4 | 0 | 3 | 2 | 7576 | 6350 | 6206 | -1226 | 11 | 3 | 211 | 4 | 1100000 | 0 | 780595 | 0 |  | 1 | 12000 | 8 | 39 | 48.5
182 | 20260531 | 13 | 7 | 5 | 13 | 25 | 5 | 1 | 5 | Active | Initiate & Design | Amber | 0.4444 | 0.278 | 871275 | 370023 | 248793 | 1058365 | 127809 | -6579 | 0.655 | 0.973 | 20270331 | 20270731 | 132 | 9 | 4 | 1 | 2 | 1 | 7752 | 6804 | 7166 | -948 | 12 | 3 | 225 | 4 | 1100000 | 0 | 754581 | 0 |  | 1 | 9000 | 7 | 41 | 48
183 | 20260630 | 13 | 7 | 5 | 13 | 25 | 5 | 1 | 5 | Active | Initiate & Design | Red | 0.5 | 0.31 | 871275 | 418212 | 288859 | 1075414 | 148117 | -18764 | 0.646 | 0.935 | 20270331 | 20270831 | 151 | 9 | 5 | 1 | 3 | 2 | 7811 | 6241 | 5971 | -1570 | 11 | 3 | 211 | 4 | 1100000 | 0 | 789070 | 0 |  | 1 | 13000 | 7 | 41 | 45.4
184 | 20260731 | 13 | 7 | 5 | 13 | 25 | 5 | 1 | 5 | Active | Deliver | Amber | 0.5556 | 0.3612 | 871275 | 466831 | 339869 | 1086817 | 152126 | -25164 | 0.674 | 0.926 | 20270331 | 20270831 | 154 | 9 | 5 | 1 | 3 | 2 | 7752 | 6064 | 6110 | -1688 | 10 | 2 | 178 | 3 | 1100000 | 0 | 766513 | 0 |  | 1 | 12000 | 7 | 46 | 53.5
185 | 20260831 | 13 | 7 | 5 | 13 | 25 | 5 | 1 | 5 | Active | Deliver | Amber | 0.6111 | 0.3856 | 871275 | 515881 | 367446 | 1098756 | 179917 | -31482 | 0.651 | 0.914 | 20270331 | 20270930 | 179 | 9 | 6 | 2 | 4 | 2 | 7576 | 5763 | 5420 | -1813 | 9 | 2 | 164 | 3 | 1100000 | 0 | 781954 | 0 |  | 2 | 17000 | 7 | 41 | 51.9
186 | 20260930 | 13 | 7 | 5 | 13 | 25 | 5 | 1 | 5 | Active | Deliver | Amber | 0.6667 | 0.4305 | 871275 | 565361 | 410255 | 1108437 | 190277 | -35171 | 0.663 | 0.914 | 20270331 | 20270930 | 188 | 9 | 6 | 1 | 4 | 2 | 7288 | 6288 | 6635 | -1000 | 11 | 2 | 193 | 4 | 1100000 | 0 | 747067 | 0 |  | 2 | 28000 | 8 | 46 | 53.8
187 | 20231031 | 14 | 4 | 3 | 14 | 26 | 6 | 1 | 6 | Active | Initiate & Design | Green | 0.1667 | 0.1142 | 2247892 | 349672 | 255652 | 2420230 | 92963 | 1057 | 0.734 | 1.004 | 20240831 | 20240930 | 26 | 6 | 1 | 0 | 0 | 0 | 15115 | 14501 | 13788 | -614 | 8 | 1 | 119 | 2 | 2500000 | 0 | 2191854 | 0 |  | 0 | 0 | 9 | 64 | 75.8
188 | 20231130 | 14 | 4 | 3 | 14 | 26 | 6 | 1 | 6 | Active | Initiate & Design | Green | 0.25 | 0.2018 | 2247892 | 528255 | 416909 | 2438963 | 74630 | 36716 | 0.859 | 1.088 | 20240831 | 20240930 | 23 | 6 | 2 | 0 | 1 | 0 | 17202 | 16777 | 16103 | -425 | 8 | 1 | 119 | 2 | 2500000 | 0 | 2283132 | 0 |  | 0 | 0 | 8 | 73 | 85.8
189 | 20231231 | 14 | 4 | 3 | 14 | 26 | 6 | 1 | 6 | Active | Initiate & Design | Green | 0.3333 | 0.2883 | 2247892 | 709335 | 634688 | 2457695 | 61268 | 13379 | 0.914 | 1.021 | 20240831 | 20240930 | 22 | 6 | 2 | 1 | 0 | 0 | 18803 | 18558 | 17757 | -245 | 7 | 1 | 106 | 2 | 2500000 | 0 | 2233875 | 0 |  | 1 | 24000 | 8 | 75 | 85.6
190 | 20240131 | 14 | 4 | 3 | 14 | 26 | 6 | 1 | 6 | Active | Deliver | Green | 0.4167 | 0.3893 | 2247892 | 892913 | 857346 | 2476428 | 17809 | 17758 | 0.98 | 1.021 | 20240831 | 20240831 | 13 | 6 | 3 | 3 | 0 | 0 | 19810 | 19095 | 20204 | -715 | 7 | 1 | 106 | 2 | 2500000 | 0 | 2219113 | 0 |  | 1 | 34000 | 9 | 74 | 87.9
191 | 20240229 | 14 | 4 | 3 | 14 | 26 | 6 | 1 | 6 | Active | Deliver | Green | 0.5 | 0.4657 | 2247892 | 1078988 | 1071775 | 2506621 | 32145 | -24932 | 0.97 | 0.977 | 20240831 | 20240930 | 16 | 6 | 3 | 3 | 0 | 0 | 20154 | 20064 | 19900 | -90 | 8 | 1 | 119 | 2 | 2500000 | 0 | 2311143 | 0 |  | 2 | 56000 | 9 | 72 | 87.6
192 | 20240331 | 14 | 4 | 3 | 14 | 26 | 6 | 1 | 6 | Active | Deliver | Green | 0.5833 | 0.5521 | 2247892 | 1267561 | 1272751 | 2526211 | 26500 | -31690 | 0.979 | 0.975 | 20240831 | 20240930 | 15 | 6 | 4 | 4 | 0 | 0 | 19810 | 19572 | 19234 | -238 | 6 | 1 | 94 | 2 | 2500000 | 0 | 2305122 | 0 |  | 2 | 56000 | 6 | 77 | 87.7
193 | 20240430 | 14 | 4 | 3 | 14 | 26 | 6 | 1 | 6 | Active | Deliver | Green | 0.6667 | 0.6261 | 2247892 | 1458632 | 1486102 | 2558800 | 51227 | -78697 | 0.965 | 0.947 | 20240831 | 20240930 | 20 | 6 | 4 | 3 | 0 | 0 | 18803 | 17198 | 17163 | -1605 | 7 | 1 | 106 | 2 | 2500000 | 0 | 2241830 | 0 |  | 2 | 65000 | 9 | 77 | 83.8
194 | 20240531 | 14 | 4 | 3 | 14 | 26 | 6 | 1 | 6 | Active | Deliver | Green | 0.75 | 0.6841 | 2247892 | 1652201 | 1638919 | 2581901 | 114418 | -101136 | 0.931 | 0.938 | 20240831 | 20240930 | 32 | 6 | 5 | 4 | 1 | 0 | 17202 | 15393 | 16047 | -1809 | 7 | 1 | 106 | 2 | 2500000 | 267857 | 2207967 | 0 | 0 | 2 | 56000 | 10 | 76 | 81.1
195 | 20240630 | 14 | 4 | 3 | 14 | 26 | 6 | 1 | 6 | Active | Deploy | Green | 0.8333 | 0.7636 | 2247892 | 1848267 | 1873983 | 2611654 | 131777 | -157493 | 0.929 | 0.916 | 20240831 | 20240930 | 34 | 6 | 5 | 3 | 1 | 0 | 15115 | 14335 | 13807 | -780 | 4 | 0 | 51 | 1 | 2500000 | 1011905 | 2227940 | 360961 | 0.3567 | 2 | 65000 | 6 | 78 | 89.7
196 | 20240731 | 14 | 4 | 3 | 14 | 26 | 6 | 1 | 6 | Active | Deploy | Green | 0.9167 | 0.8399 | 2247892 | 2046831 | 2081404 | 2634775 | 158827 | -193400 | 0.922 | 0.907 | 20240831 | 20240930 | 38 | 6 | 6 | 4 | 1 | 0 | 12685 | 11573 | 10892 | -1112 | 5 | 1 | 81 | 1 | 2500000 | 1755952 | 2265136 | 922151 | 0.5252 | 2 | 42000 | 6 | 71 | 80.7
197 | 20240831 | 14 | 4 | 3 | 14 | 26 | 6 | 1 | 6 | Active | Deploy | Green | 1 | 0.9154 | 2247892 | 2247892 | 2308410 | 2661238 | 190172 | -250690 | 0.915 | 0.891 | 20240831 | 20240930 | 40 | 6 | 6 | 4 | 1 | 0 | 10077 | 9013 | 9075 | -1064 | 5 | 1 | 81 | 1 | 2500000 | 2500000 | 2274160 | 1628752 | 0.6515 | 2 | 55000 | 4 | 72 | 79.5
198 | 20240930 | 14 | 4 | 3 | 14 | 26 | 6 | 1 | 6 | Active | Deploy | Green | 1 | 0.9384 | 2247892 | 2247892 | 2406400 | 2687320 | 138470 | -296978 | 0.938 | 0.877 | 20240831 | 20240930 | 30 | 6 | 6 | 4 | 1 | 0 | 10077 | 9194 | 9551 | -883 | 5 | 1 | 81 | 1 | 2500000 | 2500000 | 2243136 | 1968817 | 0.7875 | 2 | 57000 | 7 | 70 | 80.1
199 | 20241031 | 14 | 4 | 3 | 14 | 26 | 6 | 1 | 6 | Active | Deploy | Green | 1 | 0.9389 | 2247892 | 2247892 | 2450263 | 2713606 | 137346 | -339717 | 0.939 | 0.861 | 20240831 | 20240930 | 30 | 6 | 6 | 4 | 1 | 0 | 10077 | 9858 | 9540 | -219 | 6 | 1 | 94 | 2 | 2500000 | 2500000 | 2243171 | 1979681 | 0.7919 | 2 | 42000 | 5 | 71 | 81
200 | 20241130 | 14 | 4 | 3 | 14 | 26 | 6 | 1 | 6 | Active | Deploy | Green | 1 | 0.9389 | 2247892 | 2247892 | 2478935 | 2737265 | 137346 | -368389 | 0.939 | 0.851 | 20240831 | 20240930 | 30 | 6 | 6 | 4 | 1 | 0 | 10077 | 9615 | 9777 | -462 | 5 | 1 | 81 | 1 | 2500000 | 2500000 | 2305587 | 2252473 | 0.901 | 2 | 48000 | 8 | 67 | 80.9
201 | 20241231 | 14 | 4 | 3 | 14 | 26 | 6 | 1 | 6 | Active | Deploy | Green | 1 | 0.9389 | 2247892 | 2247892 | 2537163 | 2765660 | 137346 | -426617 | 0.939 | 0.832 | 20240831 | 20240930 | 30 | 6 | 6 | 4 | 1 | 0 | 10077 | 9257 | 8790 | -820 | 6 | 1 | 94 | 2 | 2500000 | 2500000 | 2299276 | 2173526 | 0.8694 | 3 | 75000 | 6 | 67 | 79.3
202 | 20250131 | 14 | 4 | 3 | 14 | 26 | 6 | 1 | 6 | Active | Deploy | Green | 1 | 0.9389 | 2247892 | 2247892 | 2559540 | 2773003 | 137346 | -448994 | 0.939 | 0.825 | 20240831 | 20240930 | 30 | 6 | 6 | 4 | 1 | 0 | 10077 | 9280 | 8800 | -797 | 4 | 1 | 69 | 1 | 2500000 | 2500000 | 2263654 | 2236029 | 0.8944 | 3 | 80000 | 8 | 70 | 78.7
203 | 20250228 | 14 | 4 | 3 | 14 | 26 | 6 | 1 | 6 | Active | Deploy | Green | 1 | 0.9389 | 2247892 | 2247892 | 2559540 | 2773003 | 137346 | -448994 | 0.939 | 0.825 | 20240831 | 20240930 | 30 | 6 | 6 | 4 | 1 | 0 | 10077 | 9270 | 9527 | -807 | 4 | 1 | 69 | 1 | 2500000 | 2500000 | 2288185 | 2192212 | 0.8769 | 3 | 65000 | 8 | 67 | 79
204 | 20250331 | 14 | 4 | 3 | 14 | 26 | 6 | 1 | 6 | Active | Deploy | Green | 1 | 0.9389 | 2247892 | 2247892 | 2559540 | 2773003 | 137346 | -448994 | 0.939 | 0.825 | 20240831 | 20240930 | 30 | 6 | 6 | 4 | 1 | 0 | 10077 | 9627 | 9241 | -450 | 6 | 1 | 94 | 2 | 2500000 | 2500000 | 2293352 | 2065630 | 0.8263 | 3 | 79000 | 6 | 66 | 79.8
205 | 20250430 | 14 | 4 | 3 | 14 | 26 | 6 | 1 | 6 | Active | Deploy | Green | 1 | 0.9389 | 2247892 | 2247892 | 2559540 | 2773003 | 137346 | -448994 | 0.939 | 0.825 | 20240831 | 20240930 | 30 | 6 | 6 | 5 | 1 | 0 | 10077 | 9387 | 9274 | -690 | 4 | 1 | 69 | 1 | 2500000 | 2500000 | 2265046 | 2061606 | 0.8246 | 3 | 59000 | 6 | 68 | 79
206 | 20250531 | 14 | 4 | 3 | 14 | 26 | 6 | 1 | 6 | Active | Deploy | Green | 1 | 0.9389 | 2247892 | 2247892 | 2559540 | 2773003 | 137346 | -448994 | 0.939 | 0.825 | 20240831 | 20240930 | 30 | 6 | 6 | 4 | 1 | 0 | 10077 | 9135 | 9494 | -942 | 6 | 1 | 94 | 2 | 2500000 | 2500000 | 2311691 | 2158848 | 0.8635 | 3 | 88000 | 6 | 65 | 78.9
207 | 20250630 | 14 | 4 | 3 | 14 | 26 | 6 | 1 | 6 | Active | Deploy | Green | 1 | 0.9389 | 2247892 | 2247892 | 2559540 | 2773003 | 137346 | -448994 | 0.939 | 0.825 | 20240831 | 20240930 | 30 | 6 | 6 | 5 | 1 | 0 | 10077 | 9142 | 8844 | -935 | 4 | 1 | 69 | 1 | 2500000 | 2500000 | 2235397 | 2102820 | 0.8411 | 3 | 82000 | 4 | 66 | 78.1
208 | 20250831 | 15 | 8 | 6 | 15 | 27 | 7 | 2 | 7 | Active | Initiate & Design | Green | 0.0476 | 0.0278 | 1572449 | 69173 | 43465 | 1582632 | 25459 | 249 | 0.633 | 1.007 | 20270430 | 20270430 | 13 | 11 | 1 | 0 | 1 | 0 | 8099 | 8574 | 8581 | 475 | 5 | 0 | 48 | 1 | 4200000 | 0 | 4318674 | 0 |  | 1 | 20000 | 7 | 69 | 83.7
209 | 20250930 | 15 | 8 | 6 | 15 | 27 | 7 | 2 | 7 | Active | Initiate & Design | Green | 0.0952 | 0.0892 | 1572449 | 138917 | 138426 | 1583381 | -1345 | 1836 | 1.01 | 1.014 | 20270430 | 20270430 | 4 | 11 | 1 | 0 | 0 | 0 | 9127 | 9799 | 9446 | 672 | 3 | 0 | 29 | 1 | 4200000 | 0 | 4238188 | 0 |  | 1 | 17000 | 7 | 80 | 100
210 | 20251031 | 15 | 8 | 6 | 15 | 27 | 7 | 2 | 7 | Active | Initiate & Design | Green | 0.1429 | 0.1526 | 1572449 | 209232 | 218740 | 1584130 | -30724 | 21216 | 1.147 | 1.097 | 20270430 | 20270430 | 0 | 11 | 2 | 1 | 0 | 0 | 10107 | 9841 | 9852 | -266 | 1 | 0 | 10 | 0 | 4200000 | 0 | 4252173 | 0 |  | 1 | 20000 | 7 | 91 | 100
211 | 20251130 | 15 | 8 | 6 | 15 | 27 | 7 | 2 | 7 | Active | Initiate & Design | Green | 0.1905 | 0.1975 | 1572449 | 280117 | 293724 | 1584879 | -30442 | 16835 | 1.108 | 1.057 | 20270430 | 20270430 | 0 | 11 | 2 | 2 | 0 | 0 | 11020 | 11468 | 11305 | 448 | 2 | 0 | 19 | 0 | 4200000 | 0 | 4228340 | 0 |  | 1 | 21000 | 6 | 85 | 100
212 | 20251231 | 15 | 8 | 6 | 15 | 27 | 7 | 2 | 7 | Active | Initiate & Design | Green | 0.2381 | 0.2734 | 1572449 | 351572 | 402104 | 1585628 | -78336 | 27804 | 1.223 | 1.069 | 20270430 | 20270430 | 0 | 11 | 3 | 3 | 0 | 0 | 11843 | 12093 | 11526 | 250 | 2 | 0 | 19 | 0 | 4200000 | 0 | 4295864 | 0 |  | 1 | 23000 | 6 | 91 | 100
213 | 20260131 | 15 | 8 | 6 | 15 | 27 | 7 | 2 | 7 | Active | Initiate & Design | Green | 0.2857 | 0.3151 | 1572449 | 423599 | 462727 | 1586376 | -71880 | 32752 | 1.17 | 1.071 | 20270430 | 20270430 | 0 | 11 | 3 | 3 | 0 | 0 | 12560 | 12266 | 12468 | -294 | 2 | 0 | 19 | 0 | 4200000 | 0 | 4321524 | 0 |  | 1 | 21000 | 7 | 89 | 100
214 | 20260228 | 15 | 8 | 6 | 15 | 27 | 7 | 2 | 7 | Active | Deliver | Green | 0.3333 | 0.3569 | 1572449 | 496195 | 526613 | 1587125 | -65012 | 34594 | 1.131 | 1.066 | 20270430 | 20270430 | 0 | 11 | 4 | 3 | 0 | 0 | 13153 | 13489 | 14281 | 336 | 1 | 0 | 10 | 0 | 4200000 | 0 | 4328433 | 0 |  | 1 | 20000 | 8 | 90 | 100
215 | 20260331 | 15 | 8 | 6 | 15 | 27 | 7 | 2 | 7 | Active | Deliver | Green | 0.381 | 0.3868 | 1572449 | 569362 | 586850 | 1587874 | -38861 | 21373 | 1.068 | 1.036 | 20270430 | 20270430 | 0 | 11 | 4 | 4 | 0 | 0 | 13611 | 13110 | 12930 | -501 | 3 | 0 | 29 | 1 | 4200000 | 0 | 4217798 | 0 |  | 1 | 13000 | 5 | 89 | 100
216 | 20260430 | 15 | 8 | 6 | 15 | 27 | 7 | 2 | 7 | Active | Deliver | Green | 0.4286 | 0.4294 | 1572449 | 643100 | 643152 | 1588623 | -32110 | 32058 | 1.05 | 1.05 | 20270430 | 20270430 | 0 | 11 | 5 | 5 | 0 | 0 | 13921 | 14130 | 13643 | 209 | 1 | 0 | 10 | 0 | 4200000 | 0 | 4281659 | 0 |  | 1 | 14000 | 5 | 82 | 100
217 | 20260531 | 15 | 8 | 6 | 15 | 27 | 7 | 2 | 7 | Active | Deliver | Green | 0.4762 | 0.476 | 1572449 | 717408 | 708785 | 1589372 | -31078 | 39701 | 1.043 | 1.056 | 20270430 | 20270430 | 0 | 11 | 5 | 4 | 0 | 0 | 14078 | 14094 | 14461 | 16 | 3 | 0 | 29 | 1 | 4200000 | 0 | 4355002 | 0 |  | 1 | 14000 | 5 | 87 | 100
218 | 20260630 | 15 | 8 | 6 | 15 | 27 | 7 | 2 | 7 | Active | Deliver | Green | 0.5238 | 0.5103 | 1572449 | 792286 | 774858 | 1590120 | -10135 | 27563 | 1.013 | 1.036 | 20270430 | 20270430 | 10 | 11 | 6 | 5 | 0 | 0 | 14078 | 14373 | 14575 | 295 | 4 | 0 | 38 | 1 | 4200000 | 0 | 4275298 | 0 |  | 1 | 23000 | 6 | 81 | 100
219 | 20260731 | 15 | 8 | 6 | 15 | 27 | 7 | 2 | 7 | Active | Deliver | Green | 0.5714 | 0.5732 | 1572449 | 867735 | 869022 | 1590869 | -33593 | 32306 | 1.039 | 1.037 | 20270430 | 20270430 | 0 | 11 | 6 | 5 | 0 | 0 | 13921 | 13761 | 14514 | -160 | 3 | 0 | 29 | 1 | 4200000 | 0 | 4385621 | 0 |  | 1 | 15000 | 7 | 82 | 100
220 | 20260831 | 15 | 8 | 6 | 15 | 27 | 7 | 2 | 7 | Active | Deliver | Green | 0.619 | 0.6504 | 1572449 | 943755 | 998129 | 1591618 | -78966 | 24592 | 1.084 | 1.025 | 20270430 | 20270430 | 0 | 11 | 7 | 7 | 0 | 0 | 13611 | 13207 | 13705 | -404 | 1 | 0 | 10 | 0 | 4200000 | 0 | 4351968 | 0 |  | 1 | 17000 | 8 | 86 | 100
221 | 20260930 | 15 | 8 | 6 | 15 | 27 | 7 | 2 | 7 | Active | Deliver | Green | 0.6667 | 0.6848 | 1572449 | 1020345 | 1073237 | 1592367 | -56468 | 3576 | 1.055 | 1.003 | 20270430 | 20270430 | 0 | 11 | 7 | 7 | 0 | 0 | 13153 | 12678 | 13111 | -475 | 1 | 0 | 10 | 0 | 4200000 | 0 | 4195646 | 0 |  | 1 | 13000 | 7 | 81 | 100
222 | 20250131 | 16 | 5 | 5 | 16 | 28 | 8 | 2 | 8 | Active | Initiate & Design | Green | 0.0417 | 0.0556 | 1574145 | 60561 | 87749 | 1605584 | -26961 | -227 | 1.444 | 0.997 | 20261231 | 20261231 | 0 | 12 | 1 | 0 | 0 | 0 | 7978 | 8761 | 9145 | 783 | 1 | 0 | 9 | 0 | 3200000 | 0 | 3483395 | 0 |  | 0 | 0 | 7 | 96 | 100
223 | 20250228 | 16 | 5 | 5 | 16 | 28 | 8 | 2 | 8 | Active | Initiate & Design | Green | 0.0833 | 0.1065 | 1574145 | 121559 | 156949 | 1606415 | -46087 | 10697 | 1.379 | 1.068 | 20261231 | 20261231 | 0 | 12 | 1 | 1 | 0 | 0 | 8883 | 9466 | 9081 | 583 | 0 | 0 | 0 | 0 | 3200000 | 0 | 3459037 | 0 |  | 0 | 0 | 4 | 96 | 100
224 | 20250331 | 16 | 5 | 5 | 16 | 28 | 8 | 2 | 8 | Active | Initiate & Design | Green | 0.125 | 0.1722 | 1574145 | 182994 | 245345 | 1608383 | -88074 | 25723 | 1.481 | 1.105 | 20261231 | 20261231 | 0 | 12 | 2 | 1 | 0 | 0 | 9757 | 10327 | 10346 | 570 | 0 | 0 | 0 | 0 | 3200000 | 0 | 3496796 | 0 |  | 0 | 0 | 4 | 96 | 100
225 | 20250430 | 16 | 5 | 5 | 16 | 28 | 8 | 2 | 8 | Active | Initiate & Design | Green | 0.1667 | 0.2213 | 1574145 | 244867 | 332868 | 1610350 | -103491 | 15490 | 1.423 | 1.047 | 20261231 | 20261231 | 0 | 12 | 2 | 2 | 0 | 0 | 10585 | 11071 | 11587 | 486 | 0 | 0 | 0 | 0 | 3200000 | 0 | 3457389 | 0 |  | 0 | 0 | 7 | 96 | 100
226 | 20250531 | 16 | 5 | 5 | 16 | 28 | 8 | 2 | 8 | Active | Initiate & Design | Green | 0.2083 | 0.2519 | 1574145 | 307177 | 359714 | 1612318 | -89350 | 36813 | 1.291 | 1.103 | 20261231 | 20261231 | 0 | 12 | 3 | 3 | 0 | 0 | 11352 | 12701 | 12261 | 1349 | 1 | 0 | 9 | 0 | 3200000 | 0 | 3410215 | 0 |  | 0 | 0 | 7 | 96 | 100
227 | 20250630 | 16 | 5 | 5 | 16 | 28 | 8 | 2 | 8 | Active | Initiate & Design | Green | 0.25 | 0.3037 | 1574145 | 369924 | 457941 | 1614286 | -108144 | 20127 | 1.292 | 1.044 | 20261231 | 20261231 | 0 | 12 | 3 | 2 | 0 | 0 | 12046 | 13066 | 13032 | 1020 | 0 | 0 | 0 | 0 | 3200000 | 0 | 3519291 | 0 |  | 0 | 0 | 7 | 96 | 100
228 | 20250731 | 16 | 5 | 5 | 16 | 28 | 8 | 2 | 8 | Active | Initiate & Design | Green | 0.2917 | 0.3177 | 1574145 | 433109 | 480972 | 1616253 | -66997 | 19134 | 1.155 | 1.04 | 20261231 | 20261231 | 0 | 12 | 4 | 3 | 0 | 0 | 12655 | 13314 | 13479 | 659 | 1 | 0 | 9 | 0 | 3200000 | 0 | 3395292 | 0 |  | 0 | 0 | 6 | 92 | 100
229 | 20250831 | 16 | 5 | 5 | 16 | 28 | 8 | 2 | 8 | Active | Deliver | Green | 0.3333 | 0.3608 | 1574145 | 496730 | 544835 | 1618221 | -71222 | 23117 | 1.143 | 1.043 | 20261231 | 20261231 | 0 | 12 | 4 | 4 | 0 | 0 | 13168 | 14613 | 14660 | 1445 | 3 | 0 | 27 | 0 | 3200000 | 0 | 3439908 | 0 |  | 0 | 0 | 4 | 87 | 100
230 | 20250930 | 16 | 5 | 5 | 16 | 28 | 8 | 2 | 8 | Active | Deliver | Green | 0.375 | 0.4132 | 1574145 | 560789 | 622997 | 1620189 | -89648 | 27440 | 1.16 | 1.044 | 20261231 | 20261231 | 0 | 12 | 5 | 4 | 0 | 0 | 13576 | 14173 | 13502 | 597 | 2 | 0 | 18 | 0 | 3200000 | 0 | 3401292 | 0 |  | 0 | 0 | 4 | 92 | 100
231 | 20251031 | 16 | 5 | 5 | 16 | 28 | 8 | 2 | 8 | Active | Deliver | Green | 0.4167 | 0.4596 | 1574145 | 625285 | 707539 | 1622156 | -98192 | 15938 | 1.157 | 1.023 | 20261231 | 20261231 | 0 | 12 | 5 | 4 | 0 | 0 | 13873 | 14541 | 13935 | 668 | 1 | 0 | 9 | 0 | 3200000 | 0 | 3452191 | 0 |  | 0 | 0 | 5 | 89 | 100
232 | 20251130 | 16 | 5 | 5 | 16 | 28 | 8 | 2 | 8 | Active | Deliver | Green | 0.4583 | 0.5198 | 1574145 | 690219 | 798886 | 1624124 | -128022 | 19355 | 1.185 | 1.024 | 20261231 | 20261231 | 0 | 12 | 6 | 6 | 0 | 0 | 14053 | 15161 | 16047 | 1108 | 0 | 0 | 0 | 0 | 3200000 | 0 | 3432114 | 0 |  | 1 | 14000 | 7 | 94 | 100
233 | 20251231 | 16 | 5 | 5 | 16 | 28 | 8 | 2 | 8 | Active | Deliver | Green | 0.5 | 0.5637 | 1574145 | 755590 | 863262 | 1626092 | -131756 | 24084 | 1.174 | 1.028 | 20261231 | 20261231 | 0 | 12 | 6 | 6 | 0 | 0 | 14113 | 15746 | 14929 | 1633 | 2 | 0 | 18 | 0 | 3200000 | 0 | 3401165 | 0 |  | 1 | 18000 | 7 | 91 | 100
234 | 20260131 | 16 | 5 | 5 | 16 | 28 | 8 | 2 | 8 | Active | Deliver | Green | 0.5417 | 0.6205 | 1574145 | 821398 | 948898 | 1628059 | -155359 | 27859 | 1.189 | 1.029 | 20261231 | 20261231 | 0 | 12 | 7 | 7 | 0 | 0 | 14053 | 15907 | 15934 | 1854 | 0 | 0 | 0 | 0 | 3200000 | 0 | 3447515 | 0 |  | 1 | 15000 | 6 | 90 | 100
235 | 20260228 | 16 | 5 | 5 | 16 | 28 | 8 | 2 | 8 | Active | Deliver | Green | 0.5833 | 0.6688 | 1574145 | 887643 | 1042401 | 1630027 | -165145 | 10387 | 1.186 | 1.01 | 20261231 | 20261231 | 0 | 12 | 7 | 7 | 0 | 0 | 13873 | 14598 | 14923 | 725 | 3 | 0 | 27 | 0 | 3200000 | 0 | 3408070 | 0 |  | 1 | 20000 | 5 | 89 | 100
236 | 20260331 | 16 | 5 | 5 | 16 | 28 | 8 | 2 | 8 | Active | Deliver | Green | 0.625 | 0.7089 | 1574145 | 954325 | 1114030 | 1631995 | -161586 | 1881 | 1.169 | 1.002 | 20261231 | 20261231 | 0 | 12 | 8 | 8 | 0 | 0 | 13576 | 13928 | 14447 | 352 | 0 | 0 | 0 | 0 | 3200000 | 0 | 3467236 | 0 |  | 1 | 23000 | 5 | 89 | 100
237 | 20260430 | 16 | 5 | 5 | 16 | 28 | 8 | 2 | 8 | Active | Deliver | Green | 0.6667 | 0.7316 | 1574145 | 1021445 | 1144624 | 1633963 | -130199 | 7020 | 1.128 | 1.006 | 20261231 | 20261231 | 0 | 12 | 8 | 7 | 0 | 0 | 13168 | 13516 | 12808 | 348 | 2 | 0 | 18 | 0 | 3200000 | 0 | 3508301 | 0 |  | 1 | 19000 | 6 | 85 | 100
238 | 20260531 | 16 | 5 | 5 | 16 | 28 | 8 | 2 | 8 | Active | Deploy | Green | 0.7083 | 0.7759 | 1574145 | 1089002 | 1236567 | 1640163 | -132377 | -15188 | 1.122 | 0.988 | 20261231 | 20261231 | 0 | 12 | 9 | 9 | 0 | 0 | 12655 | 13832 | 14131 | 1177 | 2 | 0 | 18 | 0 | 3200000 | 0 | 3526250 | 0 |  | 1 | 21000 | 6 | 85 | 100
239 | 20260630 | 16 | 5 | 5 | 16 | 28 | 8 | 2 | 8 | Active | Deploy | Green | 0.75 | 0.8197 | 1574145 | 1156997 | 1306273 | 1642119 | -133330 | -15946 | 1.115 | 0.988 | 20261231 | 20261231 | 0 | 12 | 9 | 8 | 0 | 0 | 12046 | 12549 | 13044 | 503 | 3 | 0 | 27 | 0 | 3200000 | 342857 | 3498468 | 0 | 0 | 1 | 24000 | 4 | 84 | 100
240 | 20260731 | 16 | 5 | 5 | 16 | 28 | 8 | 2 | 8 | Active | Deploy | Green | 0.7917 | 0.8562 | 1574145 | 1225428 | 1378310 | 1647522 | -122355 | -30527 | 1.1 | 0.978 | 20261231 | 20261231 | 0 | 12 | 10 | 10 | 0 | 0 | 11352 | 12506 | 12610 | 1154 | 2 | 0 | 18 | 0 | 3200000 | 819048 | 3395142 | 128628 | 0.157 | 1 | 15000 | 6 | 85 | 100
241 | 20260831 | 16 | 5 | 5 | 16 | 28 | 8 | 2 | 8 | Active | Deploy | Green | 0.8333 | 0.916 | 1574145 | 1294297 | 1485027 | 1651902 | -147620 | -43110 | 1.114 | 0.971 | 20261231 | 20261231 | 0 | 12 | 10 | 9 | 0 | 0 | 10585 | 11419 | 11257 | 834 | 0 | 0 | 0 | 0 | 3200000 | 1295238 | 3430568 | 574267 | 0.4434 | 1 | 24000 | 5 | 84 | 100
242 | 20260930 | 16 | 5 | 5 | 16 | 28 | 8 | 2 | 8 | Active | Deploy | Green | 0.875 | 0.9734 | 1574145 | 1363603 | 1586177 | 1655567 | -168670 | -53904 | 1.124 | 0.966 | 20261231 | 20261231 | 0 | 12 | 11 | 10 | 0 | 0 | 9757 | 9959 | 9903 | 202 | 0 | 0 | 0 | 0 | 3200000 | 1771429 | 3411656 | 1019441 | 0.5755 | 1 | 24000 | 3 | 86 | 100
243 | 20231130 | 17 | 3 | 2 | 17 | 29 | 1 | 1 | 1 | Active | Initiate & Design | Amber | 0.1111 | 0.05 | 1859401 | 191909 | 97643 | 1945226 | 98939 | -4673 | 0.484 | 0.952 | 20240731 | 20240831 | 22 | 6 | 1 | 0 | 1 | 0 | 11186 | 9104 | 9414 | -2082 | 8 | 1 | 113 | 2 | 5500000 | 0 | 5168564 | 0 |  | 0 | 0 | 7 | 51 | 61.3
244 | 20231231 | 17 | 3 | 2 | 17 | 29 | 1 | 1 | 1 | Active | Initiate & Design | Amber | 0.2222 | 0.1556 | 1859401 | 387490 | 269104 | 1935843 | 98167 | 20219 | 0.746 | 1.075 | 20240731 | 20240831 | 23 | 6 | 1 | 0 | 0 | 0 | 13693 | 11116 | 11355 | -2577 | 8 | 2 | 131 | 2 | 5500000 | 0 | 5035451 | 0 |  | 0 | 0 | 8 | 66 | 68.7
245 | 20240131 | 17 | 3 | 2 | 17 | 29 | 1 | 1 | 1 | Active | Initiate & Design | Green | 0.3333 | 0.2702 | 1859401 | 586744 | 466794 | 1946173 | 84334 | 35616 | 0.856 | 1.076 | 20240731 | 20240831 | 22 | 6 | 2 | 1 | 1 | 0 | 15554 | 12647 | 12255 | -2907 | 8 | 1 | 113 | 2 | 5500000 | 0 | 5298263 | 0 |  | 1 | 17000 | 5 | 72 | 83.1
246 | 20240229 | 17 | 3 | 2 | 17 | 29 | 1 | 1 | 1 | Active | Deliver | Green | 0.4444 | 0.3601 | 1859401 | 789672 | 665009 | 1956503 | 120102 | 4561 | 0.848 | 1.007 | 20240731 | 20240831 | 30 | 6 | 3 | 2 | 1 | 0 | 16544 | 13760 | 14675 | -2784 | 8 | 1 | 113 | 2 | 5500000 | 0 | 5264169 | 0 |  | 1 | 20000 | 7 | 67 | 80.5
247 | 20240331 | 17 | 3 | 2 | 17 | 29 | 1 | 1 | 1 | Active | Deliver | Green | 0.5556 | 0.4635 | 1859401 | 996272 | 847114 | 1966833 | 134440 | 14718 | 0.865 | 1.017 | 20240731 | 20240831 | 32 | 6 | 3 | 1 | 1 | 0 | 16544 | 12824 | 12853 | -3720 | 7 | 1 | 101 | 2 | 5500000 | 0 | 5300402 | 0 |  | 1 | 19000 | 9 | 71 | 80.6
248 | 20240430 | 17 | 3 | 2 | 17 | 29 | 1 | 1 | 1 | Active | Deliver | Green | 0.6667 | 0.5468 | 1859401 | 1206545 | 1042992 | 1987475 | 189825 | -26272 | 0.843 | 0.975 | 20240731 | 20240831 | 41 | 6 | 4 | 3 | 1 | 0 | 15554 | 13013 | 12795 | -2541 | 6 | 1 | 89 | 2 | 5500000 | 0 | 5055161 | 0 |  | 1 | 25000 | 6 | 68 | 78.2
249 | 20240531 | 17 | 3 | 2 | 17 | 29 | 1 | 1 | 1 | Active | Deliver | Green | 0.7778 | 0.6317 | 1859401 | 1420491 | 1209921 | 1999446 | 245907 | -35337 | 0.827 | 0.971 | 20240731 | 20240930 | 50 | 6 | 5 | 2 | 2 | 1 | 13693 | 10936 | 10985 | -2757 | 6 | 1 | 89 | 2 | 5500000 | 1134921 | 5210819 | 0 | 0 | 1 | 21000 | 8 | 66 | 77.3
250 | 20240630 | 17 | 3 | 2 | 17 | 29 | 1 | 1 | 1 | Active | Deliver | Green | 0.8889 | 0.7495 | 1859401 | 1638109 | 1459433 | 2016288 | 244488 | -65812 | 0.851 | 0.955 | 20240731 | 20240930 | 49 | 6 | 5 | 3 | 1 | 0 | 11186 | 8247 | 7828 | -2939 | 4 | 0 | 47 | 1 | 5500000 | 3317460 | 5259363 | 1786624 | 0.5386 | 2 | 33000 | 7 | 76 | 84.7
251 | 20240731 | 17 | 3 | 2 | 17 | 29 | 1 | 1 | 1 | Active | Deploy | Green | 1 | 0.8598 | 1859401 | 1859401 | 1710274 | 2034857 | 260688 | -111561 | 0.86 | 0.935 | 20240731 | 20240930 | 49 | 6 | 6 | 3 | 2 | 1 | 8335 | 6212 | 5995 | -2123 | 4 | 1 | 65 | 1 | 5500000 | 5500000 | 5247462 | 3545229 | 0.6446 | 2 | 47000 | 4 | 69 | 76.5
252 | 20240831 | 17 | 3 | 2 | 17 | 29 | 1 | 1 | 1 | Active | Deploy | Green | 1 | 0.8742 | 1859401 | 1859401 | 1772702 | 2052433 | 233913 | -147214 | 0.874 | 0.917 | 20240731 | 20240831 | 44 | 6 | 6 | 4 | 1 | 0 | 8335 | 6724 | 7125 | -1611 | 4 | 0 | 47 | 1 | 5500000 | 5500000 | 5272385 | 4751343 | 0.8639 | 2 | 54000 | 6 | 76 | 86
253 | 20240930 | 17 | 3 | 2 | 17 | 29 | 1 | 1 | 1 | Active | Deploy | Green | 1 | 0.8848 | 1859401 | 1859401 | 1825461 | 2069219 | 214203 | -180263 | 0.885 | 0.901 | 20240731 | 20240831 | 40 | 6 | 6 | 4 | 1 | 0 | 8335 | 6873 | 6731 | -1462 | 4 | 1 | 65 | 1 | 5500000 | 5500000 | 5089971 | 4883917 | 0.888 | 2 | 40000 | 7 | 67 | 77.4
254 | 20241031 | 17 | 3 | 2 | 17 | 29 | 1 | 1 | 1 | Active | Deploy | Green | 1 | 0.8962 | 1859401 | 1859401 | 1881482 | 2085908 | 193006 | -215087 | 0.896 | 0.886 | 20240731 | 20240831 | 36 | 6 | 6 | 5 | 1 | 0 | 8335 | 6643 | 6815 | -1692 | 3 | 0 | 36 | 1 | 5500000 | 5500000 | 5211347 | 4950738 | 0.9001 | 2 | 39000 | 7 | 71 | 85.4
255 | 20241130 | 17 | 3 | 2 | 17 | 29 | 1 | 1 | 1 | Active | Deploy | Green | 1 | 0.8962 | 1859401 | 1859401 | 1883697 | 2087883 | 193006 | -217302 | 0.896 | 0.885 | 20240731 | 20240831 | 36 | 6 | 6 | 5 | 1 | 0 | 8335 | 6609 | 6400 | -1726 | 5 | 0 | 59 | 1 | 5500000 | 5500000 | 5277458 | 4649013 | 0.8453 | 2 | 37000 | 4 | 73 | 85.6
256 | 20241231 | 17 | 3 | 2 | 17 | 29 | 1 | 1 | 1 | Active | Deploy | Green | 1 | 0.8962 | 1859401 | 1859401 | 1883697 | 2087883 | 193006 | -217302 | 0.896 | 0.885 | 20240731 | 20240831 | 36 | 6 | 6 | 4 | 1 | 0 | 8335 | 6861 | 7314 | -1474 | 6 | 1 | 89 | 2 | 5500000 | 5500000 | 5161730 | 4810849 | 0.8747 | 2 | 32000 | 5 | 66 | 77.7
257 | 20250131 | 17 | 3 | 2 | 17 | 29 | 1 | 1 | 1 | Active | Deploy | Green | 1 | 0.8962 | 1859401 | 1859401 | 1899616 | 2090916 | 193006 | -233221 | 0.896 | 0.877 | 20240731 | 20240831 | 36 | 6 | 6 | 5 | 1 | 0 | 8335 | 6474 | 6286 | -1861 | 3 | 0 | 36 | 1 | 5500000 | 5500000 | 5197386 | 4530840 | 0.8238 | 2 | 44000 | 7 | 71 | 84.6
258 | 20250228 | 17 | 3 | 2 | 17 | 29 | 1 | 1 | 1 | Active | Deploy | Green | 1 | 0.8962 | 1859401 | 1859401 | 1899616 | 2090916 | 193006 | -233221 | 0.896 | 0.877 | 20240731 | 20240831 | 36 | 6 | 6 | 5 | 1 | 0 | 8335 | 6815 | 6602 | -1520 | 4 | 1 | 65 | 1 | 5500000 | 5500000 | 5047397 | 4829610 | 0.8781 | 2 | 51000 | 6 | 71 | 76.7
259 | 20250331 | 17 | 3 | 2 | 17 | 29 | 1 | 1 | 1 | Active | Deploy | Green | 1 | 0.8962 | 1859401 | 1859401 | 1899616 | 2090916 | 193006 | -233221 | 0.896 | 0.877 | 20240731 | 20240831 | 36 | 6 | 6 | 4 | 1 | 0 | 8335 | 6147 | 6253 | -2188 | 5 | 0 | 59 | 1 | 5500000 | 5500000 | 5190495 | 4806074 | 0.8738 | 2 | 59000 | 6 | 73 | 83.7
260 | 20250430 | 17 | 3 | 2 | 17 | 29 | 1 | 1 | 1 | Active | Deploy | Green | 1 | 0.8962 | 1859401 | 1859401 | 1899616 | 2090916 | 193006 | -233221 | 0.896 | 0.877 | 20240731 | 20240831 | 36 | 6 | 6 | 4 | 1 | 0 | 8335 | 6166 | 5953 | -2169 | 4 | 0 | 47 | 1 | 5500000 | 5500000 | 5270854 | 4697800 | 0.8541 | 2 | 43000 | 5 | 73 | 84.1
261 | 20250531 | 17 | 3 | 2 | 17 | 29 | 1 | 1 | 1 | Active | Deploy | Green | 1 | 0.8962 | 1859401 | 1859401 | 1899616 | 2090916 | 193006 | -233221 | 0.896 | 0.877 | 20240731 | 20240831 | 36 | 6 | 6 | 4 | 1 | 0 | 8335 | 6565 | 6949 | -1770 | 6 | 1 | 89 | 2 | 5500000 | 5500000 | 5214938 | 4577353 | 0.8322 | 3 | 76000 | 7 | 68 | 76.9
262 | 20231031 | 18 | 7 | 5 | 18 | 30 | 2 | 1 | 2 | Active | Deliver | Green | 0.5 | 0.448 | 1309460 | 628541 | 584697 | 1410288 | 41903 | 1941 | 0.933 | 1.003 | 20241031 | 20241231 | 49 | 12 | 6 | 5 | 1 | 0 | 11740 | 10424 | 11025 | -1316 | 7 | 1 | 103 | 2 | 2000000 | 0 | 1900399 | 0 |  | 1 | 16000 | 5 | 74 | 85.2
263 | 20231130 | 18 | 7 | 5 | 18 | 30 | 2 | 1 | 2 | Active | Deliver | Green | 0.5417 | 0.4686 | 1309460 | 683284 | 617010 | 1415683 | 69671 | -3397 | 0.898 | 0.995 | 20241031 | 20241231 | 70 | 12 | 7 | 4 | 2 | 1 | 11690 | 11002 | 10581 | -688 | 7 | 1 | 103 | 2 | 2000000 | 0 | 1958890 | 0 |  | 1 | 20000 | 4 | 70 | 85.4
264 | 20231231 | 18 | 7 | 5 | 18 | 30 | 2 | 1 | 2 | Active | Deliver | Green | 0.5833 | 0.5028 | 1309460 | 738390 | 663583 | 1420204 | 79994 | -5187 | 0.892 | 0.992 | 20241031 | 20250131 | 76 | 12 | 7 | 4 | 2 | 1 | 11540 | 10780 | 10688 | -760 | 6 | 1 | 91 | 2 | 2000000 | 0 | 1926909 | 0 |  | 1 | 19000 | 3 | 71 | 84.4
265 | 20240131 | 18 | 7 | 5 | 18 | 30 | 2 | 1 | 2 | Active | Deliver | Green | 0.625 | 0.5109 | 1309460 | 793860 | 682023 | 1427271 | 124857 | -13020 | 0.843 | 0.981 | 20241031 | 20250228 | 108 | 12 | 8 | 5 | 2 | 1 | 11293 | 10864 | 10455 | -429 | 7 | 1 | 103 | 2 | 2000000 | 0 | 1880925 | 0 |  | 1 | 17000 | 6 | 72 | 81.7
266 | 20240229 | 18 | 7 | 5 | 18 | 30 | 2 | 1 | 2 | Active | Deliver | Green | 0.6667 | 0.5695 | 1309460 | 849694 | 760902 | 1431291 | 103957 | -15165 | 0.878 | 0.98 | 20241031 | 20241231 | 57 | 12 | 8 | 5 | 2 | 1 | 10954 | 9554 | 9826 | -1400 | 6 | 1 | 91 | 2 | 2000000 | 0 | 1954009 | 0 |  | 1 | 19000 | 5 | 69 | 82.3
267 | 20240331 | 18 | 7 | 5 | 18 | 30 | 2 | 1 | 2 | Active | Deliver | Green | 0.7083 | 0.6348 | 1309460 | 905892 | 850335 | 1435874 | 74647 | -19090 | 0.918 | 0.977 | 20241031 | 20241130 | 35 | 12 | 9 | 6 | 2 | 1 | 10527 | 10169 | 10526 | -358 | 8 | 1 | 115 | 2 | 2000000 | 0 | 1876304 | 0 |  | 1 | 14000 | 4 | 74 | 85
268 | 20240430 | 18 | 7 | 5 | 18 | 30 | 2 | 1 | 2 | Active | Deliver | Green | 0.75 | 0.6956 | 1309460 | 962453 | 942126 | 1442779 | 51593 | -31266 | 0.946 | 0.967 | 20241031 | 20241130 | 16 | 12 | 9 | 7 | 1 | 0 | 10021 | 9259 | 9110 | -762 | 7 | 1 | 103 | 2 | 2000000 | 214286 | 1918932 | 0 | 0 | 1 | 21000 | 5 | 77 | 85.6
269 | 20240531 | 18 | 7 | 5 | 18 | 30 | 2 | 1 | 2 | Active | Deploy | Green | 0.7917 | 0.7574 | 1309460 | 1019378 | 1032379 | 1448333 | 27593 | -40594 | 0.973 | 0.961 | 20241031 | 20241031 | -2 | 12 | 10 | 8 | 1 | 0 | 9443 | 8728 | 8792 | -715 | 6 | 1 | 91 | 2 | 2000000 | 511905 | 1935047 | 71645 | 0.14 | 2 | 41000 | 5 | 75 | 86.8
270 | 20240630 | 18 | 7 | 5 | 18 | 30 | 2 | 1 | 2 | Active | Deploy | Green | 0.8333 | 0.7983 | 1309460 | 1076667 | 1111130 | 1457900 | 31325 | -65788 | 0.971 | 0.941 | 20241031 | 20241031 | -2 | 12 | 10 | 9 | 1 | 0 | 8805 | 8228 | 8716 | -577 | 3 | 0 | 36 | 1 | 2000000 | 809524 | 1912107 | 297064 | 0.367 | 2 | 41000 | 5 | 79 | 93.9
271 | 20240731 | 18 | 7 | 5 | 18 | 30 | 2 | 1 | 2 | Active | Deploy | Green | 0.875 | 0.8519 | 1309460 | 1134320 | 1187706 | 1462154 | 18791 | -72177 | 0.983 | 0.939 | 20241031 | 20241031 | -13 | 12 | 11 | 10 | 1 | 0 | 8116 | 6982 | 7322 | -1134 | 3 | 0 | 36 | 1 | 2000000 | 1107143 | 1907516 | 539473 | 0.4873 | 2 | 22000 | 4 | 82 | 92.8
272 | 20240831 | 18 | 7 | 5 | 18 | 30 | 2 | 1 | 2 | Active | Deploy | Green | 0.9167 | 0.8726 | 1309460 | 1192336 | 1222276 | 1467248 | 49701 | -79641 | 0.958 | 0.935 | 20241031 | 20241031 | 7 | 12 | 11 | 9 | 1 | 0 | 7389 | 7215 | 7395 | -174 | 6 | 1 | 91 | 2 | 2000000 | 1404762 | 1908093 | 867409 | 0.6175 | 2 | 37000 | 2 | 76 | 86
273 | 20240930 | 18 | 7 | 5 | 18 | 30 | 2 | 1 | 2 | Active | Deploy | Green | 0.9583 | 0.9113 | 1309460 | 1250716 | 1301009 | 1476154 | 57405 | -107698 | 0.954 | 0.917 | 20241031 | 20241031 | 10 | 12 | 12 | 9 | 2 | 1 | 6636 | 6031 | 6027 | -605 | 4 | 1 | 67 | 1 | 2000000 | 1702381 | 1921215 | 1101658 | 0.6471 | 2 | 29000 | 4 | 72 | 83.9
274 | 20241031 | 18 | 7 | 5 | 18 | 30 | 2 | 1 | 2 | Active | Deploy | Green | 1 | 0.9493 | 1309460 | 1309460 | 1361234 | 1481139 | 66390 | -118164 | 0.949 | 0.913 | 20241031 | 20241031 | 14 | 12 | 12 | 9 | 2 | 1 | 5870 | 5598 | 5351 | -272 | 3 | 0 | 36 | 1 | 2000000 | 2000000 | 1886487 | 1208715 | 0.6044 | 2 | 37000 | 2 | 77 | 92.1
275 | 20241130 | 18 | 7 | 5 | 18 | 30 | 2 | 1 | 2 | Active | Deploy | Green | 1 | 0.9692 | 1309460 | 1309460 | 1397443 | 1486381 | 40331 | -128314 | 0.969 | 0.908 | 20241031 | 20241031 | -6 | 12 | 12 | 11 | 1 | 0 | 5870 | 5211 | 4992 | -659 | 5 | 1 | 79 | 1 | 2000000 | 2000000 | 1904179 | 1491732 | 0.7459 | 2 | 36000 | 3 | 75 | 83.6
276 | 20241231 | 18 | 7 | 5 | 18 | 30 | 2 | 1 | 2 | Active | Deploy | Green | 1 | 0.9932 | 1309460 | 1309460 | 1437202 | 1491136 | 8904 | -136646 | 0.993 | 0.905 | 20241031 | 20241031 | -28 | 12 | 12 | 11 | 1 | 0 | 5870 | 5083 | 4839 | -787 | 5 | 1 | 79 | 1 | 2000000 | 2000000 | 1903328 | 1671874 | 0.8359 | 2 | 41000 | 3 | 71 | 84.1
277 | 20250131 | 18 | 7 | 5 | 18 | 30 | 2 | 1 | 2 | Active | Deploy | Green | 1 | 0.9932 | 1309460 | 1309460 | 1444990 | 1496360 | 8904 | -144434 | 0.993 | 0.9 | 20241031 | 20241031 | -28 | 12 | 12 | 10 | 1 | 0 | 5870 | 5185 | 5430 | -685 | 5 | 0 | 61 | 1 | 2000000 | 2000000 | 1945955 | 1942689 | 0.9713 | 2 | 22000 | 3 | 80 | 92.9
278 | 20250228 | 18 | 7 | 5 | 18 | 30 | 2 | 1 | 2 | Completed | Completed | Green | 1 | 1 | 1309460 | 1309460 | 1466916 | 1502319 | 0 | -157456 | 1 | 0.893 | 20241031 | 20241031 | -35 | 12 | 12 | 11 | 1 | 0 | 5870 | 5307 | 5523 | -563 | 3 | 1 | 54 | 1 | 2000000 | 2000000 | 1882600 | 1750927 | 0.8755 | 2 | 33000 | 3 | 71 | 84.5
279 | 20250630 | 19 | 4 | 3 | 19 | 31 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.0333 | 0.0443 | 1165330 | 35840 | 48849 | 1187471 | -15784 | 2775 | 1.44 | 1.057 | 20271130 | 20271130 | 0 | 15 | 1 | 0 | 0 | 0 | 5770 | 5861 | 5855 | 91 | 0 | 0 | 0 | 0 | 3200000 | 0 | 2367783 | 0 |  | 0 | 0 | 3 | 91 | 100
280 | 20250731 | 19 | 4 | 3 | 19 | 31 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.0667 | 0.0969 | 1165330 | 71888 | 100472 | 1188637 | -41032 | 12448 | 1.571 | 1.124 | 20271130 | 20271130 | 0 | 15 | 1 | 1 | 0 | 0 | 6310 | 6053 | 6230 | -257 | 0 | 0 | 0 | 0 | 3200000 | 0 | 2334625 | 0 |  | 1 | 12000 | 4 | 96 | 100
281 | 20250831 | 19 | 4 | 3 | 19 | 31 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.1 | 0.1098 | 1165330 | 108143 | 112791 | 1189802 | -19810 | 15162 | 1.183 | 1.135 | 20271130 | 20271130 | 0 | 15 | 2 | 1 | 0 | 0 | 6838 | 6917 | 6818 | 79 | 2 | 0 | 20 | 0 | 3200000 | 0 | 2344142 | 0 |  | 1 | 14000 | 4 | 90 | 100
282 | 20250930 | 19 | 4 | 3 | 19 | 31 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.1333 | 0.1392 | 1165330 | 144605 | 142404 | 1190967 | -17609 | 19810 | 1.122 | 1.139 | 20271130 | 20271130 | 0 | 15 | 2 | 2 | 0 | 0 | 7349 | 7140 | 7152 | -209 | 2 | 0 | 20 | 0 | 3200000 | 0 | 2367924 | 0 |  | 1 | 15000 | 5 | 81 | 100
283 | 20251031 | 19 | 4 | 3 | 19 | 31 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.1667 | 0.1496 | 1165330 | 181274 | 153681 | 1192133 | 6941 | 20652 | 0.962 | 1.135 | 20271130 | 20271231 | 18 | 15 | 3 | 2 | 0 | 0 | 7836 | 8268 | 8723 | 432 | 4 | 0 | 41 | 1 | 3200000 | 0 | 2432195 | 0 |  | 1 | 10000 | 3 | 76 | 96.3
284 | 20251130 | 19 | 4 | 3 | 19 | 31 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.2 | 0.1815 | 1165330 | 218150 | 191461 | 1193298 | 6643 | 20046 | 0.97 | 1.105 | 20271130 | 20271231 | 20 | 15 | 3 | 3 | 0 | 0 | 8294 | 8484 | 8714 | 190 | 3 | 0 | 31 | 1 | 3200000 | 0 | 2354687 | 0 |  | 1 | 10000 | 3 | 78 | 94.9
285 | 20251231 | 19 | 4 | 3 | 19 | 31 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.2333 | 0.232 | 1165330 | 255233 | 257271 | 1194463 | -15124 | 13086 | 1.059 | 1.051 | 20271130 | 20271130 | 1 | 15 | 4 | 4 | 0 | 0 | 8719 | 9321 | 9921 | 602 | 4 | 0 | 41 | 1 | 3200000 | 0 | 2394849 | 0 |  | 1 | 13000 | 5 | 76 | 97.4
286 | 20260131 | 19 | 4 | 3 | 19 | 31 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.2667 | 0.2675 | 1165330 | 292524 | 300617 | 1195629 | -19202 | 11109 | 1.066 | 1.037 | 20271130 | 20271130 | 0 | 15 | 4 | 4 | 0 | 0 | 9106 | 9434 | 9903 | 328 | 5 | 1 | 69 | 1 | 3200000 | 0 | 2350783 | 0 |  | 1 | 17000 | 5 | 73 | 88.8
287 | 20260228 | 19 | 4 | 3 | 19 | 31 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.3 | 0.3267 | 1165330 | 330021 | 356577 | 1196794 | -50692 | 24136 | 1.154 | 1.068 | 20271130 | 20271130 | 0 | 15 | 5 | 4 | 0 | 0 | 9450 | 9887 | 10163 | 437 | 4 | 0 | 41 | 1 | 3200000 | 0 | 2435718 | 0 |  | 1 | 11000 | 3 | 82 | 100
288 | 20260331 | 19 | 4 | 3 | 19 | 31 | 3 | 2 | 3 | Active | Deliver | Green | 0.3333 | 0.3515 | 1165330 | 367726 | 392302 | 1197959 | -41887 | 17311 | 1.114 | 1.044 | 20271130 | 20271130 | 0 | 15 | 5 | 5 | 0 | 0 | 9748 | 10240 | 9931 | 492 | 5 | 0 | 51 | 1 | 3200000 | 0 | 2376721 | 0 |  | 1 | 16000 | 5 | 82 | 99.5
289 | 20260430 | 19 | 4 | 3 | 19 | 31 | 3 | 2 | 3 | Active | Deliver | Green | 0.3667 | 0.3921 | 1165330 | 405638 | 443728 | 1199125 | -51288 | 13198 | 1.126 | 1.03 | 20271130 | 20271130 | 0 | 15 | 6 | 5 | 0 | 0 | 9996 | 9966 | 10102 | -30 | 4 | 0 | 41 | 1 | 3200000 | 0 | 2404213 | 0 |  | 1 | 18000 | 2 | 81 | 99.7
290 | 20260531 | 19 | 4 | 3 | 19 | 31 | 3 | 2 | 3 | Active | Deliver | Green | 0.4 | 0.4052 | 1165330 | 443758 | 447944 | 1200290 | -28434 | 24248 | 1.064 | 1.054 | 20271130 | 20271130 | 0 | 15 | 6 | 6 | 0 | 0 | 10192 | 10760 | 11362 | 568 | 4 | 0 | 41 | 1 | 3200000 | 0 | 2376448 | 0 |  | 1 | 14000 | 3 | 81 | 97.6
291 | 20260630 | 19 | 4 | 3 | 19 | 31 | 3 | 2 | 3 | Active | Deliver | Green | 0.4333 | 0.4455 | 1165330 | 482084 | 509133 | 1201455 | -37071 | 10022 | 1.077 | 1.02 | 20271130 | 20271130 | 0 | 15 | 7 | 6 | 0 | 0 | 10334 | 10208 | 10504 | -126 | 5 | 0 | 51 | 1 | 3200000 | 0 | 2476978 | 0 |  | 1 | 11000 | 2 | 75 | 97.6
292 | 20260731 | 19 | 4 | 3 | 19 | 31 | 3 | 2 | 3 | Active | Deliver | Green | 0.4667 | 0.4688 | 1165330 | 520618 | 535575 | 1202621 | -25689 | 10732 | 1.049 | 1.02 | 20271130 | 20271130 | 0 | 15 | 7 | 6 | 0 | 0 | 10419 | 11123 | 11046 | 704 | 5 | 0 | 51 | 1 | 3200000 | 0 | 2339583 | 0 |  | 1 | 14000 | 2 | 78 | 95.4
293 | 20260831 | 19 | 4 | 3 | 19 | 31 | 3 | 2 | 3 | Active | Deliver | Green | 0.5 | 0.4822 | 1165330 | 559358 | 551004 | 1203786 | -2564 | 10918 | 1.005 | 1.02 | 20271130 | 20271231 | 19 | 15 | 8 | 8 | 0 | 0 | 10448 | 10940 | 10940 | 492 | 5 | 1 | 69 | 1 | 3200000 | 0 | 2371486 | 0 |  | 1 | 11000 | 4 | 68 | 85.6
294 | 20260930 | 19 | 4 | 3 | 19 | 31 | 3 | 2 | 3 | Active | Deliver | Green | 0.5333 | 0.5386 | 1165330 | 598306 | 616631 | 1204951 | -29341 | 11016 | 1.049 | 1.018 | 20271130 | 20271130 | 0 | 15 | 8 | 7 | 0 | 0 | 10419 | 10439 | 10885 | 20 | 4 | 0 | 41 | 1 | 3200000 | 0 | 2399709 | 0 |  | 1 | 17000 | 5 | 80 | 95.8
295 | 20231031 | 20 | 7 | 5 | 20 | 32 | 4 | 1 | 4 | Active | Deliver | Amber | 0.5833 | 0.3672 | 212221 | 119669 | 85507 | 266585 | 41741 | -7579 | 0.651 | 0.911 | 20240831 | 20250430 | 229 | 12 | 7 | 2 | 4 | 2 | 1870 | 1475 | 1501 | -395 | 10 | 2 | 178 | 3 | 200000 | 0 | 139624 | 0 |  | 1 | 2000 | 6 | 43 | 52.1
296 | 20231130 | 20 | 7 | 5 | 20 | 32 | 4 | 1 | 4 | Active | Deliver | Amber | 0.625 | 0.4105 | 212221 | 128659 | 96349 | 268687 | 41542 | -9232 | 0.677 | 0.904 | 20240831 | 20250430 | 226 | 12 | 8 | 3 | 5 | 3 | 1830 | 1500 | 1556 | -330 | 10 | 2 | 178 | 3 | 200000 | 0 | 138880 | 0 |  | 1 | 2000 | 8 | 43 | 53.6
297 | 20231231 | 20 | 7 | 5 | 20 | 32 | 4 | 1 | 4 | Active | Deliver | Red | 0.6667 | 0.4435 | 212221 | 137708 | 104435 | 270597 | 43588 | -10315 | 0.683 | 0.901 | 20240831 | 20250430 | 236 | 12 | 8 | 3 | 5 | 3 | 1775 | 1410 | 1401 | -365 | 10 | 3 | 196 | 3 | 200000 | 0 | 135105 | 0 |  | 1 | 2000 | 4 | 44 | 44.7
298 | 20240131 | 20 | 7 | 5 | 20 | 32 | 4 | 1 | 4 | Active | Deliver | Amber | 0.7083 | 0.4869 | 212221 | 146816 | 117653 | 273435 | 43486 | -14323 | 0.704 | 0.878 | 20240831 | 20250430 | 233 | 12 | 9 | 4 | 5 | 3 | 1706 | 1342 | 1310 | -364 | 10 | 2 | 178 | 3 | 200000 | 0 | 136325 | 0 |  | 2 | 7000 | 6 | 42 | 52.8
299 | 20240229 | 20 | 7 | 5 | 20 | 32 | 4 | 1 | 4 | Paused | Deliver | Amber | 0.75 | 0.5223 | 212221 | 155982 | 126064 | 275157 | 45139 | -15221 | 0.711 | 0.879 | 20240831 | 20250430 | 241 | 12 | 9 | 4 | 5 | 3 | 1624 | 1303 | 1279 | -321 | 9 | 2 | 164 | 3 | 200000 | 21429 | 144867 | 0 | 0 | 2 | 4000 | 7 | 50 | 54.7
300 | 20240331 | 20 | 7 | 5 | 20 | 32 | 4 | 1 | 4 | Paused | Deliver | Amber | 0.7917 | 0.5602 | 212221 | 165208 | 135666 | 277066 | 46322 | -16780 | 0.72 | 0.876 | 20240831 | 20250430 | 245 | 12 | 10 | 5 | 5 | 3 | 1530 | 1224 | 1231 | -306 | 9 | 2 | 164 | 3 | 200000 | 51190 | 144489 | 5149 | 0.1006 | 2 | 5000 | 7 | 42 | 54.9
301 | 20240430 | 20 | 7 | 5 | 20 | 32 | 4 | 1 | 4 | Paused | Deliver | Amber | 0.8333 | 0.5783 | 212221 | 174493 | 143429 | 279794 | 51766 | -20702 | 0.703 | 0.856 | 20240831 | 20250531 | 270 | 12 | 10 | 5 | 5 | 3 | 1427 | 1153 | 1103 | -274 | 8 | 2 | 150 | 3 | 200000 | 80952 | 141816 | 23860 | 0.2947 | 3 | 7000 | 6 | 43 | 53.2
302 | 20240531 | 20 | 7 | 5 | 20 | 32 | 4 | 1 | 4 | Paused | Deliver | Amber | 0.875 | 0.598 | 212221 | 183836 | 150087 | 282035 | 56928 | -23179 | 0.69 | 0.846 | 20240831 | 20250630 | 292 | 12 | 11 | 4 | 6 | 3 | 1315 | 1073 | 1025 | -242 | 9 | 2 | 164 | 3 | 200000 | 110714 | 142932 | 44375 | 0.4008 | 3 | 6000 | 2 | 47 | 52.6
303 | 20240630 | 20 | 7 | 5 | 20 | 32 | 4 | 1 | 4 | Paused | Deliver | Amber | 0.9167 | 0.6106 | 212221 | 193239 | 153993 | 283997 | 63657 | -24411 | 0.671 | 0.841 | 20240831 | 20250731 | 323 | 12 | 11 | 5 | 6 | 3 | 1198 | 961 | 915 | -237 | 9 | 2 | 164 | 3 | 200000 | 140476 | 142765 | 61144 | 0.4353 | 3 | 10000 | 3 | 44 | 51.3
304 | 20240731 | 20 | 7 | 5 | 20 | 32 | 4 | 1 | 4 | Paused | Deliver | Amber | 0.9583 | 0.6408 | 212221 | 202701 | 165423 | 286671 | 66710 | -29432 | 0.671 | 0.822 | 20240831 | 20250731 | 336 | 12 | 12 | 4 | 7 | 4 | 1076 | 891 | 892 | -185 | 7 | 2 | 136 | 2 | 200000 | 170238 | 143817 | 83167 | 0.4885 | 3 | 7000 | 3 | 41 | 51.3
305 | 20240831 | 20 | 7 | 5 | 20 | 32 | 4 | 1 | 4 | Paused | Deliver | Red | 1 | 0.6984 | 212221 | 212221 | 182502 | 288902 | 64006 | -34287 | 0.698 | 0.812 | 20240831 | 20250731 | 319 | 12 | 12 | 4 | 7 | 4 | 951 | 801 | 834 | -150 | 10 | 3 | 196 | 3 | 200000 | 200000 | 136219 | 94364 | 0.4718 | 3 | 10000 | 3 | 36 | 43.5
306 | 20240930 | 20 | 7 | 5 | 20 | 32 | 4 | 1 | 4 | Paused | Deliver | Amber | 1 | 0.6984 | 212221 | 212221 | 182502 | 290671 | 64006 | -34287 | 0.698 | 0.812 | 20240831 | 20250731 | 319 | 12 | 12 | 4 | 7 | 4 | 951 | 791 | 781 | -160 | 8 | 1 | 132 | 3 | 200000 | 200000 | 138192 | 118206 | 0.591 | 3 | 7000 | 2 | 48 | 59.5
307 | 20241031 | 20 | 7 | 5 | 20 | 32 | 4 | 1 | 4 | Paused | Deliver | Amber | 1 | 0.6984 | 212221 | 212221 | 185484 | 293049 | 64006 | -37269 | 0.698 | 0.799 | 20240831 | 20250731 | 319 | 12 | 12 | 4 | 7 | 4 | 951 | 741 | 732 | -210 | 8 | 2 | 150 | 3 | 200000 | 200000 | 144670 | 129076 | 0.6454 | 3 | 10000 | 4 | 40 | 50.8
308 | 20241130 | 20 | 7 | 5 | 20 | 32 | 4 | 1 | 4 | Paused | Deliver | Amber | 1 | 0.6984 | 212221 | 212221 | 186943 | 295109 | 64006 | -38728 | 0.698 | 0.793 | 20240831 | 20250731 | 319 | 12 | 12 | 4 | 7 | 4 | 951 | 730 | 762 | -221 | 7 | 1 | 118 | 2 | 200000 | 200000 | 135760 | 125352 | 0.6268 | 3 | 6000 | 4 | 44 | 57.1
309 | 20241231 | 20 | 7 | 5 | 20 | 32 | 4 | 1 | 4 | Paused | Deliver | Amber | 1 | 0.6984 | 212221 | 212221 | 189644 | 297405 | 64006 | -41429 | 0.698 | 0.782 | 20240831 | 20250731 | 319 | 12 | 12 | 5 | 7 | 4 | 951 | 827 | 842 | -124 | 8 | 2 | 150 | 3 | 200000 | 200000 | 135275 | 133444 | 0.6672 | 3 | 6000 | 5 | 41 | 50.9
310 | 20250131 | 20 | 7 | 5 | 20 | 32 | 4 | 1 | 4 | Paused | Deliver | Amber | 1 | 0.6984 | 212221 | 212221 | 192336 | 299684 | 64006 | -44121 | 0.698 | 0.771 | 20240831 | 20250731 | 319 | 12 | 12 | 5 | 7 | 4 | 951 | 771 | 755 | -180 | 9 | 2 | 164 | 3 | 200000 | 200000 | 142792 | 127702 | 0.6385 | 4 | 12000 | 5 | 41 | 50.2
311 | 20250228 | 20 | 7 | 5 | 20 | 32 | 4 | 1 | 4 | Paused | Deliver | Amber | 1 | 0.6984 | 212221 | 212221 | 195100 | 301962 | 64006 | -46885 | 0.698 | 0.76 | 20240831 | 20250731 | 319 | 12 | 12 | 4 | 7 | 4 | 951 | 749 | 747 | -202 | 8 | 2 | 150 | 3 | 200000 | 200000 | 136324 | 131689 | 0.6584 | 5 | 12000 | 4 | 43 | 48.4
312 | 20250331 | 20 | 7 | 5 | 20 | 32 | 4 | 1 | 4 | Paused | Deliver | Amber | 1 | 0.6984 | 212221 | 212221 | 196559 | 303994 | 64006 | -48344 | 0.698 | 0.754 | 20240831 | 20250731 | 319 | 12 | 12 | 4 | 7 | 4 | 951 | 732 | 727 | -219 | 9 | 2 | 164 | 3 | 200000 | 200000 | 142181 | 133876 | 0.6694 | 5 | 14000 | 4 | 38 | 48.7
313 | 20250430 | 20 | 7 | 5 | 20 | 32 | 4 | 1 | 4 | Paused | Deliver | Amber | 1 | 0.6984 | 212221 | 212221 | 199304 | 306247 | 64006 | -51089 | 0.698 | 0.744 | 20240831 | 20250731 | 319 | 12 | 12 | 5 | 7 | 4 | 951 | 794 | 840 | -157 | 9 | 2 | 164 | 3 | 200000 | 200000 | 138637 | 124983 | 0.6249 | 5 | 13000 | 4 | 44 | 49.2
314 | 20250531 | 20 | 7 | 5 | 20 | 32 | 4 | 1 | 4 | Paused | Deliver | Amber | 1 | 0.6984 | 212221 | 212221 | 200917 | 307233 | 64006 | -52702 | 0.698 | 0.738 | 20240831 | 20250731 | 319 | 12 | 12 | 4 | 7 | 4 | 951 | 792 | 784 | -159 | 9 | 2 | 164 | 3 | 200000 | 200000 | 144527 | 143600 | 0.718 | 5 | 9000 | 6 | 39 | 49.8
315 | 20250630 | 20 | 7 | 5 | 20 | 32 | 4 | 1 | 4 | Paused | Deliver | Amber | 1 | 0.6984 | 212221 | 212221 | 200941 | 307237 | 64006 | -52726 | 0.698 | 0.738 | 20240831 | 20250731 | 319 | 12 | 12 | 5 | 7 | 4 | 951 | 823 | 804 | -128 | 10 | 2 | 178 | 3 | 200000 | 200000 | 136562 | 131580 | 0.6579 | 5 | 9000 | 6 | 41 | 49.4
316 | 20251130 | 21 | 7 | 5 | 21 | 33 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.0417 | 0.0207 | 532666 | 20493 | 7533 | 566845 | 9467 | 3493 | 0.537 | 1.461 | 20271031 | 20271130 | 20 | 12 | 1 | 0 | 1 | 0 | 2699 | 2703 | 2770 | 4 | 9 | 1 | 132 | 3 | 1300000 | 0 | 1185667 | 0 |  | 0 | 0 | 4 | 70 | 84.8
317 | 20251231 | 21 | 7 | 5 | 21 | 33 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.0833 | 0.0568 | 532666 | 41134 | 26879 | 569065 | 10879 | 3376 | 0.735 | 1.125 | 20271031 | 20271130 | 26 | 12 | 1 | 1 | 0 | 0 | 3006 | 2838 | 2983 | -168 | 8 | 1 | 119 | 2 | 1300000 | 0 | 1191384 | 0 |  | 0 | 0 | 5 | 71 | 80.9
318 | 20260131 | 21 | 7 | 5 | 21 | 33 | 5 | 2 | 5 | Active | Initiate & Design | Amber | 0.125 | 0.0745 | 532666 | 61922 | 34651 | 571284 | 22238 | 5033 | 0.641 | 1.145 | 20271031 | 20271231 | 49 | 12 | 2 | 0 | 1 | 0 | 3302 | 3268 | 3271 | -34 | 9 | 2 | 150 | 3 | 1300000 | 0 | 1170164 | 0 |  | 0 | 0 | 5 | 61 | 69.9
319 | 20260228 | 21 | 7 | 5 | 21 | 33 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.1667 | 0.1326 | 532666 | 82859 | 62639 | 573504 | 12227 | 7993 | 0.852 | 1.127 | 20271031 | 20271130 | 34 | 12 | 2 | 0 | 1 | 0 | 3582 | 3498 | 3422 | -84 | 9 | 1 | 132 | 3 | 1300000 | 0 | 1139179 | 0 |  | 0 | 0 | 5 | 74 | 85.8
320 | 20260331 | 21 | 7 | 5 | 21 | 33 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.2083 | 0.1723 | 532666 | 103944 | 83238 | 575723 | 12166 | 8540 | 0.883 | 1.102 | 20271031 | 20271130 | 35 | 12 | 3 | 1 | 1 | 0 | 3841 | 3469 | 3516 | -372 | 8 | 1 | 119 | 2 | 1300000 | 0 | 1170359 | 0 |  | 0 | 0 | 6 | 75 | 85.4
321 | 20260430 | 21 | 7 | 5 | 21 | 33 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.25 | 0.229 | 532666 | 125177 | 115502 | 577943 | 3196 | 6479 | 0.974 | 1.056 | 20271031 | 20271130 | 20 | 12 | 3 | 2 | 0 | 0 | 4076 | 3643 | 3898 | -433 | 7 | 1 | 106 | 2 | 1300000 | 0 | 1178028 | 0 |  | 0 | 0 | 6 | 80 | 87.8
322 | 20260531 | 21 | 7 | 5 | 21 | 33 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.2917 | 0.2607 | 532666 | 146557 | 134164 | 580162 | 7691 | 4702 | 0.948 | 1.035 | 20271031 | 20271130 | 30 | 12 | 4 | 2 | 1 | 0 | 4282 | 4313 | 4194 | 31 | 7 | 1 | 106 | 2 | 1300000 | 0 | 1152511 | 0 |  | 0 | 0 | 5 | 78 | 87.7
323 | 20260630 | 21 | 7 | 5 | 21 | 33 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.3333 | 0.3052 | 532666 | 168086 | 161509 | 582381 | 5516 | 1061 | 0.967 | 1.006 | 20271031 | 20271130 | 27 | 12 | 4 | 3 | 0 | 0 | 4456 | 4406 | 4549 | -50 | 7 | 1 | 106 | 2 | 1300000 | 0 | 1161984 | 0 |  | 0 | 0 | 6 | 77 | 87.5
324 | 20260731 | 21 | 7 | 5 | 21 | 33 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.375 | 0.3418 | 532666 | 189762 | 181917 | 584601 | 7697 | 148 | 0.959 | 1.001 | 20271031 | 20271130 | 32 | 12 | 5 | 4 | 1 | 0 | 4594 | 4372 | 4576 | -222 | 6 | 1 | 94 | 2 | 1300000 | 0 | 1152351 | 0 |  | 1 | 7000 | 5 | 73 | 86
325 | 20260831 | 21 | 7 | 5 | 21 | 33 | 5 | 2 | 5 | Active | Deliver | Green | 0.4167 | 0.3804 | 532666 | 211587 | 197056 | 586820 | 8961 | 5570 | 0.958 | 1.028 | 20271031 | 20271130 | 35 | 12 | 5 | 3 | 1 | 0 | 4694 | 4573 | 4530 | -121 | 7 | 1 | 106 | 2 | 1300000 | 0 | 1200987 | 0 |  | 1 | 6000 | 4 | 73 | 88.4
326 | 20260930 | 21 | 7 | 5 | 21 | 33 | 5 | 2 | 5 | Active | Deliver | Green | 0.4583 | 0.4191 | 532666 | 233559 | 225749 | 590351 | 10319 | -2509 | 0.956 | 0.989 | 20271031 | 20271130 | 38 | 12 | 6 | 4 | 1 | 0 | 4755 | 4389 | 4482 | -366 | 6 | 0 | 76 | 2 | 1300000 | 0 | 1141344 | 0 |  | 2 | 16000 | 5 | 82 | 92.5
327 | 20231031 | 22 | 2 | 4 | 22 | 34 | 6 | 2 | 6 | Completed | Completed | Green | 1 | 1 | 1216075 | 1216075 | 1309457 | 1309457 | 0 | -93382 | 1 | 0.929 | 20230531 | 20230531 | 0 | 6 | 6 | 5 | 0 | 0 | 5451 | 5317 | 5653 | -134 | 0 | 0 | 0 | 0 | 1300000 | 1300000 | 1349810 | 1255593 | 0.9658 | 0 | 0 | 1 | 79 | 97
328 | 20231031 | 23 | 7 | 5 | 23 | 35 | 7 | 1 | 7 | Active | Initiate & Design | Green | 0.1667 | 0.2062 | 786376 | 122325 | 146526 | 804463 | -39826 | 15625 | 1.325 | 1.106 | 20250630 | 20250630 | 0 | 12 | 2 | 1 | 0 | 0 | 5288 | 5810 | 5514 | 522 | 0 | 0 | 0 | 0 | 1800000 | 0 | 1982148 | 0 |  | 0 | 0 | 4 | 96 | 100
329 | 20231130 | 23 | 7 | 5 | 23 | 35 | 7 | 1 | 7 | Active | Initiate & Design | Green | 0.2083 | 0.2676 | 786376 | 153453 | 192644 | 805446 | -56981 | 17790 | 1.371 | 1.092 | 20250630 | 20250630 | 0 | 12 | 3 | 2 | 0 | 0 | 5671 | 5876 | 5999 | 205 | 0 | 0 | 0 | 0 | 1800000 | 0 | 1911331 | 0 |  | 0 | 0 | 3 | 96 | 100
330 | 20231231 | 23 | 7 | 5 | 23 | 35 | 7 | 1 | 7 | Active | Initiate & Design | Green | 0.25 | 0.3214 | 786376 | 184798 | 231176 | 806429 | -67943 | 21565 | 1.368 | 1.093 | 20250630 | 20250630 | 0 | 12 | 3 | 2 | 0 | 0 | 6018 | 6370 | 6292 | 352 | 0 | 0 | 0 | 0 | 1800000 | 0 | 1954898 | 0 |  | 0 | 0 | 4 | 96 | 100
331 | 20240131 | 23 | 7 | 5 | 23 | 35 | 7 | 1 | 7 | Active | Initiate & Design | Green | 0.2917 | 0.35 | 786376 | 216363 | 262610 | 807412 | -58869 | 12622 | 1.272 | 1.048 | 20250630 | 20250630 | 0 | 12 | 4 | 3 | 0 | 0 | 6322 | 6608 | 6377 | 286 | 2 | 0 | 18 | 0 | 1800000 | 0 | 1962483 | 0 |  | 0 | 0 | 1 | 96 | 100
332 | 20240229 | 23 | 7 | 5 | 23 | 35 | 7 | 1 | 7 | Active | Deliver | Green | 0.3333 | 0.3768 | 786376 | 248145 | 275901 | 808395 | -48161 | 20405 | 1.194 | 1.074 | 20250630 | 20250630 | 0 | 12 | 4 | 3 | 0 | 0 | 6578 | 7494 | 7501 | 916 | 1 | 0 | 9 | 0 | 1800000 | 0 | 1977483 | 0 |  | 1 | 7000 | 2 | 90 | 100
333 | 20240331 | 23 | 7 | 5 | 23 | 35 | 7 | 1 | 7 | Active | Deliver | Green | 0.375 | 0.4067 | 786376 | 280146 | 310790 | 809377 | -39673 | 9029 | 1.142 | 1.029 | 20250630 | 20250630 | 0 | 12 | 5 | 4 | 0 | 0 | 6782 | 7451 | 7337 | 669 | 3 | 0 | 27 | 0 | 1800000 | 0 | 1968867 | 0 |  | 1 | 9000 | 3 | 88 | 100
334 | 20240430 | 23 | 7 | 5 | 23 | 35 | 7 | 1 | 7 | Active | Deliver | Green | 0.4167 | 0.4501 | 786376 | 312366 | 336535 | 810360 | -41582 | 17413 | 1.133 | 1.052 | 20250630 | 20250630 | 0 | 12 | 5 | 4 | 0 | 0 | 6930 | 7289 | 7308 | 359 | 2 | 0 | 18 | 0 | 1800000 | 0 | 1954096 | 0 |  | 1 | 9000 | 1 | 91 | 100
335 | 20240531 | 23 | 7 | 5 | 23 | 35 | 7 | 1 | 7 | Active | Deliver | Green | 0.4583 | 0.4923 | 786376 | 344804 | 369329 | 811343 | -42329 | 17804 | 1.123 | 1.048 | 20250630 | 20250630 | 0 | 12 | 6 | 6 | 0 | 0 | 7020 | 7583 | 8024 | 563 | 1 | 0 | 9 | 0 | 1800000 | 0 | 1982169 | 0 |  | 1 | 8000 | 1 | 90 | 100
336 | 20240630 | 23 | 7 | 5 | 23 | 35 | 7 | 1 | 7 | Active | Deliver | Green | 0.5 | 0.5504 | 786376 | 377460 | 422266 | 812326 | -55361 | 10555 | 1.147 | 1.025 | 20250630 | 20250630 | 0 | 12 | 6 | 6 | 0 | 0 | 7050 | 7875 | 7882 | 825 | 3 | 0 | 27 | 0 | 1800000 | 0 | 1978464 | 0 |  | 1 | 12000 | 5 | 92 | 100
337 | 20240731 | 23 | 7 | 5 | 23 | 35 | 7 | 1 | 7 | Active | Deliver | Green | 0.5417 | 0.6082 | 786376 | 410335 | 463389 | 813309 | -67939 | 14885 | 1.166 | 1.032 | 20250630 | 20250630 | 0 | 12 | 7 | 6 | 0 | 0 | 7020 | 7967 | 8424 | 947 | 3 | 0 | 27 | 0 | 1800000 | 0 | 1900153 | 0 |  | 1 | 8000 | 1 | 91 | 100
338 | 20240831 | 23 | 7 | 5 | 23 | 35 | 7 | 1 | 7 | Active | Deliver | Green | 0.5833 | 0.6685 | 786376 | 443429 | 515902 | 814292 | -82263 | 9790 | 1.185 | 1.019 | 20250630 | 20250630 | 0 | 12 | 7 | 7 | 0 | 0 | 6930 | 7650 | 8131 | 720 | 2 | 0 | 18 | 0 | 1800000 | 0 | 1924514 | 0 |  | 1 | 9000 | 2 | 93 | 100
339 | 20240930 | 23 | 7 | 5 | 23 | 35 | 7 | 1 | 7 | Active | Deliver | Green | 0.625 | 0.7065 | 786376 | 476740 | 549291 | 815275 | -78835 | 6284 | 1.165 | 1.011 | 20250630 | 20250630 | 0 | 12 | 8 | 7 | 0 | 0 | 6782 | 7303 | 7005 | 521 | 1 | 0 | 9 | 0 | 1800000 | 0 | 1917196 | 0 |  | 1 | 7000 | 2 | 88 | 100
340 | 20241031 | 23 | 7 | 5 | 23 | 35 | 7 | 1 | 7 | Active | Deliver | Green | 0.6667 | 0.7426 | 786376 | 510271 | 586302 | 816949 | -73692 | -2339 | 1.144 | 0.996 | 20250630 | 20250630 | 0 | 12 | 8 | 8 | 0 | 0 | 6578 | 6878 | 6645 | 300 | 2 | 0 | 18 | 0 | 1800000 | 0 | 1977206 | 0 |  | 1 | 7000 | 3 | 87 | 100
341 | 20241130 | 23 | 7 | 5 | 23 | 35 | 7 | 1 | 7 | Active | Deploy | Green | 0.7083 | 0.7987 | 786376 | 544019 | 631984 | 818303 | -84060 | -3905 | 1.155 | 0.994 | 20250630 | 20250630 | 0 | 12 | 9 | 8 | 0 | 0 | 6322 | 6714 | 6621 | 392 | 3 | 0 | 27 | 0 | 1800000 | 0 | 1944460 | 0 |  | 1 | 12000 | 1 | 88 | 100
342 | 20241231 | 23 | 7 | 5 | 23 | 35 | 7 | 1 | 7 | Active | Deploy | Green | 0.75 | 0.8269 | 786376 | 577986 | 658257 | 820335 | -72268 | -8003 | 1.125 | 0.988 | 20250630 | 20250630 | 0 | 12 | 9 | 9 | 0 | 0 | 6018 | 6842 | 7161 | 824 | 1 | 0 | 9 | 0 | 1800000 | 192857 | 1963986 | 0 | 0 | 1 | 11000 | 3 | 86 | 100
343 | 20250131 | 23 | 7 | 5 | 23 | 35 | 7 | 1 | 7 | Active | Deploy | Green | 0.7917 | 0.859 | 786376 | 612172 | 683969 | 821350 | -63325 | -8472 | 1.103 | 0.988 | 20250630 | 20250630 | 0 | 12 | 10 | 10 | 0 | 0 | 5671 | 6104 | 6370 | 433 | 1 | 0 | 9 | 0 | 1800000 | 460714 | 1929619 | 66077 | 0.1434 | 1 | 7000 | 5 | 87 | 100
344 | 20250228 | 23 | 7 | 5 | 23 | 35 | 7 | 1 | 7 | Active | Deploy | Green | 0.8333 | 0.9084 | 786376 | 646576 | 736426 | 825380 | -67768 | -22082 | 1.105 | 0.97 | 20250630 | 20250630 | 0 | 12 | 10 | 10 | 0 | 0 | 5288 | 5544 | 5240 | 256 | 1 | 0 | 9 | 0 | 1800000 | 728571 | 1943366 | 336823 | 0.4623 | 1 | 11000 | 0 | 85 | 100
345 | 20250331 | 23 | 7 | 5 | 23 | 35 | 7 | 1 | 7 | Active | Deploy | Green | 0.875 | 0.9599 | 786376 | 681198 | 772761 | 825189 | -73644 | -17919 | 1.108 | 0.977 | 20250630 | 20250630 | 0 | 12 | 11 | 11 | 0 | 0 | 4874 | 5468 | 5608 | 594 | 0 | 0 | 0 | 0 | 1800000 | 996429 | 1927852 | 595810 | 0.5979 | 1 | 7000 | 1 | 89 | 100
346 | 20250430 | 23 | 7 | 5 | 23 | 35 | 7 | 1 | 7 | Active | Deploy | Green | 0.9167 | 0.9978 | 786376 | 716039 | 817921 | 829195 | -68607 | -33275 | 1.096 | 0.959 | 20250630 | 20250630 | 0 | 12 | 11 | 11 | 0 | 0 | 4438 | 4527 | 4789 | 89 | 1 | 0 | 9 | 0 | 1800000 | 1264286 | 1971724 | 853976 | 0.6755 | 1 | 11000 | 0 | 81 | 100
347 | 20250531 | 23 | 7 | 5 | 23 | 35 | 7 | 1 | 7 | Completed | Completed | Green | 0.9583 | 1 | 786376 | 751098 | 817921 | 829811 | -35278 | -31545 | 1.047 | 0.961 | 20250630 | 20250630 | 0 | 12 | 12 | 12 | 0 | 0 | 3985 | 4127 | 3969 | 142 | 0 | 0 | 0 | 0 | 1800000 | 1532143 | 1962090 | 1060405 | 0.6921 | 1 | 8000 | 2 | 82 | 100
348 | 20240531 | 24 | 10 | 7 | 24 | 36 | 8 | 3 | 8 | Active | Initiate & Design | Red | 0.0417 | 0 | 111455 | 4288 | 0 | 115031 | 4288 | 0 | 0 | 1 | 20260430 | 20260531 | 39 | 12 | 1 | 0 | 1 | 0 | 565 | 412 | 396 | -153 | 10 | 2 | 154 | 3 | 300000 | 0 | 288106 | 0 |  | 0 | 0 | 4 | 26 | 31.9
349 | 20240630 | 24 | 10 | 7 | 24 | 36 | 8 | 3 | 8 | Active | Initiate & Design | Red | 0.0833 | 0.0152 | 111455 | 8607 | 1616 | 115263 | 6913 | 78 | 0.196 | 1.045 | 20260430 | 20260630 | 63 | 12 | 1 | 0 | 1 | 0 | 629 | 505 | 491 | -124 | 10 | 2 | 154 | 3 | 300000 | 0 | 282471 | 0 |  | 1 | 2000 | 5 | 38 | 43.4
350 | 20240731 | 24 | 10 | 7 | 24 | 36 | 8 | 3 | 8 | Active | Initiate & Design | Green | 0.125 | 0.0802 | 111455 | 12957 | 8658 | 115495 | 4018 | 281 | 0.69 | 1.033 | 20260430 | 20260531 | 41 | 12 | 2 | 0 | 1 | 0 | 691 | 561 | 558 | -130 | 8 | 1 | 113 | 2 | 300000 | 0 | 289336 | 0 |  | 1 | 1000 | 5 | 61 | 74.1
351 | 20240831 | 24 | 10 | 7 | 24 | 36 | 8 | 3 | 8 | Active | Initiate & Design | Green | 0.1667 | 0.1169 | 111455 | 17337 | 12539 | 115727 | 4308 | 490 | 0.752 | 1.039 | 20260430 | 20260630 | 46 | 12 | 2 | 0 | 1 | 0 | 749 | 596 | 603 | -153 | 7 | 1 | 101 | 2 | 300000 | 0 | 277478 | 0 |  | 1 | 1000 | 5 | 65 | 75.6
352 | 20240930 | 24 | 10 | 7 | 24 | 36 | 8 | 3 | 8 | Active | Initiate & Design | Green | 0.2083 | 0.1697 | 111455 | 21749 | 18100 | 115960 | 2835 | 814 | 0.869 | 1.045 | 20260430 | 20260531 | 36 | 12 | 3 | 1 | 1 | 0 | 804 | 674 | 649 | -130 | 7 | 1 | 101 | 2 | 300000 | 0 | 287218 | 0 |  | 1 | 2000 | 4 | 75 | 82.9
353 | 20241031 | 24 | 10 | 7 | 24 | 36 | 8 | 3 | 8 | Active | Initiate & Design | Green | 0.25 | 0.1857 | 111455 | 26192 | 19537 | 116192 | 5495 | 1160 | 0.79 | 1.059 | 20260430 | 20260630 | 59 | 12 | 3 | 1 | 1 | 0 | 853 | 624 | 591 | -229 | 8 | 1 | 113 | 2 | 300000 | 0 | 285620 | 0 |  | 1 | 1000 | 6 | 73 | 77.4
354 | 20241130 | 24 | 10 | 7 | 24 | 36 | 8 | 3 | 8 | Active | Initiate & Design | Green | 0.2917 | 0.2159 | 111455 | 30666 | 22387 | 116424 | 6603 | 1676 | 0.785 | 1.075 | 20260430 | 20260630 | 71 | 12 | 4 | 2 | 2 | 1 | 896 | 659 | 650 | -237 | 6 | 1 | 89 | 2 | 300000 | 0 | 278444 | 0 |  | 1 | 1000 | 5 | 67 | 77.1
355 | 20241231 | 24 | 10 | 7 | 24 | 36 | 8 | 3 | 8 | Active | Initiate & Design | Green | 0.3333 | 0.2523 | 111455 | 35170 | 26130 | 116656 | 7050 | 1990 | 0.8 | 1.076 | 20260430 | 20260731 | 75 | 12 | 4 | 2 | 1 | 0 | 932 | 694 | 709 | -238 | 7 | 1 | 101 | 2 | 300000 | 0 | 284448 | 0 |  | 1 | 1000 | 4 | 69 | 78.6
356 | 20250131 | 24 | 10 | 7 | 24 | 36 | 8 | 3 | 8 | Active | Initiate & Design | Green | 0.375 | 0.2793 | 111455 | 39706 | 29807 | 116888 | 8577 | 1322 | 0.784 | 1.044 | 20260430 | 20260731 | 89 | 12 | 5 | 3 | 2 | 1 | 961 | 724 | 699 | -237 | 7 | 0 | 83 | 2 | 300000 | 0 | 283561 | 0 |  | 1 | 1000 | 3 | 77 | 84.9
357 | 20250228 | 24 | 10 | 7 | 24 | 36 | 8 | 3 | 8 | Active | Initiate & Design | Green | 0.4167 | 0.2953 | 111455 | 44272 | 32572 | 117121 | 11359 | 341 | 0.743 | 1.01 | 20260430 | 20260831 | 112 | 12 | 5 | 3 | 2 | 1 | 982 | 748 | 754 | -234 | 6 | 1 | 89 | 2 | 300000 | 0 | 289440 | 0 |  | 1 | 2000 | 4 | 69 | 74.6
358 | 20250331 | 24 | 10 | 7 | 24 | 36 | 8 | 3 | 8 | Active | Initiate & Design | Green | 0.4583 | 0.3494 | 111455 | 48870 | 38502 | 117353 | 9928 | 440 | 0.797 | 1.011 | 20260430 | 20260731 | 100 | 12 | 6 | 4 | 2 | 1 | 995 | 784 | 792 | -211 | 6 | 1 | 89 | 2 | 300000 | 0 | 274627 | 0 |  | 1 | 2000 | 4 | 69 | 76.2
359 | 20250430 | 24 | 10 | 7 | 24 | 36 | 8 | 3 | 8 | Active | Deliver | Green | 0.5 | 0.3873 | 111455 | 53498 | 43203 | 117608 | 10331 | -36 | 0.807 | 0.999 | 20260430 | 20260731 | 104 | 12 | 6 | 3 | 2 | 1 | 999 | 785 | 832 | -214 | 8 | 1 | 113 | 2 | 300000 | 0 | 284411 | 0 |  | 1 | 2000 | 6 | 65 | 77.1
360 | 20250531 | 24 | 10 | 7 | 24 | 36 | 8 | 3 | 8 | Active | Deliver | Green | 0.5417 | 0.4348 | 111455 | 58158 | 47511 | 117817 | 9697 | 950 | 0.833 | 1.02 | 20260430 | 20260731 | 99 | 12 | 7 | 5 | 2 | 1 | 995 | 786 | 825 | -209 | 7 | 1 | 101 | 2 | 300000 | 0 | 283816 | 0 |  | 1 | 1000 | 6 | 67 | 79.1
361 | 20250630 | 24 | 10 | 7 | 24 | 36 | 8 | 3 | 8 | Active | Deliver | Green | 0.5833 | 0.5014 | 111455 | 62848 | 55659 | 118049 | 6964 | 225 | 0.889 | 1.004 | 20260430 | 20260731 | 76 | 12 | 7 | 4 | 2 | 1 | 982 | 774 | 775 | -208 | 6 | 0 | 71 | 2 | 300000 | 0 | 286206 | 0 |  | 1 | 1000 | 6 | 81 | 89.2
362 | 20250731 | 24 | 10 | 7 | 24 | 36 | 8 | 3 | 8 | Active | Deliver | Green | 0.625 | 0.5324 | 111455 | 67570 | 60275 | 118665 | 8231 | -936 | 0.878 | 0.984 | 20260430 | 20260731 | 86 | 12 | 8 | 6 | 2 | 1 | 961 | 693 | 704 | -268 | 8 | 1 | 113 | 2 | 300000 | 0 | 282841 | 0 |  | 1 | 1000 | 3 | 72 | 78.2
363 | 20250831 | 24 | 10 | 7 | 24 | 36 | 8 | 3 | 8 | Active | Deliver | Green | 0.6667 | 0.5517 | 111455 | 72322 | 62202 | 118792 | 10832 | -712 | 0.85 | 0.989 | 20260430 | 20260831 | 107 | 12 | 8 | 6 | 2 | 1 | 932 | 698 | 712 | -234 | 8 | 1 | 113 | 2 | 300000 | 0 | 275906 | 0 |  | 1 | 2000 | 3 | 74 | 77.1
364 | 20250930 | 24 | 10 | 7 | 24 | 36 | 8 | 3 | 8 | Active | Deliver | Green | 0.7083 | 0.5697 | 111455 | 77105 | 64976 | 119305 | 13609 | -1480 | 0.823 | 0.977 | 20260430 | 20260831 | 129 | 12 | 9 | 5 | 3 | 1 | 896 | 673 | 641 | -223 | 6 | 1 | 89 | 2 | 300000 | 0 | 285896 | 0 |  | 2 | 2000 | 5 | 68 | 76.5
365 | 20251031 | 24 | 10 | 7 | 24 | 36 | 8 | 3 | 8 | Active | Deliver | Amber | 0.75 | 0.5954 | 111455 | 81919 | 68949 | 119897 | 15559 | -2589 | 0.81 | 0.963 | 20260430 | 20260930 | 143 | 12 | 9 | 5 | 3 | 1 | 853 | 685 | 707 | -168 | 8 | 2 | 131 | 2 | 300000 | 32143 | 275345 | 0 | 0 | 2 | 3000 | 5 | 62 | 67.5
366 | 20251130 | 24 | 10 | 7 | 24 | 36 | 8 | 3 | 8 | Active | Deliver | Green | 0.7917 | 0.6502 | 111455 | 86765 | 74314 | 119819 | 14297 | -1846 | 0.835 | 0.975 | 20260430 | 20260831 | 131 | 12 | 10 | 7 | 3 | 1 | 804 | 672 | 634 | -132 | 7 | 1 | 101 | 2 | 300000 | 76786 | 284069 | 10638 | 0.1385 | 2 | 2000 | 3 | 68 | 78.6
367 | 20251231 | 24 | 10 | 7 | 24 | 36 | 8 | 3 | 8 | Active | Deliver | Green | 0.8333 | 0.6913 | 111455 | 91641 | 80662 | 120541 | 14592 | -3613 | 0.841 | 0.955 | 20260430 | 20260831 | 131 | 12 | 10 | 7 | 3 | 1 | 749 | 559 | 552 | -190 | 5 | 1 | 77 | 1 | 300000 | 121429 | 276950 | 46655 | 0.3842 | 2 | 4000 | 4 | 67 | 75.5
368 | 20260131 | 24 | 10 | 7 | 24 | 36 | 8 | 3 | 8 | Active | Deploy | Green | 0.875 | 0.7504 | 111455 | 96548 | 88271 | 120962 | 12912 | -4635 | 0.866 | 0.948 | 20260430 | 20260831 | 116 | 12 | 11 | 7 | 3 | 1 | 691 | 537 | 509 | -154 | 4 | 1 | 65 | 1 | 300000 | 166071 | 281602 | 81758 | 0.4923 | 2 | 2000 | 3 | 67 | 77.5
369 | 20260228 | 24 | 10 | 7 | 24 | 36 | 8 | 3 | 8 | Active | Deploy | Green | 0.9167 | 0.7917 | 111455 | 101486 | 92384 | 121008 | 13247 | -4145 | 0.869 | 0.955 | 20260430 | 20260831 | 116 | 12 | 11 | 8 | 3 | 1 | 629 | 490 | 513 | -139 | 3 | 1 | 54 | 1 | 300000 | 210714 | 282642 | 120935 | 0.5739 | 2 | 3000 | 4 | 68 | 78.1
370 | 20260331 | 24 | 10 | 7 | 24 | 36 | 8 | 3 | 8 | Active | Deploy | Green | 0.9583 | 0.8426 | 111455 | 106455 | 100585 | 121767 | 12543 | -6673 | 0.882 | 0.934 | 20260430 | 20260831 | 107 | 12 | 12 | 9 | 3 | 1 | 565 | 434 | 446 | -131 | 6 | 1 | 89 | 2 | 300000 | 255357 | 276132 | 149294 | 0.5846 | 2 | 3000 | 4 | 66 | 77
371 | 20260430 | 24 | 10 | 7 | 24 | 36 | 8 | 3 | 8 | Active | Deploy | Green | 1 | 0.8785 | 111455 | 111455 | 104301 | 121874 | 13542 | -6388 | 0.878 | 0.939 | 20260430 | 20260831 | 113 | 12 | 12 | 9 | 3 | 1 | 500 | 411 | 394 | -89 | 4 | 1 | 65 | 1 | 300000 | 300000 | 282293 | 202847 | 0.6762 | 2 | 3000 | 1 | 70 | 78.8
372 | 20260531 | 24 | 10 | 7 | 24 | 36 | 8 | 3 | 8 | Active | Deploy | Green | 1 | 0.8785 | 111455 | 111455 | 104824 | 122221 | 13542 | -6911 | 0.878 | 0.934 | 20260430 | 20260831 | 113 | 12 | 12 | 9 | 3 | 1 | 500 | 396 | 417 | -104 | 5 | 0 | 59 | 1 | 300000 | 300000 | 280803 | 220852 | 0.7362 | 2 | 4000 | 2 | 72 | 85.9
373 | 20260630 | 24 | 10 | 7 | 24 | 36 | 8 | 3 | 8 | Active | Deploy | Green | 1 | 0.8785 | 111455 | 111455 | 106684 | 122852 | 13542 | -8771 | 0.878 | 0.918 | 20260430 | 20260831 | 113 | 12 | 12 | 8 | 3 | 1 | 500 | 408 | 407 | -92 | 5 | 1 | 77 | 1 | 300000 | 300000 | 284897 | 283601 | 0.9453 | 2 | 3000 | 3 | 71 | 78.2
374 | 20260731 | 24 | 10 | 7 | 24 | 36 | 8 | 3 | 8 | Active | Deploy | Green | 1 | 0.8785 | 111455 | 111455 | 107858 | 123330 | 13542 | -9945 | 0.878 | 0.908 | 20260430 | 20260831 | 113 | 12 | 12 | 9 | 3 | 1 | 500 | 375 | 393 | -125 | 6 | 0 | 71 | 2 | 300000 | 300000 | 283167 | 277536 | 0.9251 | 2 | 2000 | 3 | 76 | 84.2
375 | 20260831 | 24 | 10 | 7 | 24 | 36 | 8 | 3 | 8 | Active | Deploy | Green | 1 | 0.8785 | 111455 | 111455 | 107858 | 123562 | 13542 | -9945 | 0.878 | 0.908 | 20260430 | 20260831 | 113 | 12 | 12 | 8 | 3 | 1 | 500 | 374 | 356 | -126 | 4 | 0 | 47 | 1 | 300000 | 300000 | 284665 | 263309 | 0.8777 | 2 | 3000 | 3 | 70 | 84.3
376 | 20260930 | 24 | 10 | 7 | 24 | 36 | 8 | 3 | 8 | Active | Deploy | Green | 1 | 0.8785 | 111455 | 111455 | 107915 | 123806 | 13542 | -10002 | 0.878 | 0.907 | 20260430 | 20260831 | 113 | 12 | 12 | 8 | 3 | 1 | 500 | 406 | 409 | -94 | 3 | 1 | 54 | 1 | 300000 | 300000 | 278616 | 268036 | 0.8935 | 2 | 3000 | 4 | 72 | 77.2
377 | 20231031 | 25 | 1 | 1 | 1 | 25 | 1 | 2 | 1 | Active | Initiate & Design | Green | 0.381 | 0.2999 | 577941 | 209264 | 169208 | 617626 | 35939 | 4117 | 0.828 | 1.024 | 20241130 | 20250131 | 67 | 11 | 4 | 2 | 1 | 0 | 5002 | 4403 | 4679 | -599 | 6 | 1 | 91 | 2 | 1500000 | 0 | 1407830 | 0 |  | 0 | 0 | 4 | 72 | 80.8
378 | 20231130 | 25 | 1 | 1 | 1 | 25 | 1 | 2 | 1 | Active | Initiate & Design | Green | 0.4286 | 0.345 | 577941 | 236366 | 199164 | 619553 | 36976 | 226 | 0.844 | 1.001 | 20241130 | 20250131 | 70 | 11 | 5 | 3 | 1 | 0 | 5117 | 4712 | 4848 | -405 | 6 | 1 | 91 | 2 | 1500000 | 0 | 1465668 | 0 |  | 0 | 0 | 5 | 74 | 82.6
379 | 20231231 | 25 | 1 | 1 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Green | 0.4762 | 0.4017 | 577941 | 263677 | 226149 | 621479 | 31518 | 6010 | 0.88 | 1.026 | 20241130 | 20250131 | 62 | 11 | 5 | 4 | 1 | 0 | 5174 | 4950 | 5145 | -224 | 8 | 1 | 115 | 2 | 1500000 | 0 | 1404788 | 0 |  | 1 | 7000 | 5 | 73 | 84.8
380 | 20240131 | 25 | 1 | 1 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Green | 0.5238 | 0.4435 | 577941 | 291198 | 253709 | 623406 | 34881 | 2608 | 0.88 | 1.01 | 20241130 | 20250131 | 67 | 11 | 6 | 4 | 1 | 0 | 5174 | 4859 | 4647 | -315 | 6 | 1 | 91 | 2 | 1500000 | 0 | 1459125 | 0 |  | 1 | 6000 | 4 | 71 | 84.9
381 | 20240229 | 25 | 1 | 1 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Green | 0.5714 | 0.5027 | 577941 | 318929 | 290106 | 625332 | 28398 | 425 | 0.911 | 1.002 | 20241130 | 20250131 | 56 | 11 | 6 | 5 | 1 | 0 | 5117 | 4741 | 4733 | -376 | 6 | 1 | 91 | 2 | 1500000 | 0 | 1408473 | 0 |  | 1 | 7000 | 5 | 75 | 84.7
382 | 20240331 | 25 | 1 | 1 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Green | 0.619 | 0.5411 | 577941 | 346869 | 319308 | 629877 | 34145 | -6584 | 0.902 | 0.979 | 20241130 | 20250131 | 64 | 11 | 7 | 5 | 1 | 0 | 5002 | 4390 | 4320 | -612 | 6 | 0 | 73 | 2 | 1500000 | 0 | 1422265 | 0 |  | 1 | 9000 | 5 | 80 | 90.7
383 | 20240430 | 25 | 1 | 1 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Green | 0.6667 | 0.5917 | 577941 | 375019 | 351019 | 632464 | 33051 | -9051 | 0.912 | 0.974 | 20241130 | 20241231 | 27 | 11 | 7 | 5 | 1 | 0 | 4834 | 4352 | 4437 | -482 | 5 | 1 | 79 | 1 | 1500000 | 0 | 1404905 | 0 |  | 2 | 15000 | 6 | 73 | 83.2
384 | 20240531 | 25 | 1 | 1 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Green | 0.7143 | 0.6518 | 577941 | 403379 | 390016 | 635454 | 26677 | -13314 | 0.934 | 0.966 | 20241130 | 20241231 | 16 | 11 | 8 | 6 | 1 | 0 | 4616 | 4092 | 3931 | -524 | 6 | 1 | 91 | 2 | 1500000 | 0 | 1412599 | 0 |  | 2 | 15000 | 6 | 75 | 83.7
385 | 20240630 | 25 | 1 | 1 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Green | 0.7619 | 0.6895 | 577941 | 431949 | 417093 | 638708 | 33459 | -18603 | 0.923 | 0.955 | 20241130 | 20241231 | 25 | 11 | 8 | 7 | 1 | 0 | 4353 | 4221 | 4296 | -132 | 6 | 1 | 91 | 2 | 1500000 | 224490 | 1420926 | 0 | 0 | 2 | 15000 | 5 | 69 | 84.8
386 | 20240731 | 25 | 1 | 1 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Green | 0.8095 | 0.7433 | 577941 | 460728 | 452633 | 641434 | 31144 | -23049 | 0.932 | 0.949 | 20241130 | 20241231 | 20 | 11 | 9 | 7 | 1 | 0 | 4050 | 3701 | 3609 | -349 | 6 | 1 | 91 | 2 | 1500000 | 479592 | 1438221 | 133204 | 0.2777 | 2 | 9000 | 3 | 73 | 84.1
387 | 20240831 | 25 | 1 | 1 | 1 | 25 | 1 | 2 | 1 | Active | Deploy | Green | 0.8571 | 0.7943 | 577941 | 489717 | 484460 | 643552 | 30658 | -25401 | 0.937 | 0.948 | 20241130 | 20241231 | 17 | 11 | 9 | 8 | 1 | 0 | 3715 | 3539 | 3483 | -176 | 4 | 1 | 67 | 1 | 1500000 | 734694 | 1431248 | 362260 | 0.4931 | 2 | 17000 | 1 | 76 | 85
388 | 20240930 | 25 | 1 | 1 | 1 | 25 | 1 | 2 | 1 | Active | Deploy | Green | 0.9048 | 0.8493 | 577941 | 518915 | 530616 | 648351 | 28070 | -39771 | 0.946 | 0.925 | 20241130 | 20241130 | 11 | 11 | 10 | 8 | 1 | 0 | 3354 | 3074 | 3066 | -280 | 4 | 1 | 67 | 1 | 1500000 | 989796 | 1458475 | 564417 | 0.5702 | 2 | 14000 | 1 | 68 | 84.3
389 | 20241031 | 25 | 1 | 1 | 1 | 25 | 1 | 2 | 1 | Active | Deploy | Green | 0.9524 | 0.9143 | 577941 | 548323 | 573197 | 650676 | 19912 | -44786 | 0.964 | 0.922 | 20241130 | 20241130 | -4 | 11 | 10 | 8 | 1 | 0 | 2977 | 2826 | 2755 | -151 | 3 | 0 | 36 | 1 | 1500000 | 1244898 | 1440981 | 772800 | 0.6208 | 2 | 12000 | 4 | 75 | 93.4
390 | 20241130 | 25 | 1 | 1 | 1 | 25 | 1 | 2 | 1 | Active | Deploy | Green | 1 | 0.9792 | 577941 | 577941 | 613717 | 652570 | 12021 | -47797 | 0.979 | 0.922 | 20241130 | 20241130 | -18 | 11 | 11 | 9 | 1 | 0 | 2591 | 2364 | 2515 | -227 | 5 | 0 | 61 | 1 | 1500000 | 1500000 | 1407818 | 929989 | 0.62 | 2 | 16000 | 4 | 78 | 92.7
391 | 20241231 | 25 | 1 | 1 | 1 | 25 | 1 | 2 | 1 | Completed | Completed | Green | 1 | 1 | 577941 | 577941 | 638156 | 656594 | 0 | -60215 | 1 | 0.906 | 20241130 | 20241130 | -35 | 11 | 11 | 10 | 1 | 0 | 2591 | 2457 | 2452 | -134 | 5 | 0 | 61 | 1 | 1500000 | 1500000 | 1424740 | 1241979 | 0.828 | 2 | 15000 | 4 | 79 | 94.2
392 | 20251231 | 26 | 4 | 3 | 2 | 26 | 2 | 3 | 2 | Active | Initiate & Design | Green | 0.0556 | 0.057 | 127742 | 6561 | 7289 | 130296 | -720 | -8 | 1.109 | 0.999 | 20270531 | 20270531 | 0 | 9 | 1 | 0 | 0 | 0 | 672 | 696 | 739 | 24 | 3 | 0 | 31 | 1 | 200000 | 0 | 147522 | 0 |  | 0 | 0 | 3 | 75 | 97.5
393 | 20260131 | 26 | 4 | 3 | 2 | 26 | 2 | 3 | 2 | Active | Initiate & Design | Green | 0.1111 | 0.1273 | 127742 | 13184 | 14255 | 130467 | -3078 | 2007 | 1.234 | 1.141 | 20270531 | 20270531 | 0 | 9 | 1 | 0 | 0 | 0 | 768 | 813 | 812 | 45 | 3 | 0 | 31 | 1 | 200000 | 0 | 147480 | 0 |  | 0 | 0 | 3 | 88 | 100
394 | 20260228 | 26 | 4 | 3 | 2 | 26 | 2 | 3 | 2 | Active | Initiate & Design | Green | 0.1667 | 0.1861 | 127742 | 19871 | 21630 | 130680 | -3902 | 2143 | 1.197 | 1.099 | 20270531 | 20270531 | 0 | 9 | 2 | 2 | 0 | 0 | 859 | 866 | 820 | 7 | 4 | 0 | 41 | 1 | 200000 | 0 | 146407 | 0 |  | 0 | 0 | 4 | 86 | 100
395 | 20260331 | 26 | 4 | 3 | 2 | 26 | 2 | 3 | 2 | Active | Initiate & Design | Green | 0.2222 | 0.2433 | 127742 | 26621 | 29388 | 130893 | -4459 | 1692 | 1.168 | 1.058 | 20270531 | 20270531 | 0 | 9 | 2 | 2 | 0 | 0 | 941 | 952 | 929 | 11 | 3 | 0 | 31 | 1 | 200000 | 0 | 146670 | 0 |  | 1 | 2000 | 2 | 82 | 100
396 | 20260430 | 26 | 4 | 3 | 2 | 26 | 2 | 3 | 2 | Active | Initiate & Design | Green | 0.2778 | 0.2989 | 127742 | 33434 | 35958 | 131106 | -4748 | 2224 | 1.142 | 1.062 | 20270531 | 20270531 | 0 | 9 | 3 | 2 | 0 | 0 | 1011 | 969 | 1023 | -42 | 5 | 0 | 51 | 1 | 200000 | 0 | 151913 | 0 |  | 1 | 2000 | 4 | 78 | 100
397 | 20260531 | 26 | 4 | 3 | 2 | 26 | 2 | 3 | 2 | Active | Initiate & Design | Green | 0.3333 | 0.3258 | 127742 | 40310 | 39106 | 131319 | -1308 | 2512 | 1.032 | 1.064 | 20270531 | 20270531 | 5 | 9 | 3 | 2 | 0 | 0 | 1069 | 1052 | 1102 | -17 | 5 | 1 | 69 | 1 | 200000 | 0 | 154090 | 0 |  | 1 | 1000 | 4 | 75 | 88.9
398 | 20260630 | 26 | 4 | 3 | 2 | 26 | 2 | 3 | 2 | Active | Deliver | Green | 0.3889 | 0.387 | 127742 | 47249 | 47679 | 131532 | -2187 | 1757 | 1.046 | 1.037 | 20270531 | 20270531 | 1 | 9 | 4 | 3 | 0 | 0 | 1111 | 1102 | 1111 | -9 | 3 | 1 | 49 | 1 | 200000 | 0 | 153335 | 0 |  | 1 | 2000 | 4 | 74 | 88.7
399 | 20260731 | 26 | 4 | 3 | 2 | 26 | 2 | 3 | 2 | Active | Deliver | Green | 0.4444 | 0.4383 | 127742 | 54251 | 53413 | 131745 | -1738 | 2576 | 1.032 | 1.048 | 20270531 | 20270531 | 4 | 9 | 4 | 4 | 0 | 0 | 1137 | 1192 | 1156 | 55 | 5 | 1 | 69 | 1 | 200000 | 0 | 147302 | 0 |  | 1 | 2000 | 3 | 73 | 87.7
400 | 20260831 | 26 | 4 | 3 | 2 | 26 | 2 | 3 | 2 | Active | Deliver | Green | 0.5 | 0.5019 | 127742 | 61316 | 62116 | 131957 | -2798 | 1998 | 1.046 | 1.032 | 20270531 | 20270531 | 0 | 9 | 5 | 4 | 0 | 0 | 1145 | 1199 | 1208 | 54 | 5 | 0 | 51 | 1 | 200000 | 0 | 150705 | 0 |  | 1 | 2000 | 2 | 79 | 96.3
401 | 20260930 | 26 | 4 | 3 | 2 | 26 | 2 | 3 | 2 | Active | Deliver | Green | 0.5556 | 0.5713 | 127742 | 68444 | 71425 | 132170 | -4535 | 1554 | 1.066 | 1.022 | 20270531 | 20270531 | 0 | 9 | 5 | 4 | 0 | 0 | 1137 | 1106 | 1149 | -31 | 3 | 0 | 31 | 1 | 200000 | 0 | 150856 | 0 |  | 1 | 1000 | 5 | 75 | 96.3
402 | 20231031 | 27 | 8 | 6 | 3 | 27 | 3 | 2 | 3 | Active | Initiate & Design | Red | 0.1111 | 0.0392 | 202645 | 20915 | 7556 | 231466 | 12971 | 388 | 0.38 | 1.052 | 20250228 | 20250430 | 57 | 9 | 1 | 0 | 1 | 1 | 1219 | 941 | 933 | -278 | 12 | 3 | 225 | 4 | 500000 | 0 | 344976 | 0 |  | 0 | 0 | 6 | 35 | 36.2
403 | 20231130 | 27 | 8 | 6 | 3 | 27 | 3 | 2 | 3 | Active | Initiate & Design | Red | 0.1667 | 0.0614 | 202645 | 31523 | 10881 | 233717 | 19081 | 1561 | 0.395 | 1.144 | 20250228 | 20250531 | 84 | 9 | 2 | 1 | 1 | 1 | 1363 | 1153 | 1085 | -210 | 12 | 3 | 225 | 4 | 500000 | 0 | 338298 | 0 |  | 1 | 2000 | 6 | 32 | 41.4
404 | 20231231 | 27 | 8 | 6 | 3 | 27 | 3 | 2 | 3 | Active | Initiate & Design | Red | 0.2222 | 0.0972 | 202645 | 42230 | 20365 | 237411 | 22533 | -668 | 0.467 | 0.968 | 20250228 | 20250531 | 98 | 9 | 2 | 1 | 1 | 1 | 1492 | 1143 | 1156 | -349 | 10 | 2 | 178 | 3 | 500000 | 0 | 350402 | 0 |  | 1 | 3000 | 4 | 40 | 45.3
405 | 20240131 | 27 | 8 | 6 | 3 | 27 | 3 | 2 | 3 | Active | Initiate & Design | Red | 0.2778 | 0.1268 | 202645 | 53038 | 24882 | 238220 | 27343 | 813 | 0.485 | 1.033 | 20250228 | 20250630 | 120 | 9 | 3 | 0 | 2 | 1 | 1604 | 1308 | 1368 | -296 | 12 | 3 | 225 | 4 | 500000 | 0 | 358944 | 0 |  | 1 | 3000 | 5 | 39 | 42
406 | 20240229 | 27 | 8 | 6 | 3 | 27 | 3 | 2 | 3 | Active | Initiate & Design | Amber | 0.3333 | 0.1729 | 202645 | 63946 | 36583 | 242348 | 28909 | -1546 | 0.548 | 0.958 | 20250228 | 20250630 | 128 | 9 | 3 | 0 | 2 | 1 | 1695 | 1450 | 1391 | -245 | 10 | 2 | 178 | 3 | 500000 | 0 | 354316 | 0 |  | 1 | 2000 | 8 | 38 | 50.8
407 | 20240331 | 27 | 8 | 6 | 3 | 27 | 3 | 2 | 3 | Active | Initiate & Design | Amber | 0.3889 | 0.2027 | 202645 | 74954 | 42098 | 243813 | 33878 | -1022 | 0.548 | 0.976 | 20250228 | 20250731 | 148 | 9 | 4 | 1 | 3 | 2 | 1762 | 1444 | 1374 | -318 | 10 | 2 | 178 | 3 | 500000 | 0 | 357273 | 0 |  | 1 | 3000 | 5 | 43 | 50.8
408 | 20240430 | 27 | 8 | 6 | 3 | 27 | 3 | 2 | 3 | Active | Initiate & Design | Amber | 0.4444 | 0.2534 | 202645 | 86062 | 53779 | 246983 | 34712 | -2429 | 0.597 | 0.955 | 20250228 | 20250731 | 151 | 9 | 4 | 0 | 3 | 2 | 1803 | 1546 | 1482 | -257 | 11 | 2 | 193 | 4 | 500000 | 0 | 343729 | 0 |  | 1 | 3000 | 7 | 43 | 52.4
409 | 20240531 | 27 | 8 | 6 | 3 | 27 | 3 | 2 | 3 | Active | Initiate & Design | Amber | 0.5 | 0.3103 | 202645 | 97270 | 67869 | 250499 | 34389 | -4988 | 0.647 | 0.927 | 20250228 | 20250731 | 150 | 9 | 5 | 1 | 3 | 2 | 1817 | 1538 | 1630 | -279 | 10 | 2 | 178 | 3 | 500000 | 0 | 354505 | 0 |  | 1 | 2000 | 6 | 45 | 54
410 | 20240630 | 27 | 8 | 6 | 3 | 27 | 3 | 2 | 3 | Active | Deliver | Amber | 0.5556 | 0.3574 | 202645 | 108578 | 77752 | 252535 | 36153 | -5327 | 0.667 | 0.931 | 20250228 | 20250731 | 157 | 9 | 5 | 1 | 3 | 2 | 1803 | 1556 | 1636 | -247 | 9 | 2 | 164 | 3 | 500000 | 0 | 362128 | 0 |  | 2 | 4000 | 5 | 43 | 55.9
411 | 20240731 | 27 | 8 | 6 | 3 | 27 | 3 | 2 | 3 | Active | Deliver | Amber | 0.6111 | 0.406 | 202645 | 119986 | 89640 | 255397 | 37712 | -7366 | 0.686 | 0.918 | 20250228 | 20250731 | 163 | 9 | 6 | 2 | 3 | 2 | 1762 | 1413 | 1468 | -349 | 10 | 2 | 178 | 3 | 500000 | 0 | 362008 | 0 |  | 2 | 3000 | 4 | 48 | 54.9
412 | 20240831 | 27 | 8 | 6 | 3 | 27 | 3 | 2 | 3 | Active | Deliver | Amber | 0.6667 | 0.4497 | 202645 | 131494 | 100223 | 258026 | 40365 | -9094 | 0.693 | 0.909 | 20250228 | 20250831 | 172 | 9 | 6 | 3 | 3 | 2 | 1695 | 1382 | 1321 | -313 | 10 | 2 | 178 | 3 | 500000 | 0 | 360080 | 0 |  | 2 | 5000 | 7 | 49 | 55.1
413 | 20240930 | 27 | 8 | 6 | 3 | 27 | 3 | 2 | 3 | Paused | Deliver | Amber | 0.7222 | 0.4798 | 202645 | 143102 | 108640 | 260918 | 45873 | -11411 | 0.679 | 0.895 | 20250228 | 20250831 | 192 | 9 | 7 | 2 | 4 | 2 | 1604 | 1270 | 1338 | -334 | 10 | 2 | 178 | 3 | 500000 | 3968 | 343594 | 0 | 0 | 2 | 5000 | 6 | 44 | 52.6
414 | 20241031 | 27 | 8 | 6 | 3 | 27 | 3 | 2 | 3 | Paused | Deliver | Amber | 0.7778 | 0.5207 | 202645 | 154811 | 122143 | 264556 | 49294 | -16626 | 0.682 | 0.864 | 20250228 | 20250930 | 204 | 9 | 7 | 2 | 4 | 2 | 1492 | 1206 | 1235 | -286 | 12 | 2 | 207 | 4 | 500000 | 103175 | 341011 | 0 | 0 | 2 | 4000 | 7 | 45 | 51.8
415 | 20241130 | 27 | 8 | 6 | 3 | 27 | 3 | 2 | 3 | Paused | Deliver | Amber | 0.8333 | 0.5554 | 202645 | 166619 | 130885 | 266979 | 54070 | -18336 | 0.676 | 0.86 | 20250228 | 20250930 | 220 | 9 | 8 | 3 | 5 | 3 | 1363 | 1056 | 1043 | -307 | 7 | 2 | 136 | 2 | 500000 | 202381 | 355191 | 55450 | 0.274 | 3 | 8000 | 5 | 46 | 51.4
416 | 20241231 | 27 | 8 | 6 | 3 | 27 | 3 | 2 | 3 | Paused | Deliver | Amber | 0.8889 | 0.6102 | 202645 | 178528 | 146496 | 269941 | 54874 | -22842 | 0.693 | 0.844 | 20250228 | 20250930 | 222 | 9 | 8 | 4 | 4 | 2 | 1219 | 932 | 935 | -287 | 8 | 2 | 150 | 3 | 500000 | 301587 | 361176 | 122640 | 0.4066 | 3 | 5000 | 3 | 47 | 51.8
417 | 20250131 | 27 | 8 | 6 | 3 | 27 | 3 | 2 | 3 | Paused | Deliver | Amber | 0.9444 | 0.6427 | 202645 | 190536 | 158225 | 273126 | 60296 | -27985 | 0.684 | 0.823 | 20250228 | 20251031 | 239 | 9 | 9 | 4 | 5 | 3 | 1066 | 871 | 909 | -195 | 8 | 2 | 150 | 3 | 500000 | 400794 | 337949 | 167706 | 0.4184 | 3 | 6000 | 3 | 41 | 50.5
418 | 20250228 | 27 | 8 | 6 | 3 | 27 | 3 | 2 | 3 | Paused | Deliver | Amber | 1 | 0.7059 | 202645 | 202645 | 175294 | 275695 | 59598 | -32247 | 0.706 | 0.816 | 20250228 | 20251031 | 233 | 9 | 9 | 4 | 5 | 3 | 908 | 702 | 669 | -206 | 8 | 2 | 150 | 3 | 500000 | 500000 | 346288 | 227456 | 0.4549 | 3 | 7000 | 4 | 47 | 50.7
419 | 20250331 | 27 | 8 | 6 | 3 | 27 | 3 | 2 | 3 | Paused | Deliver | Red | 1 | 0.7059 | 202645 | 202645 | 176355 | 278165 | 59598 | -33308 | 0.706 | 0.811 | 20250228 | 20251031 | 233 | 9 | 9 | 3 | 5 | 3 | 908 | 755 | 779 | -153 | 10 | 3 | 196 | 3 | 500000 | 500000 | 355505 | 325215 | 0.6504 | 3 | 5000 | 3 | 35 | 44.4
420 | 20250430 | 27 | 8 | 6 | 3 | 27 | 3 | 2 | 3 | Paused | Deliver | Amber | 1 | 0.7059 | 202645 | 202645 | 182065 | 281551 | 59598 | -39018 | 0.706 | 0.786 | 20250228 | 20251031 | 233 | 9 | 9 | 3 | 5 | 3 | 908 | 691 | 704 | -217 | 9 | 2 | 164 | 3 | 500000 | 500000 | 343265 | 300841 | 0.6017 | 4 | 7000 | 3 | 45 | 49.2
421 | 20250531 | 27 | 8 | 6 | 3 | 27 | 3 | 2 | 3 | Paused | Deliver | Amber | 1 | 0.7059 | 202645 | 202645 | 182436 | 283874 | 59598 | -39389 | 0.706 | 0.784 | 20250228 | 20251031 | 233 | 9 | 9 | 3 | 5 | 3 | 908 | 775 | 790 | -133 | 10 | 2 | 178 | 3 | 500000 | 500000 | 348175 | 314242 | 0.6285 | 4 | 10000 | 5 | 43 | 51.5
422 | 20250630 | 27 | 8 | 6 | 3 | 27 | 3 | 2 | 3 | Paused | Deliver | Amber | 1 | 0.7059 | 202645 | 202645 | 186365 | 286862 | 59598 | -43318 | 0.706 | 0.768 | 20250228 | 20251031 | 233 | 9 | 9 | 4 | 5 | 3 | 908 | 727 | 733 | -181 | 7 | 2 | 136 | 2 | 500000 | 500000 | 354358 | 317308 | 0.6346 | 5 | 9000 | 4 | 43 | 50.1
423 | 20250731 | 27 | 8 | 6 | 3 | 27 | 3 | 2 | 3 | Paused | Deliver | Amber | 1 | 0.7059 | 202645 | 202645 | 190415 | 289842 | 59598 | -47368 | 0.706 | 0.751 | 20250228 | 20251031 | 233 | 9 | 9 | 3 | 5 | 3 | 908 | 792 | 810 | -116 | 9 | 2 | 164 | 3 | 500000 | 500000 | 340378 | 333164 | 0.6663 | 5 | 9000 | 2 | 43 | 50.3
424 | 20250831 | 27 | 8 | 6 | 3 | 27 | 3 | 2 | 3 | Paused | Deliver | Amber | 1 | 0.7059 | 202645 | 202645 | 191158 | 292224 | 59598 | -48111 | 0.706 | 0.748 | 20250228 | 20251031 | 233 | 9 | 9 | 4 | 5 | 3 | 908 | 737 | 753 | -171 | 8 | 2 | 150 | 3 | 500000 | 500000 | 360450 | 354004 | 0.708 | 5 | 14000 | 4 | 39 | 50
425 | 20250930 | 27 | 8 | 6 | 3 | 27 | 3 | 2 | 3 | Paused | Deliver | Amber | 1 | 0.7059 | 202645 | 202645 | 191551 | 292968 | 59598 | -48504 | 0.706 | 0.747 | 20250228 | 20251031 | 233 | 9 | 9 | 3 | 5 | 3 | 908 | 754 | 796 | -154 | 8 | 2 | 150 | 3 | 500000 | 500000 | 359065 | 337769 | 0.6755 | 5 | 13000 | 2 | 38 | 50.3
426 | 20251031 | 27 | 8 | 6 | 3 | 27 | 3 | 2 | 3 | Paused | Deliver | Amber | 1 | 0.7059 | 202645 | 202645 | 193347 | 293277 | 59598 | -50300 | 0.706 | 0.74 | 20250228 | 20251031 | 233 | 9 | 9 | 3 | 5 | 3 | 908 | 745 | 743 | -163 | 8 | 2 | 150 | 3 | 500000 | 500000 | 350782 | 312515 | 0.625 | 5 | 16000 | 4 | 42 | 49.4
427 | 20251130 | 27 | 8 | 6 | 3 | 27 | 3 | 2 | 3 | Paused | Deliver | Amber | 1 | 0.7059 | 202645 | 202645 | 193347 | 293277 | 59598 | -50300 | 0.706 | 0.74 | 20250228 | 20251031 | 233 | 9 | 9 | 3 | 5 | 3 | 908 | 728 | 718 | -180 | 7 | 1 | 118 | 2 | 500000 | 500000 | 339529 | 307460 | 0.6149 | 5 | 11000 | 5 | 43 | 56.3
428 | 20251231 | 27 | 8 | 6 | 3 | 27 | 3 | 2 | 3 | Paused | Deliver | Amber | 1 | 0.7059 | 202645 | 202645 | 193347 | 293277 | 59598 | -50300 | 0.706 | 0.74 | 20250228 | 20251031 | 233 | 9 | 9 | 3 | 5 | 3 | 908 | 753 | 805 | -155 | 8 | 1 | 132 | 3 | 500000 | 500000 | 345599 | 343496 | 0.687 | 5 | 14000 | 5 | 44 | 57.3
429 | 20250531 | 28 | 3 | 2 | 4 | 28 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.0333 | 0.0353 | 1013339 | 31166 | 29122 | 1077517 | -4605 | 6649 | 1.148 | 1.229 | 20271031 | 20271031 | 0 | 15 | 1 | 0 | 0 | 0 | 5017 | 4834 | 4793 | -183 | 6 | 1 | 94 | 2 | 1900000 | 0 | 1756291 | 0 |  | 0 | 0 | 5 | 92 | 100
430 | 20250630 | 28 | 3 | 2 | 4 | 28 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.0667 | 0.0585 | 1013339 | 62512 | 59145 | 1080895 | 3232 | 135 | 0.948 | 1.002 | 20271031 | 20271031 | 9 | 15 | 1 | 0 | 0 | 0 | 5487 | 4891 | 4934 | -596 | 8 | 1 | 119 | 2 | 1900000 | 0 | 1697165 | 0 |  | 0 | 0 | 4 | 71 | 84.3
431 | 20250731 | 28 | 3 | 2 | 4 | 28 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.1 | 0.0926 | 1013339 | 94038 | 93467 | 1084273 | 203 | 368 | 0.997 | 1.004 | 20271031 | 20271031 | 9 | 15 | 2 | 2 | 0 | 0 | 5946 | 5360 | 5730 | -586 | 6 | 1 | 94 | 2 | 1900000 | 0 | 1686364 | 0 |  | 0 | 0 | 5 | 76 | 86.7
432 | 20250831 | 28 | 3 | 2 | 4 | 28 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.1333 | 0.1137 | 1013339 | 125744 | 100068 | 1087651 | 10527 | 15149 | 0.916 | 1.151 | 20271031 | 20271130 | 24 | 15 | 2 | 1 | 0 | 0 | 6390 | 6068 | 5729 | -322 | 6 | 1 | 94 | 2 | 1900000 | 0 | 1749833 | 0 |  | 0 | 0 | 4 | 81 | 90.2
433 | 20250930 | 28 | 3 | 2 | 4 | 28 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.1667 | 0.1351 | 1013339 | 157631 | 129400 | 1091028 | 20729 | 7502 | 0.869 | 1.058 | 20271031 | 20271130 | 38 | 15 | 3 | 1 | 1 | 0 | 6814 | 6560 | 6434 | -254 | 8 | 2 | 137 | 2 | 1900000 | 0 | 1712892 | 0 |  | 1 | 15000 | 4 | 71 | 76.6
434 | 20251031 | 28 | 3 | 2 | 4 | 28 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.2 | 0.1643 | 1013339 | 189697 | 158111 | 1094406 | 23205 | 8381 | 0.878 | 1.053 | 20271031 | 20271130 | 43 | 15 | 3 | 1 | 1 | 0 | 7213 | 6649 | 7070 | -564 | 8 | 1 | 119 | 2 | 1900000 | 0 | 1739588 | 0 |  | 1 | 15000 | 7 | 71 | 84.3
435 | 20251130 | 28 | 3 | 2 | 4 | 28 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.2333 | 0.1927 | 1013339 | 221944 | 187147 | 1097784 | 26674 | 8123 | 0.88 | 1.043 | 20271031 | 20271231 | 50 | 15 | 4 | 3 | 1 | 0 | 7582 | 7011 | 6870 | -571 | 8 | 1 | 119 | 2 | 1900000 | 0 | 1709334 | 0 |  | 1 | 11000 | 3 | 76 | 83.6
436 | 20251231 | 28 | 3 | 2 | 4 | 28 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.2667 | 0.2362 | 1013339 | 254371 | 231888 | 1101162 | 15020 | 7463 | 0.941 | 1.032 | 20271031 | 20271130 | 36 | 15 | 4 | 3 | 1 | 0 | 7918 | 7106 | 6763 | -812 | 7 | 1 | 106 | 2 | 1900000 | 0 | 1664485 | 0 |  | 1 | 15000 | 3 | 74 | 84.8
437 | 20260131 | 28 | 3 | 2 | 4 | 28 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.3 | 0.2767 | 1013339 | 286978 | 263443 | 1104540 | 6587 | 16948 | 0.977 | 1.064 | 20271031 | 20271130 | 28 | 15 | 5 | 3 | 1 | 0 | 8218 | 7721 | 8253 | -497 | 7 | 1 | 106 | 2 | 1900000 | 0 | 1665432 | 0 |  | 1 | 11000 | 5 | 82 | 88.4
438 | 20260228 | 28 | 3 | 2 | 4 | 28 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.3333 | 0.3271 | 1013339 | 319765 | 324611 | 1107917 | -11698 | 6852 | 1.037 | 1.021 | 20271031 | 20271031 | 8 | 15 | 5 | 5 | 0 | 0 | 8477 | 8035 | 8391 | -442 | 7 | 1 | 106 | 2 | 1900000 | 0 | 1665927 | 0 |  | 1 | 10000 | 4 | 80 | 89.8
439 | 20260331 | 28 | 3 | 2 | 4 | 28 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.3667 | 0.3455 | 1013339 | 352732 | 336337 | 1111295 | 2623 | 13772 | 0.993 | 1.041 | 20271031 | 20271130 | 26 | 15 | 6 | 6 | 0 | 0 | 8692 | 8027 | 8341 | -665 | 8 | 1 | 119 | 2 | 1900000 | 0 | 1683078 | 0 |  | 1 | 9000 | 7 | 77 | 88.2
440 | 20260430 | 28 | 3 | 2 | 4 | 28 | 4 | 2 | 4 | Active | Deliver | Green | 0.4 | 0.3593 | 1013339 | 385879 | 359424 | 1114673 | 21786 | 4669 | 0.944 | 1.013 | 20271031 | 20271231 | 50 | 15 | 6 | 4 | 1 | 0 | 8863 | 8432 | 8641 | -431 | 6 | 1 | 94 | 2 | 1900000 | 0 | 1751037 | 0 |  | 1 | 14000 | 3 | 74 | 86.6
441 | 20260531 | 28 | 3 | 2 | 4 | 28 | 4 | 2 | 4 | Active | Deliver | Green | 0.4333 | 0.3848 | 1013339 | 419207 | 383670 | 1118051 | 29274 | 6263 | 0.93 | 1.016 | 20271031 | 20271231 | 59 | 15 | 7 | 6 | 1 | 0 | 8986 | 8837 | 8965 | -149 | 8 | 1 | 119 | 2 | 1900000 | 0 | 1684220 | 0 |  | 1 | 12000 | 6 | 72 | 85.9
442 | 20260630 | 28 | 3 | 2 | 4 | 28 | 4 | 2 | 4 | Active | Deliver | Green | 0.4667 | 0.4114 | 1013339 | 452715 | 413114 | 1121428 | 35827 | 3774 | 0.921 | 1.009 | 20271031 | 20271231 | 67 | 15 | 7 | 6 | 1 | 0 | 9060 | 8446 | 8039 | -614 | 8 | 1 | 119 | 2 | 1900000 | 0 | 1673858 | 0 |  | 1 | 15000 | 6 | 72 | 83.9
443 | 20260731 | 28 | 3 | 2 | 4 | 28 | 4 | 2 | 4 | Active | Deliver | Green | 0.5 | 0.4485 | 1013339 | 486403 | 457843 | 1126442 | 31920 | -3360 | 0.934 | 0.993 | 20271031 | 20271231 | 62 | 15 | 8 | 6 | 1 | 0 | 9085 | 8593 | 8404 | -492 | 6 | 1 | 94 | 2 | 1900000 | 0 | 1712530 | 0 |  | 1 | 8000 | 5 | 73 | 84.8
444 | 20260831 | 28 | 3 | 2 | 4 | 28 | 4 | 2 | 4 | Active | Deliver | Green | 0.5333 | 0.4786 | 1013339 | 520271 | 485433 | 1128373 | 35287 | -449 | 0.932 | 0.999 | 20271031 | 20271231 | 66 | 15 | 8 | 7 | 1 | 0 | 9060 | 8599 | 8497 | -461 | 8 | 1 | 119 | 2 | 1900000 | 0 | 1714561 | 0 |  | 1 | 10000 | 4 | 72 | 85.1
445 | 20260930 | 28 | 3 | 2 | 4 | 28 | 4 | 2 | 4 | Active | Deliver | Green | 0.5667 | 0.5138 | 1013339 | 554319 | 537350 | 1138508 | 33665 | -16696 | 0.939 | 0.969 | 20271031 | 20271231 | 65 | 15 | 9 | 8 | 1 | 0 | 8986 | 8481 | 7975 | -505 | 8 | 1 | 119 | 2 | 1900000 | 0 | 1668159 | 0 |  | 1 | 10000 | 4 | 74 | 83.5
446 | 20231031 | 29 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.2333 | 0.2299 | 1127826 | 247019 | 247231 | 1137225 | -12268 | 12056 | 1.05 | 1.049 | 20250930 | 20250930 | 3 | 15 | 4 | 3 | 0 | 0 | 8439 | 8914 | 8988 | 475 | 4 | 0 | 38 | 1 | 1600000 | 0 | 1642999 | 0 |  | 0 | 0 | 2 | 83 | 100
447 | 20231130 | 29 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.2667 | 0.295 | 1127826 | 283109 | 304995 | 1137600 | -49600 | 27714 | 1.175 | 1.091 | 20250930 | 20250930 | 0 | 15 | 4 | 3 | 0 | 0 | 8813 | 9321 | 9254 | 508 | 2 | 0 | 19 | 0 | 1600000 | 0 | 1655772 | 0 |  | 0 | 0 | 4 | 96 | 100
448 | 20231231 | 29 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.3 | 0.3262 | 1127826 | 319400 | 337573 | 1137976 | -48497 | 30324 | 1.152 | 1.09 | 20250930 | 20250930 | 0 | 15 | 5 | 5 | 0 | 0 | 9146 | 8894 | 8411 | -252 | 2 | 0 | 19 | 0 | 1600000 | 0 | 1647542 | 0 |  | 0 | 0 | 3 | 88 | 100
449 | 20240131 | 29 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.3333 | 0.3537 | 1127826 | 355892 | 381744 | 1138352 | -43020 | 17168 | 1.121 | 1.045 | 20250930 | 20250930 | 0 | 15 | 5 | 4 | 0 | 0 | 9434 | 9503 | 9121 | 69 | 3 | 0 | 29 | 1 | 1600000 | 0 | 1628427 | 0 |  | 0 | 0 | 3 | 87 | 100
450 | 20240229 | 29 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.3667 | 0.3677 | 1127826 | 392584 | 395209 | 1138728 | -22118 | 19493 | 1.056 | 1.049 | 20250930 | 20250930 | 0 | 15 | 6 | 5 | 0 | 0 | 9674 | 9739 | 10330 | 65 | 2 | 0 | 19 | 0 | 1600000 | 0 | 1657792 | 0 |  | 0 | 0 | 4 | 88 | 100
451 | 20240331 | 29 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.4 | 0.3919 | 1127826 | 429476 | 427268 | 1139104 | -12519 | 14727 | 1.029 | 1.034 | 20250930 | 20250930 | 8 | 15 | 6 | 5 | 0 | 0 | 9864 | 10063 | 10170 | 199 | 4 | 0 | 38 | 1 | 1600000 | 0 | 1631818 | 0 |  | 0 | 0 | 3 | 85 | 100
452 | 20240430 | 29 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.4333 | 0.4311 | 1127826 | 466569 | 459861 | 1139480 | -19637 | 26345 | 1.042 | 1.057 | 20250930 | 20250930 | 2 | 15 | 7 | 6 | 0 | 0 | 10001 | 10220 | 10764 | 219 | 2 | 0 | 19 | 0 | 1600000 | 0 | 1648827 | 0 |  | 0 | 0 | 4 | 88 | 100
453 | 20240531 | 29 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.4667 | 0.4628 | 1127826 | 503863 | 499245 | 1139856 | -18095 | 22713 | 1.036 | 1.046 | 20250930 | 20250930 | 3 | 15 | 7 | 6 | 0 | 0 | 10084 | 9968 | 9525 | -116 | 2 | 0 | 19 | 0 | 1600000 | 0 | 1624191 | 0 |  | 0 | 0 | 2 | 86 | 100
454 | 20240630 | 29 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.5 | 0.4898 | 1127826 | 541356 | 528869 | 1140232 | -11053 | 23540 | 1.02 | 1.044 | 20250930 | 20250930 | 10 | 15 | 8 | 7 | 0 | 0 | 10112 | 9802 | 9444 | -310 | 2 | 0 | 19 | 0 | 1600000 | 0 | 1667971 | 0 |  | 0 | 0 | 1 | 81 | 100
455 | 20240731 | 29 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.5333 | 0.5356 | 1127826 | 579051 | 592992 | 1140608 | -25013 | 11072 | 1.043 | 1.019 | 20250930 | 20250930 | 0 | 15 | 8 | 7 | 0 | 0 | 10084 | 10163 | 10617 | 79 | 2 | 1 | 37 | 0 | 1600000 | 0 | 1619883 | 0 |  | 1 | 17000 | 2 | 78 | 94.6
456 | 20240831 | 29 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.5667 | 0.5874 | 1127826 | 616946 | 637783 | 1140984 | -45539 | 24702 | 1.074 | 1.039 | 20250930 | 20250930 | 0 | 15 | 9 | 9 | 0 | 0 | 10001 | 9716 | 9854 | -285 | 3 | 0 | 29 | 1 | 1600000 | 0 | 1595783 | 0 |  | 1 | 14000 | 2 | 86 | 100
457 | 20240930 | 29 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.6 | 0.6217 | 1127826 | 655041 | 680963 | 1141360 | -46128 | 20206 | 1.07 | 1.03 | 20250930 | 20250930 | 0 | 15 | 9 | 9 | 0 | 0 | 9864 | 9722 | 10316 | -142 | 1 | 0 | 10 | 0 | 1600000 | 0 | 1669017 | 0 |  | 1 | 14000 | 3 | 84 | 100
458 | 20241031 | 29 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.6333 | 0.668 | 1127826 | 693337 | 741205 | 1141736 | -60051 | 12183 | 1.087 | 1.016 | 20250930 | 20250930 | 0 | 15 | 10 | 9 | 0 | 0 | 9674 | 9771 | 10337 | 97 | 3 | 0 | 29 | 1 | 1600000 | 0 | 1658989 | 0 |  | 1 | 15000 | 5 | 88 | 100
459 | 20241130 | 29 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.6667 | 0.6801 | 1127826 | 731834 | 759323 | 1142112 | -35200 | 7711 | 1.048 | 1.01 | 20250930 | 20250930 | 0 | 15 | 10 | 9 | 0 | 0 | 9434 | 9439 | 9433 | 5 | 4 | 0 | 38 | 1 | 1600000 | 0 | 1602609 | 0 |  | 1 | 15000 | 3 | 85 | 100
460 | 20241231 | 29 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.7 | 0.6952 | 1127826 | 770531 | 772405 | 1142488 | -13534 | 11660 | 1.017 | 1.015 | 20250930 | 20250930 | 4 | 15 | 11 | 10 | 0 | 0 | 9146 | 8943 | 8624 | -203 | 3 | 0 | 29 | 1 | 1600000 | 0 | 1663464 | 0 |  | 1 | 16000 | 3 | 81 | 100
461 | 20250131 | 29 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.7333 | 0.7272 | 1127826 | 809428 | 809376 | 1142864 | -10727 | 10779 | 1.013 | 1.013 | 20250930 | 20250930 | 7 | 15 | 11 | 11 | 0 | 0 | 8813 | 8716 | 8406 | -97 | 4 | 0 | 38 | 1 | 1600000 | 76190 | 1608778 | 0 | 0 | 1 | 13000 | 4 | 86 | 100
462 | 20250228 | 29 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deploy | Green | 0.7667 | 0.7693 | 1127826 | 848526 | 863073 | 1143240 | -19111 | 4564 | 1.022 | 1.005 | 20250930 | 20250930 | 0 | 15 | 12 | 11 | 0 | 0 | 8439 | 8497 | 8381 | 58 | 3 | 0 | 29 | 1 | 1600000 | 266667 | 1640121 | 0 | 0 | 1 | 17000 | 3 | 83 | 100
463 | 20250331 | 29 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deploy | Green | 0.8 | 0.7992 | 1127826 | 887825 | 909673 | 1145872 | -13534 | -8314 | 1.015 | 0.991 | 20250930 | 20250930 | 1 | 15 | 12 | 11 | 0 | 0 | 8027 | 8073 | 8471 | 46 | 3 | 0 | 29 | 1 | 1600000 | 457143 | 1651489 | 97100 | 0.2124 | 1 | 17000 | 2 | 84 | 100
464 | 20250430 | 29 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deploy | Green | 0.8333 | 0.8432 | 1127826 | 927324 | 956767 | 1145485 | -23659 | -5784 | 1.026 | 0.994 | 20250930 | 20250930 | 0 | 15 | 13 | 12 | 0 | 0 | 7584 | 7905 | 8112 | 321 | 2 | 0 | 19 | 0 | 1600000 | 647619 | 1599451 | 275199 | 0.4249 | 1 | 12000 | 2 | 81 | 100
465 | 20250531 | 29 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deploy | Green | 0.8667 | 0.8875 | 1127826 | 967023 | 1010333 | 1146670 | -33923 | -9387 | 1.035 | 0.991 | 20250930 | 20250930 | 0 | 15 | 13 | 12 | 0 | 0 | 7112 | 7627 | 7573 | 515 | 2 | 0 | 19 | 0 | 1600000 | 838095 | 1614580 | 439789 | 0.5247 | 1 | 9000 | 0 | 85 | 100
466 | 20250630 | 29 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deploy | Green | 0.9 | 0.9381 | 1127826 | 1006923 | 1074867 | 1148640 | -51091 | -16853 | 1.051 | 0.984 | 20250930 | 20250930 | 0 | 15 | 14 | 13 | 0 | 0 | 6618 | 6714 | 6477 | 96 | 1 | 0 | 10 | 0 | 1600000 | 1028571 | 1596501 | 563722 | 0.5481 | 1 | 15000 | 1 | 83 | 100
467 | 20250731 | 29 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deploy | Green | 0.9333 | 0.963 | 1127826 | 1047024 | 1115292 | 1151624 | -39072 | -29196 | 1.037 | 0.974 | 20250930 | 20250930 | 0 | 15 | 14 | 14 | 0 | 0 | 6107 | 6252 | 6355 | 145 | 2 | 0 | 19 | 0 | 1600000 | 1219048 | 1615749 | 756323 | 0.6204 | 1 | 17000 | 2 | 86 | 100
468 | 20250831 | 29 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deploy | Green | 0.9667 | 0.9963 | 1127826 | 1087325 | 1148176 | 1150804 | -36328 | -24523 | 1.033 | 0.979 | 20250930 | 20250930 | 0 | 15 | 15 | 14 | 0 | 0 | 5584 | 5935 | 5970 | 351 | 1 | 0 | 10 | 0 | 1600000 | 1409524 | 1662174 | 964718 | 0.6844 | 1 | 11000 | 2 | 83 | 100
469 | 20250930 | 29 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deploy | Green | 1 | 0.9969 | 1127826 | 1127826 | 1161709 | 1161709 | 3496 | -37379 | 0.997 | 0.968 | 20250930 | 20250930 | 3 | 15 | 15 | 15 | 0 | 0 | 5056 | 5237 | 4978 | 181 | 0 | 0 | 0 | 0 | 1600000 | 1600000 | 1592792 | 1118775 | 0.6992 | 1 | 9000 | 3 | 80 | 98.6
470 | 20251031 | 29 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deploy | Green | 1 | 0.9971 | 1127826 | 1127826 | 1163294 | 1163294 | 3271 | -38739 | 0.997 | 0.967 | 20250930 | 20250930 | 3 | 15 | 15 | 14 | 0 | 0 | 5056 | 5165 | 4931 | 109 | 1 | 0 | 10 | 0 | 1600000 | 1600000 | 1624048 | 1246777 | 0.7792 | 1 | 12000 | 0 | 84 | 98.7
471 | 20251130 | 29 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Completed | Completed | Green | 1 | 1 | 1127826 | 1127826 | 1166457 | 1166457 | 0 | -38631 | 1 | 0.967 | 20250930 | 20250930 | 0 | 15 | 15 | 14 | 0 | 0 | 5056 | 5213 | 5093 | 157 | 0 | 0 | 0 | 0 | 1600000 | 1600000 | 1622573 | 1490726 | 0.9317 | 1 | 15000 | 0 | 83 | 98.8
472 | 20231031 | 30 | 4 | 3 | 6 | 30 | 6 | 2 | 6 | Active | Deliver | Green | 0.4333 | 0.4811 | 713892 | 295329 | 334233 | 736023 | -48124 | 9220 | 1.163 | 1.028 | 20250331 | 20250331 | 0 | 15 | 7 | 7 | 0 | 0 | 6330 | 7162 | 6860 | 832 | 2 | 0 | 18 | 0 | 800000 | 0 | 850629 | 0 |  | 0 | 0 | 3 | 87 | 100
473 | 20231130 | 30 | 4 | 3 | 6 | 30 | 6 | 2 | 6 | Active | Deliver | Green | 0.4667 | 0.5124 | 713892 | 318935 | 350138 | 736737 | -46863 | 15660 | 1.147 | 1.045 | 20250331 | 20250331 | 0 | 15 | 7 | 7 | 0 | 0 | 6383 | 7087 | 7326 | 704 | 1 | 0 | 9 | 0 | 800000 | 0 | 876509 | 0 |  | 0 | 0 | 4 | 89 | 100
474 | 20231231 | 30 | 4 | 3 | 6 | 30 | 6 | 2 | 6 | Active | Deliver | Green | 0.5 | 0.5689 | 713892 | 342668 | 394360 | 737450 | -63465 | 11773 | 1.185 | 1.03 | 20250331 | 20250331 | 0 | 15 | 8 | 8 | 0 | 0 | 6400 | 7203 | 7298 | 803 | 2 | 0 | 18 | 0 | 800000 | 0 | 847267 | 0 |  | 0 | 0 | 4 | 91 | 100
475 | 20240131 | 30 | 4 | 3 | 6 | 30 | 6 | 2 | 6 | Active | Deliver | Green | 0.5333 | 0.6146 | 713892 | 366528 | 427261 | 738164 | -72230 | 11497 | 1.197 | 1.027 | 20250331 | 20250331 | 0 | 15 | 8 | 7 | 0 | 0 | 6383 | 6610 | 7029 | 227 | 2 | 0 | 18 | 0 | 800000 | 0 | 875451 | 0 |  | 0 | 0 | 1 | 96 | 100
476 | 20240229 | 30 | 4 | 3 | 6 | 30 | 6 | 2 | 6 | Active | Deliver | Green | 0.5667 | 0.6521 | 713892 | 390515 | 463170 | 738878 | -75014 | 2359 | 1.192 | 1.005 | 20250331 | 20250331 | 0 | 15 | 9 | 9 | 0 | 0 | 6330 | 7182 | 7421 | 852 | 0 | 0 | 0 | 0 | 800000 | 0 | 862560 | 0 |  | 0 | 0 | 4 | 90 | 100
477 | 20240331 | 30 | 4 | 3 | 6 | 30 | 6 | 2 | 6 | Active | Deliver | Green | 0.6 | 0.6734 | 713892 | 414628 | 476446 | 739592 | -66107 | 4289 | 1.159 | 1.009 | 20250331 | 20250331 | 0 | 15 | 9 | 8 | 0 | 0 | 6244 | 6450 | 6391 | 206 | 1 | 0 | 9 | 0 | 800000 | 0 | 877138 | 0 |  | 0 | 0 | 2 | 92 | 100
478 | 20240430 | 30 | 4 | 3 | 6 | 30 | 6 | 2 | 6 | Active | Deliver | Green | 0.6333 | 0.7162 | 713892 | 438869 | 513879 | 741089 | -72420 | -2590 | 1.165 | 0.995 | 20250331 | 20250331 | 0 | 15 | 10 | 10 | 0 | 0 | 6124 | 6574 | 6963 | 450 | 2 | 0 | 18 | 0 | 800000 | 0 | 883020 | 0 |  | 0 | 0 | 4 | 90 | 100
479 | 20240531 | 30 | 4 | 3 | 6 | 30 | 6 | 2 | 6 | Active | Deliver | Green | 0.6667 | 0.721 | 713892 | 463237 | 516611 | 741599 | -51479 | -1895 | 1.111 | 0.996 | 20250331 | 20250331 | 0 | 15 | 10 | 9 | 0 | 0 | 5972 | 6626 | 6234 | 654 | 0 | 0 | 0 | 0 | 800000 | 0 | 854526 | 0 |  | 0 | 0 | 3 | 86 | 100
480 | 20240630 | 30 | 4 | 3 | 6 | 30 | 6 | 2 | 6 | Active | Deploy | Green | 0.7 | 0.7678 | 713892 | 487731 | 545382 | 741734 | -60395 | 2744 | 1.124 | 1.005 | 20250331 | 20250331 | 0 | 15 | 11 | 11 | 0 | 0 | 5789 | 6278 | 6378 | 489 | 1 | 0 | 9 | 0 | 800000 | 0 | 868554 | 0 |  | 0 | 0 | 5 | 86 | 100
481 | 20240731 | 30 | 4 | 3 | 6 | 30 | 6 | 2 | 6 | Active | Deploy | Green | 0.7333 | 0.8032 | 713892 | 512352 | 580115 | 744276 | -61046 | -6717 | 1.119 | 0.988 | 20250331 | 20250331 | 0 | 15 | 11 | 11 | 0 | 0 | 5578 | 6316 | 6356 | 738 | 2 | 0 | 18 | 0 | 800000 | 38095 | 862819 | 0 | 0 | 0 | 0 | 4 | 87 | 100
482 | 20240831 | 30 | 4 | 3 | 6 | 30 | 6 | 2 | 6 | Active | Deploy | Green | 0.7667 | 0.8261 | 713892 | 537101 | 602042 | 746363 | -52645 | -12296 | 1.098 | 0.98 | 20250331 | 20250331 | 0 | 15 | 12 | 12 | 0 | 0 | 5342 | 5845 | 6172 | 503 | 3 | 0 | 27 | 0 | 800000 | 133333 | 855030 | 0 | 0 | 1 | 8000 | 3 | 88 | 100
483 | 20240930 | 30 | 4 | 3 | 6 | 30 | 6 | 2 | 6 | Active | Deploy | Green | 0.8 | 0.8939 | 713892 | 561976 | 655801 | 748107 | -76172 | -17653 | 1.136 | 0.973 | 20250331 | 20250331 | 0 | 15 | 12 | 12 | 0 | 0 | 5081 | 5245 | 5349 | 164 | 3 | 0 | 27 | 0 | 800000 | 228571 | 851215 | 55312 | 0.242 | 1 | 11000 | 3 | 87 | 100
484 | 20241031 | 30 | 4 | 3 | 6 | 30 | 6 | 2 | 6 | Active | Deploy | Green | 0.8333 | 0.9236 | 713892 | 586978 | 672115 | 747580 | -72373 | -12764 | 1.123 | 0.981 | 20250331 | 20250331 | 0 | 15 | 13 | 13 | 0 | 0 | 4800 | 5070 | 5141 | 270 | 0 | 0 | 0 | 0 | 800000 | 323810 | 880683 | 151418 | 0.4676 | 1 | 11000 | 1 | 86 | 100
485 | 20241130 | 30 | 4 | 3 | 6 | 30 | 6 | 2 | 6 | Active | Deploy | Green | 0.8667 | 0.9804 | 713892 | 612107 | 722075 | 750124 | -87793 | -22175 | 1.143 | 0.969 | 20250331 | 20250331 | 0 | 15 | 13 | 12 | 0 | 0 | 4502 | 5014 | 5320 | 512 | 0 | 0 | 0 | 0 | 800000 | 419048 | 878784 | 243166 | 0.5803 | 1 | 10000 | 0 | 84 | 100
486 | 20241231 | 30 | 4 | 3 | 6 | 30 | 6 | 2 | 6 | Completed | Completed | Green | 0.9 | 1 | 713892 | 637363 | 739421 | 751440 | -76529 | -25529 | 1.12 | 0.965 | 20250331 | 20250331 | 0 | 15 | 14 | 14 | 0 | 0 | 4189 | 4653 | 4454 | 464 | 0 | 0 | 0 | 0 | 800000 | 514286 | 873241 | 346671 | 0.6741 | 1 | 9000 | 0 | 82 | 100
487 | 20231130 | 31 | 10 | 7 | 7 | 31 | 7 | 2 | 7 | Active | Initiate & Design | Red | 0.0833 | 0.0182 | 374954 | 28955 | 7068 | 390593 | 22131 | -244 | 0.236 | 0.966 | 20241031 | 20241130 | 30 | 6 | 1 | 0 | 1 | 0 | 2116 | 1627 | 1633 | -489 | 10 | 2 | 154 | 3 | 500000 | 0 | 460487 | 0 |  | 0 | 0 | 5 | 36 | 41.1
488 | 20231231 | 31 | 10 | 7 | 7 | 31 | 7 | 2 | 7 | Active | Initiate & Design | Green | 0.1667 | 0.0841 | 374954 | 58326 | 27152 | 389327 | 26792 | 4382 | 0.541 | 1.161 | 20241031 | 20241130 | 39 | 6 | 1 | 0 | 1 | 0 | 2521 | 2116 | 2213 | -405 | 7 | 1 | 101 | 2 | 500000 | 0 | 467425 | 0 |  | 1 | 3000 | 5 | 66 | 71.6
489 | 20240131 | 31 | 10 | 7 | 7 | 31 | 7 | 2 | 7 | Active | Initiate & Design | Green | 0.25 | 0.1594 | 374954 | 88114 | 55340 | 390890 | 28346 | 4428 | 0.678 | 1.08 | 20241031 | 20241130 | 43 | 6 | 2 | 0 | 1 | 0 | 2869 | 2244 | 2274 | -625 | 7 | 1 | 101 | 2 | 500000 | 0 | 480062 | 0 |  | 1 | 5000 | 6 | 62 | 74.4
490 | 20240229 | 31 | 10 | 7 | 7 | 31 | 7 | 2 | 7 | Active | Initiate & Design | Green | 0.3333 | 0.243 | 374954 | 118319 | 85939 | 392452 | 27205 | 5175 | 0.77 | 1.06 | 20241031 | 20241130 | 43 | 6 | 2 | 0 | 1 | 0 | 3136 | 2312 | 2218 | -824 | 7 | 1 | 101 | 2 | 500000 | 0 | 460539 | 0 |  | 1 | 6000 | 5 | 67 | 75.8
491 | 20240331 | 31 | 10 | 7 | 7 | 31 | 7 | 2 | 7 | Active | Initiate & Design | Green | 0.4167 | 0.3346 | 374954 | 148940 | 123743 | 394014 | 23480 | 1717 | 0.842 | 1.014 | 20241031 | 20241130 | 39 | 6 | 3 | 1 | 1 | 0 | 3304 | 2511 | 2572 | -793 | 7 | 1 | 101 | 2 | 500000 | 0 | 476463 | 0 |  | 1 | 5000 | 5 | 72 | 78.8
492 | 20240430 | 31 | 10 | 7 | 7 | 31 | 7 | 2 | 7 | Active | Deliver | Green | 0.5 | 0.3984 | 374954 | 179978 | 148678 | 395576 | 30596 | 704 | 0.83 | 1.005 | 20241031 | 20241231 | 48 | 6 | 3 | 2 | 1 | 0 | 3362 | 2552 | 2699 | -810 | 8 | 1 | 113 | 2 | 500000 | 0 | 462822 | 0 |  | 1 | 3000 | 3 | 72 | 77.1
493 | 20240531 | 31 | 10 | 7 | 7 | 31 | 7 | 2 | 7 | Active | Deliver | Green | 0.5833 | 0.4939 | 374954 | 211432 | 185676 | 397351 | 26242 | -486 | 0.876 | 0.997 | 20241031 | 20241130 | 41 | 6 | 4 | 3 | 1 | 0 | 3304 | 2428 | 2299 | -876 | 8 | 1 | 113 | 2 | 500000 | 0 | 476513 | 0 |  | 1 | 4000 | 3 | 74 | 79.2
494 | 20240630 | 31 | 10 | 7 | 7 | 31 | 7 | 2 | 7 | Active | Deliver | Green | 0.6667 | 0.5701 | 374954 | 243303 | 215495 | 399361 | 29542 | -1734 | 0.879 | 0.992 | 20241031 | 20241231 | 45 | 6 | 4 | 3 | 1 | 0 | 3136 | 2539 | 2414 | -597 | 7 | 1 | 101 | 2 | 500000 | 0 | 460392 | 0 |  | 1 | 4000 | 4 | 71 | 79.9
495 | 20240731 | 31 | 10 | 7 | 7 | 31 | 7 | 2 | 7 | Active | Deliver | Green | 0.75 | 0.6367 | 374954 | 275591 | 242788 | 401641 | 36858 | -4055 | 0.866 | 0.983 | 20241031 | 20241231 | 53 | 6 | 5 | 3 | 1 | 0 | 2869 | 2244 | 2302 | -625 | 7 | 1 | 101 | 2 | 500000 | 53571 | 472881 | 0 | 0 | 1 | 5000 | 6 | 73 | 79.1
496 | 20240831 | 31 | 10 | 7 | 7 | 31 | 7 | 2 | 7 | Active | Deliver | Green | 0.8333 | 0.6922 | 374954 | 308296 | 272981 | 405886 | 48753 | -13438 | 0.842 | 0.951 | 20241031 | 20241231 | 66 | 6 | 5 | 4 | 1 | 0 | 2521 | 2110 | 2085 | -411 | 6 | 1 | 89 | 2 | 500000 | 202381 | 469839 | 80915 | 0.3998 | 1 | 5000 | 1 | 70 | 77.9
497 | 20240930 | 31 | 10 | 7 | 7 | 31 | 7 | 2 | 7 | Active | Deploy | Green | 0.9167 | 0.7756 | 374954 | 341416 | 304842 | 407186 | 50602 | -14028 | 0.852 | 0.954 | 20241031 | 20241231 | 66 | 6 | 6 | 3 | 2 | 1 | 2116 | 1526 | 1492 | -590 | 5 | 1 | 77 | 1 | 500000 | 351190 | 464039 | 203043 | 0.5782 | 2 | 7000 | 2 | 72 | 75.6
498 | 20241031 | 31 | 10 | 7 | 7 | 31 | 7 | 2 | 7 | Active | Deploy | Green | 1 | 0.8502 | 374954 | 374954 | 341158 | 410362 | 56168 | -22372 | 0.85 | 0.934 | 20241031 | 20241231 | 70 | 6 | 6 | 3 | 2 | 1 | 1681 | 1270 | 1194 | -411 | 4 | 0 | 47 | 1 | 500000 | 500000 | 479922 | 323909 | 0.6478 | 2 | 8000 | 4 | 74 | 84.5
499 | 20241130 | 31 | 10 | 7 | 7 | 31 | 7 | 2 | 7 | Active | Deploy | Green | 1 | 0.8502 | 374954 | 374954 | 345830 | 412966 | 56168 | -27044 | 0.85 | 0.922 | 20241031 | 20241231 | 70 | 6 | 6 | 4 | 2 | 1 | 1681 | 1246 | 1227 | -435 | 4 | 1 | 65 | 1 | 500000 | 500000 | 469458 | 463707 | 0.9274 | 2 | 7000 | 4 | 66 | 75.1
500 | 20241231 | 31 | 10 | 7 | 7 | 31 | 7 | 2 | 7 | Active | Deploy | Green | 1 | 0.8674 | 374954 | 374954 | 355519 | 415100 | 49719 | -30284 | 0.867 | 0.915 | 20241031 | 20241231 | 62 | 6 | 6 | 3 | 2 | 1 | 1681 | 1282 | 1363 | -399 | 4 | 1 | 65 | 1 | 500000 | 500000 | 460139 | 402557 | 0.8051 | 2 | 10000 | 2 | 71 | 75.6
501 | 20250131 | 31 | 10 | 7 | 7 | 31 | 7 | 2 | 7 | Active | Deploy | Green | 1 | 0.8867 | 374954 | 374954 | 370834 | 418169 | 42482 | -38362 | 0.887 | 0.897 | 20241031 | 20241231 | 53 | 6 | 6 | 5 | 1 | 0 | 1681 | 1409 | 1464 | -272 | 3 | 1 | 54 | 1 | 500000 | 500000 | 466450 | 462830 | 0.9257 | 2 | 9000 | 2 | 70 | 77.8
502 | 20250228 | 31 | 10 | 7 | 7 | 31 | 7 | 2 | 7 | Active | Deploy | Green | 1 | 0.8867 | 374954 | 374954 | 373461 | 420251 | 42482 | -40989 | 0.887 | 0.89 | 20241031 | 20241231 | 53 | 6 | 6 | 4 | 1 | 0 | 1681 | 1295 | 1329 | -386 | 5 | 1 | 77 | 1 | 500000 | 500000 | 462547 | 403071 | 0.8061 | 2 | 6000 | 1 | 66 | 75.9
503 | 20250331 | 31 | 10 | 7 | 7 | 31 | 7 | 2 | 7 | Active | Deploy | Green | 1 | 0.8871 | 374954 | 374954 | 377854 | 421386 | 42332 | -45232 | 0.887 | 0.88 | 20241031 | 20241231 | 53 | 6 | 6 | 5 | 1 | 0 | 1681 | 1305 | 1232 | -376 | 4 | 0 | 47 | 1 | 500000 | 500000 | 472639 | 423076 | 0.8462 | 2 | 11000 | 1 | 73 | 84.3
504 | 20250430 | 31 | 10 | 7 | 7 | 31 | 7 | 2 | 7 | Active | Deploy | Green | 1 | 0.8871 | 374954 | 374954 | 377854 | 421386 | 42332 | -45232 | 0.887 | 0.88 | 20241031 | 20241231 | 53 | 6 | 6 | 4 | 1 | 0 | 1681 | 1228 | 1169 | -453 | 3 | 0 | 36 | 1 | 500000 | 500000 | 460536 | 401672 | 0.8033 | 2 | 8000 | 3 | 69 | 82.6
505 | 20250531 | 31 | 10 | 7 | 7 | 31 | 7 | 2 | 7 | Active | Deploy | Green | 1 | 0.8871 | 374954 | 374954 | 377854 | 421386 | 42332 | -45232 | 0.887 | 0.88 | 20241031 | 20241231 | 53 | 6 | 6 | 5 | 1 | 0 | 1681 | 1251 | 1177 | -430 | 5 | 1 | 77 | 1 | 500000 | 500000 | 471109 | 441928 | 0.8839 | 2 | 7000 | 1 | 67 | 75.5
506 | 20250630 | 31 | 10 | 7 | 7 | 31 | 7 | 2 | 7 | Active | Deploy | Green | 1 | 0.8871 | 374954 | 374954 | 377854 | 421386 | 42332 | -45232 | 0.887 | 0.88 | 20241031 | 20241231 | 53 | 6 | 6 | 5 | 1 | 0 | 1681 | 1392 | 1484 | -289 | 5 | 0 | 59 | 1 | 500000 | 500000 | 474016 | 446488 | 0.893 | 2 | 10000 | 2 | 72 | 85.5
507 | 20250731 | 31 | 10 | 7 | 7 | 31 | 7 | 2 | 7 | Active | Deploy | Green | 1 | 0.8871 | 374954 | 374954 | 377854 | 421386 | 42332 | -45232 | 0.887 | 0.88 | 20241031 | 20241231 | 53 | 6 | 6 | 5 | 1 | 0 | 1681 | 1328 | 1382 | -353 | 3 | 0 | 36 | 1 | 500000 | 500000 | 457917 | 405568 | 0.8111 | 2 | 12000 | 4 | 76 | 83.8
508 | 20250831 | 31 | 10 | 7 | 7 | 31 | 7 | 2 | 7 | Active | Deploy | Green | 1 | 0.8871 | 374954 | 374954 | 377854 | 421386 | 42332 | -45232 | 0.887 | 0.88 | 20241031 | 20241231 | 53 | 6 | 6 | 5 | 1 | 0 | 1681 | 1262 | 1295 | -419 | 3 | 0 | 36 | 1 | 500000 | 500000 | 457596 | 414735 | 0.8295 | 2 | 11000 | 1 | 76 | 82.9
509 | 20240831 | 32 | 2 | 4 | 8 | 32 | 8 | 1 | 8 | Active | Initiate & Design | Amber | 0.0667 | 0.0065 | 1378365 | 85030 | 6744 | 1442689 | 76071 | 2215 | 0.106 | 1.337 | 20251031 | 20251130 | 35 | 8 | 1 | 0 | 1 | 0 | 7464 | 6997 | 7195 | -467 | 10 | 1 | 140 | 3 | 2800000 | 0 | 2634437 | 0 |  | 0 | 0 | 6 | 52 | 60.5
510 | 20240930 | 32 | 2 | 4 | 8 | 32 | 8 | 1 | 8 | Active | Initiate & Design | Green | 0.1333 | 0.0635 | 1378365 | 171040 | 75650 | 1449121 | 83514 | 11876 | 0.512 | 1.157 | 20251031 | 20251130 | 41 | 8 | 1 | 0 | 1 | 0 | 8692 | 7743 | 7815 | -949 | 10 | 1 | 140 | 3 | 2800000 | 0 | 2698985 | 0 |  | 0 | 0 | 4 | 61 | 72.1
511 | 20241031 | 32 | 2 | 4 | 8 | 32 | 8 | 1 | 8 | Active | Initiate & Design | Green | 0.2 | 0.137 | 1378365 | 258030 | 180424 | 1455553 | 69194 | 8412 | 0.732 | 1.046 | 20251031 | 20251130 | 37 | 8 | 2 | 0 | 1 | 0 | 9811 | 9344 | 8981 | -467 | 9 | 1 | 127 | 2 | 2800000 | 0 | 2682230 | 0 |  | 0 | 0 | 5 | 63 | 79.3
512 | 20241130 | 32 | 2 | 4 | 8 | 32 | 8 | 1 | 8 | Active | Initiate & Design | Green | 0.2667 | 0.2017 | 1378365 | 346000 | 262848 | 1461986 | 67984 | 15168 | 0.803 | 1.058 | 20251031 | 20251130 | 38 | 8 | 2 | 1 | 1 | 0 | 10771 | 10443 | 10855 | -328 | 8 | 1 | 115 | 2 | 2800000 | 0 | 2725978 | 0 |  | 0 | 0 | 4 | 67 | 83.8
513 | 20241231 | 32 | 2 | 4 | 8 | 32 | 8 | 1 | 8 | Active | Initiate & Design | Green | 0.3333 | 0.2901 | 1378365 | 434951 | 387394 | 1468418 | 35087 | 12470 | 0.919 | 1.032 | 20251031 | 20251130 | 25 | 8 | 3 | 1 | 1 | 0 | 11530 | 9920 | 9364 | -1610 | 5 | 1 | 79 | 1 | 2800000 | 0 | 2686846 | 0 |  | 1 | 17000 | 6 | 73 | 85.3
514 | 20250131 | 32 | 2 | 4 | 8 | 32 | 8 | 1 | 8 | Active | Deliver | Green | 0.4 | 0.3518 | 1378365 | 524881 | 467089 | 1474851 | 39972 | 17820 | 0.924 | 1.038 | 20251031 | 20251130 | 29 | 8 | 3 | 2 | 1 | 0 | 12055 | 10681 | 10206 | -1374 | 7 | 1 | 103 | 2 | 2800000 | 0 | 2695215 | 0 |  | 1 | 14000 | 3 | 76 | 86.4
515 | 20250228 | 32 | 2 | 4 | 8 | 32 | 8 | 1 | 8 | Active | Deliver | Green | 0.4667 | 0.4087 | 1378365 | 615792 | 558166 | 1481283 | 52454 | 5172 | 0.915 | 1.009 | 20251031 | 20251130 | 34 | 8 | 4 | 2 | 1 | 0 | 12324 | 11727 | 11994 | -597 | 5 | 0 | 61 | 1 | 2800000 | 0 | 2740257 | 0 |  | 1 | 12000 | 5 | 80 | 94.8
516 | 20250331 | 32 | 2 | 4 | 8 | 32 | 8 | 1 | 8 | Active | Deliver | Green | 0.5333 | 0.4583 | 1378365 | 707683 | 638705 | 1491053 | 75978 | -7000 | 0.893 | 0.989 | 20251031 | 20251231 | 45 | 8 | 4 | 2 | 1 | 0 | 12324 | 11174 | 10746 | -1150 | 6 | 1 | 91 | 2 | 2800000 | 0 | 2710475 | 0 |  | 1 | 14000 | 3 | 70 | 83.8
517 | 20250430 | 32 | 2 | 4 | 8 | 32 | 8 | 1 | 8 | Active | Deliver | Green | 0.6 | 0.498 | 1378365 | 800554 | 693074 | 1497040 | 114128 | -6648 | 0.857 | 0.99 | 20251031 | 20251231 | 60 | 8 | 5 | 4 | 1 | 0 | 12055 | 11775 | 12242 | -280 | 6 | 1 | 91 | 2 | 2800000 | 0 | 2621433 | 0 |  | 1 | 14000 | 3 | 71 | 83
518 | 20250531 | 32 | 2 | 4 | 8 | 32 | 8 | 1 | 8 | Active | Deliver | Green | 0.6667 | 0.5826 | 1378365 | 894406 | 830328 | 1510547 | 91371 | -27293 | 0.898 | 0.967 | 20251031 | 20251130 | 15 | 8 | 5 | 3 | 1 | 0 | 11530 | 11054 | 11599 | -476 | 7 | 1 | 103 | 2 | 2800000 | 0 | 2695795 | 0 |  | 1 | 13000 | 3 | 68 | 84.3
519 | 20250630 | 32 | 2 | 4 | 8 | 32 | 8 | 1 | 8 | Active | Deliver | Green | 0.7333 | 0.6544 | 1378365 | 989237 | 931312 | 1516554 | 87235 | -29310 | 0.912 | 0.969 | 20251031 | 20251031 | 12 | 8 | 6 | 5 | 1 | 0 | 10771 | 9596 | 9538 | -1175 | 6 | 1 | 91 | 2 | 2800000 | 133333 | 2679774 | 0 | 0 | 1 | 15000 | 5 | 72 | 83.3
520 | 20250731 | 32 | 2 | 4 | 8 | 32 | 8 | 1 | 8 | Active | Deliver | Green | 0.8 | 0.73 | 1378365 | 1085049 | 1065411 | 1530292 | 78843 | -59205 | 0.927 | 0.944 | 20251031 | 20251031 | 6 | 8 | 6 | 5 | 1 | 0 | 9811 | 8881 | 9271 | -930 | 8 | 1 | 115 | 2 | 2800000 | 800000 | 2625314 | 157898 | 0.1974 | 1 | 17000 | 6 | 72 | 83
521 | 20250831 | 32 | 2 | 4 | 8 | 32 | 8 | 1 | 8 | Active | Deploy | Green | 0.8667 | 0.8282 | 1378365 | 1181841 | 1216377 | 1538524 | 40279 | -74815 | 0.966 | 0.939 | 20251031 | 20251031 | -13 | 8 | 7 | 5 | 1 | 0 | 8692 | 7867 | 7997 | -825 | 3 | 1 | 54 | 1 | 2800000 | 1466667 | 2625234 | 697555 | 0.4756 | 1 | 17000 | 4 | 71 | 84.5
522 | 20250930 | 32 | 2 | 4 | 8 | 32 | 8 | 1 | 8 | Active | Deploy | Green | 0.9333 | 0.9014 | 1378365 | 1279613 | 1338593 | 1548097 | 37155 | -96135 | 0.971 | 0.928 | 20251031 | 20251031 | -17 | 8 | 7 | 5 | 1 | 0 | 7464 | 6586 | 6502 | -878 | 4 | 0 | 49 | 1 | 2800000 | 2133333 | 2673944 | 1260734 | 0.591 | 1 | 17000 | 1 | 82 | 92.3
523 | 20251031 | 32 | 2 | 4 | 8 | 32 | 8 | 1 | 8 | Completed | Completed | Green | 1 | 1 | 1378365 | 1378365 | 1507347 | 1558690 | 0 | -128982 | 1 | 0.914 | 20251031 | 20251031 | -35 | 8 | 8 | 7 | 0 | 0 | 6179 | 5655 | 5646 | -524 | 3 | 0 | 36 | 1 | 2800000 | 2800000 | 2693135 | 1728023 | 0.6172 | 2 | 23000 | 1 | 81 | 94.1
524 | 20231130 | 33 | 2 | 4 | 9 | 33 | 1 | 1 | 1 | Active | Initiate & Design | Green | 0.1111 | 0.0935 | 411545 | 42476 | 32887 | 420325 | 3997 | 5592 | 0.905 | 1.169 | 20240731 | 20240731 | 6 | 6 | 1 | 1 | 0 | 0 | 2476 | 2612 | 2525 | 136 | 4 | 0 | 41 | 1 | 500000 | 0 | 379361 | 0 |  | 0 | 0 | 5 | 74 | 94.9
525 | 20231231 | 33 | 2 | 4 | 9 | 33 | 1 | 1 | 1 | Active | Initiate & Design | Green | 0.2222 | 0.2056 | 411545 | 85764 | 79588 | 421696 | 1150 | 5026 | 0.987 | 1.063 | 20240731 | 20240731 | 5 | 6 | 1 | 0 | 0 | 0 | 3031 | 3100 | 3281 | 69 | 3 | 0 | 31 | 1 | 500000 | 0 | 364739 | 0 |  | 0 | 0 | 4 | 79 | 94
526 | 20240131 | 33 | 2 | 4 | 9 | 33 | 1 | 1 | 1 | Active | Deliver | Green | 0.3333 | 0.3523 | 411545 | 129865 | 135369 | 423068 | -15122 | 9618 | 1.116 | 1.071 | 20240731 | 20240731 | 0 | 6 | 2 | 2 | 0 | 0 | 3443 | 3341 | 3381 | -102 | 4 | 0 | 41 | 1 | 500000 | 0 | 379573 | 0 |  | 1 | 6000 | 4 | 78 | 100
527 | 20240229 | 33 | 2 | 4 | 9 | 33 | 1 | 1 | 1 | Active | Deliver | Green | 0.4444 | 0.466 | 411545 | 174780 | 183495 | 424440 | -17000 | 8285 | 1.097 | 1.045 | 20240731 | 20240731 | 0 | 6 | 3 | 2 | 0 | 0 | 3662 | 3858 | 3649 | 196 | 2 | 0 | 20 | 0 | 500000 | 0 | 366614 | 0 |  | 1 | 6000 | 4 | 79 | 98.5
528 | 20240331 | 33 | 2 | 4 | 9 | 33 | 1 | 1 | 1 | Active | Deliver | Green | 0.5556 | 0.5926 | 411545 | 220507 | 241765 | 425812 | -23375 | 2117 | 1.106 | 1.009 | 20240731 | 20240731 | 0 | 6 | 3 | 2 | 0 | 0 | 3662 | 3661 | 3444 | -1 | 2 | 1 | 38 | 0 | 500000 | 0 | 371254 | 0 |  | 1 | 5000 | 3 | 72 | 89.9
529 | 20240430 | 33 | 2 | 4 | 9 | 33 | 1 | 1 | 1 | Active | Deliver | Green | 0.6667 | 0.6946 | 411545 | 267047 | 285986 | 427220 | -18812 | -127 | 1.07 | 1 | 20240731 | 20240731 | 0 | 6 | 4 | 3 | 0 | 0 | 3443 | 3394 | 3428 | -49 | 4 | 0 | 41 | 1 | 500000 | 0 | 372614 | 0 |  | 1 | 5000 | 2 | 76 | 95.7
530 | 20240531 | 33 | 2 | 4 | 9 | 33 | 1 | 1 | 1 | Active | Deploy | Green | 0.7778 | 0.8017 | 411545 | 314400 | 338287 | 430788 | -15536 | -8351 | 1.049 | 0.975 | 20240731 | 20240731 | 0 | 6 | 5 | 4 | 0 | 0 | 3031 | 3060 | 2987 | 29 | 3 | 0 | 31 | 1 | 500000 | 103175 | 378747 | 0 | 0 | 1 | 4000 | 3 | 71 | 94.6
531 | 20240630 | 33 | 2 | 4 | 9 | 33 | 1 | 1 | 1 | Active | Deploy | Green | 0.8889 | 0.903 | 411545 | 362566 | 381527 | 432281 | -9059 | -9902 | 1.025 | 0.974 | 20240731 | 20240731 | 0 | 6 | 5 | 4 | 0 | 0 | 2476 | 2569 | 2422 | 93 | 0 | 0 | 0 | 0 | 500000 | 301587 | 380320 | 136380 | 0.4522 | 1 | 4000 | 3 | 70 | 93.5
532 | 20240731 | 33 | 2 | 4 | 9 | 33 | 1 | 1 | 1 | Active | Deploy | Green | 1 | 0.9999 | 411545 | 411545 | 430636 | 435320 | 41 | -19132 | 1 | 0.956 | 20240731 | 20240731 | 0 | 6 | 6 | 5 | 0 | 0 | 1845 | 1793 | 1848 | -52 | 1 | 0 | 10 | 0 | 500000 | 500000 | 382620 | 278221 | 0.5564 | 1 | 3000 | 2 | 69 | 91.2
533 | 20240831 | 33 | 2 | 4 | 9 | 33 | 1 | 1 | 1 | Completed | Completed | Green | 1 | 1 | 411545 | 411545 | 441491 | 441491 | 0 | -29946 | 1 | 0.932 | 20240731 | 20240731 | 0 | 6 | 6 | 5 | 0 | 0 | 1845 | 1802 | 1763 | -43 | 1 | 0 | 10 | 0 | 500000 | 500000 | 372597 | 329483 | 0.659 | 1 | 4000 | 2 | 69 | 90
534 | 20231031 | 34 | 4 | 3 | 10 | 34 | 2 | 2 | 2 | Active | Initiate & Design | Amber | 0.4762 | 0.2948 | 1066231 | 486453 | 324665 | 1303216 | 172128 | -10340 | 0.646 | 0.968 | 20240930 | 20250331 | 167 | 11 | 5 | 2 | 3 | 2 | 9546 | 7322 | 7175 | -2224 | 11 | 2 | 193 | 4 | 2700000 | 0 | 1900633 | 0 |  | 0 | 0 | 7 | 47 | 53.5
535 | 20231130 | 34 | 4 | 3 | 10 | 34 | 2 | 2 | 2 | Active | Initiate & Design | Amber | 0.5238 | 0.3222 | 1066231 | 537226 | 366931 | 1320812 | 193686 | -23391 | 0.64 | 0.936 | 20240930 | 20250331 | 186 | 11 | 6 | 1 | 4 | 2 | 9546 | 8353 | 8489 | -1193 | 9 | 2 | 164 | 3 | 2700000 | 0 | 1835384 | 0 |  | 1 | 12000 | 5 | 46 | 53.8
536 | 20231231 | 34 | 4 | 3 | 10 | 34 | 2 | 2 | 2 | Active | Deliver | Amber | 0.5714 | 0.3905 | 1066231 | 588385 | 449519 | 1333336 | 172022 | -33156 | 0.708 | 0.926 | 20240930 | 20250331 | 167 | 11 | 6 | 3 | 3 | 2 | 9439 | 8265 | 8206 | -1174 | 11 | 3 | 211 | 4 | 2700000 | 0 | 1862764 | 0 |  | 1 | 15000 | 8 | 40 | 48.8
537 | 20240131 | 34 | 4 | 3 | 10 | 34 | 2 | 2 | 2 | Active | Deliver | Amber | 0.619 | 0.4123 | 1066231 | 639932 | 481393 | 1346546 | 200325 | -41786 | 0.687 | 0.913 | 20240930 | 20250331 | 191 | 11 | 7 | 2 | 4 | 2 | 9229 | 7917 | 8369 | -1312 | 9 | 2 | 164 | 3 | 2700000 | 0 | 1896908 | 0 |  | 2 | 22000 | 6 | 49 | 55.4
538 | 20240229 | 34 | 4 | 3 | 10 | 34 | 2 | 2 | 2 | Active | Deliver | Amber | 0.6667 | 0.4701 | 1066231 | 691865 | 563508 | 1362270 | 190630 | -62273 | 0.724 | 0.889 | 20240930 | 20250331 | 182 | 11 | 7 | 2 | 4 | 2 | 8919 | 7264 | 7315 | -1655 | 10 | 2 | 178 | 3 | 2700000 | 0 | 1903329 | 0 |  | 2 | 19000 | 8 | 43 | 55.4
539 | 20240331 | 34 | 4 | 3 | 10 | 34 | 2 | 2 | 2 | Active | Deliver | Red | 0.7143 | 0.4932 | 1066231 | 744186 | 588401 | 1371441 | 218321 | -62536 | 0.707 | 0.894 | 20240930 | 20250430 | 204 | 11 | 8 | 4 | 4 | 2 | 8517 | 6803 | 6627 | -1714 | 11 | 3 | 211 | 4 | 2700000 | 0 | 1905646 | 0 |  | 3 | 40000 | 5 | 42 | 46.4
540 | 20240430 | 34 | 4 | 3 | 10 | 34 | 2 | 2 | 2 | Active | Deliver | Amber | 0.7619 | 0.5081 | 1066231 | 796893 | 624143 | 1387618 | 255141 | -82391 | 0.68 | 0.868 | 20240930 | 20250531 | 235 | 11 | 8 | 2 | 5 | 3 | 8031 | 6115 | 6020 | -1916 | 9 | 2 | 164 | 3 | 2700000 | 404082 | 1835772 | 0 | 0 | 3 | 37000 | 8 | 41 | 50.8
541 | 20240531 | 34 | 4 | 3 | 10 | 34 | 2 | 2 | 2 | Active | Deliver | Amber | 0.8095 | 0.5317 | 1066231 | 849987 | 652091 | 1397441 | 283072 | -85176 | 0.667 | 0.869 | 20240930 | 20250630 | 257 | 11 | 9 | 3 | 5 | 3 | 7472 | 6442 | 6543 | -1030 | 8 | 2 | 150 | 3 | 2700000 | 863265 | 1924980 | 174765 | 0.2024 | 3 | 43000 | 3 | 44 | 53.4
542 | 20240630 | 34 | 4 | 3 | 10 | 34 | 2 | 2 | 2 | Active | Deliver | Amber | 0.8571 | 0.5794 | 1066231 | 903468 | 722252 | 1410893 | 285694 | -104478 | 0.684 | 0.855 | 20240930 | 20250630 | 257 | 11 | 9 | 3 | 5 | 3 | 6853 | 6021 | 6327 | -832 | 7 | 2 | 136 | 2 | 2700000 | 1322449 | 1832412 | 434691 | 0.3287 | 3 | 28000 | 5 | 46 | 53
543 | 20240731 | 34 | 4 | 3 | 10 | 34 | 2 | 2 | 2 | Active | Deliver | Amber | 0.9048 | 0.613 | 1066231 | 957335 | 780851 | 1425328 | 303735 | -127251 | 0.683 | 0.837 | 20240930 | 20250630 | 270 | 11 | 10 | 4 | 6 | 3 | 6188 | 4889 | 4956 | -1299 | 8 | 2 | 150 | 3 | 2700000 | 1781633 | 1839756 | 701211 | 0.3936 | 3 | 46000 | 5 | 45 | 50.5
544 | 20240831 | 34 | 4 | 3 | 10 | 34 | 2 | 2 | 2 | Active | Deliver | Amber | 0.9524 | 0.6725 | 1066231 | 1011590 | 870570 | 1438640 | 294550 | -153530 | 0.709 | 0.824 | 20240930 | 20250630 | 258 | 11 | 10 | 4 | 5 | 3 | 5492 | 4345 | 4158 | -1147 | 7 | 2 | 136 | 2 | 2700000 | 2240816 | 1830633 | 969872 | 0.4328 | 3 | 40000 | 3 | 46 | 51.1
545 | 20240930 | 34 | 4 | 3 | 10 | 34 | 2 | 2 | 2 | Active | Deliver | Amber | 1 | 0.7242 | 1066231 | 1066231 | 941283 | 1449577 | 294067 | -169119 | 0.724 | 0.82 | 20240930 | 20250630 | 255 | 11 | 11 | 4 | 6 | 3 | 4780 | 3710 | 3586 | -1070 | 9 | 2 | 164 | 3 | 2700000 | 2700000 | 1885023 | 1206221 | 0.4467 | 3 | 28000 | 5 | 41 | 51.9
546 | 20241031 | 34 | 4 | 3 | 10 | 34 | 2 | 2 | 2 | Active | Deliver | Amber | 1 | 0.7242 | 1066231 | 1066231 | 964198 | 1464305 | 294067 | -192034 | 0.724 | 0.801 | 20240930 | 20250630 | 255 | 11 | 11 | 5 | 6 | 3 | 4780 | 4025 | 4183 | -755 | 9 | 2 | 164 | 3 | 2700000 | 2700000 | 1949785 | 1580586 | 0.5854 | 3 | 35000 | 4 | 42 | 53.4
547 | 20241130 | 34 | 4 | 3 | 10 | 34 | 2 | 2 | 2 | Active | Deliver | Amber | 1 | 0.7242 | 1066231 | 1066231 | 967618 | 1475123 | 294067 | -195454 | 0.724 | 0.798 | 20240930 | 20250630 | 255 | 11 | 11 | 5 | 6 | 3 | 4780 | 3987 | 3896 | -793 | 7 | 2 | 136 | 2 | 2700000 | 2700000 | 1865982 | 1784430 | 0.6609 | 3 | 34000 | 3 | 42 | 52.2
548 | 20241231 | 34 | 4 | 3 | 10 | 34 | 2 | 2 | 2 | Active | Deliver | Amber | 1 | 0.7242 | 1066231 | 1066231 | 989637 | 1489443 | 294067 | -217473 | 0.724 | 0.78 | 20240930 | 20250630 | 255 | 11 | 11 | 4 | 6 | 3 | 4780 | 3922 | 3826 | -858 | 7 | 1 | 118 | 2 | 2700000 | 2700000 | 1934350 | 1904933 | 0.7055 | 4 | 37000 | 3 | 49 | 60
549 | 20250131 | 34 | 4 | 3 | 10 | 34 | 2 | 2 | 2 | Active | Deliver | Amber | 1 | 0.7242 | 1066231 | 1066231 | 998026 | 1501135 | 294067 | -225862 | 0.724 | 0.774 | 20240930 | 20250630 | 255 | 11 | 11 | 4 | 6 | 3 | 4780 | 3785 | 4012 | -995 | 10 | 2 | 178 | 3 | 2700000 | 2700000 | 1934377 | 1751970 | 0.6489 | 4 | 52000 | 6 | 47 | 51.1
550 | 20250228 | 34 | 4 | 3 | 10 | 34 | 2 | 2 | 2 | Active | Deliver | Amber | 1 | 0.7242 | 1066231 | 1066231 | 1014689 | 1514270 | 294067 | -242525 | 0.724 | 0.761 | 20240930 | 20250630 | 255 | 11 | 11 | 5 | 6 | 3 | 4780 | 3661 | 3460 | -1119 | 7 | 1 | 118 | 2 | 2700000 | 2700000 | 1912137 | 1838258 | 0.6808 | 4 | 49000 | 5 | 46 | 57.9
551 | 20250331 | 34 | 4 | 3 | 10 | 34 | 2 | 2 | 2 | Active | Deliver | Amber | 1 | 0.7242 | 1066231 | 1066231 | 1020027 | 1525359 | 294067 | -247863 | 0.724 | 0.757 | 20240930 | 20250630 | 255 | 11 | 11 | 4 | 6 | 3 | 4780 | 3777 | 3802 | -1003 | 8 | 2 | 150 | 3 | 2700000 | 2700000 | 1851899 | 1636936 | 0.6063 | 4 | 43000 | 4 | 38 | 49.7
552 | 20250430 | 34 | 4 | 3 | 10 | 34 | 2 | 2 | 2 | Active | Deliver | Amber | 1 | 0.7242 | 1066231 | 1066231 | 1037385 | 1538485 | 294067 | -265221 | 0.724 | 0.744 | 20240930 | 20250630 | 255 | 11 | 11 | 4 | 6 | 3 | 4780 | 3890 | 3835 | -890 | 8 | 2 | 150 | 3 | 2700000 | 2700000 | 1880040 | 1656271 | 0.6134 | 4 | 40000 | 4 | 41 | 50
553 | 20250531 | 34 | 4 | 3 | 10 | 34 | 2 | 2 | 2 | Active | Deliver | Amber | 1 | 0.7242 | 1066231 | 1066231 | 1041571 | 1542740 | 294067 | -269407 | 0.724 | 0.741 | 20240930 | 20250630 | 255 | 11 | 11 | 4 | 6 | 3 | 4780 | 4092 | 4190 | -688 | 9 | 2 | 164 | 3 | 2700000 | 2700000 | 1929911 | 1819999 | 0.6741 | 4 | 61000 | 3 | 43 | 51.4
554 | 20250630 | 34 | 4 | 3 | 10 | 34 | 2 | 2 | 2 | Active | Deliver | Amber | 1 | 0.7242 | 1066231 | 1066231 | 1041571 | 1542740 | 294067 | -269407 | 0.724 | 0.741 | 20240930 | 20250630 | 255 | 11 | 11 | 4 | 6 | 3 | 4780 | 3991 | 3890 | -789 | 9 | 2 | 164 | 3 | 2700000 | 2700000 | 1908951 | 1837073 | 0.6804 | 4 | 38000 | 2 | 41 | 50.7
555 | 20250731 | 34 | 4 | 3 | 10 | 34 | 2 | 2 | 2 | Active | Deliver | Amber | 1 | 0.7242 | 1066231 | 1066231 | 1041571 | 1542740 | 294067 | -269407 | 0.724 | 0.741 | 20240930 | 20250630 | 255 | 11 | 11 | 4 | 6 | 3 | 4780 | 3693 | 3871 | -1087 | 9 | 2 | 164 | 3 | 2700000 | 2700000 | 1847532 | 1810158 | 0.6704 | 4 | 64000 | 5 | 44 | 48.7
556 | 20251130 | 35 | 5 | 5 | 11 | 35 | 3 | 3 | 3 | Active | Initiate & Design | Green | 0.1111 | 0.0914 | 867267 | 89511 | 69895 | 928939 | 10243 | 9373 | 0.885 | 1.134 | 20260731 | 20260731 | 7 | 6 | 1 | 1 | 0 | 0 | 5217 | 5118 | 5343 | -99 | 6 | 1 | 94 | 2 | 2200000 | 0 | 1952257 | 0 |  | 0 | 0 | 4 | 74 | 87.9
557 | 20251231 | 35 | 5 | 5 | 11 | 35 | 3 | 3 | 3 | Active | Initiate & Design | Green | 0.2222 | 0.1964 | 867267 | 180734 | 160396 | 938576 | 10403 | 9935 | 0.942 | 1.062 | 20260731 | 20260731 | 9 | 6 | 1 | 1 | 0 | 0 | 6387 | 6011 | 6256 | -376 | 8 | 2 | 137 | 2 | 2200000 | 0 | 2025348 | 0 |  | 0 | 0 | 3 | 72 | 80
558 | 20260131 | 35 | 5 | 5 | 11 | 35 | 3 | 3 | 3 | Active | Initiate & Design | Green | 0.3333 | 0.3227 | 867267 | 273671 | 271328 | 948212 | -6196 | 8539 | 1.022 | 1.031 | 20260731 | 20260731 | 4 | 6 | 2 | 2 | 0 | 0 | 7255 | 6958 | 6880 | -297 | 7 | 1 | 106 | 2 | 2200000 | 0 | 1956009 | 0 |  | 1 | 14000 | 6 | 80 | 90.1
559 | 20260228 | 35 | 5 | 5 | 11 | 35 | 3 | 3 | 3 | Active | Deliver | Green | 0.4444 | 0.4307 | 867267 | 368321 | 371556 | 957848 | -5211 | 1976 | 1.014 | 1.005 | 20260731 | 20260731 | 5 | 6 | 3 | 3 | 0 | 0 | 7716 | 7139 | 6977 | -577 | 6 | 1 | 94 | 2 | 2200000 | 0 | 1933874 | 0 |  | 1 | 13000 | 3 | 76 | 87.8
560 | 20260331 | 35 | 5 | 5 | 11 | 35 | 3 | 3 | 3 | Active | Deliver | Green | 0.5556 | 0.5266 | 867267 | 464684 | 463657 | 970360 | 7981 | -6954 | 0.983 | 0.985 | 20260731 | 20260731 | 11 | 6 | 3 | 3 | 0 | 0 | 7716 | 7337 | 7188 | -379 | 6 | 1 | 94 | 2 | 2200000 | 0 | 2004278 | 0 |  | 1 | 12000 | 3 | 76 | 87.1
561 | 20260430 | 35 | 5 | 5 | 11 | 35 | 3 | 3 | 3 | Active | Deliver | Green | 0.6667 | 0.5982 | 867267 | 562760 | 539459 | 984420 | 43961 | -20660 | 0.922 | 0.962 | 20260731 | 20260831 | 24 | 6 | 4 | 3 | 1 | 0 | 7255 | 7253 | 6874 | -2 | 8 | 1 | 119 | 2 | 2200000 | 0 | 1942925 | 0 |  | 1 | 11000 | 4 | 71 | 83.9
562 | 20260531 | 35 | 5 | 5 | 11 | 35 | 3 | 3 | 3 | Active | Deliver | Green | 0.7778 | 0.7007 | 867267 | 662549 | 647177 | 998392 | 54855 | -39483 | 0.917 | 0.939 | 20260731 | 20260831 | 28 | 6 | 5 | 4 | 1 | 0 | 6387 | 6330 | 6711 | -57 | 8 | 1 | 119 | 2 | 2200000 | 453968 | 1934331 | 0 | 0 | 2 | 17000 | 7 | 74 | 82.6
563 | 20260630 | 35 | 5 | 5 | 11 | 35 | 3 | 3 | 3 | Active | Deploy | Green | 0.8889 | 0.8208 | 867267 | 764052 | 781609 | 1013431 | 52199 | -69756 | 0.932 | 0.911 | 20260731 | 20260831 | 24 | 6 | 5 | 3 | 1 | 0 | 5217 | 4927 | 4642 | -290 | 4 | 0 | 51 | 1 | 2200000 | 1326984 | 1959796 | 702398 | 0.5293 | 2 | 25000 | 3 | 72 | 89.5
564 | 20260731 | 35 | 5 | 5 | 11 | 35 | 3 | 3 | 3 | Active | Deploy | Green | 1 | 0.9135 | 867267 | 867267 | 887231 | 1026447 | 75019 | -94983 | 0.914 | 0.893 | 20260731 | 20260831 | 31 | 6 | 6 | 4 | 1 | 0 | 3888 | 3769 | 3637 | -119 | 5 | 1 | 81 | 1 | 2200000 | 2200000 | 1941694 | 1268983 | 0.5768 | 3 | 26000 | 2 | 69 | 80.4
565 | 20260831 | 35 | 5 | 5 | 11 | 35 | 3 | 3 | 3 | Active | Deploy | Green | 1 | 0.9388 | 867267 | 867267 | 934116 | 1040159 | 53077 | -119926 | 0.939 | 0.872 | 20260731 | 20260831 | 23 | 6 | 6 | 4 | 1 | 0 | 3888 | 3925 | 3952 | 37 | 5 | 0 | 63 | 1 | 2200000 | 2200000 | 1951613 | 1786316 | 0.812 | 3 | 35000 | 5 | 79 | 89.6
566 | 20260930 | 35 | 5 | 5 | 11 | 35 | 3 | 3 | 3 | Active | Deploy | Green | 1 | 0.9388 | 867267 | 867267 | 961955 | 1054608 | 53077 | -147765 | 0.939 | 0.846 | 20260731 | 20260831 | 23 | 6 | 6 | 4 | 1 | 0 | 3888 | 3748 | 3597 | -140 | 6 | 1 | 94 | 2 | 2200000 | 2200000 | 1966042 | 1712745 | 0.7785 | 3 | 28000 | 5 | 72 | 80.1
567 | 20251031 | 36 | 2 | 4 | 12 | 36 | 4 | 1 | 4 | Active | Initiate & Design | Green | 0.0556 | 0.0685 | 1074171 | 55167 | 68380 | 1081213 | -18414 | 5201 | 1.333 | 1.076 | 20270331 | 20270331 | 0 | 9 | 1 | 0 | 0 | 0 | 5651 | 5512 | 5705 | -139 | 1 | 0 | 10 | 0 | 1200000 | 0 | 1251061 | 0 |  | 0 | 0 | 8 | 96 | 100
568 | 20251130 | 36 | 2 | 4 | 12 | 36 | 4 | 1 | 4 | Active | Initiate & Design | Green | 0.1111 | 0.1311 | 1074171 | 110865 | 122677 | 1081810 | -29959 | 18147 | 1.27 | 1.148 | 20270331 | 20270331 | 0 | 9 | 1 | 1 | 0 | 0 | 6462 | 6582 | 6487 | 120 | 2 | 0 | 19 | 0 | 1200000 | 0 | 1225407 | 0 |  | 0 | 0 | 6 | 96 | 100
569 | 20251231 | 36 | 2 | 4 | 12 | 36 | 4 | 1 | 4 | Active | Initiate & Design | Green | 0.1667 | 0.1957 | 1074171 | 167093 | 200984 | 1082406 | -43122 | 9231 | 1.258 | 1.046 | 20270331 | 20270331 | 0 | 9 | 2 | 1 | 0 | 0 | 7223 | 7310 | 7540 | 87 | 2 | 0 | 19 | 0 | 1200000 | 0 | 1252578 | 0 |  | 0 | 0 | 6 | 96 | 100
570 | 20260131 | 36 | 2 | 4 | 12 | 36 | 4 | 1 | 4 | Active | Initiate & Design | Green | 0.2222 | 0.2298 | 1074171 | 223852 | 221540 | 1083003 | -22992 | 25304 | 1.103 | 1.114 | 20270331 | 20270331 | 0 | 9 | 2 | 2 | 0 | 0 | 7910 | 7745 | 8217 | -165 | 2 | 0 | 19 | 0 | 1200000 | 0 | 1229486 | 0 |  | 0 | 0 | 7 | 90 | 100
571 | 20260228 | 36 | 2 | 4 | 12 | 36 | 4 | 1 | 4 | Active | Initiate & Design | Green | 0.2778 | 0.2862 | 1074171 | 281141 | 290311 | 1083600 | -26287 | 17117 | 1.093 | 1.059 | 20270331 | 20270331 | 0 | 9 | 3 | 3 | 0 | 0 | 8504 | 8293 | 8190 | -211 | 2 | 0 | 19 | 0 | 1200000 | 0 | 1201359 | 0 |  | 0 | 0 | 6 | 87 | 100
572 | 20260331 | 36 | 2 | 4 | 12 | 36 | 4 | 1 | 4 | Active | Initiate & Design | Green | 0.3333 | 0.3272 | 1074171 | 338961 | 329686 | 1084197 | -12508 | 21783 | 1.037 | 1.066 | 20270331 | 20270331 | 3 | 9 | 3 | 2 | 0 | 0 | 8985 | 8661 | 8742 | -324 | 3 | 0 | 29 | 1 | 1200000 | 0 | 1209378 | 0 |  | 0 | 0 | 6 | 89 | 100
573 | 20260430 | 36 | 2 | 4 | 12 | 36 | 4 | 1 | 4 | Active | Deliver | Green | 0.3889 | 0.3906 | 1074171 | 397311 | 398303 | 1084793 | -22260 | 21268 | 1.056 | 1.053 | 20270331 | 20270331 | 0 | 9 | 4 | 3 | 0 | 0 | 9340 | 9983 | 10544 | 643 | 4 | 0 | 38 | 1 | 1200000 | 0 | 1245108 | 0 |  | 1 | 14000 | 4 | 83 | 100
574 | 20260531 | 36 | 2 | 4 | 12 | 36 | 4 | 1 | 4 | Active | Deliver | Green | 0.4444 | 0.4521 | 1074171 | 456191 | 464963 | 1085390 | -29442 | 20670 | 1.065 | 1.044 | 20270331 | 20270331 | 0 | 9 | 4 | 3 | 0 | 0 | 9557 | 9430 | 9007 | -127 | 2 | 1 | 37 | 0 | 1200000 | 0 | 1211435 | 0 |  | 1 | 15000 | 7 | 80 | 96.2
575 | 20260630 | 36 | 2 | 4 | 12 | 36 | 4 | 1 | 4 | Active | Deliver | Green | 0.5 | 0.5205 | 1074171 | 515602 | 532503 | 1085987 | -43504 | 26603 | 1.084 | 1.05 | 20270331 | 20270331 | 0 | 9 | 5 | 5 | 0 | 0 | 9630 | 9326 | 9514 | -304 | 3 | 0 | 29 | 1 | 1200000 | 0 | 1218280 | 0 |  | 1 | 16000 | 4 | 88 | 100
576 | 20260731 | 36 | 2 | 4 | 12 | 36 | 4 | 1 | 4 | Active | Deliver | Green | 0.5556 | 0.5679 | 1074171 | 575543 | 597798 | 1086584 | -34479 | 12224 | 1.06 | 1.02 | 20270331 | 20270331 | 0 | 9 | 5 | 4 | 0 | 0 | 9557 | 9240 | 8826 | -317 | 3 | 0 | 29 | 1 | 1200000 | 0 | 1206154 | 0 |  | 1 | 12000 | 5 | 84 | 100
577 | 20260831 | 36 | 2 | 4 | 12 | 36 | 4 | 1 | 4 | Active | Deliver | Green | 0.6111 | 0.6357 | 1074171 | 636015 | 674670 | 1087180 | -46836 | 8181 | 1.074 | 1.012 | 20270331 | 20270331 | 0 | 9 | 6 | 5 | 0 | 0 | 9340 | 9546 | 10028 | 206 | 3 | 0 | 29 | 1 | 1200000 | 0 | 1244652 | 0 |  | 1 | 16000 | 6 | 88 | 100
578 | 20260930 | 36 | 2 | 4 | 12 | 36 | 4 | 1 | 4 | Active | Deliver | Green | 0.6667 | 0.7013 | 1074171 | 697018 | 747881 | 1087777 | -56298 | 5435 | 1.081 | 1.007 | 20270331 | 20270331 | 0 | 9 | 6 | 6 | 0 | 0 | 8985 | 9268 | 9904 | 283 | 3 | 0 | 29 | 1 | 1200000 | 0 | 1205755 | 0 |  | 1 | 14000 | 4 | 84 | 100
579 | 20231031 | 37 | 10 | 7 | 13 | 25 | 5 | 1 | 5 | Active | Deploy | Green | 0.75 | 0.8408 | 2229854 | 1638943 | 1905031 | 2327920 | -235918 | -30170 | 1.144 | 0.984 | 20240131 | 20240131 | 0 | 6 | 5 | 4 | 0 | 0 | 17064 | 18558 | 17887 | 1494 | 1 | 0 | 9 | 0 | 6200000 | 664286 | 6824100 | 0 | 0 | 0 | 0 | 7 | 84 | 100
580 | 20231130 | 37 | 10 | 7 | 13 | 25 | 5 | 1 | 5 | Active | Deploy | Green | 0.8333 | 0.939 | 2229854 | 1833436 | 2142727 | 2336955 | -260397 | -48894 | 1.142 | 0.977 | 20240131 | 20240131 | 0 | 6 | 5 | 4 | 0 | 0 | 14994 | 15426 | 15782 | 432 | 0 | 0 | 0 | 0 | 6200000 | 2509524 | 6660961 | 1156908 | 0.461 | 0 | 0 | 4 | 91 | 100
581 | 20231231 | 37 | 10 | 7 | 13 | 25 | 5 | 1 | 5 | Completed | Completed | Green | 0.9167 | 1 | 2229854 | 2030406 | 2304217 | 2347144 | -199448 | -74363 | 1.098 | 0.968 | 20240131 | 20240131 | 0 | 6 | 6 | 6 | 0 | 0 | 12583 | 14339 | 13999 | 1756 | 1 | 0 | 9 | 0 | 6200000 | 4354762 | 6543899 | 2914844 | 0.6693 | 1 | 26000 | 5 | 83 | 100
582 | 20240731 | 38 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Initiate & Design | Green | 0.0476 | 0.0157 | 1234837 | 54322 | 14037 | 1274822 | 34935 | 5350 | 0.356 | 1.379 | 20260331 | 20260430 | 26 | 11 | 1 | 0 | 1 | 0 | 6360 | 4990 | 5158 | -1370 | 10 | 1 | 136 | 3 | 1200000 | 0 | 1157963 | 0 |  | 0 | 0 | 3 | 62 | 70.6
583 | 20240831 | 38 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Initiate & Design | Amber | 0.0952 | 0.0403 | 1234837 | 109091 | 51677 | 1287647 | 59327 | -1913 | 0.456 | 0.964 | 20260331 | 20260531 | 45 | 11 | 1 | 0 | 1 | 0 | 7167 | 5771 | 6113 | -1396 | 9 | 2 | 143 | 2 | 1200000 | 0 | 1112617 | 0 |  | 0 | 0 | 5 | 46 | 51.9
584 | 20240930 | 38 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Initiate & Design | Green | 0.1429 | 0.0861 | 1234837 | 164309 | 95722 | 1280702 | 57990 | 10597 | 0.647 | 1.111 | 20260331 | 20260531 | 46 | 11 | 2 | 1 | 1 | 0 | 7937 | 6062 | 6247 | -1875 | 7 | 1 | 101 | 2 | 1200000 | 0 | 1113615 | 0 |  | 0 | 0 | 2 | 69 | 72.8
585 | 20241031 | 38 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Initiate & Design | Green | 0.1905 | 0.1111 | 1234837 | 219975 | 126920 | 1283642 | 82785 | 10270 | 0.623 | 1.081 | 20260331 | 20260531 | 64 | 11 | 2 | 1 | 1 | 0 | 8654 | 7217 | 6968 | -1437 | 7 | 1 | 101 | 2 | 1200000 | 0 | 1130123 | 0 |  | 0 | 0 | 3 | 65 | 72.6
586 | 20241130 | 38 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Initiate & Design | Green | 0.2381 | 0.1524 | 1234837 | 276088 | 183728 | 1286583 | 87899 | 4461 | 0.682 | 1.024 | 20260331 | 20260531 | 70 | 11 | 3 | 1 | 2 | 1 | 9301 | 6826 | 6501 | -2475 | 7 | 1 | 101 | 2 | 1200000 | 0 | 1143952 | 0 |  | 0 | 0 | 6 | 64 | 71.4
587 | 20241231 | 38 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Initiate & Design | Green | 0.2857 | 0.1974 | 1234837 | 332650 | 239252 | 1289523 | 88893 | 4505 | 0.733 | 1.019 | 20260331 | 20260531 | 72 | 11 | 3 | 2 | 1 | 0 | 9863 | 8190 | 7938 | -1673 | 8 | 1 | 113 | 2 | 1200000 | 0 | 1131827 | 0 |  | 0 | 0 | 3 | 62 | 75.3
588 | 20250131 | 38 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Initiate & Design | Green | 0.3333 | 0.2589 | 1234837 | 389660 | 302293 | 1292463 | 69961 | 17406 | 0.82 | 1.057 | 20260331 | 20260531 | 61 | 11 | 4 | 2 | 1 | 0 | 10329 | 7611 | 7189 | -2718 | 6 | 1 | 89 | 2 | 1200000 | 0 | 1126856 | 0 |  | 1 | 11000 | 3 | 72 | 78.4
589 | 20250228 | 38 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Initiate & Design | Green | 0.381 | 0.302 | 1234837 | 447117 | 356235 | 1295403 | 74196 | 16686 | 0.834 | 1.047 | 20260331 | 20260531 | 64 | 11 | 4 | 2 | 1 | 0 | 10688 | 8601 | 8893 | -2087 | 8 | 1 | 113 | 2 | 1200000 | 0 | 1110581 | 0 |  | 1 | 12000 | 3 | 69 | 79.8
590 | 20250331 | 38 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deliver | Green | 0.4286 | 0.3565 | 1234837 | 505023 | 433493 | 1298343 | 64804 | 6726 | 0.872 | 1.016 | 20260331 | 20260531 | 58 | 11 | 5 | 3 | 1 | 0 | 10932 | 8802 | 9335 | -2130 | 8 | 1 | 113 | 2 | 1200000 | 0 | 1103660 | 0 |  | 1 | 13000 | 4 | 69 | 80.2
591 | 20250430 | 38 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deliver | Green | 0.4762 | 0.3837 | 1234837 | 563377 | 455096 | 1301283 | 89570 | 18711 | 0.841 | 1.041 | 20260331 | 20260630 | 75 | 11 | 5 | 4 | 1 | 0 | 11055 | 8218 | 8138 | -2837 | 8 | 1 | 113 | 2 | 1200000 | 0 | 1124596 | 0 |  | 1 | 16000 | 3 | 68 | 78.9
592 | 20250531 | 38 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deliver | Green | 0.5238 | 0.4323 | 1234837 | 622179 | 519674 | 1304223 | 88359 | 14146 | 0.858 | 1.027 | 20260331 | 20260630 | 75 | 11 | 6 | 4 | 2 | 1 | 11055 | 8241 | 8713 | -2814 | 5 | 0 | 59 | 1 | 1200000 | 0 | 1127463 | 0 |  | 1 | 11000 | 5 | 73 | 87.3
593 | 20250630 | 38 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deliver | Green | 0.5714 | 0.4654 | 1234837 | 681428 | 580822 | 1310006 | 106735 | -6129 | 0.843 | 0.99 | 20260331 | 20260630 | 86 | 11 | 6 | 3 | 2 | 1 | 10932 | 8675 | 8252 | -2257 | 6 | 0 | 71 | 2 | 1200000 | 0 | 1128253 | 0 |  | 1 | 19000 | 5 | 73 | 86.4
594 | 20250731 | 38 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deliver | Green | 0.619 | 0.4924 | 1234837 | 741126 | 610328 | 1311102 | 133092 | -2294 | 0.82 | 0.996 | 20260331 | 20260630 | 103 | 11 | 7 | 5 | 2 | 1 | 10688 | 7952 | 8373 | -2736 | 6 | 1 | 89 | 2 | 1200000 | 0 | 1123474 | 0 |  | 1 | 13000 | 4 | 69 | 76.4
595 | 20250831 | 38 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deliver | Green | 0.6667 | 0.5347 | 1234837 | 801272 | 677104 | 1319817 | 141005 | -16837 | 0.824 | 0.975 | 20260331 | 20260731 | 107 | 11 | 7 | 4 | 2 | 1 | 10329 | 7909 | 8136 | -2420 | 6 | 1 | 89 | 2 | 1200000 | 0 | 1112734 | 0 |  | 1 | 13000 | 3 | 72 | 76
596 | 20250930 | 38 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deliver | Green | 0.7143 | 0.5886 | 1234837 | 861866 | 745907 | 1322942 | 135041 | -19082 | 0.843 | 0.974 | 20260331 | 20260630 | 102 | 11 | 8 | 5 | 2 | 1 | 9863 | 8076 | 8637 | -1787 | 7 | 1 | 101 | 2 | 1200000 | 0 | 1122088 | 0 |  | 1 | 11000 | 4 | 70 | 78.2
597 | 20251031 | 38 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deliver | Green | 0.7619 | 0.6316 | 1234837 | 922908 | 798824 | 1325335 | 142985 | -18901 | 0.845 | 0.976 | 20260331 | 20260731 | 106 | 11 | 8 | 5 | 2 | 1 | 9301 | 7633 | 8006 | -1668 | 8 | 1 | 113 | 2 | 1200000 | 179592 | 1141927 | 0 | 0 | 1 | 20000 | 3 | 68 | 78.9
598 | 20251130 | 38 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deliver | Green | 0.8095 | 0.6868 | 1234837 | 984397 | 879562 | 1331597 | 136311 | -31476 | 0.861 | 0.964 | 20260331 | 20260630 | 99 | 11 | 9 | 7 | 2 | 1 | 8654 | 6865 | 6971 | -1789 | 5 | 0 | 59 | 1 | 1200000 | 383673 | 1105799 | 104616 | 0.2727 | 2 | 32000 | 4 | 73 | 85.8
599 | 20251231 | 38 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deliver | Green | 0.8571 | 0.7379 | 1234837 | 1046335 | 954965 | 1337246 | 135149 | -43779 | 0.871 | 0.954 | 20260331 | 20260630 | 97 | 11 | 9 | 6 | 2 | 1 | 7937 | 5769 | 5760 | -2168 | 5 | 1 | 77 | 1 | 1200000 | 587755 | 1107730 | 282782 | 0.4811 | 2 | 28000 | 3 | 69 | 76.4
600 | 20260131 | 38 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deploy | Green | 0.9048 | 0.7891 | 1234837 | 1108721 | 1024810 | 1341103 | 134311 | -50400 | 0.879 | 0.951 | 20260331 | 20260630 | 94 | 11 | 10 | 7 | 2 | 1 | 7167 | 5627 | 5721 | -1540 | 5 | 0 | 59 | 1 | 1200000 | 791837 | 1155146 | 423627 | 0.535 | 2 | 28000 | 2 | 76 | 87.1
601 | 20260228 | 38 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deploy | Green | 0.9524 | 0.8199 | 1234837 | 1171555 | 1078818 | 1347398 | 159112 | -66375 | 0.864 | 0.938 | 20260331 | 20260731 | 107 | 11 | 10 | 6 | 3 | 1 | 6360 | 4603 | 4652 | -1757 | 6 | 1 | 89 | 2 | 1200000 | 995918 | 1156714 | 656508 | 0.6592 | 2 | 24000 | 3 | 73 | 76.6
602 | 20260331 | 38 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deploy | Green | 1 | 0.8603 | 1234837 | 1234837 | 1144612 | 1353161 | 172507 | -82282 | 0.86 | 0.928 | 20260331 | 20260731 | 113 | 11 | 11 | 7 | 3 | 1 | 5535 | 4127 | 4122 | -1408 | 5 | 0 | 59 | 1 | 1200000 | 1200000 | 1115236 | 800205 | 0.6668 | 2 | 38000 | 2 | 73 | 83.6
603 | 20260430 | 38 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deploy | Green | 1 | 0.8646 | 1234837 | 1234837 | 1147323 | 1355428 | 167197 | -79683 | 0.865 | 0.931 | 20260331 | 20260731 | 109 | 11 | 11 | 8 | 3 | 1 | 5535 | 4003 | 4015 | -1532 | 6 | 1 | 89 | 2 | 1200000 | 1200000 | 1110977 | 896867 | 0.7474 | 2 | 27000 | 1 | 68 | 75.3
604 | 20260531 | 38 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deploy | Green | 1 | 0.8646 | 1234837 | 1234837 | 1156998 | 1360482 | 167197 | -89358 | 0.865 | 0.923 | 20260331 | 20260731 | 109 | 11 | 11 | 8 | 3 | 1 | 5535 | 4210 | 4314 | -1325 | 5 | 1 | 77 | 1 | 1200000 | 1200000 | 1131893 | 990920 | 0.8258 | 2 | 37000 | 1 | 71 | 76.3
605 | 20260630 | 38 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deploy | Green | 1 | 0.8741 | 1234837 | 1234837 | 1185006 | 1366672 | 155466 | -105635 | 0.874 | 0.911 | 20260331 | 20260630 | 102 | 11 | 11 | 8 | 3 | 1 | 5535 | 4241 | 4255 | -1294 | 4 | 1 | 65 | 1 | 1200000 | 1200000 | 1143563 | 999294 | 0.8327 | 2 | 37000 | 2 | 66 | 76.8
606 | 20260731 | 38 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deploy | Green | 1 | 0.8761 | 1234837 | 1234837 | 1204316 | 1373009 | 152996 | -122475 | 0.876 | 0.898 | 20260331 | 20260630 | 100 | 11 | 11 | 8 | 3 | 1 | 5535 | 4230 | 4160 | -1305 | 4 | 1 | 65 | 1 | 1200000 | 1200000 | 1113796 | 1009537 | 0.8413 | 2 | 37000 | 2 | 67 | 75.7
607 | 20260831 | 38 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deploy | Green | 1 | 0.8935 | 1234837 | 1234837 | 1224976 | 1375295 | 131510 | -121649 | 0.894 | 0.901 | 20260331 | 20260630 | 86 | 11 | 11 | 9 | 2 | 1 | 5535 | 4400 | 4371 | -1135 | 4 | 0 | 47 | 1 | 1200000 | 1200000 | 1146860 | 1033339 | 0.8611 | 2 | 28000 | 4 | 75 | 86
608 | 20260930 | 38 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deploy | Green | 1 | 0.8935 | 1234837 | 1234837 | 1238651 | 1380937 | 131510 | -135324 | 0.894 | 0.891 | 20260331 | 20260630 | 86 | 11 | 11 | 8 | 2 | 1 | 5535 | 4144 | 3922 | -1391 | 3 | 0 | 36 | 1 | 1200000 | 1200000 | 1142889 | 1133253 | 0.9444 | 2 | 31000 | 2 | 75 | 84.5
609 | 20231031 | 39 | 6 | 4 | 15 | 27 | 7 | 3 | 7 | Active | Initiate & Design | Green | 0.2333 | 0.1959 | 437915 | 95913 | 83226 | 463460 | 10125 | 2562 | 0.895 | 1.031 | 20250930 | 20251130 | 45 | 15 | 4 | 3 | 1 | 0 | 3277 | 3201 | 3057 | -76 | 7 | 1 | 103 | 2 | 500000 | 0 | 482754 | 0 |  | 1 | 6000 | 3 | 71 | 86.9
610 | 20231130 | 39 | 6 | 4 | 15 | 27 | 7 | 3 | 7 | Active | Initiate & Design | Green | 0.2667 | 0.2181 | 437915 | 109926 | 93203 | 464482 | 14417 | 2306 | 0.869 | 1.025 | 20250930 | 20251130 | 58 | 15 | 4 | 2 | 1 | 0 | 3422 | 3191 | 3406 | -231 | 8 | 1 | 115 | 2 | 500000 | 0 | 480252 | 0 |  | 1 | 4000 | 3 | 72 | 84.4
611 | 20231231 | 39 | 6 | 4 | 15 | 27 | 7 | 3 | 7 | Active | Initiate & Design | Green | 0.3 | 0.2573 | 437915 | 124018 | 108534 | 465504 | 11342 | 4142 | 0.909 | 1.038 | 20250930 | 20251130 | 50 | 15 | 5 | 3 | 1 | 0 | 3551 | 3167 | 3352 | -384 | 6 | 1 | 91 | 2 | 500000 | 0 | 484341 | 0 |  | 1 | 5000 | 4 | 77 | 86
612 | 20240131 | 39 | 6 | 4 | 15 | 27 | 7 | 3 | 7 | Active | Initiate & Design | Green | 0.3333 | 0.272 | 437915 | 138187 | 112689 | 466525 | 19074 | 6424 | 0.862 | 1.057 | 20250930 | 20251130 | 72 | 15 | 5 | 3 | 1 | 0 | 3663 | 3251 | 3121 | -412 | 7 | 1 | 103 | 2 | 500000 | 0 | 476999 | 0 |  | 1 | 5000 | 5 | 75 | 84
613 | 20240229 | 39 | 6 | 4 | 15 | 27 | 7 | 3 | 7 | Active | Initiate & Design | Green | 0.3667 | 0.2938 | 437915 | 152433 | 125582 | 467547 | 23774 | 3077 | 0.844 | 1.024 | 20250930 | 20251231 | 87 | 15 | 6 | 3 | 2 | 1 | 3756 | 3411 | 3333 | -345 | 6 | 1 | 91 | 2 | 500000 | 0 | 468981 | 0 |  | 1 | 7000 | 4 | 70 | 82.1
614 | 20240331 | 39 | 6 | 4 | 15 | 27 | 7 | 3 | 7 | Active | Initiate & Design | Green | 0.4 | 0.3245 | 437915 | 166758 | 138273 | 468569 | 24655 | 3830 | 0.852 | 1.028 | 20250930 | 20251231 | 89 | 15 | 6 | 3 | 2 | 1 | 3830 | 3623 | 3476 | -207 | 6 | 1 | 91 | 2 | 500000 | 0 | 472713 | 0 |  | 1 | 6000 | 6 | 73 | 83.6
615 | 20240430 | 39 | 6 | 4 | 15 | 27 | 7 | 3 | 7 | Active | Initiate & Design | Green | 0.4333 | 0.3388 | 437915 | 181161 | 143709 | 469591 | 32795 | 4657 | 0.819 | 1.032 | 20250930 | 20260131 | 112 | 15 | 7 | 5 | 2 | 1 | 3883 | 3794 | 4044 | -89 | 8 | 1 | 115 | 2 | 500000 | 0 | 472599 | 0 |  | 1 | 6000 | 5 | 67 | 82.9
616 | 20240531 | 39 | 6 | 4 | 15 | 27 | 7 | 3 | 7 | Active | Deliver | Green | 0.4667 | 0.3852 | 437915 | 195641 | 165141 | 470613 | 26956 | 3544 | 0.862 | 1.022 | 20250930 | 20251231 | 96 | 15 | 7 | 4 | 2 | 1 | 3915 | 3478 | 3469 | -437 | 6 | 1 | 91 | 2 | 500000 | 0 | 483095 | 0 |  | 1 | 6000 | 6 | 70 | 83.2
617 | 20240630 | 39 | 6 | 4 | 15 | 27 | 7 | 3 | 7 | Active | Deliver | Green | 0.5 | 0.4294 | 437915 | 210199 | 184034 | 471634 | 22158 | 4007 | 0.895 | 1.022 | 20250930 | 20251231 | 84 | 15 | 8 | 5 | 2 | 1 | 3926 | 3432 | 3464 | -494 | 8 | 1 | 115 | 2 | 500000 | 0 | 484688 | 0 |  | 1 | 5000 | 4 | 70 | 84.4
618 | 20240731 | 39 | 6 | 4 | 15 | 27 | 7 | 3 | 7 | Active | Deliver | Green | 0.5333 | 0.4635 | 437915 | 224835 | 204081 | 473186 | 21861 | -1107 | 0.903 | 0.995 | 20250930 | 20251231 | 83 | 15 | 8 | 6 | 2 | 1 | 3915 | 3788 | 3854 | -127 | 8 | 1 | 115 | 2 | 500000 | 0 | 483781 | 0 |  | 1 | 5000 | 5 | 75 | 85.8
619 | 20240831 | 39 | 6 | 4 | 15 | 27 | 7 | 3 | 7 | Active | Deliver | Green | 0.5667 | 0.4925 | 437915 | 239549 | 214477 | 473678 | 23876 | 1196 | 0.9 | 1.006 | 20250930 | 20251231 | 88 | 15 | 9 | 6 | 2 | 1 | 3883 | 3724 | 3745 | -159 | 6 | 1 | 91 | 2 | 500000 | 0 | 484285 | 0 |  | 1 | 6000 | 4 | 72 | 85.9
620 | 20240930 | 39 | 6 | 4 | 15 | 27 | 7 | 3 | 7 | Active | Deliver | Green | 0.6 | 0.5183 | 437915 | 254341 | 230363 | 476116 | 27370 | -3392 | 0.892 | 0.985 | 20250930 | 20251231 | 97 | 15 | 9 | 7 | 2 | 1 | 3830 | 3474 | 3671 | -356 | 5 | 1 | 79 | 1 | 500000 | 0 | 479999 | 0 |  | 1 | 5000 | 5 | 70 | 83.5
621 | 20241031 | 39 | 6 | 4 | 15 | 27 | 7 | 3 | 7 | Active | Deliver | Green | 0.6333 | 0.5647 | 437915 | 269211 | 250597 | 476989 | 21920 | -3306 | 0.919 | 0.987 | 20250930 | 20251231 | 81 | 15 | 10 | 7 | 2 | 1 | 3756 | 3665 | 3882 | -91 | 6 | 1 | 91 | 2 | 500000 | 0 | 473214 | 0 |  | 1 | 5000 | 3 | 72 | 85.8
622 | 20241130 | 39 | 6 | 4 | 15 | 27 | 7 | 3 | 7 | Active | Deliver | Green | 0.6667 | 0.5804 | 437915 | 284158 | 259753 | 478812 | 29992 | -5587 | 0.894 | 0.979 | 20250930 | 20251130 | 67 | 15 | 10 | 7 | 2 | 1 | 3663 | 3214 | 3167 | -449 | 8 | 1 | 115 | 2 | 500000 | 0 | 480129 | 0 |  | 1 | 5000 | 3 | 71 | 82.7
623 | 20241231 | 39 | 6 | 4 | 15 | 27 | 7 | 3 | 7 | Active | Deliver | Green | 0.7 | 0.6168 | 437915 | 299184 | 281057 | 481520 | 29078 | -10951 | 0.903 | 0.961 | 20250930 | 20251130 | 63 | 15 | 11 | 9 | 2 | 1 | 3551 | 3256 | 3080 | -295 | 7 | 1 | 103 | 2 | 500000 | 0 | 485567 | 0 |  | 1 | 4000 | 6 | 69 | 83.6
624 | 20250131 | 39 | 6 | 4 | 15 | 27 | 7 | 3 | 7 | Active | Deliver | Green | 0.7333 | 0.6512 | 437915 | 314287 | 293628 | 481563 | 29117 | -8458 | 0.907 | 0.971 | 20250930 | 20251130 | 62 | 15 | 11 | 9 | 2 | 1 | 3422 | 3328 | 3265 | -94 | 8 | 1 | 115 | 2 | 500000 | 23810 | 476879 | 0 | 0 | 1 | 4000 | 6 | 69 | 84.9
625 | 20250228 | 39 | 6 | 4 | 15 | 27 | 7 | 3 | 7 | Active | Deliver | Green | 0.7667 | 0.6896 | 437915 | 329468 | 313605 | 483374 | 27482 | -11619 | 0.917 | 0.963 | 20250930 | 20251130 | 56 | 15 | 12 | 10 | 2 | 1 | 3277 | 3127 | 3013 | -150 | 7 | 1 | 103 | 2 | 500000 | 83333 | 490284 | 0 | 0 | 1 | 5000 | 3 | 73 | 85.4
626 | 20250331 | 39 | 6 | 4 | 15 | 27 | 7 | 3 | 7 | Active | Deploy | Green | 0.8 | 0.7505 | 437915 | 344727 | 348012 | 486194 | 16072 | -19357 | 0.953 | 0.944 | 20250930 | 20251031 | 24 | 15 | 12 | 10 | 2 | 1 | 3117 | 2871 | 2717 | -246 | 5 | 0 | 61 | 1 | 500000 | 142857 | 476125 | 30370 | 0.2126 | 2 | 9000 | 4 | 74 | 92.9
627 | 20250430 | 39 | 6 | 4 | 15 | 27 | 7 | 3 | 7 | Active | Deploy | Green | 0.8333 | 0.7985 | 437915 | 360063 | 368527 | 486783 | 10388 | -18852 | 0.971 | 0.949 | 20250930 | 20250930 | 6 | 15 | 13 | 12 | 1 | 0 | 2945 | 2642 | 2594 | -303 | 3 | 1 | 54 | 1 | 500000 | 202381 | 469945 | 80324 | 0.3969 | 2 | 8000 | 4 | 77 | 85
628 | 20250531 | 39 | 6 | 4 | 15 | 27 | 7 | 3 | 7 | Active | Deploy | Green | 0.8667 | 0.8279 | 437915 | 375478 | 383111 | 488050 | 12928 | -20561 | 0.966 | 0.946 | 20250930 | 20250930 | 11 | 15 | 13 | 11 | 1 | 0 | 2762 | 2508 | 2625 | -254 | 4 | 1 | 67 | 1 | 500000 | 261905 | 489676 | 134756 | 0.5145 | 2 | 8000 | 4 | 78 | 86
629 | 20250630 | 39 | 6 | 4 | 15 | 27 | 7 | 3 | 7 | Active | Deploy | Green | 0.9 | 0.8763 | 437915 | 390971 | 411787 | 490458 | 7226 | -28042 | 0.982 | 0.932 | 20250930 | 20250930 | -7 | 15 | 14 | 13 | 1 | 0 | 2570 | 2266 | 2206 | -304 | 6 | 0 | 73 | 2 | 500000 | 321429 | 480001 | 178397 | 0.555 | 2 | 8000 | 3 | 77 | 93.1
630 | 20250731 | 39 | 6 | 4 | 15 | 27 | 7 | 3 | 7 | Active | Deploy | Green | 0.9333 | 0.9008 | 437915 | 406541 | 423947 | 491612 | 12067 | -29473 | 0.97 | 0.931 | 20250930 | 20250930 | 3 | 15 | 14 | 12 | 1 | 0 | 2371 | 2290 | 2223 | -81 | 3 | 0 | 36 | 1 | 500000 | 380952 | 469939 | 230737 | 0.6057 | 2 | 7000 | 2 | 77 | 93.8
631 | 20250831 | 39 | 6 | 4 | 15 | 27 | 7 | 3 | 7 | Active | Deploy | Green | 0.9667 | 0.9213 | 437915 | 422189 | 440516 | 494042 | 18738 | -37065 | 0.956 | 0.916 | 20250930 | 20251031 | 19 | 15 | 15 | 13 | 2 | 1 | 2168 | 2084 | 2212 | -84 | 5 | 1 | 79 | 1 | 500000 | 440476 | 482735 | 299372 | 0.6797 | 2 | 13000 | 4 | 74 | 85.2
632 | 20250930 | 39 | 6 | 4 | 15 | 27 | 7 | 3 | 7 | Active | Deploy | Green | 1 | 0.9598 | 437915 | 437915 | 457995 | 494884 | 17604 | -37684 | 0.96 | 0.918 | 20250930 | 20250930 | 12 | 15 | 15 | 12 | 2 | 1 | 1963 | 1915 | 1846 | -48 | 4 | 0 | 49 | 1 | 500000 | 500000 | 469218 | 324378 | 0.6488 | 2 | 7000 | 2 | 79 | 93.1
633 | 20251031 | 39 | 6 | 4 | 15 | 27 | 7 | 3 | 7 | Active | Deploy | Green | 1 | 0.9669 | 437915 | 437915 | 467227 | 497015 | 14495 | -43807 | 0.967 | 0.906 | 20250930 | 20250930 | 4 | 15 | 15 | 13 | 2 | 1 | 1963 | 1859 | 1839 | -104 | 3 | 1 | 54 | 1 | 500000 | 500000 | 485810 | 357961 | 0.7159 | 2 | 8000 | 1 | 71 | 85.3
634 | 20251130 | 39 | 6 | 4 | 15 | 27 | 7 | 3 | 7 | Active | Deploy | Green | 1 | 0.9876 | 437915 | 437915 | 480736 | 498676 | 5430 | -48251 | 0.988 | 0.9 | 20250930 | 20250930 | -21 | 15 | 15 | 14 | 1 | 0 | 1963 | 1780 | 1868 | -183 | 5 | 1 | 79 | 1 | 500000 | 500000 | 474698 | 415285 | 0.8306 | 2 | 7000 | 2 | 70 | 84.5
635 | 20251231 | 39 | 6 | 4 | 15 | 27 | 7 | 3 | 7 | Active | Deploy | Green | 1 | 0.9916 | 437915 | 437915 | 480736 | 499349 | 3678 | -46499 | 0.992 | 0.903 | 20250930 | 20250930 | -25 | 15 | 15 | 13 | 1 | 0 | 1963 | 1765 | 1768 | -198 | 4 | 1 | 67 | 1 | 500000 | 500000 | 485417 | 479385 | 0.9588 | 2 | 10000 | 1 | 71 | 85.2
636 | 20260131 | 39 | 6 | 4 | 15 | 27 | 7 | 3 | 7 | Completed | Completed | Green | 1 | 1 | 437915 | 437915 | 492458 | 501719 | 0 | -54543 | 1 | 0.889 | 20250930 | 20250930 | -35 | 15 | 15 | 14 | 1 | 0 | 1963 | 1723 | 1789 | -240 | 6 | 1 | 91 | 2 | 500000 | 500000 | 484729 | 441290 | 0.8826 | 2 | 10000 | 2 | 76 | 84.6
637 | 20251130 | 40 | 6 | 4 | 16 | 28 | 8 | 2 | 8 | Active | Initiate & Design | Green | 0.0333 | 0.0358 | 450993 | 13871 | 15628 | 459562 | -2275 | 518 | 1.163 | 1.033 | 20280430 | 20280430 | 0 | 15 | 1 | 0 | 0 | 0 | 2233 | 2187 | 2145 | -46 | 3 | 0 | 31 | 1 | 1300000 | 0 | 949740 | 0 |  | 0 | 0 | 2 | 80 | 100
638 | 20251231 | 40 | 6 | 4 | 16 | 28 | 8 | 2 | 8 | Active | Initiate & Design | Green | 0.0667 | 0.046 | 450993 | 27821 | 19105 | 460013 | 7075 | 1641 | 0.745 | 1.086 | 20280430 | 20280531 | 22 | 15 | 1 | 1 | 0 | 0 | 2442 | 2514 | 2455 | 72 | 5 | 1 | 69 | 1 | 1300000 | 0 | 957316 | 0 |  | 0 | 0 | 2 | 60 | 76.2
639 | 20260131 | 40 | 6 | 4 | 16 | 28 | 8 | 2 | 8 | Active | Initiate & Design | Green | 0.1 | 0.0767 | 450993 | 41852 | 32202 | 460464 | 7261 | 2389 | 0.826 | 1.074 | 20280430 | 20280531 | 25 | 15 | 2 | 1 | 1 | 0 | 2646 | 2776 | 2881 | 130 | 6 | 0 | 61 | 1 | 1300000 | 0 | 960212 | 0 |  | 0 | 0 | 5 | 70 | 87.5
640 | 20260228 | 40 | 6 | 4 | 16 | 28 | 8 | 2 | 8 | Active | Initiate & Design | Green | 0.1333 | 0.1388 | 450993 | 55963 | 56884 | 460915 | -6635 | 5714 | 1.118 | 1.1 | 20280430 | 20280430 | 0 | 15 | 2 | 1 | 0 | 0 | 2844 | 2768 | 2653 | -76 | 3 | 0 | 31 | 1 | 1300000 | 0 | 947380 | 0 |  | 0 | 0 | 2 | 86 | 100
641 | 20260331 | 40 | 6 | 4 | 16 | 28 | 8 | 2 | 8 | Active | Initiate & Design | Green | 0.1667 | 0.1797 | 450993 | 70154 | 75716 | 461366 | -10889 | 5327 | 1.155 | 1.071 | 20280430 | 20280430 | 0 | 15 | 3 | 3 | 0 | 0 | 3033 | 3233 | 3240 | 200 | 3 | 0 | 31 | 1 | 1300000 | 0 | 958873 | 0 |  | 0 | 0 | 2 | 80 | 100
642 | 20260430 | 40 | 6 | 4 | 16 | 28 | 8 | 2 | 8 | Active | Initiate & Design | Green | 0.2 | 0.2058 | 450993 | 84426 | 83291 | 461817 | -8388 | 9523 | 1.099 | 1.114 | 20280430 | 20280430 | 0 | 15 | 3 | 2 | 0 | 0 | 3210 | 3219 | 3416 | 9 | 4 | 0 | 41 | 1 | 1300000 | 0 | 977454 | 0 |  | 0 | 0 | 4 | 82 | 100
643 | 20260531 | 40 | 6 | 4 | 16 | 28 | 8 | 2 | 8 | Active | Initiate & Design | Green | 0.2333 | 0.2546 | 450993 | 98777 | 110575 | 462268 | -16046 | 4248 | 1.163 | 1.039 | 20280430 | 20280430 | 0 | 15 | 4 | 4 | 0 | 0 | 3374 | 3268 | 3495 | -106 | 3 | 0 | 31 | 1 | 1300000 | 0 | 960111 | 0 |  | 0 | 0 | 3 | 81 | 100
644 | 20260630 | 40 | 6 | 4 | 16 | 28 | 8 | 2 | 8 | Active | Initiate & Design | Green | 0.2667 | 0.2966 | 450993 | 113209 | 126633 | 462719 | -20556 | 7132 | 1.182 | 1.056 | 20280430 | 20280430 | 0 | 15 | 4 | 3 | 0 | 0 | 3524 | 3688 | 3873 | 164 | 3 | 0 | 31 | 1 | 1300000 | 0 | 1002929 | 0 |  | 0 | 0 | 4 | 80 | 100
645 | 20260731 | 40 | 6 | 4 | 16 | 28 | 8 | 2 | 8 | Active | Initiate & Design | Green | 0.3 | 0.2989 | 450993 | 127721 | 127505 | 463170 | -7081 | 7297 | 1.055 | 1.057 | 20280430 | 20280430 | 1 | 15 | 5 | 4 | 0 | 0 | 3657 | 3738 | 3989 | 81 | 2 | 0 | 20 | 0 | 1300000 | 0 | 957890 | 0 |  | 1 | 5000 | 4 | 77 | 97.1
646 | 20260831 | 40 | 6 | 4 | 16 | 28 | 8 | 2 | 8 | Active | Initiate & Design | Green | 0.3333 | 0.3255 | 450993 | 142313 | 139718 | 463621 | -4485 | 7080 | 1.031 | 1.051 | 20280430 | 20280430 | 8 | 15 | 5 | 4 | 0 | 0 | 3773 | 3739 | 3930 | -34 | 4 | 0 | 41 | 1 | 1300000 | 0 | 984173 | 0 |  | 1 | 6000 | 4 | 79 | 96.2
647 | 20260930 | 40 | 6 | 4 | 16 | 28 | 8 | 2 | 8 | Active | Deliver | Green | 0.3667 | 0.3608 | 450993 | 156986 | 153651 | 464072 | -5732 | 9067 | 1.036 | 1.059 | 20280430 | 20280430 | 6 | 15 | 6 | 5 | 0 | 0 | 3869 | 3862 | 3733 | -7 | 5 | 0 | 51 | 1 | 1300000 | 0 | 986349 | 0 |  | 1 | 5000 | 5 | 78 | 96.9
648 | 20250430 | 41 | 8 | 6 | 17 | 29 | 1 | 1 | 1 | Active | Initiate & Design | Red | 0.1111 | 0.0054 | 907110 | 93623 | 0 | 1036121 | 88725 | 4898 | 0.052 | 1 | 20251231 | 20260131 | 43 | 6 | 1 | 0 | 1 | 1 | 5457 | 4228 | 4297 | -1229 | 15 | 3 | 268 | 5 | 1200000 | 0 | 864869 | 0 |  | 0 | 0 | 7 | 24 | 20.6
649 | 20250531 | 41 | 8 | 6 | 17 | 29 | 1 | 1 | 1 | Active | Initiate & Design | Red | 0.2222 | 0.0873 | 907110 | 189037 | 77971 | 1056279 | 109846 | 1220 | 0.419 | 1.015 | 20251231 | 20260228 | 53 | 6 | 1 | 0 | 1 | 1 | 6680 | 5674 | 5908 | -1006 | 11 | 2 | 193 | 4 | 1200000 | 0 | 851061 | 0 |  | 1 | 12000 | 8 | 40 | 46.9
650 | 20250630 | 41 | 8 | 6 | 17 | 29 | 1 | 1 | 1 | Active | Initiate & Design | Red | 0.3333 | 0.1708 | 907110 | 286244 | 161876 | 1084957 | 131310 | -6942 | 0.541 | 0.957 | 20251231 | 20260228 | 65 | 6 | 2 | 0 | 1 | 1 | 7588 | 6474 | 6113 | -1114 | 12 | 3 | 225 | 4 | 1200000 | 0 | 817480 | 0 |  | 2 | 21000 | 4 | 33 | 41.7
651 | 20250731 | 41 | 8 | 6 | 17 | 29 | 1 | 1 | 1 | Active | Initiate & Design | Amber | 0.4444 | 0.2686 | 907110 | 385242 | 247379 | 1099619 | 141592 | -3729 | 0.632 | 0.985 | 20251231 | 20260228 | 69 | 6 | 3 | 1 | 2 | 1 | 8071 | 6137 | 5771 | -1934 | 10 | 2 | 178 | 3 | 1200000 | 0 | 848911 | 0 |  | 2 | 26000 | 7 | 48 | 53.5
652 | 20250831 | 41 | 8 | 6 | 17 | 29 | 1 | 1 | 1 | Active | Deliver | Amber | 0.5556 | 0.3629 | 907110 | 486032 | 350544 | 1128912 | 156842 | -21354 | 0.677 | 0.939 | 20251231 | 20260331 | 76 | 6 | 3 | 1 | 2 | 1 | 8071 | 6217 | 5857 | -1854 | 9 | 2 | 164 | 3 | 1200000 | 0 | 810546 | 0 |  | 2 | 23000 | 5 | 43 | 53.2
653 | 20250930 | 41 | 8 | 6 | 17 | 29 | 1 | 1 | 1 | Active | Deliver | Red | 0.6667 | 0.4514 | 907110 | 588614 | 448207 | 1154166 | 179145 | -38738 | 0.696 | 0.914 | 20251231 | 20260331 | 85 | 6 | 4 | 2 | 2 | 1 | 7588 | 5869 | 5974 | -1719 | 11 | 3 | 211 | 4 | 1200000 | 0 | 838872 | 0 |  | 2 | 19000 | 7 | 44 | 45.9
654 | 20251031 | 41 | 8 | 6 | 17 | 29 | 1 | 1 | 1 | Active | Deliver | Amber | 0.7778 | 0.5525 | 907110 | 692987 | 568503 | 1180707 | 191809 | -67325 | 0.723 | 0.882 | 20251231 | 20260331 | 90 | 6 | 5 | 1 | 3 | 2 | 6680 | 5305 | 5365 | -1375 | 11 | 2 | 193 | 4 | 1200000 | 247619 | 816139 | 0 | 0 | 2 | 16000 | 5 | 46 | 53.9
655 | 20251130 | 41 | 8 | 6 | 17 | 29 | 1 | 1 | 1 | Active | Deliver | Amber | 0.8889 | 0.6266 | 907110 | 799153 | 679776 | 1209933 | 230758 | -111381 | 0.711 | 0.836 | 20251231 | 20260331 | 104 | 6 | 5 | 2 | 3 | 2 | 5457 | 4508 | 4628 | -949 | 10 | 2 | 178 | 3 | 1200000 | 723810 | 856793 | 272687 | 0.3767 | 2 | 26000 | 5 | 47 | 53.4
656 | 20251231 | 41 | 8 | 6 | 17 | 29 | 1 | 1 | 1 | Active | Deliver | Amber | 1 | 0.707 | 907110 | 907110 | 787965 | 1234524 | 265783 | -146638 | 0.707 | 0.814 | 20251231 | 20260430 | 116 | 6 | 6 | 3 | 3 | 2 | 4066 | 3358 | 3576 | -708 | 7 | 2 | 136 | 2 | 1200000 | 1200000 | 864910 | 622169 | 0.5185 | 3 | 34000 | 2 | 42 | 52.7
657 | 20260131 | 41 | 8 | 6 | 17 | 29 | 1 | 1 | 1 | Active | Deliver | Amber | 1 | 0.707 | 907110 | 907110 | 812299 | 1259548 | 265783 | -170972 | 0.707 | 0.79 | 20251231 | 20260430 | 116 | 6 | 6 | 3 | 3 | 2 | 4066 | 3319 | 3220 | -747 | 9 | 2 | 164 | 3 | 1200000 | 1200000 | 832983 | 830746 | 0.6923 | 3 | 35000 | 3 | 46 | 50.8
658 | 20260228 | 41 | 8 | 6 | 17 | 29 | 1 | 1 | 1 | Active | Deliver | Amber | 1 | 0.707 | 907110 | 907110 | 835509 | 1284083 | 265783 | -194182 | 0.707 | 0.768 | 20251231 | 20260430 | 116 | 6 | 6 | 2 | 3 | 2 | 4066 | 3478 | 3460 | -588 | 9 | 2 | 164 | 3 | 1200000 | 1200000 | 868507 | 830471 | 0.6921 | 4 | 42000 | 6 | 46 | 51.8
659 | 20260331 | 41 | 8 | 6 | 17 | 29 | 1 | 1 | 1 | Active | Deliver | Amber | 1 | 0.707 | 907110 | 907110 | 864789 | 1309428 | 265783 | -223462 | 0.707 | 0.742 | 20251231 | 20260430 | 116 | 6 | 6 | 3 | 3 | 2 | 4066 | 3482 | 3361 | -584 | 9 | 2 | 164 | 3 | 1200000 | 1200000 | 816658 | 735981 | 0.6133 | 4 | 53000 | 3 | 39 | 49.7
660 | 20260430 | 41 | 8 | 6 | 17 | 29 | 1 | 1 | 1 | Active | Deliver | Amber | 1 | 0.707 | 907110 | 907110 | 868586 | 1313098 | 265783 | -227259 | 0.707 | 0.738 | 20251231 | 20260430 | 116 | 6 | 6 | 3 | 3 | 2 | 4066 | 3494 | 3521 | -572 | 7 | 1 | 118 | 2 | 1200000 | 1200000 | 811184 | 803988 | 0.67 | 4 | 57000 | 3 | 48 | 57.5
661 | 20260531 | 41 | 8 | 6 | 17 | 29 | 1 | 1 | 1 | Active | Deliver | Amber | 1 | 0.707 | 907110 | 907110 | 869796 | 1313303 | 265783 | -228469 | 0.707 | 0.737 | 20251231 | 20260430 | 116 | 6 | 6 | 3 | 3 | 2 | 4066 | 3254 | 3204 | -812 | 9 | 2 | 164 | 3 | 1200000 | 1200000 | 866218 | 800556 | 0.6671 | 4 | 57000 | 3 | 40 | 49.4
662 | 20260630 | 41 | 8 | 6 | 17 | 29 | 1 | 1 | 1 | Active | Deliver | Amber | 1 | 0.707 | 907110 | 907110 | 871653 | 1313617 | 265783 | -230326 | 0.707 | 0.736 | 20251231 | 20260430 | 116 | 6 | 6 | 3 | 3 | 2 | 4066 | 3383 | 3195 | -683 | 8 | 2 | 150 | 3 | 1200000 | 1200000 | 823628 | 775156 | 0.646 | 4 | 50000 | 5 | 37 | 49.1
663 | 20260731 | 41 | 8 | 6 | 17 | 29 | 1 | 1 | 1 | Active | Deliver | Amber | 1 | 0.707 | 907110 | 907110 | 871653 | 1313617 | 265783 | -230326 | 0.707 | 0.736 | 20251231 | 20260430 | 116 | 6 | 6 | 2 | 3 | 2 | 4066 | 3381 | 3433 | -685 | 7 | 1 | 118 | 2 | 1200000 | 1200000 | 813828 | 745019 | 0.6208 | 5 | 61000 | 6 | 43 | 56.8
664 | 20260831 | 41 | 8 | 6 | 17 | 29 | 1 | 1 | 1 | Active | Deliver | Amber | 1 | 0.707 | 907110 | 907110 | 871653 | 1313617 | 265783 | -230326 | 0.707 | 0.736 | 20251231 | 20260430 | 116 | 6 | 6 | 3 | 3 | 2 | 4066 | 3355 | 3405 | -711 | 9 | 2 | 164 | 3 | 1200000 | 1200000 | 851037 | 769098 | 0.6409 | 5 | 44000 | 2 | 43 | 49.6
665 | 20260930 | 41 | 8 | 6 | 17 | 29 | 1 | 1 | 1 | Active | Deliver | Amber | 1 | 0.707 | 907110 | 907110 | 871653 | 1313617 | 265783 | -230326 | 0.707 | 0.736 | 20251231 | 20260430 | 116 | 6 | 6 | 2 | 3 | 2 | 4066 | 3467 | 3705 | -599 | 7 | 1 | 118 | 2 | 1200000 | 1200000 | 835675 | 796375 | 0.6636 | 5 | 67000 | 2 | 48 | 57.8
666 | 20251231 | 42 | 4 | 3 | 18 | 30 | 2 | 1 | 2 | Active | Initiate & Design | Green | 0.0476 | 0.022 | 1103129 | 48528 | 16736 | 1174570 | 24259 | 7533 | 0.499 | 1.447 | 20270831 | 20270930 | 22 | 11 | 1 | 0 | 1 | 0 | 5682 | 5086 | 5022 | -596 | 9 | 2 | 150 | 3 | 1500000 | 0 | 1323618 | 0 |  | 0 | 0 | 4 | 64 | 71.5
667 | 20260131 | 42 | 4 | 3 | 18 | 30 | 2 | 1 | 2 | Active | Initiate & Design | Green | 0.0952 | 0.0698 | 1103129 | 97456 | 67033 | 1179823 | 20458 | 9965 | 0.79 | 1.149 | 20270831 | 20270930 | 22 | 11 | 1 | 0 | 0 | 0 | 6403 | 6153 | 6303 | -250 | 8 | 1 | 119 | 2 | 1500000 | 0 | 1356336 | 0 |  | 0 | 0 | 7 | 74 | 84.2
668 | 20260228 | 42 | 4 | 3 | 18 | 30 | 2 | 1 | 2 | Active | Initiate & Design | Green | 0.1429 | 0.1235 | 1103129 | 146784 | 134616 | 1185076 | 10548 | 1620 | 0.928 | 1.012 | 20270831 | 20270930 | 16 | 11 | 2 | 2 | 0 | 0 | 7091 | 7066 | 7148 | -25 | 7 | 1 | 106 | 2 | 1500000 | 0 | 1377937 | 0 |  | 0 | 0 | 3 | 71 | 86.8
669 | 20260331 | 42 | 4 | 3 | 18 | 30 | 2 | 1 | 2 | Active | Initiate & Design | Green | 0.1905 | 0.1751 | 1103129 | 196512 | 182305 | 1190329 | 3354 | 10853 | 0.983 | 1.059 | 20270831 | 20270831 | 13 | 11 | 2 | 1 | 0 | 0 | 7731 | 7665 | 7601 | -66 | 8 | 1 | 119 | 2 | 1500000 | 0 | 1372719 | 0 |  | 0 | 0 | 5 | 77 | 90.7
670 | 20260430 | 42 | 4 | 3 | 18 | 30 | 2 | 1 | 2 | Active | Initiate & Design | Green | 0.2381 | 0.226 | 1103129 | 246641 | 239475 | 1195582 | -2666 | 9832 | 1.011 | 1.041 | 20270831 | 20270831 | 11 | 11 | 3 | 3 | 0 | 0 | 8309 | 7567 | 7600 | -742 | 7 | 1 | 106 | 2 | 1500000 | 0 | 1359312 | 0 |  | 0 | 0 | 4 | 79 | 89.3
671 | 20260531 | 42 | 4 | 3 | 18 | 30 | 2 | 1 | 2 | Active | Initiate & Design | Green | 0.2857 | 0.2579 | 1103129 | 297169 | 265796 | 1200835 | 12672 | 18701 | 0.958 | 1.071 | 20270831 | 20270930 | 23 | 11 | 3 | 2 | 0 | 0 | 8811 | 7954 | 7631 | -857 | 6 | 1 | 94 | 2 | 1500000 | 0 | 1318904 | 0 |  | 0 | 0 | 6 | 77 | 87
672 | 20260630 | 42 | 4 | 3 | 18 | 30 | 2 | 1 | 2 | Active | Initiate & Design | Green | 0.3333 | 0.2961 | 1103129 | 348098 | 311265 | 1206088 | 21462 | 15371 | 0.938 | 1.049 | 20270831 | 20270930 | 31 | 11 | 4 | 2 | 1 | 0 | 9228 | 9053 | 9106 | -175 | 9 | 2 | 150 | 3 | 1500000 | 0 | 1341711 | 0 |  | 0 | 0 | 5 | 72 | 79.6
673 | 20260731 | 42 | 4 | 3 | 18 | 30 | 2 | 1 | 2 | Active | Initiate & Design | Green | 0.381 | 0.3299 | 1103129 | 399428 | 358627 | 1211341 | 35506 | 5295 | 0.911 | 1.015 | 20270831 | 20270930 | 43 | 11 | 4 | 3 | 1 | 0 | 9548 | 9189 | 9524 | -359 | 6 | 1 | 94 | 2 | 1500000 | 0 | 1370689 | 0 |  | 1 | 12000 | 6 | 70 | 85.3
674 | 20260831 | 42 | 4 | 3 | 18 | 30 | 2 | 1 | 2 | Active | Deliver | Green | 0.4286 | 0.3669 | 1103129 | 451157 | 396253 | 1216594 | 46419 | 8485 | 0.897 | 1.021 | 20270831 | 20271031 | 53 | 11 | 5 | 3 | 1 | 0 | 9766 | 9764 | 9256 | -2 | 6 | 1 | 94 | 2 | 1500000 | 0 | 1341345 | 0 |  | 1 | 9000 | 5 | 73 | 85.2
675 | 20260930 | 42 | 4 | 3 | 18 | 30 | 2 | 1 | 2 | Active | Deliver | Green | 0.4762 | 0.4213 | 1103129 | 503287 | 471543 | 1225342 | 38539 | -6795 | 0.923 | 0.986 | 20270831 | 20271031 | 47 | 11 | 5 | 3 | 1 | 0 | 9876 | 9298 | 9861 | -578 | 8 | 2 | 137 | 2 | 1500000 | 0 | 1313502 | 0 |  | 1 | 13000 | 7 | 69 | 75.3
676 | 20240731 | 43 | 10 | 7 | 19 | 31 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.0556 | 0.0455 | 940783 | 48317 | 40234 | 946950 | 5511 | 2572 | 0.886 | 1.063 | 20251231 | 20251231 | 6 | 9 | 1 | 1 | 0 | 0 | 4950 | 4953 | 5230 | 3 | 3 | 0 | 29 | 1 | 2400000 | 0 | 2416373 | 0 |  | 0 | 0 | 5 | 80 | 97.1
677 | 20240831 | 43 | 10 | 7 | 19 | 31 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.1111 | 0.1134 | 940783 | 97098 | 100567 | 947473 | -9587 | 6118 | 1.099 | 1.061 | 20251231 | 20251231 | 0 | 9 | 1 | 0 | 0 | 0 | 5660 | 5848 | 6231 | 188 | 2 | 0 | 19 | 0 | 2400000 | 0 | 2455923 | 0 |  | 0 | 0 | 3 | 89 | 100
678 | 20240930 | 43 | 10 | 7 | 19 | 31 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.1667 | 0.179 | 940783 | 146344 | 148737 | 947996 | -22056 | 19663 | 1.151 | 1.132 | 20251231 | 20251231 | 0 | 9 | 2 | 1 | 0 | 0 | 6326 | 6451 | 6592 | 125 | 4 | 0 | 38 | 1 | 2400000 | 0 | 2430002 | 0 |  | 0 | 0 | 2 | 93 | 100
679 | 20241031 | 43 | 10 | 7 | 19 | 31 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.2222 | 0.2543 | 940783 | 196055 | 216380 | 948518 | -43186 | 22861 | 1.22 | 1.106 | 20251231 | 20251231 | 0 | 9 | 2 | 1 | 0 | 0 | 6928 | 6949 | 6869 | 21 | 3 | 0 | 29 | 1 | 2400000 | 0 | 2402636 | 0 |  | 0 | 0 | 4 | 96 | 100
680 | 20241130 | 43 | 10 | 7 | 19 | 31 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.2778 | 0.2997 | 940783 | 246230 | 263221 | 949041 | -35723 | 18732 | 1.145 | 1.071 | 20251231 | 20251231 | 0 | 9 | 3 | 2 | 0 | 0 | 7448 | 7190 | 7253 | -258 | 1 | 0 | 10 | 0 | 2400000 | 0 | 2490956 | 0 |  | 0 | 0 | 5 | 90 | 100
681 | 20241231 | 43 | 10 | 7 | 19 | 31 | 3 | 2 | 3 | Active | Deliver | Green | 0.3333 | 0.3518 | 940783 | 296869 | 315872 | 949564 | -34098 | 15095 | 1.115 | 1.048 | 20251231 | 20251231 | 0 | 9 | 3 | 2 | 0 | 0 | 7870 | 7938 | 8369 | 68 | 2 | 0 | 19 | 0 | 2400000 | 0 | 2504843 | 0 |  | 0 | 0 | 3 | 93 | 100
682 | 20250131 | 43 | 10 | 7 | 19 | 31 | 3 | 2 | 3 | Active | Deliver | Green | 0.3889 | 0.3838 | 940783 | 347974 | 345907 | 950086 | -13099 | 15166 | 1.038 | 1.044 | 20251231 | 20251231 | 3 | 9 | 4 | 4 | 0 | 0 | 8180 | 8001 | 7713 | -179 | 2 | 1 | 37 | 0 | 2400000 | 0 | 2504108 | 0 |  | 0 | 0 | 1 | 77 | 94.8
683 | 20250228 | 43 | 10 | 7 | 19 | 31 | 3 | 2 | 3 | Active | Deliver | Green | 0.4444 | 0.4433 | 940783 | 399542 | 403978 | 950609 | -17507 | 13071 | 1.044 | 1.032 | 20251231 | 20251231 | 1 | 9 | 4 | 3 | 0 | 0 | 8371 | 8945 | 8998 | 574 | 3 | 0 | 29 | 1 | 2400000 | 0 | 2481123 | 0 |  | 0 | 0 | 2 | 82 | 100
684 | 20250331 | 43 | 10 | 7 | 19 | 31 | 3 | 2 | 3 | Active | Deliver | Green | 0.5 | 0.4877 | 940783 | 451576 | 447146 | 951132 | -7244 | 11674 | 1.016 | 1.026 | 20251231 | 20251231 | 8 | 9 | 5 | 4 | 0 | 0 | 8435 | 9106 | 9340 | 671 | 3 | 1 | 47 | 1 | 2400000 | 0 | 2422885 | 0 |  | 0 | 0 | 1 | 80 | 93.6
685 | 20250430 | 43 | 10 | 7 | 19 | 31 | 3 | 2 | 3 | Active | Deliver | Green | 0.5556 | 0.5582 | 940783 | 504074 | 504286 | 951654 | -21071 | 20859 | 1.042 | 1.041 | 20251231 | 20251231 | 0 | 9 | 5 | 5 | 0 | 0 | 8371 | 8482 | 8065 | 111 | 3 | 0 | 29 | 1 | 2400000 | 0 | 2477468 | 0 |  | 0 | 0 | 2 | 83 | 100
686 | 20250531 | 43 | 10 | 7 | 19 | 31 | 3 | 2 | 3 | Active | Deliver | Green | 0.6111 | 0.6194 | 940783 | 557036 | 568597 | 952177 | -25685 | 14124 | 1.046 | 1.025 | 20251231 | 20251231 | 0 | 9 | 6 | 5 | 0 | 0 | 8180 | 8202 | 7920 | 22 | 3 | 0 | 29 | 1 | 2400000 | 0 | 2469241 | 0 |  | 0 | 0 | 4 | 84 | 100
687 | 20250630 | 43 | 10 | 7 | 19 | 31 | 3 | 2 | 3 | Active | Deliver | Green | 0.6667 | 0.6886 | 940783 | 610464 | 633401 | 952700 | -37359 | 14422 | 1.061 | 1.023 | 20251231 | 20251231 | 0 | 9 | 6 | 5 | 0 | 0 | 7870 | 7896 | 7790 | 26 | 2 | 0 | 19 | 0 | 2400000 | 0 | 2491975 | 0 |  | 1 | 8000 | 2 | 87 | 100
688 | 20250731 | 43 | 10 | 7 | 19 | 31 | 3 | 2 | 3 | Active | Deliver | Green | 0.7222 | 0.7434 | 940783 | 664355 | 695963 | 953222 | -35023 | 3415 | 1.053 | 1.005 | 20251231 | 20251231 | 0 | 9 | 7 | 6 | 0 | 0 | 7448 | 7472 | 7156 | 24 | 3 | 0 | 29 | 1 | 2400000 | 19048 | 2445758 | 0 | 0 | 1 | 14000 | 4 | 86 | 100
689 | 20250831 | 43 | 10 | 7 | 19 | 31 | 3 | 2 | 3 | Active | Deploy | Green | 0.7778 | 0.8056 | 940783 | 718712 | 752807 | 953745 | -39183 | 5088 | 1.055 | 1.007 | 20251231 | 20251231 | 0 | 9 | 7 | 7 | 0 | 0 | 6928 | 6933 | 6930 | 5 | 2 | 0 | 19 | 0 | 2400000 | 495238 | 2440026 | 0 | 0 | 1 | 11000 | 5 | 84 | 100
690 | 20250930 | 43 | 10 | 7 | 19 | 31 | 3 | 2 | 3 | Active | Deploy | Green | 0.8333 | 0.8521 | 940783 | 773533 | 808510 | 956029 | -28108 | -6869 | 1.036 | 0.991 | 20251231 | 20251231 | 0 | 9 | 8 | 8 | 0 | 0 | 6326 | 6188 | 6588 | -138 | 1 | 0 | 10 | 0 | 2400000 | 971429 | 2495652 | 403524 | 0.4154 | 1 | 8000 | 0 | 82 | 100
691 | 20251031 | 43 | 10 | 7 | 19 | 31 | 3 | 2 | 3 | Active | Deploy | Green | 0.8889 | 0.8969 | 940783 | 828818 | 862206 | 959202 | -14970 | -18418 | 1.018 | 0.979 | 20251231 | 20251231 | 0 | 9 | 8 | 8 | 0 | 0 | 5660 | 5563 | 5599 | -97 | 0 | 0 | 0 | 0 | 2400000 | 1447619 | 2407632 | 787145 | 0.5438 | 1 | 9000 | 0 | 79 | 99.7
692 | 20251130 | 43 | 10 | 7 | 19 | 31 | 3 | 2 | 3 | Active | Deploy | Green | 0.9444 | 0.9308 | 940783 | 884568 | 900088 | 960922 | 8887 | -24407 | 0.99 | 0.973 | 20251231 | 20251231 | 8 | 9 | 9 | 9 | 0 | 0 | 4950 | 4898 | 4657 | -52 | 1 | 0 | 10 | 0 | 2400000 | 1923810 | 2422672 | 1269691 | 0.66 | 1 | 14000 | 0 | 82 | 98.4
693 | 20251231 | 43 | 10 | 7 | 19 | 31 | 3 | 2 | 3 | Active | Deploy | Green | 1 | 0.9848 | 940783 | 940783 | 959198 | 962896 | 14300 | -32715 | 0.985 | 0.966 | 20251231 | 20251231 | 9 | 9 | 9 | 8 | 0 | 0 | 4217 | 4310 | 4190 | 93 | 2 | 0 | 19 | 0 | 2400000 | 2400000 | 2411967 | 1685028 | 0.7021 | 1 | 8000 | 0 | 83 | 98.1
694 | 20260131 | 43 | 10 | 7 | 19 | 31 | 3 | 2 | 3 | Active | Deploy | Green | 1 | 0.9919 | 940783 | 940783 | 966941 | 966941 | 7620 | -33778 | 0.992 | 0.965 | 20251231 | 20251231 | 4 | 9 | 9 | 8 | 0 | 0 | 4217 | 4184 | 4011 | -33 | 0 | 0 | 0 | 0 | 2400000 | 2400000 | 2408774 | 2197468 | 0.9156 | 1 | 10000 | 2 | 79 | 98.2
695 | 20260228 | 43 | 10 | 7 | 19 | 31 | 3 | 2 | 3 | Completed | Completed | Green | 1 | 1 | 940783 | 940783 | 987629 | 987629 | 0 | -46846 | 1 | 0.953 | 20251231 | 20251231 | 0 | 9 | 9 | 8 | 0 | 0 | 4217 | 4273 | 4559 | 56 | 1 | 0 | 10 | 0 | 2400000 | 2400000 | 2410458 | 2131505 | 0.8881 | 1 | 15000 | 0 | 78 | 98.3
696 | 20251031 | 44 | 6 | 4 | 20 | 32 | 4 | 3 | 4 | Active | Initiate & Design | Green | 0.0417 | 0.0665 | 1995047 | 76754 | 117394 | 2033452 | -55917 | 15277 | 1.728 | 1.13 | 20270930 | 20270930 | 0 | 12 | 1 | 1 | 0 | 0 | 10111 | 10335 | 10528 | 224 | 0 | 0 | 0 | 0 | 1800000 | 0 | 1983410 | 0 |  | 0 | 0 | 5 | 96 | 100
697 | 20251130 | 44 | 6 | 4 | 20 | 32 | 4 | 3 | 4 | Active | Initiate & Design | Green | 0.0833 | 0.132 | 1995047 | 154062 | 227903 | 2035945 | -109284 | 35443 | 1.709 | 1.155 | 20270930 | 20270930 | 0 | 12 | 1 | 1 | 0 | 0 | 11258 | 12253 | 13097 | 995 | 0 | 0 | 0 | 0 | 1800000 | 0 | 1923366 | 0 |  | 0 | 0 | 5 | 96 | 100
698 | 20251231 | 44 | 6 | 4 | 20 | 32 | 4 | 3 | 4 | Active | Initiate & Design | Green | 0.125 | 0.1674 | 1995047 | 231924 | 319956 | 2038439 | -102047 | 14015 | 1.44 | 1.044 | 20270930 | 20270930 | 0 | 12 | 2 | 2 | 0 | 0 | 12366 | 12764 | 13346 | 398 | 0 | 0 | 0 | 0 | 1800000 | 0 | 1932850 | 0 |  | 0 | 0 | 4 | 96 | 100
699 | 20260131 | 44 | 6 | 4 | 20 | 32 | 4 | 3 | 4 | Active | Initiate & Design | Green | 0.1667 | 0.211 | 1995047 | 310341 | 376847 | 2040933 | -110614 | 44108 | 1.356 | 1.117 | 20270930 | 20270930 | 0 | 12 | 2 | 1 | 0 | 0 | 13415 | 14735 | 15312 | 1320 | 1 | 0 | 9 | 0 | 1800000 | 0 | 1981876 | 0 |  | 0 | 0 | 4 | 96 | 100
700 | 20260228 | 44 | 6 | 4 | 20 | 32 | 4 | 3 | 4 | Active | Initiate & Design | Green | 0.2083 | 0.2452 | 1995047 | 389311 | 442850 | 2043427 | -99875 | 46336 | 1.257 | 1.105 | 20270930 | 20270930 | 0 | 12 | 3 | 2 | 0 | 0 | 14388 | 14991 | 14808 | 603 | 2 | 0 | 18 | 0 | 1800000 | 0 | 1983262 | 0 |  | 0 | 0 | 7 | 96 | 100
701 | 20260331 | 44 | 6 | 4 | 20 | 32 | 4 | 3 | 4 | Active | Initiate & Design | Green | 0.25 | 0.277 | 1995047 | 468836 | 529841 | 2045921 | -83792 | 22787 | 1.179 | 1.043 | 20270930 | 20270930 | 0 | 12 | 3 | 3 | 0 | 0 | 15267 | 17269 | 18139 | 2002 | 2 | 0 | 18 | 0 | 1800000 | 0 | 1988529 | 0 |  | 0 | 0 | 6 | 94 | 100
702 | 20260430 | 44 | 6 | 4 | 20 | 32 | 4 | 3 | 4 | Active | Initiate & Design | Green | 0.2917 | 0.3315 | 1995047 | 548915 | 624868 | 2048415 | -112443 | 36490 | 1.205 | 1.059 | 20270930 | 20270930 | 0 | 12 | 4 | 3 | 0 | 0 | 16039 | 17879 | 17461 | 1840 | 2 | 0 | 18 | 0 | 1800000 | 0 | 1907517 | 0 |  | 1 | 28000 | 4 | 94 | 100
703 | 20260531 | 44 | 6 | 4 | 20 | 32 | 4 | 3 | 4 | Active | Deliver | Green | 0.3333 | 0.3695 | 1995047 | 629548 | 705448 | 2050908 | -107622 | 31722 | 1.171 | 1.045 | 20270930 | 20270930 | 0 | 12 | 4 | 3 | 0 | 0 | 16688 | 17833 | 18637 | 1145 | 1 | 0 | 9 | 0 | 1800000 | 0 | 1984495 | 0 |  | 1 | 23000 | 4 | 92 | 100
704 | 20260630 | 44 | 6 | 4 | 20 | 32 | 4 | 3 | 4 | Active | Deliver | Green | 0.375 | 0.4278 | 1995047 | 710735 | 824793 | 2053402 | -142746 | 28688 | 1.201 | 1.035 | 20270930 | 20270930 | 0 | 12 | 5 | 4 | 0 | 0 | 17206 | 18023 | 17262 | 817 | 2 | 0 | 18 | 0 | 1800000 | 0 | 1964313 | 0 |  | 1 | 18000 | 7 | 95 | 100
705 | 20260731 | 44 | 6 | 4 | 20 | 32 | 4 | 3 | 4 | Active | Deliver | Green | 0.4167 | 0.4709 | 1995047 | 792477 | 894770 | 2055896 | -146991 | 44698 | 1.186 | 1.05 | 20270930 | 20270930 | 0 | 12 | 5 | 4 | 0 | 0 | 17582 | 19259 | 18196 | 1677 | 1 | 0 | 9 | 0 | 1800000 | 0 | 1962372 | 0 |  | 1 | 26000 | 7 | 92 | 100
706 | 20260831 | 44 | 6 | 4 | 20 | 32 | 4 | 3 | 4 | Active | Deliver | Green | 0.4583 | 0.5175 | 1995047 | 874773 | 985783 | 2058390 | -157664 | 46654 | 1.18 | 1.047 | 20270930 | 20270930 | 0 | 12 | 6 | 6 | 0 | 0 | 17810 | 20125 | 20475 | 2315 | 2 | 0 | 18 | 0 | 1800000 | 0 | 1953837 | 0 |  | 1 | 29000 | 5 | 94 | 100
707 | 20260930 | 44 | 6 | 4 | 20 | 32 | 4 | 3 | 4 | Active | Deliver | Green | 0.5 | 0.578 | 1995047 | 957623 | 1120600 | 2060884 | -195514 | 32537 | 1.204 | 1.029 | 20270930 | 20270930 | 0 | 12 | 6 | 6 | 0 | 0 | 17887 | 18344 | 17576 | 457 | 2 | 0 | 18 | 0 | 1800000 | 0 | 1975476 | 0 |  | 1 | 28000 | 8 | 96 | 100
708 | 20231031 | 45 | 5 | 5 | 21 | 33 | 5 | 1 | 5 | Active | Initiate & Design | Green | 0.1905 | 0.1356 | 1223605 | 217974 | 156056 | 1271967 | 52053 | 9865 | 0.761 | 1.063 | 20250331 | 20250531 | 45 | 11 | 2 | 0 | 1 | 0 | 8575 | 6245 | 6358 | -2330 | 6 | 1 | 89 | 2 | 1300000 | 0 | 1227115 | 0 |  | 0 | 0 | 8 | 69 | 75.9
709 | 20231130 | 45 | 5 | 5 | 21 | 33 | 5 | 1 | 5 | Active | Initiate & Design | Green | 0.2381 | 0.1679 | 1223605 | 273577 | 190234 | 1274880 | 68134 | 15209 | 0.751 | 1.08 | 20250331 | 20250531 | 57 | 11 | 3 | 2 | 1 | 0 | 9216 | 7001 | 6978 | -2215 | 8 | 1 | 113 | 2 | 1300000 | 0 | 1243883 | 0 |  | 0 | 0 | 6 | 71 | 77.1
710 | 20231231 | 45 | 5 | 5 | 21 | 33 | 5 | 1 | 5 | Active | Initiate & Design | Green | 0.2857 | 0.1956 | 1223605 | 329624 | 229201 | 1277793 | 90287 | 10136 | 0.726 | 1.044 | 20250331 | 20250531 | 73 | 11 | 3 | 2 | 1 | 0 | 9774 | 7742 | 7812 | -2032 | 7 | 1 | 101 | 2 | 1300000 | 0 | 1195429 | 0 |  | 0 | 0 | 7 | 64 | 74.4
711 | 20240131 | 45 | 5 | 5 | 21 | 33 | 5 | 1 | 5 | Active | Initiate & Design | Green | 0.3333 | 0.2259 | 1223605 | 386115 | 260062 | 1280707 | 109703 | 16350 | 0.716 | 1.063 | 20250331 | 20250630 | 88 | 11 | 4 | 1 | 2 | 1 | 10235 | 7650 | 7607 | -2585 | 7 | 1 | 101 | 2 | 1300000 | 0 | 1248203 | 0 |  | 0 | 0 | 9 | 67 | 74.7
712 | 20240229 | 45 | 5 | 5 | 21 | 33 | 5 | 1 | 5 | Active | Initiate & Design | Green | 0.381 | 0.2927 | 1223605 | 443050 | 350293 | 1283620 | 84901 | 7856 | 0.808 | 1.023 | 20250331 | 20250531 | 72 | 11 | 4 | 3 | 1 | 0 | 10591 | 8856 | 8380 | -1735 | 6 | 1 | 89 | 2 | 1300000 | 0 | 1222526 | 0 |  | 1 | 13000 | 9 | 73 | 78.9
713 | 20240331 | 45 | 5 | 5 | 21 | 33 | 5 | 1 | 5 | Active | Initiate & Design | Green | 0.4286 | 0.3438 | 1223605 | 500429 | 414978 | 1286533 | 79754 | 5697 | 0.841 | 1.014 | 20250331 | 20250531 | 68 | 11 | 5 | 4 | 1 | 0 | 10833 | 8866 | 9038 | -1967 | 7 | 1 | 101 | 2 | 1300000 | 0 | 1190740 | 0 |  | 1 | 17000 | 7 | 69 | 79
714 | 20240430 | 45 | 5 | 5 | 21 | 33 | 5 | 1 | 5 | Active | Deliver | Green | 0.4762 | 0.3978 | 1223605 | 558252 | 471025 | 1289447 | 71502 | 15725 | 0.872 | 1.033 | 20250331 | 20250531 | 63 | 11 | 5 | 4 | 1 | 0 | 10955 | 9188 | 9053 | -1767 | 5 | 1 | 77 | 1 | 1300000 | 0 | 1248938 | 0 |  | 1 | 10000 | 8 | 73 | 82.7
715 | 20240531 | 45 | 5 | 5 | 21 | 33 | 5 | 1 | 5 | Active | Deliver | Green | 0.5238 | 0.4251 | 1223605 | 616519 | 520536 | 1292573 | 96365 | -382 | 0.844 | 0.999 | 20250331 | 20250630 | 80 | 11 | 6 | 3 | 2 | 1 | 10955 | 8211 | 7990 | -2744 | 5 | 0 | 59 | 1 | 1300000 | 0 | 1220403 | 0 |  | 1 | 16000 | 6 | 73 | 85.7
716 | 20240630 | 45 | 5 | 5 | 21 | 33 | 5 | 1 | 5 | Active | Deliver | Green | 0.5714 | 0.4844 | 1223605 | 675230 | 592969 | 1295384 | 82516 | -255 | 0.878 | 1 | 20250331 | 20250531 | 71 | 11 | 6 | 5 | 1 | 0 | 10833 | 7933 | 8219 | -2900 | 6 | 1 | 89 | 2 | 1300000 | 0 | 1202840 | 0 |  | 1 | 13000 | 6 | 70 | 78.5
717 | 20240731 | 45 | 5 | 5 | 21 | 33 | 5 | 1 | 5 | Active | Deliver | Green | 0.619 | 0.5026 | 1223605 | 734385 | 620956 | 1300798 | 119401 | -5972 | 0.837 | 0.99 | 20250331 | 20250630 | 94 | 11 | 7 | 4 | 2 | 1 | 10591 | 8452 | 8788 | -2139 | 7 | 1 | 101 | 2 | 1300000 | 0 | 1193741 | 0 |  | 1 | 16000 | 6 | 69 | 77.6
718 | 20240831 | 45 | 5 | 5 | 21 | 33 | 5 | 1 | 5 | Active | Deliver | Green | 0.6667 | 0.5394 | 1223605 | 793984 | 672243 | 1306004 | 133971 | -12230 | 0.831 | 0.982 | 20250331 | 20250630 | 103 | 11 | 7 | 5 | 2 | 1 | 10235 | 7882 | 8161 | -2353 | 7 | 1 | 101 | 2 | 1300000 | 0 | 1204026 | 0 |  | 1 | 18000 | 9 | 70 | 76.6
719 | 20240930 | 45 | 5 | 5 | 21 | 33 | 5 | 1 | 5 | Active | Deliver | Green | 0.7143 | 0.5787 | 1223605 | 854026 | 714721 | 1306526 | 145926 | -6621 | 0.829 | 0.991 | 20250331 | 20250731 | 109 | 11 | 8 | 4 | 3 | 1 | 9774 | 7457 | 7912 | -2317 | 6 | 0 | 71 | 2 | 1300000 | 0 | 1230100 | 0 |  | 1 | 11000 | 8 | 73 | 85.3
720 | 20241031 | 45 | 5 | 5 | 21 | 33 | 5 | 1 | 5 | Active | Deliver | Green | 0.7619 | 0.6109 | 1223605 | 914513 | 771557 | 1315314 | 167013 | -24057 | 0.817 | 0.969 | 20250331 | 20250731 | 122 | 11 | 8 | 4 | 3 | 1 | 9216 | 6794 | 6419 | -2422 | 6 | 1 | 89 | 2 | 1300000 | 194558 | 1207177 | 0 | 0 | 1 | 18000 | 6 | 68 | 74.9
721 | 20241130 | 45 | 5 | 5 | 21 | 33 | 5 | 1 | 5 | Active | Deliver | Green | 0.8095 | 0.6817 | 1223605 | 975443 | 858347 | 1317422 | 141311 | -24215 | 0.855 | 0.972 | 20250331 | 20250630 | 104 | 11 | 9 | 6 | 2 | 1 | 8575 | 6905 | 6855 | -1670 | 3 | 0 | 36 | 1 | 1300000 | 415646 | 1195531 | 112136 | 0.2698 | 1 | 16000 | 6 | 78 | 86
722 | 20241231 | 45 | 5 | 5 | 21 | 33 | 5 | 1 | 5 | Active | Deliver | Green | 0.8571 | 0.7345 | 1223605 | 1036818 | 947121 | 1326521 | 138080 | -48383 | 0.867 | 0.949 | 20250331 | 20250630 | 99 | 11 | 9 | 6 | 2 | 1 | 7865 | 6377 | 6529 | -1488 | 4 | 1 | 65 | 1 | 1300000 | 636735 | 1199004 | 277698 | 0.4361 | 1 | 18000 | 7 | 72 | 77.9
723 | 20250131 | 45 | 5 | 5 | 21 | 33 | 5 | 1 | 5 | Active | Deploy | Green | 0.9048 | 0.7972 | 1223605 | 1098636 | 1020668 | 1327606 | 123178 | -45210 | 0.888 | 0.956 | 20250331 | 20250630 | 88 | 11 | 10 | 7 | 2 | 1 | 7102 | 5594 | 5576 | -1508 | 6 | 1 | 89 | 2 | 1300000 | 857823 | 1239865 | 507539 | 0.5917 | 1 | 14000 | 6 | 73 | 79.4
724 | 20250228 | 45 | 5 | 5 | 21 | 33 | 5 | 1 | 5 | Active | Deploy | Green | 0.9524 | 0.8407 | 1223605 | 1160899 | 1096886 | 1335324 | 132214 | -68201 | 0.886 | 0.938 | 20250331 | 20250630 | 90 | 11 | 10 | 7 | 2 | 1 | 6303 | 4912 | 5029 | -1391 | 4 | 0 | 47 | 1 | 1300000 | 1078912 | 1206539 | 683565 | 0.6336 | 1 | 12000 | 5 | 78 | 85.8
725 | 20250331 | 45 | 5 | 5 | 21 | 33 | 5 | 1 | 5 | Active | Deploy | Green | 1 | 0.8858 | 1223605 | 1223605 | 1161998 | 1339600 | 139736 | -78129 | 0.886 | 0.933 | 20250331 | 20250630 | 93 | 11 | 11 | 8 | 3 | 1 | 5485 | 4489 | 4625 | -996 | 4 | 0 | 47 | 1 | 1300000 | 1300000 | 1203203 | 772400 | 0.5942 | 1 | 10000 | 4 | 76 | 86.4
726 | 20250430 | 45 | 5 | 5 | 21 | 33 | 5 | 1 | 5 | Active | Deploy | Green | 1 | 0.8858 | 1223605 | 1223605 | 1171948 | 1344646 | 139736 | -88079 | 0.886 | 0.925 | 20250331 | 20250630 | 93 | 11 | 11 | 7 | 3 | 1 | 5485 | 4416 | 4158 | -1069 | 6 | 1 | 89 | 2 | 1300000 | 1300000 | 1208548 | 1040833 | 0.8006 | 1 | 11000 | 6 | 69 | 78
727 | 20250531 | 45 | 5 | 5 | 21 | 33 | 5 | 1 | 5 | Active | Deploy | Green | 1 | 0.8858 | 1223605 | 1223605 | 1171948 | 1347559 | 139736 | -88079 | 0.886 | 0.925 | 20250331 | 20250630 | 93 | 11 | 11 | 7 | 3 | 1 | 5485 | 4298 | 4558 | -1187 | 3 | 0 | 36 | 1 | 1300000 | 1300000 | 1224066 | 1203911 | 0.9261 | 1 | 12000 | 5 | 73 | 85.8
728 | 20250630 | 45 | 5 | 5 | 21 | 33 | 5 | 1 | 5 | Active | Deploy | Green | 1 | 0.8858 | 1223605 | 1223605 | 1194305 | 1355133 | 139736 | -110436 | 0.886 | 0.908 | 20250331 | 20250630 | 93 | 11 | 11 | 7 | 3 | 1 | 5485 | 4007 | 4027 | -1478 | 5 | 1 | 77 | 1 | 1300000 | 1300000 | 1208899 | 1152157 | 0.8863 | 1 | 18000 | 7 | 66 | 75.7
729 | 20250731 | 45 | 5 | 5 | 21 | 33 | 5 | 1 | 5 | Active | Deploy | Green | 1 | 0.8858 | 1223605 | 1223605 | 1194305 | 1358046 | 139736 | -110436 | 0.886 | 0.908 | 20250331 | 20250630 | 93 | 11 | 11 | 8 | 3 | 1 | 5485 | 4383 | 4589 | -1102 | 4 | 1 | 65 | 1 | 1300000 | 1300000 | 1220844 | 1068145 | 0.8217 | 1 | 10000 | 6 | 70 | 77.5
730 | 20250831 | 45 | 5 | 5 | 21 | 33 | 5 | 1 | 5 | Active | Deploy | Green | 1 | 0.8858 | 1223605 | 1223605 | 1198901 | 1361896 | 139736 | -115032 | 0.886 | 0.904 | 20250331 | 20250630 | 93 | 11 | 11 | 7 | 3 | 1 | 5485 | 3998 | 4012 | -1487 | 4 | 0 | 47 | 1 | 1300000 | 1300000 | 1217621 | 1180625 | 0.9082 | 2 | 25000 | 5 | 73 | 83.8
731 | 20250930 | 45 | 5 | 5 | 21 | 33 | 5 | 1 | 5 | Active | Deploy | Green | 1 | 0.8858 | 1223605 | 1223605 | 1220386 | 1369094 | 139736 | -136517 | 0.886 | 0.888 | 20250331 | 20250630 | 93 | 11 | 11 | 8 | 3 | 1 | 5485 | 4352 | 4110 | -1133 | 4 | 0 | 47 | 1 | 1300000 | 1300000 | 1252393 | 1173943 | 0.903 | 2 | 23000 | 7 | 72 | 85.4
732 | 20251031 | 45 | 5 | 5 | 21 | 33 | 5 | 1 | 5 | Active | Deploy | Green | 1 | 0.8962 | 1223605 | 1223605 | 1248508 | 1374637 | 127010 | -151913 | 0.896 | 0.878 | 20250331 | 20250630 | 84 | 11 | 11 | 8 | 2 | 1 | 5485 | 4518 | 4358 | -967 | 4 | 1 | 65 | 1 | 1300000 | 1300000 | 1207697 | 1060649 | 0.8159 | 3 | 44000 | 4 | 65 | 77.2
733 | 20251130 | 45 | 5 | 5 | 21 | 33 | 5 | 1 | 5 | Active | Deploy | Green | 1 | 0.8997 | 1223605 | 1223605 | 1248508 | 1374730 | 122728 | -147631 | 0.9 | 0.882 | 20250331 | 20250630 | 81 | 11 | 11 | 8 | 2 | 1 | 5485 | 4359 | 4580 | -1126 | 3 | 0 | 36 | 1 | 1300000 | 1300000 | 1196866 | 1187363 | 0.9134 | 3 | 51000 | 5 | 75 | 84.6
734 | 20251231 | 45 | 5 | 5 | 21 | 33 | 5 | 1 | 5 | Active | Deploy | Green | 1 | 0.8997 | 1223605 | 1223605 | 1248508 | 1374730 | 122728 | -147631 | 0.9 | 0.882 | 20250331 | 20250630 | 81 | 11 | 11 | 9 | 2 | 1 | 5485 | 4105 | 4239 | -1380 | 4 | 0 | 47 | 1 | 1300000 | 1300000 | 1221037 | 1187242 | 0.9133 | 3 | 54000 | 7 | 76 | 84.1
735 | 20260131 | 45 | 5 | 5 | 21 | 33 | 5 | 1 | 5 | Active | Deploy | Green | 1 | 0.8997 | 1223605 | 1223605 | 1248508 | 1374730 | 122728 | -147631 | 0.9 | 0.882 | 20250331 | 20250630 | 81 | 11 | 11 | 8 | 2 | 1 | 5485 | 4071 | 4167 | -1414 | 5 | 1 | 77 | 1 | 1300000 | 1300000 | 1251489 | 1177071 | 0.9054 | 3 | 58000 | 5 | 67 | 76.6
736 | 20251130 | 46 | 4 | 3 | 22 | 34 | 6 | 3 | 6 | Active | Initiate & Design | Green | 0.0667 | 0.0561 | 167313 | 10321 | 9303 | 175121 | 935 | 83 | 0.91 | 1.009 | 20270131 | 20270131 | 7 | 8 | 1 | 1 | 0 | 0 | 906 | 817 | 866 | -89 | 7 | 1 | 103 | 2 | 200000 | 0 | 196461 | 0 |  | 0 | 0 | 4 | 74 | 85.6
737 | 20251231 | 46 | 4 | 3 | 22 | 34 | 6 | 3 | 6 | Active | Initiate & Design | Green | 0.1333 | 0.1158 | 167313 | 20762 | 18972 | 175902 | 1387 | 403 | 0.933 | 1.021 | 20270131 | 20270131 | 10 | 8 | 1 | 0 | 0 | 0 | 1055 | 962 | 1007 | -93 | 6 | 1 | 91 | 2 | 200000 | 0 | 187744 | 0 |  | 1 | 2000 | 3 | 73 | 86.1
738 | 20260131 | 46 | 4 | 3 | 22 | 34 | 6 | 3 | 6 | Active | Initiate & Design | Green | 0.2 | 0.1573 | 167313 | 31321 | 24425 | 176683 | 5003 | 1893 | 0.841 | 1.078 | 20270131 | 20270228 | 25 | 8 | 2 | 0 | 1 | 0 | 1191 | 1083 | 1128 | -108 | 6 | 1 | 91 | 2 | 200000 | 0 | 189237 | 0 |  | 1 | 2000 | 4 | 74 | 84
739 | 20260228 | 46 | 4 | 3 | 22 | 34 | 6 | 3 | 6 | Active | Initiate & Design | Green | 0.2667 | 0.2147 | 167313 | 41999 | 32927 | 177463 | 6077 | 2995 | 0.855 | 1.091 | 20270131 | 20270228 | 30 | 8 | 2 | 1 | 1 | 0 | 1307 | 1239 | 1169 | -68 | 6 | 1 | 91 | 2 | 200000 | 0 | 190696 | 0 |  | 1 | 2000 | 4 | 72 | 86.2
740 | 20260331 | 46 | 4 | 3 | 22 | 34 | 6 | 3 | 6 | Active | Initiate & Design | Green | 0.3333 | 0.2624 | 167313 | 52797 | 42609 | 178244 | 8894 | 1294 | 0.831 | 1.03 | 20270131 | 20270228 | 42 | 8 | 3 | 2 | 1 | 0 | 1400 | 1362 | 1356 | -38 | 7 | 1 | 103 | 2 | 200000 | 0 | 190130 | 0 |  | 1 | 2000 | 5 | 73 | 83.5
741 | 20260430 | 46 | 4 | 3 | 22 | 34 | 6 | 3 | 6 | Active | Initiate & Design | Green | 0.4 | 0.3055 | 167313 | 63713 | 50664 | 179025 | 12599 | 450 | 0.802 | 1.009 | 20270131 | 20270331 | 56 | 8 | 3 | 1 | 1 | 0 | 1463 | 1356 | 1302 | -107 | 8 | 1 | 115 | 2 | 200000 | 0 | 193040 | 0 |  | 1 | 1000 | 3 | 71 | 80.8
742 | 20260531 | 46 | 4 | 3 | 22 | 34 | 6 | 3 | 6 | Active | Deliver | Green | 0.4667 | 0.3906 | 167313 | 74748 | 63787 | 179806 | 9396 | 1565 | 0.874 | 1.024 | 20270131 | 20270331 | 45 | 8 | 4 | 3 | 1 | 0 | 1496 | 1357 | 1432 | -139 | 7 | 1 | 103 | 2 | 200000 | 0 | 190238 | 0 |  | 1 | 2000 | 4 | 69 | 83.8
743 | 20260630 | 46 | 4 | 3 | 22 | 34 | 6 | 3 | 6 | Active | Deliver | Green | 0.5333 | 0.4666 | 167313 | 85902 | 78754 | 180905 | 7834 | -686 | 0.909 | 0.991 | 20270131 | 20270228 | 39 | 8 | 4 | 2 | 1 | 0 | 1496 | 1361 | 1367 | -135 | 7 | 1 | 103 | 2 | 200000 | 0 | 189657 | 0 |  | 1 | 2000 | 4 | 70 | 84.2
744 | 20260731 | 46 | 4 | 3 | 22 | 34 | 6 | 3 | 6 | Active | Deliver | Green | 0.6 | 0.5344 | 167313 | 97175 | 90231 | 181701 | 7763 | -819 | 0.92 | 0.991 | 20270131 | 20270228 | 39 | 8 | 5 | 3 | 1 | 0 | 1463 | 1401 | 1375 | -62 | 8 | 2 | 133 | 2 | 200000 | 0 | 189468 | 0 |  | 1 | 2000 | 7 | 71 | 77.7
745 | 20260831 | 46 | 4 | 3 | 22 | 34 | 6 | 3 | 6 | Active | Deliver | Green | 0.6667 | 0.6095 | 167313 | 108568 | 104788 | 183133 | 6591 | -2811 | 0.939 | 0.973 | 20270131 | 20270131 | -1 | 8 | 5 | 4 | 1 | 0 | 1400 | 1346 | 1367 | -54 | 7 | 1 | 103 | 2 | 200000 | 0 | 189996 | 0 |  | 1 | 2000 | 6 | 75 | 86.1
746 | 20260930 | 46 | 4 | 3 | 22 | 34 | 6 | 3 | 6 | Active | Deliver | Green | 0.7333 | 0.6674 | 167313 | 120079 | 115323 | 184098 | 8414 | -3658 | 0.93 | 0.968 | 20270131 | 20270131 | 4 | 8 | 6 | 5 | 1 | 0 | 1307 | 1256 | 1235 | -51 | 7 | 1 | 103 | 2 | 200000 | 9524 | 193529 | 0 | 0 | 1 | 2000 | 6 | 70 | 86
747 | 20241130 | 47 | 9 | 8 | 23 | 35 | 7 | 1 | 7 | Active | Initiate & Design | Green | 0.0476 | 0.0544 | 514577 | 22637 | 24577 | 524574 | -5356 | 3416 | 1.236 | 1.138 | 20260731 | 20260731 | 0 | 11 | 1 | 1 | 0 | 0 | 2651 | 2521 | 2676 | -130 | 2 | 0 | 20 | 0 | 1000000 | 0 | 740444 | 0 |  | 0 | 0 | 2 | 85 | 100
748 | 20241231 | 47 | 9 | 8 | 23 | 35 | 7 | 1 | 7 | Active | Initiate & Design | Green | 0.0952 | 0.1067 | 514577 | 45460 | 48395 | 525310 | -9445 | 6510 | 1.208 | 1.135 | 20260731 | 20260731 | 0 | 11 | 1 | 1 | 0 | 0 | 2987 | 3048 | 3183 | 61 | 2 | 0 | 20 | 0 | 1000000 | 0 | 734565 | 0 |  | 0 | 0 | 3 | 90 | 100
749 | 20250131 | 47 | 9 | 8 | 23 | 35 | 7 | 1 | 7 | Active | Initiate & Design | Green | 0.1429 | 0.1449 | 514577 | 68470 | 71862 | 526045 | -6092 | 2700 | 1.089 | 1.038 | 20260731 | 20260731 | 0 | 11 | 2 | 2 | 0 | 0 | 3308 | 3464 | 3312 | 156 | 4 | 0 | 41 | 1 | 1000000 | 0 | 762472 | 0 |  | 1 | 5000 | 2 | 75 | 98.7
750 | 20250228 | 47 | 9 | 8 | 23 | 35 | 7 | 1 | 7 | Active | Initiate & Design | Green | 0.1905 | 0.1783 | 514577 | 91667 | 81926 | 526780 | -82 | 9823 | 1.001 | 1.12 | 20260731 | 20260731 | 9 | 11 | 2 | 2 | 0 | 0 | 3606 | 3580 | 3533 | -26 | 3 | 0 | 31 | 1 | 1000000 | 0 | 771955 | 0 |  | 1 | 5000 | 4 | 81 | 97.7
751 | 20250331 | 47 | 9 | 8 | 23 | 35 | 7 | 1 | 7 | Active | Initiate & Design | Green | 0.2381 | 0.2202 | 514577 | 115051 | 105269 | 527515 | 1741 | 8041 | 0.985 | 1.076 | 20260731 | 20260731 | 13 | 11 | 3 | 3 | 0 | 0 | 3876 | 3918 | 4141 | 42 | 5 | 0 | 51 | 1 | 1000000 | 0 | 729360 | 0 |  | 1 | 5000 | 2 | 78 | 94.4
752 | 20250430 | 47 | 9 | 8 | 23 | 35 | 7 | 1 | 7 | Active | Initiate & Design | Green | 0.2857 | 0.2902 | 514577 | 138621 | 138330 | 528250 | -10709 | 11000 | 1.077 | 1.08 | 20260731 | 20260731 | 0 | 11 | 3 | 3 | 0 | 0 | 4110 | 3964 | 4111 | -146 | 2 | 0 | 20 | 0 | 1000000 | 0 | 740680 | 0 |  | 1 | 7000 | 5 | 80 | 98.2
753 | 20250531 | 47 | 9 | 8 | 23 | 35 | 7 | 1 | 7 | Active | Initiate & Design | Green | 0.3333 | 0.3407 | 514577 | 162378 | 166294 | 528985 | -12938 | 9022 | 1.08 | 1.054 | 20260731 | 20260731 | 0 | 11 | 4 | 3 | 0 | 0 | 4304 | 4368 | 4644 | 64 | 2 | 0 | 20 | 0 | 1000000 | 0 | 770314 | 0 |  | 1 | 6000 | 2 | 77 | 99.1
754 | 20250630 | 47 | 9 | 8 | 23 | 35 | 7 | 1 | 7 | Active | Deliver | Green | 0.381 | 0.399 | 514577 | 186321 | 197473 | 529720 | -18995 | 7843 | 1.102 | 1.04 | 20260731 | 20260731 | 0 | 11 | 4 | 3 | 0 | 0 | 4454 | 4695 | 4709 | 241 | 2 | 0 | 20 | 0 | 1000000 | 0 | 735544 | 0 |  | 1 | 8000 | 4 | 78 | 98.6
755 | 20250731 | 47 | 9 | 8 | 23 | 35 | 7 | 1 | 7 | Active | Deliver | Green | 0.4286 | 0.4638 | 514577 | 210451 | 226894 | 530455 | -28210 | 11767 | 1.134 | 1.052 | 20260731 | 20260731 | 0 | 11 | 5 | 5 | 0 | 0 | 4556 | 4758 | 4526 | 202 | 3 | 0 | 31 | 1 | 1000000 | 0 | 730226 | 0 |  | 1 | 7000 | 2 | 79 | 100
756 | 20250831 | 47 | 9 | 8 | 23 | 35 | 7 | 1 | 7 | Active | Deliver | Green | 0.4762 | 0.505 | 514577 | 234768 | 252897 | 531190 | -25093 | 6964 | 1.107 | 1.027 | 20260731 | 20260731 | 0 | 11 | 5 | 4 | 0 | 0 | 4607 | 4443 | 4451 | -164 | 2 | 0 | 20 | 0 | 1000000 | 0 | 754249 | 0 |  | 1 | 5000 | 5 | 81 | 98.1
757 | 20250930 | 47 | 9 | 8 | 23 | 35 | 7 | 1 | 7 | Active | Deliver | Green | 0.5238 | 0.5265 | 514577 | 259272 | 263727 | 531926 | -11653 | 7198 | 1.045 | 1.027 | 20260731 | 20260731 | 0 | 11 | 6 | 5 | 0 | 0 | 4607 | 4508 | 4820 | -99 | 3 | 0 | 31 | 1 | 1000000 | 0 | 757917 | 0 |  | 1 | 5000 | 2 | 78 | 95.7
758 | 20251031 | 47 | 9 | 8 | 23 | 35 | 7 | 1 | 7 | Active | Deliver | Green | 0.5714 | 0.5829 | 514577 | 283962 | 297963 | 532661 | -15985 | 1984 | 1.056 | 1.007 | 20260731 | 20260731 | 0 | 11 | 6 | 5 | 0 | 0 | 4556 | 4373 | 4307 | -183 | 4 | 0 | 41 | 1 | 1000000 | 0 | 757380 | 0 |  | 1 | 7000 | 4 | 73 | 95.1
759 | 20251130 | 47 | 9 | 8 | 23 | 35 | 7 | 1 | 7 | Active | Deliver | Green | 0.619 | 0.6164 | 514577 | 308840 | 316684 | 533396 | -8345 | 501 | 1.027 | 1.002 | 20260731 | 20260731 | 2 | 11 | 7 | 6 | 0 | 0 | 4454 | 4239 | 4223 | -215 | 3 | 0 | 31 | 1 | 1000000 | 0 | 752036 | 0 |  | 1 | 6000 | 5 | 75 | 93.3
760 | 20251231 | 47 | 9 | 8 | 23 | 35 | 7 | 1 | 7 | Active | Deliver | Green | 0.6667 | 0.6706 | 514577 | 333903 | 347529 | 534936 | -11172 | -2454 | 1.033 | 0.993 | 20260731 | 20260731 | 0 | 11 | 7 | 7 | 0 | 0 | 4304 | 4295 | 4529 | -9 | 3 | 1 | 49 | 1 | 1000000 | 0 | 753081 | 0 |  | 1 | 7000 | 3 | 69 | 86.3
761 | 20260131 | 47 | 9 | 8 | 23 | 35 | 7 | 1 | 7 | Active | Deliver | Green | 0.7143 | 0.7173 | 514577 | 359154 | 373440 | 536173 | -9952 | -4334 | 1.028 | 0.988 | 20260731 | 20260731 | 0 | 11 | 8 | 7 | 0 | 0 | 4110 | 4259 | 4422 | 149 | 3 | 0 | 31 | 1 | 1000000 | 0 | 739963 | 0 |  | 1 | 5000 | 4 | 74 | 93.6
762 | 20260228 | 47 | 9 | 8 | 23 | 35 | 7 | 1 | 7 | Active | Deploy | Green | 0.7619 | 0.7803 | 514577 | 384591 | 409814 | 537896 | -16933 | -8290 | 1.044 | 0.98 | 20260731 | 20260731 | 0 | 11 | 8 | 7 | 0 | 0 | 3876 | 3706 | 3586 | -170 | 3 | 0 | 31 | 1 | 1000000 | 149660 | 761598 | 0 | 0 | 1 | 6000 | 5 | 73 | 93.6
763 | 20260331 | 47 | 9 | 8 | 23 | 35 | 7 | 1 | 7 | Active | Deploy | Green | 0.8095 | 0.8337 | 514577 | 410215 | 441753 | 539607 | -18788 | -12750 | 1.046 | 0.971 | 20260731 | 20260731 | 0 | 11 | 9 | 8 | 0 | 0 | 3606 | 3785 | 3623 | 179 | 1 | 0 | 10 | 0 | 1000000 | 319728 | 730359 | 67788 | 0.212 | 1 | 5000 | 1 | 77 | 93.5
764 | 20260430 | 47 | 9 | 8 | 23 | 35 | 7 | 1 | 7 | Active | Deploy | Green | 0.8571 | 0.89 | 514577 | 436025 | 470787 | 540155 | -21949 | -12813 | 1.05 | 0.973 | 20260731 | 20260731 | 0 | 11 | 9 | 9 | 0 | 0 | 3308 | 3526 | 3607 | 218 | 2 | 0 | 20 | 0 | 1000000 | 489796 | 769065 | 178086 | 0.3636 | 1 | 7000 | 0 | 76 | 94.8
765 | 20260531 | 47 | 9 | 8 | 23 | 35 | 7 | 1 | 7 | Active | Deploy | Green | 0.9048 | 0.926 | 514577 | 462022 | 492934 | 541584 | -14476 | -16436 | 1.031 | 0.967 | 20260731 | 20260731 | 0 | 11 | 10 | 10 | 0 | 0 | 2987 | 3002 | 3083 | 15 | 1 | 0 | 10 | 0 | 1000000 | 659864 | 767530 | 291508 | 0.4418 | 1 | 7000 | 1 | 75 | 93.7
766 | 20260630 | 47 | 9 | 8 | 23 | 35 | 7 | 1 | 7 | Active | Deploy | Green | 0.9524 | 0.9719 | 514577 | 488206 | 524938 | 543898 | -11911 | -24821 | 1.024 | 0.953 | 20260731 | 20260731 | 0 | 11 | 10 | 10 | 0 | 0 | 2651 | 2539 | 2592 | -112 | 2 | 0 | 20 | 0 | 1000000 | 829932 | 767238 | 407658 | 0.4912 | 1 | 5000 | 1 | 69 | 92
767 | 20260731 | 47 | 9 | 8 | 23 | 35 | 7 | 1 | 7 | Completed | Completed | Green | 1 | 1 | 514577 | 514577 | 537659 | 544137 | 0 | -23082 | 1 | 0.957 | 20260731 | 20260731 | 0 | 11 | 11 | 10 | 0 | 0 | 2307 | 2308 | 2250 | 1 | 1 | 0 | 10 | 0 | 1000000 | 1000000 | 753736 | 522495 | 0.5225 | 1 | 5000 | 3 | 75 | 91.6
768 | 20250930 | 48 | 7 | 5 | 24 | 36 | 8 | 3 | 8 | Active | Initiate & Design | Red | 0.0667 | 0 | 800465 | 49380 | 3835 | 1083296 | 49380 | -3835 | 0 | 0 | 20261130 | 20261231 | 44 | 8 | 1 | 0 | 1 | 1 | 4334 | 3461 | 3542 | -873 | 14 | 3 | 253 | 5 | 2100000 | 0 | 1495344 | 0 |  | 0 | 0 | 7 | 24 | 0
769 | 20251031 | 48 | 7 | 5 | 24 | 36 | 8 | 3 | 8 | Active | Initiate & Design | Red | 0.1333 | 0.0149 | 800465 | 99329 | 7761 | 917867 | 87402 | 4166 | 0.12 | 1.535 | 20261130 | 20270228 | 78 | 8 | 1 | 0 | 1 | 1 | 5048 | 3855 | 4070 | -1193 | 14 | 3 | 253 | 5 | 2100000 | 0 | 1463716 | 0 |  | 0 | 0 | 6 | 39 | 41.4
770 | 20251130 | 48 | 7 | 5 | 24 | 36 | 8 | 3 | 8 | Active | Initiate & Design | Red | 0.2 | 0.0647 | 800465 | 149847 | 55586 | 940453 | 98057 | -3796 | 0.346 | 0.932 | 20261130 | 20270228 | 90 | 8 | 2 | 1 | 1 | 1 | 5697 | 4630 | 4878 | -1067 | 13 | 3 | 239 | 4 | 2100000 | 0 | 1490240 | 0 |  | 0 | 0 | 6 | 27 | 31.9
771 | 20251231 | 48 | 7 | 5 | 24 | 36 | 8 | 3 | 8 | Active | Initiate & Design | Amber | 0.2667 | 0.1155 | 800465 | 200935 | 87392 | 939212 | 108481 | 5062 | 0.46 | 1.058 | 20261130 | 20270228 | 100 | 8 | 2 | 0 | 1 | 1 | 6255 | 5496 | 5828 | -759 | 10 | 2 | 178 | 3 | 2100000 | 0 | 1501806 | 0 |  | 0 | 0 | 6 | 45 | 51.1
772 | 20260131 | 48 | 7 | 5 | 24 | 36 | 8 | 3 | 8 | Active | Initiate & Design | Red | 0.3333 | 0.1664 | 800465 | 252591 | 133120 | 949885 | 119394 | 77 | 0.527 | 1 | 20261130 | 20270331 | 110 | 8 | 3 | 1 | 2 | 1 | 6696 | 5572 | 5932 | -1124 | 10 | 3 | 196 | 3 | 2100000 | 0 | 1509277 | 0 |  | 0 | 0 | 6 | 34 | 43.2
773 | 20260228 | 48 | 7 | 5 | 24 | 36 | 8 | 3 | 8 | Active | Initiate & Design | Red | 0.4 | 0.2296 | 800465 | 304817 | 192667 | 968645 | 121030 | -8880 | 0.603 | 0.954 | 20261130 | 20270331 | 113 | 8 | 3 | 1 | 2 | 1 | 7001 | 6144 | 6153 | -857 | 11 | 3 | 211 | 4 | 2100000 | 0 | 1437336 | 0 |  | 2 | 19000 | 4 | 40 | 45
774 | 20260331 | 48 | 7 | 5 | 24 | 36 | 8 | 3 | 8 | Active | Initiate & Design | Amber | 0.4667 | 0.3001 | 800465 | 357612 | 255629 | 981828 | 117392 | -15409 | 0.672 | 0.94 | 20261130 | 20270331 | 110 | 8 | 4 | 1 | 2 | 1 | 7157 | 6243 | 6100 | -914 | 10 | 2 | 178 | 3 | 2100000 | 0 | 1439553 | 0 |  | 2 | 13000 | 7 | 45 | 55.5
775 | 20260430 | 48 | 7 | 5 | 24 | 36 | 8 | 3 | 8 | Active | Deliver | Amber | 0.5333 | 0.3537 | 800465 | 410977 | 306950 | 995555 | 127853 | -23826 | 0.689 | 0.922 | 20261130 | 20270331 | 119 | 8 | 4 | 2 | 2 | 1 | 7157 | 5727 | 6090 | -1430 | 9 | 2 | 164 | 3 | 2100000 | 0 | 1454055 | 0 |  | 2 | 26000 | 5 | 44 | 54.3
776 | 20260531 | 48 | 7 | 5 | 24 | 36 | 8 | 3 | 8 | Active | Deliver | Red | 0.6 | 0.3959 | 800465 | 464910 | 343088 | 1006007 | 148006 | -26184 | 0.682 | 0.924 | 20261130 | 20270430 | 135 | 8 | 5 | 2 | 3 | 2 | 7001 | 5707 | 6034 | -1294 | 12 | 3 | 225 | 4 | 2100000 | 0 | 1499846 | 0 |  | 2 | 14000 | 5 | 43 | 46.9
777 | 20260630 | 48 | 7 | 5 | 24 | 36 | 8 | 3 | 8 | Active | Deliver | Red | 0.6667 | 0.4573 | 800465 | 519413 | 403774 | 1019713 | 153360 | -37721 | 0.705 | 0.907 | 20261130 | 20270430 | 138 | 8 | 5 | 2 | 3 | 2 | 6696 | 5480 | 5306 | -1216 | 12 | 3 | 225 | 4 | 2100000 | 0 | 1450058 | 0 |  | 2 | 14000 | 5 | 42 | 46.8
778 | 20260731 | 48 | 7 | 5 | 24 | 36 | 8 | 3 | 8 | Active | Deliver | Amber | 0.7333 | 0.4798 | 800465 | 574485 | 430701 | 1032992 | 190422 | -46638 | 0.669 | 0.892 | 20261130 | 20270531 | 167 | 8 | 6 | 1 | 4 | 2 | 6255 | 5374 | 5381 | -881 | 11 | 2 | 193 | 4 | 2100000 | 100000 | 1503986 | 0 | 0 | 2 | 18000 | 4 | 46 | 54.2
779 | 20260831 | 48 | 7 | 5 | 24 | 36 | 8 | 3 | 8 | Active | Deliver | Red | 0.8 | 0.5406 | 800465 | 630126 | 497290 | 1047452 | 197395 | -64559 | 0.687 | 0.87 | 20261130 | 20270531 | 172 | 8 | 6 | 2 | 3 | 2 | 5697 | 4627 | 4769 | -1070 | 12 | 3 | 225 | 4 | 2100000 | 600000 | 1520308 | 100921 | 0.1682 | 3 | 38000 | 8 | 38 | 45.5
780 | 20260930 | 48 | 7 | 5 | 24 | 36 | 8 | 3 | 8 | Active | Deliver | Amber | 0.8667 | 0.5898 | 800465 | 686336 | 553928 | 1061276 | 214222 | -81814 | 0.688 | 0.852 | 20261130 | 20270531 | 184 | 8 | 7 | 3 | 4 | 2 | 5048 | 4341 | 4106 | -707 | 7 | 1 | 118 | 2 | 2100000 | 1100000 | 1445389 | 382622 | 0.3478 | 3 | 21000 | 4 | 52 | 61
781 | 20240531 | 49 | 5 | 5 | 1 | 25 | 1 | 3 | 1 | Active | Initiate & Design | Red | 0.0476 | 0.0116 | 681298 | 29971 | 7858 | 725420 | 22068 | 45 | 0.263 | 1.003 | 20260131 | 20260228 | 31 | 11 | 1 | 0 | 1 | 0 | 3509 | 3290 | 3395 | -219 | 10 | 2 | 162 | 3 | 1900000 | 0 | 1697931 | 0 |  | 0 | 0 | 5 | 40 | 46.6
782 | 20240630 | 49 | 5 | 5 | 1 | 25 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.0952 | 0.053 | 681298 | 60189 | 29789 | 728664 | 24080 | 6320 | 0.599 | 1.211 | 20260131 | 20260228 | 36 | 11 | 1 | 0 | 1 | 0 | 3954 | 3939 | 3728 | -15 | 9 | 2 | 150 | 3 | 1900000 | 0 | 1683819 | 0 |  | 1 | 9000 | 7 | 60 | 70.1
783 | 20240731 | 49 | 5 | 5 | 1 | 25 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.1429 | 0.0993 | 681298 | 90654 | 64612 | 731909 | 23001 | 3041 | 0.746 | 1.047 | 20260131 | 20260228 | 36 | 11 | 2 | 1 | 1 | 0 | 4379 | 4051 | 4060 | -328 | 7 | 1 | 106 | 2 | 1900000 | 0 | 1726879 | 0 |  | 1 | 7000 | 7 | 67 | 78
784 | 20240831 | 49 | 5 | 5 | 1 | 25 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.1905 | 0.1429 | 681298 | 121367 | 95672 | 735153 | 24010 | 1685 | 0.802 | 1.018 | 20260131 | 20260228 | 40 | 11 | 2 | 0 | 1 | 0 | 4775 | 4804 | 4664 | 29 | 8 | 1 | 119 | 2 | 1900000 | 0 | 1706279 | 0 |  | 1 | 7000 | 3 | 73 | 80.9
785 | 20240930 | 49 | 5 | 5 | 1 | 25 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.2381 | 0.2118 | 681298 | 152326 | 141442 | 738397 | 8027 | 2857 | 0.947 | 1.02 | 20260131 | 20260228 | 23 | 11 | 3 | 3 | 0 | 0 | 5131 | 4829 | 4720 | -302 | 7 | 1 | 106 | 2 | 1900000 | 0 | 1751342 | 0 |  | 1 | 8000 | 4 | 75 | 86.9
786 | 20241031 | 49 | 5 | 5 | 1 | 25 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.2857 | 0.2637 | 681298 | 183533 | 174554 | 741642 | 3875 | 5104 | 0.979 | 1.029 | 20260131 | 20260228 | 19 | 11 | 3 | 2 | 0 | 0 | 5442 | 5375 | 5399 | -67 | 6 | 1 | 94 | 2 | 1900000 | 0 | 1665599 | 0 |  | 1 | 7000 | 4 | 78 | 88.4
787 | 20241130 | 49 | 5 | 5 | 1 | 25 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.3333 | 0.3199 | 681298 | 214987 | 213854 | 744886 | -2960 | 4093 | 1.014 | 1.019 | 20260131 | 20260131 | 11 | 11 | 4 | 3 | 0 | 0 | 5699 | 5400 | 5450 | -299 | 8 | 2 | 137 | 2 | 1900000 | 0 | 1753036 | 0 |  | 1 | 7000 | 4 | 76 | 82
788 | 20241231 | 49 | 5 | 5 | 1 | 25 | 1 | 3 | 1 | Active | Deliver | Green | 0.381 | 0.3557 | 681298 | 246689 | 233975 | 748130 | 4351 | 8363 | 0.982 | 1.036 | 20260131 | 20260228 | 22 | 11 | 4 | 4 | 0 | 0 | 5897 | 5511 | 5889 | -386 | 6 | 1 | 94 | 2 | 1900000 | 0 | 1755715 | 0 |  | 1 | 10000 | 5 | 79 | 88.9
789 | 20250131 | 49 | 5 | 5 | 1 | 25 | 1 | 3 | 1 | Active | Deliver | Green | 0.4286 | 0.4 | 681298 | 278637 | 272536 | 751385 | 6118 | -17 | 0.978 | 1 | 20260131 | 20260228 | 24 | 11 | 5 | 3 | 1 | 0 | 6032 | 5839 | 5509 | -193 | 7 | 1 | 106 | 2 | 1900000 | 0 | 1757125 | 0 |  | 1 | 8000 | 5 | 76 | 88.2
790 | 20250228 | 49 | 5 | 5 | 1 | 25 | 1 | 3 | 1 | Active | Deliver | Green | 0.4762 | 0.4215 | 681298 | 310833 | 287755 | 754933 | 23666 | -588 | 0.924 | 0.998 | 20260131 | 20260331 | 46 | 11 | 5 | 3 | 1 | 0 | 6100 | 6065 | 5794 | -35 | 6 | 1 | 94 | 2 | 1900000 | 0 | 1662555 | 0 |  | 1 | 7000 | 6 | 72 | 84.9
791 | 20250331 | 49 | 5 | 5 | 1 | 25 | 1 | 3 | 1 | Active | Deliver | Green | 0.5238 | 0.4666 | 681298 | 343275 | 320165 | 758924 | 25381 | -2271 | 0.926 | 0.993 | 20260131 | 20260331 | 49 | 11 | 6 | 5 | 1 | 0 | 6100 | 5481 | 5650 | -619 | 8 | 1 | 119 | 2 | 1900000 | 0 | 1714519 | 0 |  | 1 | 8000 | 4 | 75 | 83.5
792 | 20250430 | 49 | 5 | 5 | 1 | 25 | 1 | 3 | 1 | Active | Deliver | Green | 0.5714 | 0.5125 | 681298 | 375965 | 359747 | 765525 | 26800 | -10582 | 0.929 | 0.971 | 20260131 | 20260331 | 50 | 11 | 6 | 5 | 1 | 0 | 6032 | 5770 | 5988 | -262 | 7 | 2 | 124 | 2 | 1900000 | 0 | 1743401 | 0 |  | 1 | 7000 | 5 | 69 | 76.5
793 | 20250531 | 49 | 5 | 5 | 1 | 25 | 1 | 3 | 1 | Active | Deliver | Green | 0.619 | 0.5545 | 681298 | 408902 | 391851 | 769745 | 31122 | -14071 | 0.924 | 0.964 | 20260131 | 20260331 | 55 | 11 | 7 | 6 | 1 | 0 | 5897 | 5649 | 5959 | -248 | 6 | 1 | 94 | 2 | 1900000 | 0 | 1755074 | 0 |  | 1 | 11000 | 4 | 70 | 84.3
794 | 20250630 | 49 | 5 | 5 | 1 | 25 | 1 | 3 | 1 | Active | Deliver | Green | 0.6667 | 0.6115 | 681298 | 442087 | 430473 | 772417 | 25473 | -13859 | 0.942 | 0.968 | 20260131 | 20260331 | 47 | 11 | 7 | 5 | 1 | 0 | 5699 | 5546 | 5441 | -153 | 7 | 1 | 106 | 2 | 1900000 | 0 | 1723435 | 0 |  | 1 | 11000 | 6 | 77 | 85.1
795 | 20250731 | 49 | 5 | 5 | 1 | 25 | 1 | 3 | 1 | Active | Deliver | Green | 0.7143 | 0.6623 | 681298 | 475518 | 473523 | 777896 | 24294 | -22299 | 0.949 | 0.953 | 20260131 | 20260228 | 44 | 11 | 8 | 6 | 1 | 0 | 5442 | 5457 | 5254 | 15 | 6 | 1 | 94 | 2 | 1900000 | 0 | 1744453 | 0 |  | 2 | 19000 | 4 | 72 | 85.8
796 | 20250831 | 49 | 5 | 5 | 1 | 25 | 1 | 3 | 1 | Active | Deliver | Green | 0.7619 | 0.7218 | 681298 | 509197 | 524234 | 783368 | 17436 | -32473 | 0.966 | 0.938 | 20260131 | 20260228 | 34 | 11 | 8 | 6 | 1 | 0 | 5131 | 5011 | 5345 | -120 | 6 | 1 | 94 | 2 | 1900000 | 284354 | 1690625 | 0 | 0 | 2 | 21000 | 6 | 70 | 84.7
797 | 20250930 | 49 | 5 | 5 | 1 | 25 | 1 | 3 | 1 | Active | Deploy | Green | 0.8095 | 0.7751 | 681298 | 543123 | 570997 | 788597 | 15049 | -42923 | 0.972 | 0.925 | 20260131 | 20260228 | 30 | 11 | 9 | 8 | 1 | 0 | 4775 | 4451 | 4556 | -324 | 4 | 1 | 69 | 1 | 1900000 | 607483 | 1678103 | 149844 | 0.2467 | 2 | 19000 | 4 | 71 | 83.4
798 | 20251031 | 49 | 5 | 5 | 1 | 25 | 1 | 3 | 1 | Active | Deploy | Green | 0.8571 | 0.7921 | 681298 | 577296 | 585851 | 792395 | 37640 | -46195 | 0.935 | 0.921 | 20260131 | 20260331 | 55 | 11 | 9 | 6 | 2 | 1 | 4379 | 4238 | 4323 | -141 | 5 | 1 | 81 | 1 | 1900000 | 930612 | 1702918 | 393779 | 0.4231 | 2 | 22000 | 2 | 68 | 82.7
799 | 20251130 | 49 | 5 | 5 | 1 | 25 | 1 | 3 | 1 | Active | Deploy | Green | 0.9048 | 0.8358 | 681298 | 611716 | 625185 | 797177 | 42287 | -55756 | 0.931 | 0.911 | 20260131 | 20260331 | 58 | 11 | 10 | 7 | 2 | 1 | 3954 | 3804 | 3576 | -150 | 4 | 0 | 51 | 1 | 1900000 | 1253741 | 1727279 | 675907 | 0.5391 | 2 | 13000 | 4 | 80 | 90.4
800 | 20251231 | 49 | 5 | 5 | 1 | 25 | 1 | 3 | 1 | Active | Deploy | Green | 0.9524 | 0.8626 | 681298 | 646383 | 657253 | 802924 | 58695 | -69565 | 0.909 | 0.894 | 20260131 | 20260430 | 77 | 11 | 10 | 7 | 2 | 1 | 3509 | 3457 | 3684 | -52 | 5 | 1 | 81 | 1 | 1900000 | 1576871 | 1722356 | 950508 | 0.6028 | 2 | 16000 | 3 | 69 | 81.3
801 | 20260131 | 49 | 5 | 5 | 1 | 25 | 1 | 3 | 1 | Active | Deploy | Green | 1 | 0.909 | 681298 | 681298 | 695532 | 806735 | 61998 | -76232 | 0.909 | 0.89 | 20260131 | 20260430 | 77 | 11 | 11 | 9 | 2 | 1 | 3054 | 2756 | 2718 | -298 | 7 | 1 | 106 | 2 | 1900000 | 1900000 | 1745169 | 1132928 | 0.5963 | 2 | 14000 | 4 | 70 | 79.6
802 | 20260228 | 49 | 5 | 5 | 1 | 25 | 1 | 3 | 1 | Active | Deploy | Green | 1 | 0.9246 | 681298 | 681298 | 713155 | 811045 | 51370 | -83227 | 0.925 | 0.883 | 20260131 | 20260331 | 65 | 11 | 11 | 8 | 2 | 1 | 3054 | 2764 | 2653 | -290 | 5 | 1 | 81 | 1 | 1900000 | 1900000 | 1751285 | 1433897 | 0.7547 | 2 | 14000 | 4 | 72 | 80.2
803 | 20260331 | 49 | 5 | 5 | 1 | 25 | 1 | 3 | 1 | Active | Deploy | Green | 1 | 0.9361 | 681298 | 681298 | 730811 | 815875 | 43535 | -93048 | 0.936 | 0.873 | 20260131 | 20260331 | 54 | 11 | 11 | 9 | 2 | 1 | 3054 | 2742 | 2628 | -312 | 4 | 0 | 51 | 1 | 1900000 | 1900000 | 1664453 | 1541080 | 0.8111 | 2 | 14000 | 5 | 77 | 87
804 | 20260430 | 49 | 5 | 5 | 1 | 25 | 1 | 3 | 1 | Active | Deploy | Green | 1 | 0.9438 | 681298 | 681298 | 740619 | 819786 | 38289 | -97610 | 0.944 | 0.868 | 20260131 | 20260331 | 47 | 11 | 11 | 9 | 2 | 1 | 3054 | 2864 | 3041 | -190 | 5 | 1 | 81 | 1 | 1900000 | 1900000 | 1736096 | 1616265 | 0.8507 | 2 | 20000 | 4 | 71 | 81.1
805 | 20260531 | 49 | 5 | 5 | 1 | 25 | 1 | 3 | 1 | Active | Deploy | Green | 1 | 0.9438 | 681298 | 681298 | 749252 | 824530 | 38289 | -106243 | 0.944 | 0.858 | 20260131 | 20260331 | 47 | 11 | 11 | 9 | 2 | 1 | 3054 | 2780 | 2724 | -274 | 5 | 1 | 81 | 1 | 1900000 | 1900000 | 1726909 | 1598217 | 0.8412 | 2 | 18000 | 5 | 73 | 80
806 | 20260630 | 49 | 5 | 5 | 1 | 25 | 1 | 3 | 1 | Active | Deploy | Green | 1 | 0.9438 | 681298 | 681298 | 762112 | 829945 | 38289 | -119103 | 0.944 | 0.844 | 20260131 | 20260331 | 47 | 11 | 11 | 8 | 2 | 1 | 3054 | 2951 | 2998 | -103 | 4 | 0 | 51 | 1 | 1900000 | 1900000 | 1720947 | 1682529 | 0.8855 | 2 | 18000 | 3 | 74 | 88.6
807 | 20260731 | 49 | 5 | 5 | 1 | 25 | 1 | 3 | 1 | Active | Deploy | Green | 1 | 0.9438 | 681298 | 681298 | 764185 | 833532 | 38289 | -121176 | 0.944 | 0.841 | 20260131 | 20260331 | 47 | 11 | 11 | 8 | 2 | 1 | 3054 | 2872 | 2829 | -182 | 4 | 1 | 69 | 1 | 1900000 | 1900000 | 1679528 | 1471584 | 0.7745 | 3 | 18000 | 3 | 66 | 79.4
808 | 20260831 | 49 | 5 | 5 | 1 | 25 | 1 | 3 | 1 | Active | Deploy | Green | 1 | 0.9438 | 681298 | 681298 | 773826 | 838348 | 38289 | -130817 | 0.944 | 0.831 | 20260131 | 20260331 | 47 | 11 | 11 | 8 | 2 | 1 | 3054 | 2987 | 3102 | -67 | 5 | 1 | 81 | 1 | 1900000 | 1900000 | 1677564 | 1486640 | 0.7824 | 3 | 26000 | 2 | 65 | 79.8
809 | 20260930 | 49 | 5 | 5 | 1 | 25 | 1 | 3 | 1 | Active | Deploy | Green | 1 | 0.9438 | 681298 | 681298 | 777470 | 840067 | 38289 | -134461 | 0.944 | 0.827 | 20260131 | 20260331 | 47 | 11 | 11 | 8 | 2 | 1 | 3054 | 3040 | 3168 | -14 | 6 | 1 | 94 | 2 | 1900000 | 1900000 | 1715778 | 1586229 | 0.8349 | 3 | 32000 | 1 | 68 | 80.6
810 | 20231031 | 50 | 2 | 4 | 2 | 26 | 2 | 2 | 2 | Active | Initiate & Design | Green | 0.3333 | 0.3432 | 335963 | 106015 | 109159 | 339099 | -9288 | 6144 | 1.088 | 1.056 | 20241231 | 20241231 | 0 | 11 | 4 | 3 | 0 | 0 | 2810 | 2918 | 2971 | 108 | 4 | 0 | 38 | 1 | 300000 | 0 | 298810 | 0 |  | 0 | 0 | 2 | 85 | 100
811 | 20231130 | 50 | 2 | 4 | 2 | 26 | 2 | 2 | 2 | Active | Deliver | Green | 0.381 | 0.3802 | 335963 | 121648 | 123662 | 339259 | -6085 | 4071 | 1.05 | 1.033 | 20241231 | 20241231 | 0 | 11 | 4 | 4 | 0 | 0 | 2908 | 2806 | 2687 | -102 | 2 | 0 | 19 | 0 | 300000 | 0 | 303443 | 0 |  | 0 | 0 | 4 | 87 | 100
812 | 20231231 | 50 | 2 | 4 | 2 | 26 | 2 | 2 | 2 | Active | Deliver | Green | 0.4286 | 0.42 | 335963 | 137402 | 134649 | 339419 | -3702 | 6455 | 1.027 | 1.048 | 20241231 | 20241231 | 6 | 11 | 5 | 5 | 0 | 0 | 2974 | 3008 | 2943 | 34 | 2 | 0 | 19 | 0 | 300000 | 0 | 298845 | 0 |  | 0 | 0 | 2 | 88 | 100
813 | 20240131 | 50 | 2 | 4 | 2 | 26 | 2 | 2 | 2 | Active | Deliver | Green | 0.4762 | 0.4792 | 335963 | 153278 | 153369 | 339579 | -7715 | 7624 | 1.05 | 1.05 | 20241231 | 20241231 | 0 | 11 | 5 | 4 | 0 | 0 | 3008 | 2984 | 2860 | -24 | 4 | 0 | 38 | 1 | 300000 | 0 | 310144 | 0 |  | 1 | 4000 | 1 | 87 | 100
814 | 20240229 | 50 | 2 | 4 | 2 | 26 | 2 | 2 | 2 | Active | Deliver | Green | 0.5238 | 0.5095 | 335963 | 169277 | 165119 | 339739 | -1896 | 6054 | 1.011 | 1.037 | 20241231 | 20241231 | 10 | 11 | 6 | 6 | 0 | 0 | 3008 | 3085 | 3114 | 77 | 4 | 1 | 56 | 1 | 300000 | 0 | 308745 | 0 |  | 1 | 4000 | 5 | 76 | 93.8
815 | 20240331 | 50 | 2 | 4 | 2 | 26 | 2 | 2 | 2 | Active | Deliver | Green | 0.5714 | 0.5752 | 335963 | 185397 | 186736 | 339899 | -7849 | 6510 | 1.042 | 1.035 | 20241231 | 20241231 | 0 | 11 | 6 | 6 | 0 | 0 | 2974 | 3110 | 3162 | 136 | 2 | 0 | 19 | 0 | 300000 | 0 | 301652 | 0 |  | 1 | 5000 | 3 | 85 | 100
816 | 20240430 | 50 | 2 | 4 | 2 | 26 | 2 | 2 | 2 | Active | Deliver | Green | 0.619 | 0.6415 | 335963 | 201639 | 212400 | 340059 | -13881 | 3120 | 1.069 | 1.015 | 20241231 | 20241231 | 0 | 11 | 7 | 6 | 0 | 0 | 2908 | 3075 | 3041 | 167 | 3 | 0 | 29 | 1 | 300000 | 0 | 304446 | 0 |  | 1 | 5000 | 1 | 84 | 100
817 | 20240531 | 50 | 2 | 4 | 2 | 26 | 2 | 2 | 2 | Active | Deliver | Green | 0.6667 | 0.695 | 335963 | 218003 | 228625 | 340219 | -15491 | 4869 | 1.071 | 1.021 | 20241231 | 20241231 | 0 | 11 | 7 | 6 | 0 | 0 | 2810 | 2902 | 3088 | 92 | 2 | 1 | 37 | 0 | 300000 | 0 | 309844 | 0 |  | 1 | 3000 | 3 | 82 | 95.9
818 | 20240630 | 50 | 2 | 4 | 2 | 26 | 2 | 2 | 2 | Active | Deliver | Green | 0.7143 | 0.7493 | 335963 | 234488 | 252044 | 340468 | -17249 | -307 | 1.074 | 0.999 | 20241231 | 20241231 | 0 | 11 | 8 | 7 | 0 | 0 | 2684 | 2580 | 2664 | -104 | 4 | 0 | 38 | 1 | 300000 | 0 | 298591 | 0 |  | 1 | 4000 | 3 | 87 | 100
819 | 20240731 | 50 | 2 | 4 | 2 | 26 | 2 | 2 | 2 | Active | Deploy | Green | 0.7619 | 0.7859 | 335963 | 251096 | 265683 | 341001 | -12937 | -1650 | 1.051 | 0.994 | 20241231 | 20241231 | 0 | 11 | 8 | 7 | 0 | 0 | 2530 | 2441 | 2548 | -89 | 1 | 0 | 10 | 0 | 300000 | 44898 | 309921 | 0 | 0 | 1 | 5000 | 2 | 82 | 100
820 | 20240831 | 50 | 2 | 4 | 2 | 26 | 2 | 2 | 2 | Active | Deploy | Green | 0.8095 | 0.8285 | 335963 | 267826 | 280182 | 341181 | -10519 | -1837 | 1.039 | 0.993 | 20241231 | 20241231 | 0 | 11 | 9 | 8 | 0 | 0 | 2354 | 2316 | 2400 | -38 | 1 | 0 | 10 | 0 | 300000 | 95918 | 302291 | 27670 | 0.2885 | 1 | 3000 | 0 | 80 | 100
821 | 20240930 | 50 | 2 | 4 | 2 | 26 | 2 | 2 | 2 | Active | Deploy | Green | 0.8571 | 0.8659 | 335963 | 284677 | 294276 | 341705 | -6233 | -3366 | 1.022 | 0.989 | 20241231 | 20241231 | 0 | 11 | 9 | 8 | 0 | 0 | 2159 | 2287 | 2226 | 128 | 2 | 0 | 19 | 0 | 300000 | 146939 | 305149 | 78204 | 0.5322 | 1 | 5000 | 2 | 87 | 100
822 | 20241031 | 50 | 2 | 4 | 2 | 26 | 2 | 2 | 2 | Active | Deploy | Green | 0.9048 | 0.8915 | 335963 | 301651 | 303590 | 342014 | 2140 | -4079 | 0.993 | 0.987 | 20241231 | 20241231 | 9 | 11 | 10 | 10 | 0 | 0 | 1950 | 2078 | 2106 | 128 | 1 | 0 | 10 | 0 | 300000 | 197959 | 310783 | 127126 | 0.6422 | 1 | 4000 | 1 | 85 | 99.2
823 | 20241130 | 50 | 2 | 4 | 2 | 26 | 2 | 2 | 2 | Active | Deploy | Green | 0.9524 | 0.9361 | 335963 | 318746 | 321397 | 342766 | 4251 | -6902 | 0.987 | 0.979 | 20241231 | 20241231 | 11 | 11 | 10 | 9 | 0 | 0 | 1731 | 1847 | 1768 | 116 | 0 | 0 | 0 | 0 | 300000 | 248980 | 310149 | 155944 | 0.6263 | 1 | 4000 | 3 | 79 | 98.6
824 | 20241231 | 50 | 2 | 4 | 2 | 26 | 2 | 2 | 2 | Completed | Completed | Green | 1 | 1 | 335963 | 335963 | 346501 | 346501 | 0 | -10538 | 1 | 0.97 | 20241231 | 20241231 | 0 | 11 | 11 | 10 | 0 | 0 | 1506 | 1465 | 1476 | -41 | 1 | 0 | 10 | 0 | 300000 | 300000 | 307809 | 202050 | 0.6735 | 1 | 3000 | 1 | 84 | 98.3
825 | 20250228 | 51 | 8 | 6 | 3 | 27 | 3 | 1 | 3 | Active | Initiate & Design | Green | 0.0333 | 0.0452 | 188310 | 5792 | 6513 | 191888 | -2720 | 1999 | 1.47 | 1.307 | 20270731 | 20270731 | 0 | 15 | 1 | 0 | 0 | 0 | 932 | 969 | 927 | 37 | 0 | 0 | 0 | 0 | 400000 | 0 | 437520 | 0 |  | 1 | 2000 | 2 | 96 | 100
826 | 20250331 | 51 | 8 | 6 | 3 | 27 | 3 | 1 | 3 | Active | Initiate & Design | Green | 0.0667 | 0.0775 | 188310 | 11617 | 13985 | 192076 | -2977 | 609 | 1.257 | 1.044 | 20270731 | 20270731 | 0 | 15 | 1 | 0 | 0 | 0 | 1020 | 1071 | 1098 | 51 | 0 | 0 | 0 | 0 | 400000 | 0 | 431629 | 0 |  | 1 | 2000 | 1 | 93 | 100
827 | 20250430 | 51 | 8 | 6 | 3 | 27 | 3 | 1 | 3 | Active | Initiate & Design | Green | 0.1 | 0.1216 | 188310 | 17475 | 20922 | 192265 | -5423 | 1976 | 1.31 | 1.094 | 20270731 | 20270731 | 0 | 15 | 2 | 2 | 0 | 0 | 1105 | 1238 | 1283 | 133 | 1 | 0 | 9 | 0 | 400000 | 0 | 439955 | 0 |  | 1 | 2000 | 2 | 96 | 100
828 | 20250531 | 51 | 8 | 6 | 3 | 27 | 3 | 1 | 3 | Active | Initiate & Design | Green | 0.1333 | 0.19 | 188310 | 23367 | 34103 | 192453 | -12412 | 1676 | 1.532 | 1.049 | 20270731 | 20270731 | 0 | 15 | 2 | 1 | 0 | 0 | 1187 | 1293 | 1232 | 106 | 0 | 0 | 0 | 0 | 400000 | 0 | 435163 | 0 |  | 1 | 3000 | 1 | 96 | 100
829 | 20250630 | 51 | 8 | 6 | 3 | 27 | 3 | 1 | 3 | Active | Initiate & Design | Green | 0.1667 | 0.2102 | 188310 | 29293 | 36972 | 192641 | -10290 | 2611 | 1.351 | 1.071 | 20270731 | 20270731 | 0 | 15 | 3 | 3 | 0 | 0 | 1266 | 1384 | 1335 | 118 | 1 | 0 | 9 | 0 | 400000 | 0 | 427550 | 0 |  | 1 | 2000 | 4 | 96 | 100
830 | 20250731 | 51 | 8 | 6 | 3 | 27 | 3 | 1 | 3 | Active | Initiate & Design | Green | 0.2 | 0.2566 | 188310 | 35252 | 44500 | 192829 | -13068 | 3820 | 1.371 | 1.086 | 20270731 | 20270731 | 0 | 15 | 3 | 3 | 0 | 0 | 1340 | 1398 | 1325 | 58 | 2 | 0 | 18 | 0 | 400000 | 0 | 435649 | 0 |  | 1 | 3000 | 2 | 96 | 100
831 | 20250831 | 51 | 8 | 6 | 3 | 27 | 3 | 1 | 3 | Active | Initiate & Design | Green | 0.2333 | 0.2676 | 188310 | 41244 | 48084 | 193018 | -9148 | 2308 | 1.222 | 1.048 | 20270731 | 20270731 | 0 | 15 | 4 | 4 | 0 | 0 | 1409 | 1561 | 1643 | 152 | 1 | 0 | 9 | 0 | 400000 | 0 | 432691 | 0 |  | 1 | 2000 | 4 | 91 | 100
832 | 20250930 | 51 | 8 | 6 | 3 | 27 | 3 | 1 | 3 | Active | Initiate & Design | Green | 0.2667 | 0.3118 | 188310 | 47270 | 55150 | 193206 | -11445 | 3565 | 1.242 | 1.065 | 20270731 | 20270731 | 0 | 15 | 4 | 4 | 0 | 0 | 1471 | 1655 | 1653 | 184 | 0 | 0 | 0 | 0 | 400000 | 0 | 441180 | 0 |  | 1 | 2000 | 2 | 92 | 100
833 | 20251031 | 51 | 8 | 6 | 3 | 27 | 3 | 1 | 3 | Active | Initiate & Design | Green | 0.3 | 0.3284 | 188310 | 53329 | 58351 | 193394 | -8512 | 3490 | 1.159 | 1.06 | 20270731 | 20270731 | 0 | 15 | 5 | 5 | 0 | 0 | 1527 | 1732 | 1777 | 205 | 3 | 0 | 27 | 0 | 400000 | 0 | 440984 | 0 |  | 1 | 3000 | 2 | 91 | 100
834 | 20251130 | 51 | 8 | 6 | 3 | 27 | 3 | 1 | 3 | Active | Deliver | Green | 0.3333 | 0.3561 | 188310 | 59422 | 63350 | 193583 | -7635 | 3707 | 1.129 | 1.059 | 20270731 | 20270731 | 0 | 15 | 5 | 4 | 0 | 0 | 1575 | 1734 | 1835 | 159 | 2 | 0 | 18 | 0 | 400000 | 0 | 428407 | 0 |  | 1 | 3000 | 4 | 92 | 100
835 | 20251231 | 51 | 8 | 6 | 3 | 27 | 3 | 1 | 3 | Active | Deliver | Green | 0.3667 | 0.4066 | 188310 | 65549 | 74283 | 193771 | -11018 | 2284 | 1.168 | 1.031 | 20270731 | 20270731 | 0 | 15 | 6 | 5 | 0 | 0 | 1615 | 1839 | 1938 | 224 | 3 | 0 | 27 | 0 | 400000 | 0 | 432676 | 0 |  | 1 | 3000 | 2 | 87 | 100
836 | 20260131 | 51 | 8 | 6 | 3 | 27 | 3 | 1 | 3 | Active | Deliver | Green | 0.4 | 0.4587 | 188310 | 71708 | 83762 | 193959 | -14670 | 2616 | 1.205 | 1.031 | 20270731 | 20270731 | 0 | 15 | 6 | 5 | 0 | 0 | 1647 | 1756 | 1704 | 109 | 0 | 0 | 0 | 0 | 400000 | 0 | 434117 | 0 |  | 1 | 3000 | 2 | 90 | 100
837 | 20260228 | 51 | 8 | 6 | 3 | 27 | 3 | 1 | 3 | Active | Deliver | Green | 0.4333 | 0.5009 | 188310 | 77902 | 91197 | 194148 | -16422 | 3127 | 1.211 | 1.034 | 20270731 | 20270731 | 0 | 15 | 7 | 7 | 0 | 0 | 1670 | 1822 | 1751 | 152 | 1 | 0 | 9 | 0 | 400000 | 0 | 440468 | 0 |  | 1 | 2000 | 1 | 90 | 100
838 | 20260331 | 51 | 8 | 6 | 3 | 27 | 3 | 1 | 3 | Active | Deliver | Green | 0.4667 | 0.53 | 188310 | 84129 | 97771 | 194336 | -15675 | 2033 | 1.186 | 1.021 | 20270731 | 20270731 | 0 | 15 | 7 | 6 | 0 | 0 | 1684 | 1761 | 1862 | 77 | 2 | 0 | 18 | 0 | 400000 | 0 | 424158 | 0 |  | 1 | 3000 | 3 | 90 | 100
839 | 20260430 | 51 | 8 | 6 | 3 | 27 | 3 | 1 | 3 | Active | Deliver | Green | 0.5 | 0.5857 | 188310 | 90389 | 107189 | 194524 | -19904 | 3104 | 1.22 | 1.029 | 20270731 | 20270731 | 0 | 15 | 8 | 8 | 0 | 0 | 1688 | 1746 | 1741 | 58 | 1 | 0 | 9 | 0 | 400000 | 0 | 435572 | 0 |  | 1 | 2000 | 2 | 95 | 100
840 | 20260531 | 51 | 8 | 6 | 3 | 27 | 3 | 1 | 3 | Active | Deliver | Green | 0.5333 | 0.597 | 188310 | 96683 | 108705 | 194713 | -15738 | 3716 | 1.163 | 1.034 | 20270731 | 20270731 | 0 | 15 | 8 | 7 | 0 | 0 | 1684 | 1801 | 1746 | 117 | 0 | 0 | 0 | 0 | 400000 | 0 | 436722 | 0 |  | 1 | 2000 | 2 | 89 | 100
841 | 20260630 | 51 | 8 | 6 | 3 | 27 | 3 | 1 | 3 | Active | Deliver | Green | 0.5667 | 0.6342 | 188310 | 103010 | 116933 | 194901 | -16416 | 2493 | 1.159 | 1.021 | 20270731 | 20270731 | 0 | 15 | 9 | 9 | 0 | 0 | 1670 | 1764 | 1743 | 94 | 1 | 0 | 9 | 0 | 400000 | 0 | 433557 | 0 |  | 1 | 3000 | 3 | 87 | 100
842 | 20260731 | 51 | 8 | 6 | 3 | 27 | 3 | 1 | 3 | Active | Deliver | Green | 0.6 | 0.6462 | 188310 | 109370 | 121109 | 195089 | -12316 | 577 | 1.113 | 1.005 | 20270731 | 20270731 | 0 | 15 | 9 | 8 | 0 | 0 | 1647 | 1800 | 1711 | 153 | 2 | 0 | 18 | 0 | 400000 | 0 | 437817 | 0 |  | 1 | 2000 | 4 | 85 | 100
843 | 20260831 | 51 | 8 | 6 | 3 | 27 | 3 | 1 | 3 | Active | Deliver | Green | 0.6333 | 0.694 | 188310 | 115765 | 130307 | 195277 | -14922 | 380 | 1.129 | 1.003 | 20270731 | 20270731 | 0 | 15 | 10 | 9 | 0 | 0 | 1615 | 1765 | 1729 | 150 | 0 | 0 | 0 | 0 | 400000 | 0 | 428883 | 0 |  | 1 | 2000 | 2 | 84 | 100
844 | 20260930 | 51 | 8 | 6 | 3 | 27 | 3 | 1 | 3 | Active | Deliver | Green | 0.6667 | 0.732 | 188310 | 122192 | 137732 | 195466 | -15651 | 111 | 1.128 | 1.001 | 20270731 | 20270731 | 0 | 15 | 10 | 10 | 0 | 0 | 1575 | 1638 | 1545 | 63 | 1 | 0 | 9 | 0 | 400000 | 0 | 434731 | 0 |  | 1 | 3000 | 2 | 85 | 100
845 | 20231031 | 52 | 2 | 4 | 4 | 28 | 4 | 3 | 4 | Active | Deliver | Green | 0.4667 | 0.3508 | 1750409 | 782005 | 592444 | 1843764 | 167962 | 21599 | 0.785 | 1.036 | 20240630 | 20240831 | 67 | 8 | 4 | 1 | 2 | 1 | 15650 | 12536 | 12016 | -3114 | 8 | 1 | 113 | 2 | 3700000 | 0 | 3397614 | 0 |  | 1 | 24000 | 9 | 69 | 76.9
846 | 20231130 | 52 | 2 | 4 | 4 | 28 | 4 | 3 | 4 | Active | Deliver | Green | 0.5333 | 0.4152 | 1750409 | 898699 | 728644 | 1850550 | 171929 | -1874 | 0.809 | 0.998 | 20240630 | 20240831 | 68 | 8 | 4 | 2 | 1 | 0 | 15650 | 12601 | 12358 | -3049 | 8 | 1 | 113 | 2 | 3700000 | 0 | 3408019 | 0 |  | 1 | 22000 | 9 | 70 | 76.8
847 | 20231231 | 52 | 2 | 4 | 4 | 28 | 4 | 3 | 4 | Active | Deliver | Green | 0.6 | 0.4729 | 1750409 | 1016638 | 823422 | 1855434 | 188870 | 4346 | 0.814 | 1.005 | 20240630 | 20240831 | 73 | 8 | 5 | 3 | 2 | 1 | 15309 | 11544 | 12137 | -3765 | 7 | 1 | 101 | 2 | 3700000 | 0 | 3550010 | 0 |  | 1 | 26000 | 7 | 67 | 77.3
848 | 20240131 | 52 | 2 | 4 | 4 | 28 | 4 | 3 | 4 | Active | Deliver | Green | 0.6667 | 0.5444 | 1750409 | 1135821 | 976497 | 1870532 | 182898 | -23574 | 0.839 | 0.976 | 20240630 | 20240831 | 71 | 8 | 5 | 4 | 1 | 0 | 14642 | 10963 | 11616 | -3679 | 8 | 1 | 113 | 2 | 3700000 | 0 | 3502272 | 0 |  | 1 | 28000 | 9 | 70 | 76.9
849 | 20240229 | 52 | 2 | 4 | 4 | 28 | 4 | 3 | 4 | Active | Deliver | Green | 0.7333 | 0.6055 | 1750409 | 1256249 | 1097838 | 1880448 | 196376 | -37965 | 0.844 | 0.965 | 20240630 | 20240930 | 75 | 8 | 6 | 3 | 2 | 1 | 13678 | 11420 | 11936 | -2258 | 8 | 1 | 113 | 2 | 3700000 | 176190 | 3470970 | 0 | 0 | 1 | 25000 | 9 | 67 | 78.4
850 | 20240331 | 52 | 2 | 4 | 4 | 28 | 4 | 3 | 4 | Active | Deliver | Green | 0.8 | 0.686 | 1750409 | 1377922 | 1235781 | 1883865 | 177141 | -35000 | 0.871 | 0.972 | 20240630 | 20240831 | 66 | 8 | 6 | 3 | 2 | 1 | 12459 | 10383 | 10006 | -2076 | 7 | 1 | 101 | 2 | 3700000 | 1057143 | 3566622 | 236934 | 0.2241 | 1 | 21000 | 7 | 68 | 80.5
851 | 20240430 | 52 | 2 | 4 | 4 | 28 | 4 | 3 | 4 | Active | Deploy | Green | 0.8667 | 0.7565 | 1750409 | 1500840 | 1392574 | 1897667 | 176656 | -68390 | 0.882 | 0.951 | 20240630 | 20240831 | 64 | 8 | 7 | 4 | 2 | 1 | 11038 | 8767 | 9220 | -2271 | 4 | 0 | 47 | 1 | 3700000 | 1938095 | 3498586 | 896660 | 0.4627 | 1 | 20000 | 6 | 77 | 86.9
852 | 20240531 | 52 | 2 | 4 | 4 | 28 | 4 | 3 | 4 | Active | Deploy | Green | 0.9333 | 0.8249 | 1750409 | 1625002 | 1537448 | 1908029 | 181090 | -93536 | 0.889 | 0.939 | 20240630 | 20240831 | 63 | 8 | 7 | 5 | 2 | 1 | 9478 | 7113 | 7082 | -2365 | 4 | 0 | 47 | 1 | 3700000 | 2819048 | 3437207 | 1677395 | 0.595 | 1 | 16000 | 5 | 78 | 85.4
853 | 20240630 | 52 | 2 | 4 | 4 | 28 | 4 | 3 | 4 | Active | Deploy | Green | 1 | 0.8761 | 1750409 | 1750409 | 1650878 | 1917812 | 216876 | -117345 | 0.876 | 0.929 | 20240630 | 20240831 | 72 | 8 | 8 | 6 | 2 | 1 | 7847 | 6054 | 6260 | -1793 | 4 | 1 | 65 | 1 | 3700000 | 3700000 | 3567736 | 2442067 | 0.66 | 1 | 21000 | 6 | 70 | 77.9
854 | 20240731 | 52 | 2 | 4 | 4 | 28 | 4 | 3 | 4 | Active | Deploy | Green | 1 | 0.8761 | 1750409 | 1750409 | 1650878 | 1923646 | 216876 | -117345 | 0.876 | 0.929 | 20240630 | 20240831 | 72 | 8 | 8 | 5 | 2 | 1 | 7847 | 5892 | 5690 | -1955 | 6 | 1 | 89 | 2 | 3700000 | 3700000 | 3435929 | 3015220 | 0.8149 | 1 | 15000 | 5 | 69 | 76.5
855 | 20240831 | 52 | 2 | 4 | 4 | 28 | 4 | 3 | 4 | Active | Deploy | Green | 1 | 0.8761 | 1750409 | 1750409 | 1665964 | 1932720 | 216876 | -132431 | 0.876 | 0.921 | 20240630 | 20240831 | 72 | 8 | 8 | 5 | 2 | 1 | 7847 | 6286 | 6193 | -1561 | 4 | 0 | 47 | 1 | 3700000 | 3700000 | 3448879 | 3252116 | 0.879 | 2 | 49000 | 5 | 72 | 85.4
856 | 20240930 | 52 | 2 | 4 | 4 | 28 | 4 | 3 | 4 | Active | Deploy | Green | 1 | 0.8761 | 1750409 | 1750409 | 1692943 | 1944204 | 216876 | -159410 | 0.876 | 0.906 | 20240630 | 20240831 | 72 | 8 | 8 | 6 | 2 | 1 | 7847 | 6186 | 6595 | -1661 | 5 | 1 | 77 | 1 | 3700000 | 3700000 | 3505573 | 3130179 | 0.846 | 2 | 46000 | 5 | 66 | 77
857 | 20241031 | 52 | 2 | 4 | 4 | 28 | 4 | 3 | 4 | Active | Deploy | Green | 1 | 0.8761 | 1750409 | 1750409 | 1728323 | 1957179 | 216876 | -194790 | 0.876 | 0.887 | 20240630 | 20240831 | 72 | 8 | 8 | 5 | 2 | 1 | 7847 | 6229 | 6062 | -1618 | 3 | 1 | 54 | 1 | 3700000 | 3700000 | 3568223 | 3292195 | 0.8898 | 2 | 53000 | 7 | 66 | 76.9
858 | 20241130 | 52 | 2 | 4 | 4 | 28 | 4 | 3 | 4 | Active | Deploy | Green | 1 | 0.8761 | 1750409 | 1750409 | 1739608 | 1965231 | 216876 | -206075 | 0.876 | 0.882 | 20240630 | 20240831 | 72 | 8 | 8 | 6 | 2 | 1 | 7847 | 6151 | 6250 | -1696 | 5 | 1 | 77 | 1 | 3700000 | 3700000 | 3482732 | 3203938 | 0.8659 | 2 | 42000 | 7 | 66 | 75.9
859 | 20241231 | 52 | 2 | 4 | 4 | 28 | 4 | 3 | 4 | Active | Deploy | Green | 1 | 0.882 | 1750409 | 1750409 | 1750889 | 1966602 | 206548 | -207028 | 0.882 | 0.882 | 20240630 | 20240831 | 68 | 8 | 8 | 5 | 2 | 1 | 7847 | 6283 | 6603 | -1564 | 5 | 1 | 77 | 1 | 3700000 | 3700000 | 3388603 | 3185132 | 0.8608 | 2 | 28000 | 5 | 66 | 75.8
860 | 20250131 | 52 | 2 | 4 | 4 | 28 | 4 | 3 | 4 | Active | Deploy | Green | 1 | 0.882 | 1750409 | 1750409 | 1761148 | 1968580 | 206548 | -217287 | 0.882 | 0.877 | 20240630 | 20240831 | 68 | 8 | 8 | 6 | 2 | 1 | 7847 | 5807 | 5879 | -2040 | 5 | 1 | 77 | 1 | 3700000 | 3700000 | 3511219 | 3186369 | 0.8612 | 3 | 82000 | 7 | 70 | 75.2
861 | 20250228 | 52 | 2 | 4 | 4 | 28 | 4 | 3 | 4 | Active | Deploy | Green | 1 | 0.882 | 1750409 | 1750409 | 1761148 | 1968580 | 206548 | -217287 | 0.882 | 0.877 | 20240630 | 20240831 | 68 | 8 | 8 | 5 | 2 | 1 | 7847 | 6518 | 6811 | -1329 | 5 | 0 | 59 | 1 | 3700000 | 3700000 | 3511172 | 3370082 | 0.9108 | 3 | 62000 | 4 | 72 | 85.2
862 | 20250331 | 52 | 2 | 4 | 4 | 28 | 4 | 3 | 4 | Active | Deploy | Green | 1 | 0.882 | 1750409 | 1750409 | 1761148 | 1968580 | 206548 | -217287 | 0.882 | 0.877 | 20240630 | 20240831 | 68 | 8 | 8 | 6 | 2 | 1 | 7847 | 6351 | 6042 | -1496 | 4 | 1 | 65 | 1 | 3700000 | 3700000 | 3436203 | 3171333 | 0.8571 | 3 | 52000 | 6 | 65 | 76.2
863 | 20250430 | 52 | 2 | 4 | 4 | 28 | 4 | 3 | 4 | Active | Deploy | Green | 1 | 0.882 | 1750409 | 1750409 | 1762717 | 1968881 | 206548 | -218856 | 0.882 | 0.876 | 20240630 | 20240831 | 68 | 8 | 8 | 6 | 2 | 1 | 7847 | 5970 | 6065 | -1877 | 3 | 0 | 36 | 1 | 3700000 | 3700000 | 3530303 | 3340443 | 0.9028 | 3 | 53000 | 7 | 71 | 83.8
864 | 20240331 | 53 | 8 | 6 | 5 | 29 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.0476 | 0.0071 | 406078 | 17864 | 947 | 424487 | 14981 | 1936 | 0.16 | 3.025 | 20251130 | 20251231 | 34 | 11 | 1 | 0 | 1 | 0 | 2092 | 1830 | 1853 | -262 | 11 | 1 | 152 | 3 | 900000 | 0 | 882141 | 0 |  | 0 | 0 | 4 | 96 | 100
865 | 20240430 | 53 | 8 | 6 | 5 | 29 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.0952 | 0.0766 | 406078 | 35875 | 28429 | 425840 | 4769 | 2677 | 0.867 | 1.094 | 20251130 | 20251231 | 16 | 11 | 1 | 1 | 0 | 0 | 2357 | 2177 | 2210 | -180 | 6 | 1 | 91 | 2 | 900000 | 0 | 876482 | 0 |  | 0 | 0 | 5 | 78 | 86.9
866 | 20240531 | 53 | 8 | 6 | 5 | 29 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.1429 | 0.1111 | 406078 | 54033 | 41181 | 427194 | 8918 | 3934 | 0.835 | 1.095 | 20251130 | 20251231 | 26 | 11 | 2 | 1 | 1 | 0 | 2610 | 2356 | 2354 | -254 | 7 | 1 | 103 | 2 | 900000 | 0 | 871851 | 0 |  | 1 | 4000 | 4 | 75 | 84.9
867 | 20240630 | 53 | 8 | 6 | 5 | 29 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.1905 | 0.158 | 406078 | 72339 | 57816 | 428548 | 8179 | 6344 | 0.887 | 1.11 | 20251130 | 20251231 | 26 | 11 | 2 | 1 | 0 | 0 | 2846 | 2635 | 2636 | -211 | 6 | 1 | 91 | 2 | 900000 | 0 | 863761 | 0 |  | 1 | 6000 | 6 | 75 | 88
868 | 20240731 | 53 | 8 | 6 | 5 | 29 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.2381 | 0.1893 | 406078 | 90792 | 72809 | 429901 | 13921 | 4062 | 0.847 | 1.056 | 20251130 | 20251231 | 41 | 11 | 3 | 1 | 1 | 0 | 3059 | 2748 | 2891 | -311 | 8 | 1 | 115 | 2 | 900000 | 0 | 843144 | 0 |  | 1 | 6000 | 5 | 71 | 83.1
869 | 20240831 | 53 | 8 | 6 | 5 | 29 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.2857 | 0.2153 | 406078 | 109392 | 86033 | 431255 | 21963 | 1396 | 0.799 | 1.016 | 20251130 | 20260131 | 58 | 11 | 3 | 2 | 1 | 0 | 3244 | 3026 | 2889 | -218 | 6 | 1 | 91 | 2 | 900000 | 0 | 865931 | 0 |  | 1 | 4000 | 4 | 72 | 81
870 | 20240930 | 53 | 8 | 6 | 5 | 29 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.3333 | 0.2471 | 406078 | 128140 | 95883 | 432608 | 27798 | 4459 | 0.783 | 1.047 | 20251130 | 20260131 | 71 | 11 | 4 | 2 | 2 | 1 | 3397 | 3217 | 3288 | -180 | 8 | 1 | 115 | 2 | 900000 | 0 | 884685 | 0 |  | 1 | 4000 | 5 | 71 | 82.2
871 | 20241031 | 53 | 8 | 6 | 5 | 29 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.381 | 0.2953 | 406078 | 147035 | 115738 | 433962 | 27120 | 4177 | 0.815 | 1.036 | 20251130 | 20260131 | 71 | 11 | 4 | 3 | 1 | 0 | 3515 | 3399 | 3282 | -116 | 6 | 1 | 91 | 2 | 900000 | 0 | 871038 | 0 |  | 1 | 4000 | 4 | 67 | 83.3
872 | 20241130 | 53 | 8 | 6 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.4286 | 0.3579 | 406078 | 166078 | 139786 | 435316 | 20743 | 5549 | 0.875 | 1.04 | 20251130 | 20260131 | 59 | 11 | 5 | 4 | 1 | 0 | 3595 | 3195 | 3023 | -400 | 8 | 1 | 115 | 2 | 900000 | 0 | 851010 | 0 |  | 1 | 4000 | 3 | 73 | 83.8
873 | 20241231 | 53 | 8 | 6 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.4762 | 0.4053 | 406078 | 185267 | 164211 | 436669 | 20684 | 372 | 0.888 | 1.002 | 20251130 | 20260131 | 59 | 11 | 5 | 3 | 1 | 0 | 3636 | 3207 | 3388 | -429 | 8 | 1 | 115 | 2 | 900000 | 0 | 882126 | 0 |  | 1 | 6000 | 5 | 70 | 83.9
874 | 20250131 | 53 | 8 | 6 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.5238 | 0.4527 | 406078 | 204604 | 182026 | 438023 | 20772 | 1806 | 0.899 | 1.01 | 20251130 | 20260131 | 59 | 11 | 6 | 4 | 1 | 0 | 3636 | 3364 | 3504 | -272 | 7 | 1 | 103 | 2 | 900000 | 0 | 870046 | 0 |  | 1 | 5000 | 4 | 75 | 85.2
875 | 20250228 | 53 | 8 | 6 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.5714 | 0.499 | 406078 | 224089 | 206944 | 441243 | 21456 | -4311 | 0.904 | 0.979 | 20251130 | 20260131 | 60 | 11 | 6 | 4 | 1 | 0 | 3595 | 3165 | 3264 | -430 | 8 | 1 | 115 | 2 | 900000 | 0 | 848140 | 0 |  | 1 | 6000 | 7 | 74 | 82.7
876 | 20250331 | 53 | 8 | 6 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.619 | 0.5512 | 406078 | 243720 | 225709 | 441468 | 19890 | -1879 | 0.918 | 0.992 | 20251130 | 20260131 | 56 | 11 | 7 | 5 | 1 | 0 | 3515 | 3041 | 2996 | -474 | 7 | 1 | 103 | 2 | 900000 | 0 | 880074 | 0 |  | 1 | 4000 | 5 | 74 | 84.5
877 | 20250430 | 53 | 8 | 6 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.6667 | 0.5914 | 406078 | 263500 | 246890 | 444519 | 23345 | -6735 | 0.911 | 0.973 | 20251130 | 20251231 | 27 | 11 | 7 | 5 | 1 | 0 | 3397 | 3029 | 3041 | -368 | 7 | 1 | 103 | 2 | 900000 | 0 | 869051 | 0 |  | 1 | 5000 | 3 | 70 | 83.7
878 | 20250531 | 53 | 8 | 6 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.7143 | 0.6364 | 406078 | 283426 | 266765 | 446235 | 24998 | -8337 | 0.912 | 0.969 | 20251130 | 20251231 | 29 | 11 | 8 | 5 | 2 | 1 | 3244 | 3014 | 3090 | -230 | 6 | 1 | 91 | 2 | 900000 | 0 | 866267 | 0 |  | 1 | 5000 | 4 | 75 | 84.3
879 | 20250630 | 53 | 8 | 6 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.7619 | 0.6834 | 406078 | 303500 | 287537 | 447907 | 25986 | -10023 | 0.914 | 0.965 | 20251130 | 20251231 | 29 | 11 | 8 | 6 | 2 | 1 | 3059 | 2643 | 2692 | -416 | 5 | 1 | 79 | 1 | 900000 | 134694 | 855467 | 0 | 0 | 1 | 4000 | 6 | 74 | 82.5
880 | 20250731 | 53 | 8 | 6 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.8095 | 0.7281 | 406078 | 323721 | 309456 | 450121 | 28056 | -13791 | 0.913 | 0.955 | 20251130 | 20251231 | 32 | 11 | 9 | 6 | 2 | 1 | 2846 | 2544 | 2561 | -302 | 5 | 1 | 79 | 1 | 900000 | 287755 | 864188 | 78306 | 0.2721 | 1 | 4000 | 1 | 68 | 83.1
881 | 20250831 | 53 | 8 | 6 | 5 | 29 | 5 | 2 | 5 | Active | Deploy | Green | 0.8571 | 0.7975 | 406078 | 344089 | 342019 | 452243 | 20242 | -18172 | 0.941 | 0.947 | 20251130 | 20251231 | 15 | 11 | 9 | 7 | 1 | 0 | 2610 | 2245 | 2121 | -365 | 5 | 0 | 61 | 1 | 900000 | 440816 | 871216 | 197958 | 0.4491 | 1 | 5000 | 3 | 78 | 91.5
882 | 20250930 | 53 | 8 | 6 | 5 | 29 | 5 | 2 | 5 | Active | Deploy | Green | 0.9048 | 0.8686 | 406078 | 364605 | 377081 | 454622 | 11886 | -24362 | 0.967 | 0.935 | 20251130 | 20251130 | -5 | 11 | 10 | 9 | 1 | 0 | 2357 | 2079 | 2217 | -278 | 3 | 1 | 54 | 1 | 900000 | 593878 | 852858 | 318968 | 0.5371 | 1 | 4000 | 3 | 72 | 84.2
883 | 20251031 | 53 | 8 | 6 | 5 | 29 | 5 | 2 | 5 | Active | Deploy | Green | 0.9524 | 0.9394 | 406078 | 385268 | 412192 | 456864 | 3798 | -30722 | 0.99 | 0.925 | 20251130 | 20251130 | -25 | 11 | 10 | 8 | 1 | 0 | 2092 | 1835 | 1879 | -257 | 4 | 0 | 49 | 1 | 900000 | 746939 | 851625 | 444241 | 0.5947 | 1 | 6000 | 3 | 75 | 92.7
884 | 20251130 | 53 | 8 | 6 | 5 | 29 | 5 | 2 | 5 | Completed | Completed | Green | 1 | 1 | 406078 | 406078 | 441538 | 458733 | 0 | -35460 | 1 | 0.92 | 20251130 | 20251130 | -35 | 11 | 11 | 9 | 1 | 0 | 1820 | 1762 | 1858 | -58 | 5 | 1 | 79 | 1 | 900000 | 900000 | 842386 | 609825 | 0.6776 | 1 | 4000 | 3 | 74 | 86.7
885 | 20231031 | 54 | 10 | 7 | 6 | 30 | 6 | 2 | 6 | Active | Initiate & Design | Green | 0.1111 | 0.1189 | 615332 | 63508 | 62518 | 628459 | -9655 | 10645 | 1.152 | 1.17 | 20240630 | 20240630 | 0 | 6 | 1 | 1 | 0 | 0 | 3702 | 3522 | 3331 | -180 | 2 | 0 | 20 | 0 | 1400000 | 0 | 1041037 | 0 |  | 0 | 0 | 3 | 88 | 100
886 | 20231130 | 54 | 10 | 7 | 6 | 30 | 6 | 2 | 6 | Active | Initiate & Design | Green | 0.2222 | 0.2568 | 615332 | 128232 | 149869 | 630510 | -29785 | 8148 | 1.232 | 1.055 | 20240630 | 20240630 | 0 | 6 | 1 | 1 | 0 | 0 | 4531 | 4559 | 4748 | 28 | 3 | 0 | 31 | 1 | 1400000 | 0 | 1031438 | 0 |  | 0 | 0 | 3 | 87 | 100
887 | 20231231 | 54 | 10 | 7 | 6 | 30 | 6 | 2 | 6 | Active | Deliver | Green | 0.3333 | 0.3569 | 615332 | 194171 | 210086 | 632561 | -25441 | 9526 | 1.131 | 1.045 | 20240630 | 20240630 | 0 | 6 | 2 | 2 | 0 | 0 | 5147 | 5292 | 5082 | 145 | 3 | 0 | 31 | 1 | 1400000 | 0 | 1032579 | 0 |  | 0 | 0 | 3 | 83 | 100
888 | 20240131 | 54 | 10 | 7 | 6 | 30 | 6 | 2 | 6 | Active | Deliver | Green | 0.4444 | 0.4527 | 615332 | 261326 | 271666 | 634612 | -17235 | 6895 | 1.066 | 1.025 | 20240630 | 20240630 | 0 | 6 | 3 | 3 | 0 | 0 | 5475 | 5463 | 5338 | -12 | 3 | 0 | 31 | 1 | 1400000 | 0 | 1018182 | 0 |  | 0 | 0 | 2 | 78 | 96.2
889 | 20240229 | 54 | 10 | 7 | 6 | 30 | 6 | 2 | 6 | Active | Deliver | Green | 0.5556 | 0.5549 | 615332 | 329696 | 337200 | 636664 | -11752 | 4248 | 1.036 | 1.013 | 20240630 | 20240630 | 0 | 6 | 3 | 2 | 0 | 0 | 5475 | 5305 | 5561 | -170 | 2 | 1 | 38 | 0 | 1400000 | 0 | 1078628 | 0 |  | 1 | 8000 | 1 | 72 | 86.9
890 | 20240331 | 54 | 10 | 7 | 6 | 30 | 6 | 2 | 6 | Active | Deliver | Green | 0.6667 | 0.6595 | 615332 | 399282 | 401051 | 638715 | -6529 | 4760 | 1.016 | 1.012 | 20240630 | 20240630 | 2 | 6 | 4 | 3 | 0 | 0 | 5147 | 5476 | 5858 | 329 | 2 | 0 | 20 | 0 | 1400000 | 0 | 1015037 | 0 |  | 1 | 8000 | 3 | 72 | 93.4
891 | 20240430 | 54 | 10 | 7 | 6 | 30 | 6 | 2 | 6 | Active | Deploy | Green | 0.7778 | 0.7635 | 615332 | 470083 | 478744 | 643297 | 277 | -8938 | 0.999 | 0.981 | 20240630 | 20240630 | 5 | 6 | 5 | 4 | 0 | 0 | 4531 | 4785 | 5118 | 254 | 5 | 0 | 51 | 1 | 1400000 | 288889 | 1026526 | 0 | 0 | 1 | 9000 | 5 | 72 | 91.8
892 | 20240531 | 54 | 10 | 7 | 6 | 30 | 6 | 2 | 6 | Active | Deploy | Green | 0.8889 | 0.8861 | 615332 | 542100 | 564100 | 647339 | -3146 | -18854 | 1.006 | 0.967 | 20240630 | 20240630 | 1 | 6 | 5 | 5 | 0 | 0 | 3702 | 3669 | 3701 | -33 | 0 | 0 | 0 | 0 | 1400000 | 844444 | 1060536 | 383229 | 0.4538 | 1 | 9000 | 2 | 75 | 92.1
893 | 20240630 | 54 | 10 | 7 | 6 | 30 | 6 | 2 | 6 | Completed | Completed | Green | 1 | 1 | 615332 | 615332 | 644157 | 650926 | 0 | -28825 | 1 | 0.955 | 20240630 | 20240630 | 0 | 6 | 6 | 6 | 0 | 0 | 2758 | 2747 | 2608 | -11 | 2 | 0 | 20 | 0 | 1400000 | 1400000 | 1023690 | 670625 | 0.479 | 1 | 8000 | 0 | 72 | 90.8
894 | 20231031 | 55 | 4 | 3 | 7 | 31 | 7 | 3 | 7 | Active | Deliver | Red | 0.8889 | 0.6282 | 781114 | 688152 | 584873 | 1041391 | 197456 | -94177 | 0.713 | 0.839 | 20231130 | 20240229 | 103 | 6 | 5 | 1 | 3 | 2 | 4699 | 3657 | 3721 | -1042 | 10 | 3 | 196 | 3 | 2200000 | 1326984 | 1491795 | 535608 | 0.4036 | 3 | 29000 | 4 | 39 | 43.6
895 | 20231130 | 55 | 4 | 3 | 7 | 31 | 7 | 3 | 7 | Active | Deliver | Amber | 1 | 0.7212 | 781114 | 781114 | 685138 | 1061613 | 217775 | -121799 | 0.721 | 0.822 | 20231130 | 20240331 | 110 | 6 | 6 | 2 | 3 | 2 | 3502 | 2855 | 2901 | -647 | 9 | 2 | 164 | 3 | 2200000 | 2200000 | 1536378 | 1055497 | 0.4798 | 3 | 37000 | 5 | 46 | 52.7
896 | 20231231 | 55 | 4 | 3 | 7 | 31 | 7 | 3 | 7 | Active | Deliver | Amber | 1 | 0.7212 | 781114 | 781114 | 707393 | 1083417 | 217775 | -144054 | 0.721 | 0.796 | 20231130 | 20240331 | 110 | 6 | 6 | 2 | 3 | 2 | 3502 | 2894 | 2952 | -608 | 8 | 2 | 150 | 3 | 2200000 | 2200000 | 1536204 | 1379459 | 0.627 | 4 | 39000 | 2 | 41 | 52.1
897 | 20240131 | 55 | 4 | 3 | 7 | 31 | 7 | 3 | 7 | Active | Deliver | Amber | 1 | 0.7212 | 781114 | 781114 | 729058 | 1104842 | 217775 | -165719 | 0.721 | 0.773 | 20231130 | 20240331 | 110 | 6 | 6 | 3 | 3 | 2 | 3502 | 2840 | 2748 | -662 | 7 | 1 | 118 | 2 | 2200000 | 2200000 | 1591764 | 1513410 | 0.6879 | 4 | 43000 | 5 | 46 | 59.6
898 | 20240229 | 55 | 4 | 3 | 7 | 31 | 7 | 3 | 7 | Active | Deliver | Amber | 1 | 0.7212 | 781114 | 781114 | 750635 | 1126017 | 217775 | -187296 | 0.721 | 0.751 | 20231130 | 20240331 | 110 | 6 | 6 | 3 | 3 | 2 | 3502 | 2885 | 2752 | -617 | 9 | 2 | 164 | 3 | 2200000 | 2200000 | 1515179 | 1448200 | 0.6583 | 4 | 26000 | 5 | 40 | 50.1
899 | 20240331 | 55 | 4 | 3 | 7 | 31 | 7 | 3 | 7 | Active | Deliver | Amber | 1 | 0.7212 | 781114 | 781114 | 757281 | 1129752 | 217775 | -193942 | 0.721 | 0.744 | 20231130 | 20240331 | 110 | 6 | 6 | 2 | 3 | 2 | 3502 | 2789 | 2960 | -713 | 8 | 1 | 132 | 3 | 2200000 | 2200000 | 1561532 | 1391935 | 0.6327 | 4 | 42000 | 5 | 43 | 57.9
900 | 20240430 | 55 | 4 | 3 | 7 | 31 | 7 | 3 | 7 | Active | Deliver | Amber | 1 | 0.7212 | 781114 | 781114 | 758443 | 1129948 | 217775 | -195104 | 0.721 | 0.743 | 20231130 | 20240331 | 110 | 6 | 6 | 3 | 3 | 2 | 3502 | 2939 | 3137 | -563 | 9 | 2 | 164 | 3 | 2200000 | 2200000 | 1574542 | 1444064 | 0.6564 | 4 | 38000 | 3 | 39 | 51
901 | 20240531 | 55 | 4 | 3 | 7 | 31 | 7 | 3 | 7 | Active | Deliver | Amber | 1 | 0.7212 | 781114 | 781114 | 758443 | 1129948 | 217775 | -195104 | 0.721 | 0.743 | 20231130 | 20240331 | 110 | 6 | 6 | 2 | 3 | 2 | 3502 | 2855 | 2989 | -647 | 10 | 2 | 178 | 3 | 2200000 | 2200000 | 1586200 | 1516959 | 0.6895 | 4 | 25000 | 5 | 38 | 50.6
902 | 20240630 | 55 | 4 | 3 | 7 | 31 | 7 | 3 | 7 | Active | Deliver | Amber | 1 | 0.7212 | 781114 | 781114 | 758926 | 1130029 | 217775 | -195587 | 0.721 | 0.742 | 20231130 | 20240331 | 110 | 6 | 6 | 2 | 3 | 2 | 3502 | 2893 | 2878 | -609 | 7 | 1 | 118 | 2 | 2200000 | 2200000 | 1500975 | 1448116 | 0.6582 | 4 | 33000 | 4 | 44 | 57.7
903 | 20240731 | 55 | 4 | 3 | 7 | 31 | 7 | 3 | 7 | Active | Deliver | Amber | 1 | 0.7212 | 781114 | 781114 | 758926 | 1130029 | 217775 | -195587 | 0.721 | 0.742 | 20231130 | 20240331 | 110 | 6 | 6 | 2 | 3 | 2 | 3502 | 2754 | 2869 | -748 | 8 | 2 | 150 | 3 | 2200000 | 2200000 | 1574480 | 1452472 | 0.6602 | 4 | 36000 | 6 | 43 | 49.8
904 | 20240831 | 55 | 4 | 3 | 7 | 31 | 7 | 3 | 7 | Active | Deliver | Amber | 1 | 0.7212 | 781114 | 781114 | 758926 | 1130029 | 217775 | -195587 | 0.721 | 0.742 | 20231130 | 20240331 | 110 | 6 | 6 | 2 | 3 | 2 | 3502 | 3037 | 2991 | -465 | 10 | 2 | 178 | 3 | 2200000 | 2200000 | 1551753 | 1387124 | 0.6305 | 4 | 27000 | 2 | 39 | 51.3
905 | 20240930 | 55 | 4 | 3 | 7 | 31 | 7 | 3 | 7 | Active | Deliver | Amber | 1 | 0.7212 | 781114 | 781114 | 759380 | 1130106 | 217775 | -196041 | 0.721 | 0.742 | 20231130 | 20240331 | 110 | 6 | 6 | 2 | 3 | 2 | 3502 | 2695 | 2568 | -807 | 9 | 2 | 164 | 3 | 2200000 | 2200000 | 1495222 | 1483979 | 0.6745 | 4 | 27000 | 5 | 45 | 48.4
906 | 20231031 | 56 | 5 | 5 | 8 | 32 | 8 | 3 | 8 | Active | Initiate & Design | Green | 0.2857 | 0.2368 | 647994 | 174562 | 144338 | 705388 | 21117 | 9107 | 0.879 | 1.063 | 20250131 | 20250228 | 42 | 11 | 3 | 2 | 1 | 0 | 5176 | 5168 | 4923 | -8 | 8 | 1 | 119 | 2 | 800000 | 0 | 700178 | 0 |  | 0 | 0 | 3 | 74 | 85.2
907 | 20231130 | 56 | 5 | 5 | 8 | 32 | 8 | 3 | 8 | Active | Initiate & Design | Green | 0.3333 | 0.313 | 647994 | 204478 | 196217 | 708473 | 1656 | 6605 | 0.992 | 1.034 | 20250131 | 20250228 | 18 | 11 | 4 | 3 | 0 | 0 | 5420 | 4853 | 4745 | -567 | 8 | 1 | 119 | 2 | 800000 | 0 | 700202 | 0 |  | 0 | 0 | 7 | 78 | 87
908 | 20231231 | 56 | 5 | 5 | 8 | 32 | 8 | 3 | 8 | Active | Initiate & Design | Green | 0.381 | 0.3479 | 647994 | 234630 | 221787 | 711559 | 9193 | 3650 | 0.961 | 1.017 | 20250131 | 20250228 | 28 | 11 | 4 | 3 | 1 | 0 | 5609 | 5160 | 4864 | -449 | 7 | 1 | 106 | 2 | 800000 | 0 | 700570 | 0 |  | 1 | 8000 | 6 | 72 | 85.6
909 | 20240131 | 56 | 5 | 5 | 8 | 32 | 8 | 3 | 8 | Active | Deliver | Green | 0.4286 | 0.4166 | 647994 | 265016 | 265811 | 714645 | -4938 | 4143 | 1.019 | 1.016 | 20250131 | 20250131 | 11 | 11 | 5 | 5 | 0 | 0 | 5737 | 5149 | 4876 | -588 | 7 | 1 | 106 | 2 | 800000 | 0 | 702157 | 0 |  | 1 | 6000 | 7 | 77 | 87.7
910 | 20240229 | 56 | 5 | 5 | 8 | 32 | 8 | 3 | 8 | Active | Deliver | Green | 0.4762 | 0.4477 | 647994 | 295638 | 290980 | 718152 | 5531 | -873 | 0.981 | 0.997 | 20250131 | 20250228 | 24 | 11 | 5 | 5 | 0 | 0 | 5801 | 5279 | 5370 | -522 | 7 | 1 | 106 | 2 | 800000 | 0 | 707281 | 0 |  | 1 | 7000 | 3 | 78 | 85.8
911 | 20240331 | 56 | 5 | 5 | 8 | 32 | 8 | 3 | 8 | Active | Deliver | Green | 0.5238 | 0.4951 | 647994 | 326495 | 327508 | 723738 | 5673 | -6686 | 0.983 | 0.98 | 20250131 | 20250228 | 24 | 11 | 6 | 4 | 1 | 0 | 5801 | 5515 | 5803 | -286 | 8 | 2 | 137 | 2 | 800000 | 0 | 718381 | 0 |  | 2 | 20000 | 5 | 67 | 78.6
912 | 20240430 | 56 | 5 | 5 | 8 | 32 | 8 | 3 | 8 | Active | Deliver | Green | 0.5714 | 0.5165 | 647994 | 357587 | 341087 | 726575 | 22898 | -6398 | 0.936 | 0.981 | 20250131 | 20250331 | 47 | 11 | 6 | 5 | 1 | 0 | 5737 | 5401 | 5561 | -336 | 7 | 1 | 106 | 2 | 800000 | 0 | 707299 | 0 |  | 2 | 20000 | 5 | 72 | 83.9
913 | 20240531 | 56 | 5 | 5 | 8 | 32 | 8 | 3 | 8 | Active | Deliver | Green | 0.619 | 0.5473 | 647994 | 388914 | 366239 | 731496 | 34267 | -11592 | 0.912 | 0.968 | 20250131 | 20250331 | 61 | 11 | 7 | 6 | 1 | 0 | 5609 | 5594 | 5368 | -15 | 8 | 1 | 119 | 2 | 800000 | 0 | 719000 | 0 |  | 2 | 15000 | 3 | 72 | 84
914 | 20240630 | 56 | 5 | 5 | 8 | 32 | 8 | 3 | 8 | Active | Deliver | Green | 0.6667 | 0.5905 | 647994 | 420476 | 404751 | 737871 | 37836 | -22111 | 0.91 | 0.945 | 20250131 | 20250331 | 65 | 11 | 7 | 5 | 1 | 0 | 5420 | 5068 | 4871 | -352 | 8 | 2 | 137 | 2 | 800000 | 0 | 723208 | 0 |  | 2 | 19000 | 5 | 68 | 73.9
915 | 20240731 | 56 | 5 | 5 | 8 | 32 | 8 | 3 | 8 | Active | Deliver | Green | 0.7143 | 0.6513 | 647994 | 452273 | 444557 | 740386 | 30235 | -22519 | 0.933 | 0.949 | 20250131 | 20250331 | 54 | 11 | 8 | 7 | 1 | 0 | 5176 | 4792 | 4530 | -384 | 8 | 2 | 137 | 2 | 800000 | 0 | 738619 | 0 |  | 2 | 17000 | 4 | 65 | 75.4
916 | 20240831 | 56 | 5 | 5 | 8 | 32 | 8 | 3 | 8 | Active | Deliver | Green | 0.7619 | 0.7102 | 647994 | 484306 | 494390 | 746104 | 24101 | -34185 | 0.95 | 0.931 | 20250131 | 20250228 | 44 | 11 | 8 | 6 | 1 | 0 | 4881 | 4457 | 4237 | -424 | 7 | 1 | 106 | 2 | 800000 | 119728 | 720381 | 0 | 0 | 2 | 15000 | 3 | 71 | 82.6
917 | 20240930 | 56 | 5 | 5 | 8 | 32 | 8 | 3 | 8 | Active | Deploy | Green | 0.8095 | 0.7697 | 647994 | 516573 | 539457 | 750078 | 17812 | -40696 | 0.966 | 0.925 | 20250131 | 20250228 | 34 | 11 | 9 | 7 | 1 | 0 | 4541 | 4050 | 4026 | -491 | 6 | 1 | 94 | 2 | 800000 | 255782 | 704809 | 65405 | 0.2557 | 2 | 19000 | 3 | 76 | 82.1
918 | 20241031 | 56 | 5 | 5 | 8 | 32 | 8 | 3 | 8 | Active | Deploy | Green | 0.8571 | 0.8217 | 647994 | 549076 | 582733 | 754718 | 16619 | -50276 | 0.97 | 0.914 | 20250131 | 20250228 | 30 | 11 | 9 | 8 | 1 | 0 | 4165 | 3860 | 3804 | -305 | 6 | 1 | 94 | 2 | 800000 | 391837 | 711277 | 160727 | 0.4102 | 2 | 17000 | 2 | 72 | 82.9
919 | 20241130 | 56 | 5 | 5 | 8 | 32 | 8 | 3 | 8 | Active | Deploy | Green | 0.9048 | 0.8531 | 647994 | 581813 | 605074 | 757817 | 29009 | -52270 | 0.95 | 0.914 | 20250131 | 20250228 | 44 | 11 | 10 | 9 | 1 | 0 | 3761 | 3371 | 3422 | -390 | 6 | 1 | 94 | 2 | 800000 | 527891 | 715932 | 297458 | 0.5635 | 2 | 13000 | 2 | 71 | 81.5
920 | 20241231 | 56 | 5 | 5 | 8 | 32 | 8 | 3 | 8 | Active | Deploy | Green | 0.9524 | 0.8998 | 647994 | 614786 | 647377 | 762751 | 31721 | -64312 | 0.948 | 0.901 | 20250131 | 20250228 | 44 | 11 | 10 | 8 | 1 | 0 | 3338 | 2974 | 2811 | -364 | 5 | 1 | 81 | 1 | 800000 | 663946 | 709859 | 383034 | 0.5769 | 2 | 16000 | 3 | 68 | 80.6
921 | 20250131 | 56 | 5 | 5 | 8 | 32 | 8 | 3 | 8 | Active | Deploy | Green | 1 | 0.9341 | 647994 | 647994 | 674314 | 766264 | 42703 | -69023 | 0.934 | 0.898 | 20250131 | 20250331 | 57 | 11 | 11 | 8 | 2 | 1 | 2905 | 2647 | 2583 | -258 | 5 | 0 | 63 | 1 | 800000 | 800000 | 734196 | 523053 | 0.6538 | 2 | 15000 | 3 | 72 | 89.2
922 | 20250228 | 56 | 5 | 5 | 8 | 32 | 8 | 3 | 8 | Active | Deploy | Green | 1 | 0.9341 | 647994 | 647994 | 682659 | 770914 | 42703 | -77368 | 0.934 | 0.887 | 20250131 | 20250331 | 57 | 11 | 11 | 8 | 2 | 1 | 2905 | 2751 | 2688 | -154 | 6 | 1 | 94 | 2 | 800000 | 800000 | 703444 | 608213 | 0.7603 | 3 | 17000 | 4 | 68 | 80.5
923 | 20250331 | 56 | 5 | 5 | 8 | 32 | 8 | 3 | 8 | Active | Deploy | Green | 1 | 0.9341 | 647994 | 647994 | 695449 | 776324 | 42703 | -90158 | 0.934 | 0.87 | 20250131 | 20250331 | 57 | 11 | 11 | 8 | 2 | 1 | 2905 | 2641 | 2517 | -264 | 5 | 1 | 81 | 1 | 800000 | 800000 | 717080 | 660974 | 0.8262 | 3 | 20000 | 3 | 67 | 79.6
924 | 20250430 | 56 | 5 | 5 | 8 | 32 | 8 | 3 | 8 | Active | Deploy | Green | 1 | 0.9341 | 647994 | 647994 | 695449 | 779410 | 42703 | -90158 | 0.934 | 0.87 | 20250131 | 20250331 | 57 | 11 | 11 | 9 | 2 | 1 | 2905 | 2638 | 2768 | -267 | 5 | 1 | 81 | 1 | 800000 | 800000 | 717571 | 640053 | 0.8001 | 3 | 21000 | 5 | 72 | 79.6
925 | 20250531 | 56 | 5 | 5 | 8 | 32 | 8 | 3 | 8 | Active | Deploy | Green | 1 | 0.9341 | 647994 | 647994 | 702979 | 783825 | 42703 | -97688 | 0.934 | 0.861 | 20250131 | 20250331 | 57 | 11 | 11 | 9 | 2 | 1 | 2905 | 2750 | 2813 | -155 | 7 | 1 | 106 | 2 | 800000 | 800000 | 725286 | 659962 | 0.825 | 3 | 27000 | 2 | 72 | 80.4
926 | 20250630 | 56 | 5 | 5 | 8 | 32 | 8 | 3 | 8 | Active | Deploy | Green | 1 | 0.9341 | 647994 | 647994 | 715279 | 789021 | 42703 | -109988 | 0.934 | 0.846 | 20250131 | 20250331 | 57 | 11 | 11 | 8 | 2 | 1 | 2905 | 2624 | 2553 | -281 | 5 | 1 | 81 | 1 | 800000 | 800000 | 704405 | 691713 | 0.8646 | 3 | 19000 | 1 | 70 | 78.2
927 | 20250731 | 56 | 5 | 5 | 8 | 32 | 8 | 3 | 8 | Active | Deploy | Green | 1 | 0.938 | 647994 | 647994 | 723698 | 793018 | 40176 | -115880 | 0.938 | 0.84 | 20250131 | 20250331 | 53 | 11 | 11 | 8 | 2 | 1 | 2905 | 2811 | 2643 | -94 | 5 | 1 | 81 | 1 | 800000 | 800000 | 700755 | 616890 | 0.7711 | 3 | 23000 | 5 | 69 | 79.4
928 | 20250831 | 56 | 5 | 5 | 8 | 32 | 8 | 3 | 8 | Active | Deploy | Green | 1 | 0.938 | 647994 | 647994 | 731321 | 797352 | 40176 | -123503 | 0.938 | 0.831 | 20250131 | 20250331 | 53 | 11 | 11 | 9 | 2 | 1 | 2905 | 2803 | 2949 | -102 | 4 | 1 | 69 | 1 | 800000 | 800000 | 719091 | 641766 | 0.8022 | 3 | 29000 | 4 | 69 | 79.7
929 | 20250930 | 56 | 5 | 5 | 8 | 32 | 8 | 3 | 8 | Active | Deploy | Green | 1 | 0.938 | 647994 | 647994 | 736254 | 799226 | 40176 | -128436 | 0.938 | 0.826 | 20250131 | 20250331 | 53 | 11 | 11 | 9 | 2 | 1 | 2905 | 2886 | 3083 | -19 | 5 | 1 | 81 | 1 | 800000 | 800000 | 726410 | 653883 | 0.8174 | 3 | 27000 | 3 | 69 | 80.4
930 | 20251031 | 56 | 5 | 5 | 8 | 32 | 8 | 3 | 8 | Active | Deploy | Green | 1 | 0.938 | 647994 | 647994 | 736254 | 799226 | 40176 | -128436 | 0.938 | 0.826 | 20250131 | 20250331 | 53 | 11 | 11 | 9 | 2 | 1 | 2905 | 2808 | 2714 | -97 | 4 | 1 | 69 | 1 | 800000 | 800000 | 734024 | 642497 | 0.8031 | 3 | 28000 | 1 | 70 | 80.1
931 | 20251130 | 56 | 5 | 5 | 8 | 32 | 8 | 3 | 8 | Active | Deploy | Green | 1 | 0.938 | 647994 | 647994 | 736254 | 799226 | 40176 | -128436 | 0.938 | 0.826 | 20250131 | 20250331 | 53 | 11 | 11 | 9 | 2 | 1 | 2905 | 2783 | 2773 | -122 | 4 | 1 | 69 | 1 | 800000 | 800000 | 722810 | 665633 | 0.832 | 3 | 20000 | 3 | 69 | 79.5
932 | 20250731 | 57 | 9 | 8 | 9 | 33 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.0556 | 0.0702 | 739670 | 37988 | 51391 | 744519 | -13937 | 534 | 1.366 | 1.01 | 20261231 | 20261231 | 0 | 9 | 1 | 0 | 0 | 0 | 3892 | 4001 | 4220 | 109 | 2 | 0 | 19 | 0 | 1300000 | 0 | 1343133 | 0 |  | 0 | 0 | 3 | 96 | 100
933 | 20250831 | 57 | 9 | 8 | 9 | 33 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.1111 | 0.1156 | 739670 | 76341 | 76771 | 744930 | -9165 | 8735 | 1.12 | 1.114 | 20261231 | 20261231 | 0 | 9 | 1 | 0 | 0 | 0 | 4450 | 4428 | 4462 | -22 | 3 | 0 | 29 | 1 | 1300000 | 0 | 1306738 | 0 |  | 0 | 0 | 1 | 88 | 100
934 | 20250930 | 57 | 9 | 8 | 9 | 33 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.1667 | 0.16 | 739670 | 115060 | 104196 | 745341 | -3287 | 14151 | 1.028 | 1.135 | 20261231 | 20261231 | 4 | 9 | 2 | 2 | 0 | 0 | 4974 | 5015 | 4839 | 41 | 2 | 0 | 19 | 0 | 1300000 | 0 | 1315759 | 0 |  | 0 | 0 | 3 | 85 | 100
935 | 20251031 | 57 | 9 | 8 | 9 | 33 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.2222 | 0.2169 | 739670 | 154144 | 147314 | 745752 | -6290 | 13120 | 1.041 | 1.089 | 20261231 | 20261231 | 3 | 9 | 2 | 1 | 0 | 0 | 5447 | 5621 | 5696 | 174 | 4 | 1 | 56 | 1 | 1300000 | 0 | 1341677 | 0 |  | 0 | 0 | 2 | 82 | 96.9
936 | 20251130 | 57 | 9 | 8 | 9 | 33 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.2778 | 0.2796 | 739670 | 193593 | 196562 | 746163 | -13219 | 10250 | 1.068 | 1.052 | 20261231 | 20261231 | 0 | 9 | 3 | 3 | 0 | 0 | 5856 | 5636 | 5766 | -220 | 3 | 0 | 29 | 1 | 1300000 | 0 | 1311266 | 0 |  | 0 | 0 | 2 | 85 | 100
937 | 20251231 | 57 | 9 | 8 | 9 | 33 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.3333 | 0.3439 | 739670 | 233407 | 237903 | 746574 | -20966 | 16470 | 1.09 | 1.069 | 20261231 | 20261231 | 0 | 9 | 3 | 3 | 0 | 0 | 6187 | 6455 | 6536 | 268 | 3 | 0 | 29 | 1 | 1300000 | 0 | 1340371 | 0 |  | 0 | 0 | 2 | 88 | 100
938 | 20260131 | 57 | 9 | 8 | 9 | 33 | 1 | 3 | 1 | Active | Deliver | Green | 0.3889 | 0.4171 | 739670 | 273587 | 288230 | 746985 | -34929 | 20286 | 1.128 | 1.07 | 20261231 | 20261231 | 0 | 9 | 4 | 4 | 0 | 0 | 6432 | 6718 | 7128 | 286 | 4 | 0 | 38 | 1 | 1300000 | 0 | 1313486 | 0 |  | 1 | 11000 | 3 | 90 | 100
939 | 20260228 | 57 | 9 | 8 | 9 | 33 | 1 | 3 | 1 | Active | Deliver | Green | 0.4444 | 0.4655 | 739670 | 314131 | 324419 | 747395 | -30185 | 19897 | 1.096 | 1.061 | 20261231 | 20261231 | 0 | 9 | 4 | 4 | 0 | 0 | 6581 | 6953 | 6968 | 372 | 4 | 1 | 56 | 1 | 1300000 | 0 | 1314463 | 0 |  | 1 | 11000 | 1 | 87 | 98.5
940 | 20260331 | 57 | 9 | 8 | 9 | 33 | 1 | 3 | 1 | Active | Deliver | Green | 0.5 | 0.5127 | 739670 | 355042 | 366038 | 747806 | -24187 | 13191 | 1.068 | 1.036 | 20261231 | 20261231 | 0 | 9 | 5 | 5 | 0 | 0 | 6632 | 6518 | 6493 | -114 | 3 | 0 | 29 | 1 | 1300000 | 0 | 1294480 | 0 |  | 1 | 11000 | 1 | 87 | 100
941 | 20260430 | 57 | 9 | 8 | 9 | 33 | 1 | 3 | 1 | Active | Deliver | Green | 0.5556 | 0.5736 | 739670 | 396317 | 417106 | 748217 | -27958 | 7169 | 1.07 | 1.017 | 20261231 | 20261231 | 0 | 9 | 5 | 4 | 0 | 0 | 6581 | 6711 | 6982 | 130 | 2 | 0 | 19 | 0 | 1300000 | 0 | 1312575 | 0 |  | 1 | 12000 | 2 | 89 | 100
942 | 20260531 | 57 | 9 | 8 | 9 | 33 | 1 | 3 | 1 | Active | Deliver | Green | 0.6111 | 0.6081 | 739670 | 437958 | 439793 | 748628 | -11835 | 10000 | 1.027 | 1.023 | 20261231 | 20261231 | 2 | 9 | 6 | 5 | 0 | 0 | 6432 | 6439 | 6825 | 7 | 4 | 0 | 38 | 1 | 1300000 | 0 | 1321631 | 0 |  | 1 | 9000 | 2 | 85 | 100
943 | 20260630 | 57 | 9 | 8 | 9 | 33 | 1 | 3 | 1 | Active | Deliver | Green | 0.6667 | 0.6699 | 739670 | 479964 | 484588 | 749039 | -15541 | 10917 | 1.032 | 1.022 | 20261231 | 20261231 | 0 | 9 | 6 | 6 | 0 | 0 | 6187 | 6508 | 6427 | 321 | 3 | 0 | 29 | 1 | 1300000 | 0 | 1339859 | 0 |  | 1 | 6000 | 2 | 81 | 100
944 | 20260731 | 57 | 9 | 8 | 9 | 33 | 1 | 3 | 1 | Active | Deliver | Green | 0.7222 | 0.7123 | 739670 | 522335 | 526233 | 749450 | -4532 | 634 | 1.009 | 1.001 | 20261231 | 20261231 | 6 | 9 | 7 | 7 | 0 | 0 | 5856 | 6059 | 6389 | 203 | 4 | 0 | 38 | 1 | 1300000 | 10317 | 1336486 | 0 | 0 | 1 | 7000 | 2 | 84 | 100
945 | 20260831 | 57 | 9 | 8 | 9 | 33 | 1 | 3 | 1 | Active | Deploy | Green | 0.7778 | 0.7863 | 739670 | 565071 | 584112 | 750566 | -16532 | -2509 | 1.029 | 0.996 | 20261231 | 20261231 | 0 | 9 | 7 | 7 | 0 | 0 | 5447 | 5517 | 5900 | 70 | 2 | 0 | 19 | 0 | 1300000 | 268254 | 1328939 | 0 | 0 | 1 | 9000 | 4 | 86 | 100
946 | 20260930 | 57 | 9 | 8 | 9 | 33 | 1 | 3 | 1 | Active | Deploy | Green | 0.8333 | 0.8554 | 739670 | 608173 | 643227 | 752923 | -24541 | -10513 | 1.04 | 0.984 | 20261231 | 20261231 | 0 | 9 | 8 | 8 | 0 | 0 | 4974 | 4919 | 5168 | -55 | 0 | 0 | 0 | 0 | 1300000 | 526190 | 1304522 | 208547 | 0.3963 | 1 | 12000 | 0 | 84 | 100
947 | 20231031 | 58 | 10 | 7 | 10 | 34 | 2 | 1 | 2 | Active | Deliver | Green | 0.4 | 0.4584 | 896037 | 341211 | 389032 | 922918 | -69532 | 21711 | 1.204 | 1.056 | 20240731 | 20240731 | 0 | 8 | 3 | 3 | 0 | 0 | 7837 | 8500 | 8965 | 663 | 2 | 0 | 18 | 0 | 1200000 | 0 | 1316173 | 0 |  | 0 | 0 | 4 | 96 | 100
948 | 20231130 | 58 | 10 | 7 | 10 | 34 | 2 | 1 | 2 | Active | Deliver | Green | 0.4667 | 0.5325 | 896037 | 400310 | 459044 | 924710 | -76830 | 18096 | 1.192 | 1.039 | 20240731 | 20240731 | 0 | 8 | 4 | 4 | 0 | 0 | 8011 | 9035 | 8661 | 1024 | 0 | 0 | 0 | 0 | 1200000 | 0 | 1317805 | 0 |  | 1 | 7000 | 5 | 89 | 100
949 | 20231231 | 58 | 10 | 7 | 10 | 34 | 2 | 1 | 2 | Active | Deliver | Green | 0.5333 | 0.6176 | 896037 | 460045 | 545391 | 926502 | -93347 | 8001 | 1.203 | 1.015 | 20240731 | 20240731 | 0 | 8 | 4 | 3 | 0 | 0 | 8011 | 8917 | 9095 | 906 | 2 | 0 | 18 | 0 | 1200000 | 0 | 1296703 | 0 |  | 1 | 10000 | 2 | 92 | 100
950 | 20240131 | 58 | 10 | 7 | 10 | 34 | 2 | 1 | 2 | Active | Deliver | Green | 0.6 | 0.6793 | 896037 | 520418 | 603568 | 928294 | -88260 | 5110 | 1.17 | 1.008 | 20240731 | 20240731 | 0 | 8 | 5 | 4 | 0 | 0 | 7837 | 8840 | 8550 | 1003 | 2 | 0 | 18 | 0 | 1200000 | 0 | 1307596 | 0 |  | 1 | 13000 | 2 | 93 | 100
951 | 20240229 | 58 | 10 | 7 | 10 | 34 | 2 | 1 | 2 | Active | Deliver | Green | 0.6667 | 0.7377 | 896037 | 581428 | 665276 | 931340 | -79578 | -4270 | 1.137 | 0.994 | 20240731 | 20240731 | 0 | 8 | 5 | 5 | 0 | 0 | 7495 | 7763 | 8138 | 268 | 1 | 0 | 9 | 0 | 1200000 | 0 | 1300250 | 0 |  | 1 | 11000 | 4 | 86 | 100
952 | 20240331 | 58 | 10 | 7 | 10 | 34 | 2 | 1 | 2 | Active | Deploy | Green | 0.7333 | 0.7865 | 896037 | 643076 | 716083 | 934991 | -61657 | -11350 | 1.096 | 0.984 | 20240731 | 20240731 | 0 | 8 | 6 | 6 | 0 | 0 | 7002 | 7787 | 7515 | 785 | 3 | 1 | 45 | 0 | 1200000 | 57143 | 1267012 | 0 | 0 | 1 | 14000 | 3 | 80 | 95.8
953 | 20240430 | 58 | 10 | 7 | 10 | 34 | 2 | 1 | 2 | Active | Deploy | Green | 0.8 | 0.8519 | 896037 | 705360 | 776286 | 936970 | -57974 | -12952 | 1.082 | 0.983 | 20240731 | 20240731 | 0 | 8 | 6 | 5 | 0 | 0 | 6378 | 6654 | 6965 | 276 | 3 | 0 | 27 | 0 | 1200000 | 342857 | 1275370 | 83149 | 0.2425 | 1 | 10000 | 3 | 82 | 100
954 | 20240531 | 58 | 10 | 7 | 10 | 34 | 2 | 1 | 2 | Active | Deploy | Green | 0.8667 | 0.9482 | 896037 | 768282 | 871224 | 940350 | -81340 | -21602 | 1.106 | 0.975 | 20240731 | 20240731 | 0 | 8 | 7 | 7 | 0 | 0 | 5650 | 6215 | 6136 | 565 | 1 | 0 | 9 | 0 | 1200000 | 628571 | 1320912 | 361321 | 0.5748 | 1 | 12000 | 0 | 84 | 100
955 | 20240630 | 58 | 10 | 7 | 10 | 34 | 2 | 1 | 2 | Completed | Completed | Green | 0.9333 | 1 | 896037 | 831841 | 933473 | 945160 | -64196 | -37436 | 1.077 | 0.96 | 20240731 | 20240731 | 0 | 8 | 7 | 7 | 0 | 0 | 4852 | 5214 | 5278 | 362 | 1 | 0 | 9 | 0 | 1200000 | 914286 | 1267797 | 626151 | 0.6849 | 1 | 13000 | 0 | 83 | 100
956 | 20240630 | 59 | 10 | 7 | 11 | 35 | 3 | 1 | 3 | Active | Initiate & Design | Amber | 0.1111 | 0.0327 | 924518 | 95419 | 31015 | 962692 | 65187 | -783 | 0.317 | 0.974 | 20250228 | 20250331 | 27 | 6 | 1 | 0 | 1 | 0 | 5562 | 4568 | 4862 | -994 | 9 | 1 | 125 | 2 | 1500000 | 0 | 1409420 | 0 |  | 0 | 0 | 4 | 48 | 54.7
957 | 20240731 | 59 | 10 | 7 | 11 | 35 | 3 | 1 | 3 | Active | Initiate & Design | Green | 0.2222 | 0.1429 | 924518 | 192665 | 119770 | 962526 | 60551 | 12344 | 0.686 | 1.103 | 20250228 | 20250331 | 27 | 6 | 1 | 0 | 1 | 0 | 6808 | 4945 | 4798 | -1863 | 6 | 1 | 89 | 2 | 1500000 | 0 | 1409184 | 0 |  | 0 | 0 | 3 | 67 | 73.8
958 | 20240831 | 59 | 10 | 7 | 11 | 35 | 3 | 1 | 3 | Active | Initiate & Design | Green | 0.3333 | 0.2386 | 924518 | 291737 | 208505 | 967662 | 71147 | 12085 | 0.756 | 1.058 | 20250228 | 20250331 | 33 | 6 | 2 | 0 | 1 | 0 | 7734 | 5699 | 5720 | -2035 | 7 | 1 | 101 | 2 | 1500000 | 0 | 1424013 | 0 |  | 0 | 0 | 3 | 72 | 75.8
959 | 20240930 | 59 | 10 | 7 | 11 | 35 | 3 | 1 | 3 | Active | Deliver | Green | 0.4444 | 0.3562 | 924518 | 392635 | 319664 | 972798 | 63322 | 9649 | 0.839 | 1.03 | 20250228 | 20250331 | 31 | 6 | 3 | 2 | 1 | 0 | 8226 | 6877 | 7061 | -1349 | 8 | 1 | 113 | 2 | 1500000 | 0 | 1392002 | 0 |  | 1 | 10000 | 5 | 70 | 80.2
960 | 20241031 | 59 | 10 | 7 | 11 | 35 | 3 | 1 | 3 | Active | Deliver | Green | 0.5556 | 0.4618 | 924518 | 495359 | 421771 | 977935 | 68417 | 5171 | 0.862 | 1.012 | 20250228 | 20250331 | 32 | 6 | 3 | 1 | 1 | 0 | 8226 | 6176 | 6143 | -2050 | 6 | 1 | 89 | 2 | 1500000 | 0 | 1417333 | 0 |  | 1 | 13000 | 6 | 74 | 79.2
961 | 20241130 | 59 | 10 | 7 | 11 | 35 | 3 | 1 | 3 | Active | Deliver | Green | 0.6667 | 0.5569 | 924518 | 599909 | 519754 | 984981 | 85045 | -4890 | 0.858 | 0.991 | 20250228 | 20250331 | 39 | 6 | 4 | 3 | 1 | 0 | 7734 | 6236 | 6399 | -1498 | 5 | 1 | 77 | 1 | 1500000 | 0 | 1409513 | 0 |  | 1 | 12000 | 5 | 67 | 79.3
962 | 20241231 | 59 | 10 | 7 | 11 | 35 | 3 | 1 | 3 | Active | Deliver | Green | 0.7778 | 0.6696 | 924518 | 706286 | 643597 | 995959 | 87229 | -24540 | 0.877 | 0.962 | 20250228 | 20250331 | 37 | 6 | 5 | 4 | 1 | 0 | 6808 | 5052 | 4816 | -1756 | 8 | 1 | 113 | 2 | 1500000 | 309524 | 1416520 | 0 | 0 | 1 | 11000 | 3 | 71 | 77.9
963 | 20250131 | 59 | 10 | 7 | 11 | 35 | 3 | 1 | 3 | Active | Deploy | Green | 0.8889 | 0.7725 | 924518 | 814489 | 747825 | 1002479 | 100299 | -33635 | 0.877 | 0.955 | 20250228 | 20250331 | 40 | 6 | 5 | 4 | 1 | 0 | 5562 | 4294 | 4053 | -1268 | 3 | 1 | 54 | 1 | 1500000 | 904762 | 1386903 | 503309 | 0.5563 | 1 | 14000 | 2 | 67 | 77.8
964 | 20250228 | 59 | 10 | 7 | 11 | 35 | 3 | 1 | 3 | Active | Deploy | Green | 1 | 0.8606 | 924518 | 924518 | 847616 | 1010955 | 128878 | -51976 | 0.861 | 0.939 | 20250228 | 20250430 | 49 | 6 | 6 | 3 | 2 | 1 | 4144 | 3435 | 3233 | -709 | 4 | 0 | 47 | 1 | 1500000 | 1500000 | 1431651 | 943656 | 0.6291 | 1 | 10000 | 3 | 76 | 86.5
965 | 20250331 | 59 | 10 | 7 | 11 | 35 | 3 | 1 | 3 | Active | Deploy | Green | 1 | 0.8606 | 924518 | 924518 | 870749 | 1021164 | 128878 | -75109 | 0.861 | 0.914 | 20250228 | 20250430 | 49 | 6 | 6 | 4 | 2 | 1 | 4144 | 3049 | 2876 | -1095 | 4 | 1 | 65 | 1 | 1500000 | 1500000 | 1395645 | 1240045 | 0.8267 | 1 | 14000 | 1 | 64 | 74.9
966 | 20250430 | 59 | 10 | 7 | 11 | 35 | 3 | 1 | 3 | Active | Deploy | Green | 1 | 0.8606 | 924518 | 924518 | 885493 | 1029394 | 128878 | -89853 | 0.861 | 0.899 | 20250228 | 20250430 | 49 | 6 | 6 | 3 | 2 | 1 | 4144 | 3142 | 3004 | -1002 | 6 | 1 | 89 | 2 | 1500000 | 1500000 | 1442423 | 1387234 | 0.9248 | 1 | 10000 | 4 | 67 | 75.8
967 | 20250531 | 59 | 10 | 7 | 11 | 35 | 3 | 1 | 3 | Active | Deploy | Green | 1 | 0.8657 | 924518 | 924518 | 902063 | 1036822 | 124163 | -101708 | 0.866 | 0.887 | 20250228 | 20250430 | 46 | 6 | 6 | 4 | 2 | 1 | 4144 | 3252 | 3106 | -892 | 6 | 0 | 71 | 2 | 1500000 | 1500000 | 1441623 | 1349145 | 0.8994 | 3 | 32000 | 1 | 73 | 84.2
968 | 20250630 | 59 | 10 | 7 | 11 | 35 | 3 | 1 | 3 | Active | Deploy | Green | 1 | 0.8727 | 924518 | 924518 | 918090 | 1039314 | 117691 | -111263 | 0.873 | 0.879 | 20250228 | 20250331 | 44 | 6 | 6 | 5 | 1 | 0 | 4144 | 3089 | 3239 | -1055 | 5 | 1 | 77 | 1 | 1500000 | 1500000 | 1439221 | 1435860 | 0.9572 | 3 | 28000 | 3 | 69 | 75.3
969 | 20250731 | 59 | 10 | 7 | 11 | 35 | 3 | 1 | 3 | Active | Deploy | Green | 1 | 0.8776 | 924518 | 924518 | 922476 | 1039165 | 113161 | -111119 | 0.878 | 0.88 | 20250228 | 20250331 | 43 | 6 | 6 | 4 | 1 | 0 | 4144 | 3418 | 3512 | -726 | 5 | 1 | 77 | 1 | 1500000 | 1500000 | 1400684 | 1331546 | 0.8877 | 3 | 33000 | 3 | 71 | 76.6
970 | 20250831 | 59 | 10 | 7 | 11 | 35 | 3 | 1 | 3 | Active | Deploy | Green | 1 | 0.8776 | 924518 | 924518 | 924518 | 1039560 | 113161 | -113161 | 0.878 | 0.878 | 20250228 | 20250331 | 43 | 6 | 6 | 4 | 1 | 0 | 4144 | 3252 | 3354 | -892 | 3 | 0 | 36 | 1 | 1500000 | 1500000 | 1440221 | 1283772 | 0.8558 | 3 | 40000 | 3 | 71 | 84.4
971 | 20250930 | 59 | 10 | 7 | 11 | 35 | 3 | 1 | 3 | Active | Deploy | Green | 1 | 0.8873 | 924518 | 924518 | 929381 | 1038517 | 104193 | -109056 | 0.887 | 0.883 | 20250228 | 20250331 | 39 | 6 | 6 | 5 | 1 | 0 | 4144 | 3127 | 2992 | -1017 | 5 | 1 | 77 | 1 | 1500000 | 1500000 | 1420983 | 1411044 | 0.9407 | 3 | 26000 | 1 | 68 | 76
972 | 20251031 | 59 | 10 | 7 | 11 | 35 | 3 | 1 | 3 | Active | Deploy | Green | 1 | 0.8873 | 924518 | 924518 | 929381 | 1038517 | 104193 | -109056 | 0.887 | 0.883 | 20250228 | 20250331 | 39 | 6 | 6 | 4 | 1 | 0 | 4144 | 3217 | 3283 | -927 | 3 | 0 | 36 | 1 | 1500000 | 1500000 | 1398383 | 1350438 | 0.9003 | 3 | 41000 | 1 | 71 | 84
973 | 20251130 | 59 | 10 | 7 | 11 | 35 | 3 | 1 | 3 | Active | Deploy | Green | 1 | 0.8873 | 924518 | 924518 | 935427 | 1039677 | 104193 | -115102 | 0.887 | 0.877 | 20250228 | 20250331 | 39 | 6 | 6 | 4 | 1 | 0 | 4144 | 3174 | 3259 | -970 | 5 | 1 | 77 | 1 | 1500000 | 1500000 | 1409958 | 1332354 | 0.8882 | 3 | 28000 | 1 | 68 | 75.8
974 | 20251231 | 59 | 10 | 7 | 11 | 35 | 3 | 1 | 3 | Active | Deploy | Green | 1 | 0.8873 | 924518 | 924518 | 935427 | 1039677 | 104193 | -115102 | 0.887 | 0.877 | 20250228 | 20250331 | 39 | 6 | 6 | 5 | 1 | 0 | 4144 | 3372 | 3260 | -772 | 4 | 0 | 47 | 1 | 1500000 | 1500000 | 1441643 | 1314779 | 0.8765 | 3 | 38000 | 3 | 69 | 85.4
975 | 20250731 | 60 | 5 | 5 | 12 | 36 | 4 | 2 | 4 | Active | Initiate & Design | Red | 0.0417 | 0 | 1287634 | 49538 | 0 | 1345470 | 49538 | 0 | 0 | 1 | 20270630 | 20270731 | 39 | 12 | 1 | 0 | 1 | 0 | 6526 | 5915 | 5980 | -611 | 11 | 2 | 170 | 3 | 2400000 | 0 | 2344643 | 0 |  | 0 | 0 | 6 | 26 | 36.3
976 | 20250831 | 60 | 5 | 5 | 12 | 36 | 4 | 2 | 4 | Active | Initiate & Design | Amber | 0.0833 | 0.0439 | 1287634 | 99434 | 60790 | 1369197 | 42907 | -4263 | 0.568 | 0.929 | 20270630 | 20270731 | 37 | 12 | 1 | 0 | 1 | 0 | 7266 | 6473 | 6423 | -793 | 8 | 1 | 115 | 2 | 2400000 | 0 | 2335689 | 0 |  | 0 | 0 | 4 | 55 | 67
977 | 20250930 | 60 | 5 | 5 | 12 | 36 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.125 | 0.0934 | 1287634 | 149687 | 114513 | 1352981 | 29422 | 5752 | 0.803 | 1.05 | 20270630 | 20270731 | 30 | 12 | 2 | 1 | 1 | 0 | 7981 | 6940 | 7194 | -1041 | 7 | 1 | 103 | 2 | 2400000 | 0 | 2247112 | 0 |  | 0 | 0 | 6 | 68 | 80.2
978 | 20251031 | 60 | 5 | 5 | 12 | 36 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.1667 | 0.1332 | 1287634 | 200299 | 167165 | 1356737 | 28786 | 4348 | 0.856 | 1.026 | 20270630 | 20270731 | 31 | 12 | 2 | 1 | 1 | 0 | 8658 | 8053 | 7723 | -605 | 7 | 1 | 103 | 2 | 2400000 | 0 | 2325699 | 0 |  | 1 | 16000 | 5 | 73 | 84.1
979 | 20251130 | 60 | 5 | 5 | 12 | 36 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.2083 | 0.1834 | 1287634 | 251267 | 217673 | 1360493 | 15115 | 18479 | 0.94 | 1.085 | 20270630 | 20270731 | 24 | 12 | 3 | 3 | 0 | 0 | 9286 | 8080 | 8601 | -1206 | 5 | 1 | 79 | 1 | 2400000 | 0 | 2301769 | 0 |  | 1 | 15000 | 5 | 73 | 88.2
980 | 20251231 | 60 | 5 | 5 | 12 | 36 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.25 | 0.202 | 1287634 | 302594 | 247378 | 1364248 | 42492 | 12724 | 0.86 | 1.051 | 20270630 | 20270831 | 46 | 12 | 3 | 2 | 1 | 0 | 9854 | 9047 | 8885 | -807 | 6 | 1 | 91 | 2 | 2400000 | 0 | 2276863 | 0 |  | 1 | 16000 | 6 | 72 | 84.2
981 | 20260131 | 60 | 5 | 5 | 12 | 36 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.2917 | 0.235 | 1287634 | 354278 | 285679 | 1368004 | 51684 | 16915 | 0.854 | 1.059 | 20270630 | 20270831 | 54 | 12 | 4 | 2 | 1 | 0 | 10352 | 9544 | 10202 | -808 | 8 | 2 | 133 | 2 | 2400000 | 0 | 2315270 | 0 |  | 1 | 14000 | 6 | 68 | 76.8
982 | 20260228 | 60 | 5 | 5 | 12 | 36 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.3333 | 0.2547 | 1287634 | 406320 | 321096 | 1371759 | 78360 | 6864 | 0.807 | 1.021 | 20270630 | 20270930 | 75 | 12 | 4 | 2 | 1 | 0 | 10771 | 10165 | 10777 | -606 | 6 | 1 | 91 | 2 | 2400000 | 0 | 2298171 | 0 |  | 1 | 11000 | 5 | 69 | 81.6
983 | 20260331 | 60 | 5 | 5 | 12 | 36 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.375 | 0.2838 | 1287634 | 458720 | 348615 | 1375515 | 93289 | 16816 | 0.797 | 1.048 | 20270630 | 20270930 | 87 | 12 | 5 | 3 | 2 | 1 | 11105 | 9759 | 9611 | -1346 | 8 | 1 | 115 | 2 | 2400000 | 0 | 2297535 | 0 |  | 1 | 19000 | 5 | 69 | 80.7
984 | 20260430 | 60 | 5 | 5 | 12 | 36 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.4167 | 0.3336 | 1287634 | 511477 | 412580 | 1379271 | 81922 | 16975 | 0.84 | 1.041 | 20270630 | 20270930 | 79 | 12 | 5 | 2 | 2 | 1 | 11348 | 11117 | 10594 | -231 | 8 | 1 | 115 | 2 | 2400000 | 0 | 2297946 | 0 |  | 1 | 16000 | 6 | 75 | 84.6
985 | 20260531 | 60 | 5 | 5 | 12 | 36 | 4 | 2 | 4 | Active | Deliver | Green | 0.4583 | 0.3828 | 1287634 | 564592 | 487170 | 1383026 | 71686 | 5736 | 0.873 | 1.012 | 20270630 | 20270831 | 71 | 12 | 6 | 3 | 2 | 1 | 11495 | 11092 | 11195 | -403 | 8 | 2 | 133 | 2 | 2400000 | 0 | 2263090 | 0 |  | 1 | 16000 | 6 | 70 | 76.3
986 | 20260630 | 60 | 5 | 5 | 12 | 36 | 4 | 2 | 4 | Active | Deliver | Green | 0.5 | 0.4171 | 1287634 | 618064 | 535105 | 1386782 | 80992 | 1967 | 0.869 | 1.004 | 20270630 | 20270930 | 79 | 12 | 6 | 3 | 2 | 1 | 11544 | 10838 | 11115 | -706 | 8 | 1 | 115 | 2 | 2400000 | 0 | 2312872 | 0 |  | 1 | 12000 | 5 | 71 | 83.9
987 | 20260731 | 60 | 5 | 5 | 12 | 36 | 4 | 2 | 4 | Active | Deliver | Green | 0.5417 | 0.4633 | 1287634 | 671895 | 594064 | 1390537 | 75334 | 2497 | 0.888 | 1.004 | 20270630 | 20270831 | 73 | 12 | 7 | 4 | 2 | 1 | 11495 | 11261 | 10880 | -234 | 8 | 1 | 115 | 2 | 2400000 | 0 | 2284846 | 0 |  | 1 | 13000 | 5 | 72 | 85.3
988 | 20260831 | 60 | 5 | 5 | 12 | 36 | 4 | 2 | 4 | Active | Deliver | Green | 0.5833 | 0.5209 | 1287634 | 726083 | 685090 | 1400252 | 55354 | -14361 | 0.924 | 0.979 | 20270630 | 20270831 | 59 | 12 | 7 | 5 | 1 | 0 | 11348 | 10954 | 11693 | -394 | 7 | 1 | 103 | 2 | 2400000 | 0 | 2344080 | 0 |  | 1 | 11000 | 6 | 71 | 86.4
989 | 20260930 | 60 | 5 | 5 | 12 | 36 | 4 | 2 | 4 | Active | Deliver | Green | 0.625 | 0.5607 | 1287634 | 780628 | 743676 | 1406300 | 58652 | -21700 | 0.925 | 0.971 | 20270630 | 20270831 | 60 | 12 | 8 | 6 | 1 | 0 | 11105 | 10066 | 10340 | -1039 | 8 | 2 | 133 | 2 | 2400000 | 0 | 2273569 | 0 |  | 1 | 16000 | 5 | 66 | 76.1
990 | 20250331 | 61 | 1 | 1 | 13 | 25 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.0417 | 0.0389 | 924312 | 35560 | 28109 | 942105 | -396 | 7847 | 1.011 | 1.279 | 20270228 | 20270228 | 2 | 12 | 1 | 1 | 0 | 0 | 4684 | 4780 | 4803 | 96 | 4 | 0 | 41 | 1 | 1800000 | 0 | 1328647 | 0 |  | 0 | 0 | 3 | 86 | 100
991 | 20250430 | 61 | 1 | 1 | 13 | 25 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.0833 | 0.0791 | 924312 | 71377 | 69980 | 943260 | -1736 | 3133 | 1.024 | 1.045 | 20270228 | 20270228 | 4 | 12 | 1 | 1 | 0 | 0 | 5216 | 4959 | 4738 | -257 | 4 | 0 | 41 | 1 | 1800000 | 0 | 1341274 | 0 |  | 0 | 0 | 2 | 79 | 94.5
992 | 20250531 | 61 | 1 | 1 | 13 | 25 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.125 | 0.135 | 924312 | 107451 | 111624 | 944416 | -17331 | 13158 | 1.162 | 1.118 | 20270228 | 20270228 | 0 | 12 | 2 | 2 | 0 | 0 | 5729 | 6008 | 5884 | 279 | 4 | 1 | 59 | 1 | 1800000 | 0 | 1333297 | 0 |  | 1 | 15000 | 4 | 78 | 96.2
993 | 20250630 | 61 | 1 | 1 | 13 | 25 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.1667 | 0.1794 | 924312 | 143782 | 149153 | 945571 | -22040 | 16669 | 1.153 | 1.112 | 20270228 | 20270228 | 0 | 12 | 2 | 1 | 0 | 0 | 6215 | 6281 | 6169 | 66 | 3 | 0 | 31 | 1 | 1800000 | 0 | 1361975 | 0 |  | 1 | 8000 | 5 | 82 | 100
994 | 20250731 | 61 | 1 | 1 | 13 | 25 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.2083 | 0.2328 | 924312 | 180369 | 205648 | 946727 | -34811 | 9532 | 1.193 | 1.046 | 20270228 | 20270228 | 0 | 12 | 3 | 2 | 0 | 0 | 6666 | 6942 | 6679 | 276 | 4 | 0 | 41 | 1 | 1800000 | 0 | 1315818 | 0 |  | 1 | 9000 | 4 | 80 | 100
995 | 20250831 | 61 | 1 | 1 | 13 | 25 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.25 | 0.2668 | 924312 | 217213 | 237146 | 947882 | -29393 | 9460 | 1.135 | 1.04 | 20270228 | 20270228 | 0 | 12 | 3 | 2 | 0 | 0 | 7073 | 7355 | 7619 | 282 | 2 | 0 | 20 | 0 | 1800000 | 0 | 1329802 | 0 |  | 1 | 8000 | 5 | 77 | 100
996 | 20250930 | 61 | 1 | 1 | 13 | 25 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.2917 | 0.2856 | 924312 | 254314 | 255051 | 949037 | -9670 | 8933 | 1.038 | 1.035 | 20270228 | 20270228 | 5 | 12 | 4 | 3 | 0 | 0 | 7431 | 7282 | 7732 | -149 | 5 | 0 | 51 | 1 | 1800000 | 0 | 1383378 | 0 |  | 1 | 11000 | 4 | 72 | 96
997 | 20251031 | 61 | 1 | 1 | 13 | 25 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.3333 | 0.3224 | 924312 | 291672 | 286515 | 950193 | -6326 | 11483 | 1.022 | 1.04 | 20270228 | 20270228 | 9 | 12 | 4 | 3 | 0 | 0 | 7732 | 8176 | 8458 | 444 | 5 | 0 | 51 | 1 | 1800000 | 0 | 1387359 | 0 |  | 1 | 11000 | 3 | 78 | 96
998 | 20251130 | 61 | 1 | 1 | 13 | 25 | 5 | 2 | 5 | Active | Deliver | Green | 0.375 | 0.3678 | 924312 | 329286 | 326917 | 951348 | -10676 | 13045 | 1.032 | 1.04 | 20270228 | 20270228 | 6 | 12 | 5 | 4 | 0 | 0 | 7972 | 8208 | 8434 | 236 | 3 | 0 | 31 | 1 | 1800000 | 0 | 1394903 | 0 |  | 1 | 10000 | 5 | 73 | 96.6
999 | 20251231 | 61 | 1 | 1 | 13 | 25 | 5 | 2 | 5 | Active | Deliver | Green | 0.4167 | 0.4173 | 924312 | 367157 | 366519 | 952504 | -18558 | 19196 | 1.05 | 1.052 | 20270228 | 20270228 | 0 | 12 | 5 | 4 | 0 | 0 | 8146 | 8292 | 8024 | 146 | 4 | 1 | 59 | 1 | 1800000 | 0 | 1370476 | 0 |  | 1 | 8000 | 5 | 72 | 89.4
1000 | 20260131 | 61 | 1 | 1 | 13 | 25 | 5 | 2 | 5 | Active | Deliver | Green | 0.4583 | 0.4774 | 924312 | 405285 | 421327 | 953659 | -35982 | 19940 | 1.089 | 1.047 | 20270228 | 20270228 | 0 | 12 | 6 | 5 | 0 | 0 | 8251 | 7854 | 7619 | -397 | 2 | 0 | 20 | 0 | 1800000 | 0 | 1346641 | 0 |  | 1 | 9000 | 5 | 77 | 97.5
1001 | 20260228 | 61 | 1 | 1 | 13 | 25 | 5 | 2 | 5 | Active | Deliver | Green | 0.5 | 0.5189 | 924312 | 443670 | 467018 | 954814 | -35955 | 12607 | 1.081 | 1.027 | 20270228 | 20270228 | 0 | 12 | 6 | 5 | 0 | 0 | 8287 | 8468 | 8703 | 181 | 4 | 0 | 41 | 1 | 1800000 | 0 | 1364505 | 0 |  | 1 | 9000 | 5 | 81 | 97.8
1002 | 20260331 | 61 | 1 | 1 | 13 | 25 | 5 | 2 | 5 | Active | Deliver | Green | 0.5417 | 0.5807 | 924312 | 482311 | 533179 | 955970 | -54437 | 3569 | 1.113 | 1.007 | 20270228 | 20270228 | 0 | 12 | 7 | 7 | 0 | 0 | 8251 | 8414 | 8291 | 163 | 2 | 0 | 20 | 0 | 1800000 | 0 | 1314312 | 0 |  | 1 | 13000 | 4 | 77 | 97.8
1003 | 20260430 | 61 | 1 | 1 | 13 | 25 | 5 | 2 | 5 | Active | Deliver | Green | 0.5833 | 0.6014 | 924312 | 521209 | 542293 | 957125 | -34672 | 13588 | 1.067 | 1.025 | 20270228 | 20270228 | 0 | 12 | 7 | 6 | 0 | 0 | 8146 | 8329 | 8435 | 183 | 4 | 0 | 41 | 1 | 1800000 | 0 | 1364758 | 0 |  | 1 | 13000 | 5 | 77 | 97.1
1004 | 20260531 | 61 | 1 | 1 | 13 | 25 | 5 | 2 | 5 | Active | Deliver | Green | 0.625 | 0.638 | 924312 | 560364 | 588425 | 958280 | -29347 | 1286 | 1.052 | 1.002 | 20270228 | 20270228 | 0 | 12 | 8 | 8 | 0 | 0 | 7972 | 8427 | 8206 | 455 | 3 | 0 | 31 | 1 | 1800000 | 0 | 1311117 | 0 |  | 1 | 12000 | 5 | 74 | 94.8
1005 | 20260630 | 61 | 1 | 1 | 13 | 25 | 5 | 2 | 5 | Active | Deliver | Green | 0.6667 | 0.6587 | 924312 | 599776 | 606514 | 959436 | -9068 | 2330 | 1.015 | 1.004 | 20270228 | 20270228 | 7 | 12 | 8 | 7 | 0 | 0 | 7732 | 8202 | 8605 | 470 | 5 | 0 | 51 | 1 | 1800000 | 0 | 1314546 | 0 |  | 1 | 8000 | 2 | 75 | 93.3
1006 | 20260731 | 61 | 1 | 1 | 13 | 25 | 5 | 2 | 5 | Active | Deliver | Green | 0.7083 | 0.7094 | 924312 | 639444 | 654887 | 960591 | -16263 | 820 | 1.025 | 1.001 | 20270228 | 20270228 | 0 | 12 | 9 | 8 | 0 | 0 | 7431 | 7948 | 8271 | 517 | 4 | 0 | 41 | 1 | 1800000 | 0 | 1347463 | 0 |  | 1 | 14000 | 5 | 77 | 94.2
1007 | 20260831 | 61 | 1 | 1 | 13 | 25 | 5 | 2 | 5 | Active | Deploy | Green | 0.75 | 0.7556 | 924312 | 679369 | 704807 | 963592 | -19041 | -6397 | 1.028 | 0.991 | 20270228 | 20270228 | 0 | 12 | 9 | 8 | 0 | 0 | 7073 | 7113 | 7190 | 40 | 3 | 0 | 31 | 1 | 1800000 | 192857 | 1394441 | 0 | 0 | 1 | 13000 | 3 | 73 | 94.6
1008 | 20260930 | 61 | 1 | 1 | 13 | 25 | 5 | 2 | 5 | Active | Deploy | Green | 0.7917 | 0.8001 | 924312 | 719551 | 759708 | 968288 | -19991 | -20166 | 1.028 | 0.974 | 20270228 | 20270228 | 0 | 12 | 10 | 9 | 0 | 0 | 6666 | 6476 | 6478 | -190 | 5 | 0 | 51 | 1 | 1800000 | 460714 | 1317801 | 48196 | 0.1046 | 1 | 9000 | 4 | 75 | 92.2
1009 | 20241031 | 62 | 7 | 5 | 14 | 26 | 6 | 3 | 6 | Active | Initiate & Design | Red | 0.0417 | 0 | 206728 | 7953 | 0 | 233258 | 7953 | 0 | 0 | 1 | 20260930 | 20261031 | 44 | 12 | 1 | 0 | 1 | 1 | 1048 | 909 | 960 | -139 | 15 | 3 | 268 | 5 | 500000 | 0 | 352191 | 0 |  | 1 | 2000 | 5 | 24 | 19.8
1010 | 20241130 | 62 | 7 | 5 | 14 | 26 | 6 | 3 | 6 | Active | Initiate & Design | Red | 0.0833 | 0 | 206728 | 15964 | 0 | 234981 | 15964 | 0 | 0 | 1 | 20260930 | 20261231 | 88 | 12 | 1 | 0 | 1 | 1 | 1167 | 927 | 893 | -240 | 15 | 4 | 286 | 5 | 500000 | 0 | 343183 | 0 |  | 1 | 3000 | 5 | 24 | 9.7
1011 | 20241231 | 62 | 7 | 5 | 14 | 26 | 6 | 3 | 6 | Active | Initiate & Design | Red | 0.125 | 0.0484 | 206728 | 24032 | 10000 | 236704 | 14026 | 6 | 0.417 | 1.001 | 20260930 | 20261231 | 81 | 12 | 2 | 1 | 1 | 1 | 1281 | 1115 | 1049 | -166 | 11 | 3 | 211 | 4 | 500000 | 0 | 342146 | 0 |  | 1 | 2000 | 7 | 30 | 38.1
1012 | 20250131 | 62 | 7 | 5 | 14 | 26 | 6 | 3 | 6 | Active | Initiate & Design | Red | 0.1667 | 0.0626 | 206728 | 32158 | 12478 | 238426 | 19217 | 463 | 0.402 | 1.037 | 20260930 | 20270131 | 110 | 12 | 2 | 0 | 1 | 1 | 1390 | 1076 | 1014 | -314 | 13 | 3 | 239 | 4 | 500000 | 0 | 337787 | 0 |  | 1 | 2000 | 8 | 31 | 36.3
1013 | 20250228 | 62 | 7 | 5 | 14 | 26 | 6 | 3 | 6 | Active | Initiate & Design | Red | 0.2083 | 0.0915 | 206728 | 40341 | 19441 | 241396 | 21425 | -525 | 0.469 | 0.973 | 20260930 | 20270131 | 123 | 12 | 3 | 0 | 2 | 1 | 1491 | 1196 | 1199 | -295 | 10 | 2 | 178 | 3 | 500000 | 0 | 341999 | 0 |  | 1 | 3000 | 5 | 37 | 45.9
1014 | 20250331 | 62 | 7 | 5 | 14 | 26 | 6 | 3 | 6 | Active | Initiate & Design | Amber | 0.25 | 0.1134 | 206728 | 48581 | 22174 | 241872 | 25138 | 1269 | 0.482 | 1.057 | 20260930 | 20270228 | 144 | 12 | 3 | 1 | 2 | 1 | 1582 | 1294 | 1272 | -288 | 10 | 2 | 178 | 3 | 500000 | 0 | 343551 | 0 |  | 1 | 2000 | 7 | 46 | 49.9
1015 | 20250430 | 62 | 7 | 5 | 14 | 26 | 6 | 3 | 6 | Active | Initiate & Design | Red | 0.2917 | 0.1319 | 206728 | 56879 | 26396 | 243594 | 29612 | 871 | 0.479 | 1.033 | 20260930 | 20270331 | 169 | 12 | 4 | 1 | 3 | 2 | 1662 | 1346 | 1395 | -316 | 12 | 3 | 225 | 4 | 500000 | 0 | 352304 | 0 |  | 1 | 3000 | 8 | 36 | 41.3
1016 | 20250531 | 62 | 7 | 5 | 14 | 26 | 6 | 3 | 6 | Active | Initiate & Design | Red | 0.3333 | 0.1571 | 206728 | 65234 | 32234 | 245317 | 32757 | 243 | 0.498 | 1.008 | 20260930 | 20270331 | 186 | 12 | 4 | 1 | 3 | 2 | 1729 | 1515 | 1523 | -214 | 12 | 3 | 225 | 4 | 500000 | 0 | 361638 | 0 |  | 1 | 2000 | 7 | 36 | 43.2
1017 | 20250630 | 62 | 7 | 5 | 14 | 26 | 6 | 3 | 6 | Active | Initiate & Design | Amber | 0.375 | 0.209 | 206728 | 73647 | 42658 | 247040 | 30441 | 548 | 0.587 | 1.013 | 20260930 | 20270331 | 176 | 12 | 5 | 1 | 3 | 2 | 1783 | 1360 | 1333 | -423 | 12 | 2 | 207 | 4 | 500000 | 0 | 343140 | 0 |  | 1 | 3000 | 5 | 41 | 51.8
1018 | 20250731 | 62 | 7 | 5 | 14 | 26 | 6 | 3 | 6 | Active | Initiate & Design | Amber | 0.4167 | 0.2482 | 206728 | 82117 | 51853 | 249237 | 30807 | -543 | 0.625 | 0.99 | 20260930 | 20270331 | 178 | 12 | 5 | 2 | 3 | 2 | 1822 | 1419 | 1355 | -403 | 9 | 2 | 164 | 3 | 500000 | 0 | 340036 | 0 |  | 1 | 2000 | 8 | 42 | 52.9
1019 | 20250831 | 62 | 7 | 5 | 14 | 26 | 6 | 3 | 6 | Active | Initiate & Design | Red | 0.4583 | 0.2938 | 206728 | 90644 | 64424 | 253092 | 29907 | -3687 | 0.67 | 0.943 | 20260930 | 20270331 | 173 | 12 | 6 | 2 | 4 | 2 | 1845 | 1463 | 1438 | -382 | 11 | 3 | 211 | 4 | 500000 | 0 | 359143 | 0 |  | 2 | 5000 | 6 | 41 | 46.7
1020 | 20250930 | 62 | 7 | 5 | 14 | 26 | 6 | 3 | 6 | Active | Initiate & Design | Amber | 0.5 | 0.3294 | 206728 | 99229 | 70505 | 253760 | 31133 | -2409 | 0.686 | 0.966 | 20260930 | 20270331 | 181 | 12 | 6 | 2 | 3 | 2 | 1853 | 1611 | 1652 | -242 | 10 | 2 | 178 | 3 | 500000 | 0 | 339179 | 0 |  | 2 | 4000 | 5 | 51 | 56.8
1021 | 20251031 | 62 | 7 | 5 | 14 | 26 | 6 | 3 | 6 | Active | Deliver | Amber | 0.5417 | 0.3521 | 206728 | 107872 | 78475 | 257229 | 35083 | -5686 | 0.675 | 0.927 | 20260930 | 20270430 | 201 | 12 | 7 | 2 | 4 | 2 | 1845 | 1430 | 1500 | -415 | 11 | 2 | 193 | 4 | 500000 | 0 | 355527 | 0 |  | 2 | 5000 | 7 | 46 | 53.8
1022 | 20251130 | 62 | 7 | 5 | 14 | 26 | 6 | 3 | 6 | Active | Deliver | Amber | 0.5833 | 0.3802 | 206728 | 116572 | 85053 | 259106 | 37974 | -6455 | 0.674 | 0.924 | 20260930 | 20270430 | 214 | 12 | 7 | 2 | 4 | 2 | 1822 | 1521 | 1478 | -301 | 11 | 2 | 193 | 4 | 500000 | 0 | 350294 | 0 |  | 2 | 5000 | 5 | 42 | 54.7
1023 | 20251231 | 62 | 7 | 5 | 14 | 26 | 6 | 3 | 6 | Active | Deliver | Red | 0.625 | 0.393 | 206728 | 125329 | 88961 | 261324 | 44085 | -7717 | 0.648 | 0.913 | 20260930 | 20270531 | 245 | 12 | 8 | 2 | 5 | 3 | 1783 | 1540 | 1567 | -243 | 11 | 3 | 211 | 4 | 500000 | 0 | 338777 | 0 |  | 2 | 6000 | 7 | 37 | 45.1
1024 | 20260131 | 62 | 7 | 5 | 14 | 26 | 6 | 3 | 6 | Active | Deliver | Amber | 0.6667 | 0.4267 | 206728 | 134144 | 99017 | 264059 | 45933 | -10806 | 0.658 | 0.891 | 20260930 | 20270531 | 254 | 12 | 8 | 2 | 5 | 3 | 1729 | 1344 | 1335 | -385 | 10 | 2 | 178 | 3 | 500000 | 0 | 361069 | 0 |  | 2 | 5000 | 5 | 47 | 52.1
1025 | 20260228 | 62 | 7 | 5 | 14 | 26 | 6 | 3 | 6 | Active | Deliver | Amber | 0.7083 | 0.4552 | 206728 | 143016 | 107145 | 266356 | 48913 | -13042 | 0.658 | 0.878 | 20260930 | 20270630 | 267 | 12 | 9 | 4 | 5 | 3 | 1662 | 1337 | 1324 | -325 | 9 | 2 | 164 | 3 | 500000 | 0 | 356431 | 0 |  | 3 | 8000 | 5 | 47 | 52
1026 | 20260331 | 62 | 7 | 5 | 14 | 26 | 6 | 3 | 6 | Paused | Deliver | Red | 0.75 | 0.4939 | 206728 | 151945 | 115139 | 267694 | 49842 | -13036 | 0.672 | 0.887 | 20260930 | 20270630 | 270 | 12 | 9 | 4 | 5 | 3 | 1582 | 1210 | 1262 | -372 | 10 | 3 | 196 | 3 | 500000 | 53571 | 351009 | 0 | 0 | 3 | 8000 | 7 | 36 | 43.8
1027 | 20260430 | 62 | 7 | 5 | 14 | 26 | 6 | 3 | 6 | Paused | Deliver | Amber | 0.7917 | 0.5393 | 206728 | 160932 | 127418 | 269953 | 49444 | -15930 | 0.693 | 0.875 | 20260930 | 20270630 | 267 | 12 | 10 | 3 | 6 | 3 | 1491 | 1157 | 1167 | -334 | 10 | 2 | 178 | 3 | 500000 | 127976 | 341900 | 12578 | 0.0983 | 3 | 7000 | 8 | 45 | 52
1028 | 20260531 | 62 | 7 | 5 | 14 | 26 | 6 | 3 | 6 | Paused | Deliver | Amber | 0.8333 | 0.5841 | 206728 | 169976 | 140744 | 272450 | 49226 | -19994 | 0.71 | 0.858 | 20260930 | 20270630 | 263 | 12 | 10 | 4 | 5 | 3 | 1390 | 1201 | 1189 | -189 | 10 | 2 | 178 | 3 | 500000 | 202381 | 339246 | 58971 | 0.2914 | 3 | 8000 | 5 | 48 | 54
1029 | 20260630 | 62 | 7 | 5 | 14 | 26 | 6 | 3 | 6 | Paused | Deliver | Amber | 0.875 | 0.6206 | 206728 | 179078 | 150953 | 274539 | 50783 | -22658 | 0.716 | 0.85 | 20260930 | 20270630 | 269 | 12 | 11 | 4 | 6 | 3 | 1281 | 1034 | 1052 | -247 | 9 | 2 | 164 | 3 | 500000 | 276786 | 349227 | 101446 | 0.3665 | 3 | 9000 | 4 | 44 | 53.3
1030 | 20260731 | 62 | 7 | 5 | 14 | 26 | 6 | 3 | 6 | Paused | Deliver | Amber | 0.9167 | 0.6602 | 206728 | 188237 | 164123 | 277096 | 51755 | -27641 | 0.725 | 0.832 | 20260930 | 20270630 | 272 | 12 | 11 | 4 | 6 | 3 | 1167 | 906 | 917 | -261 | 8 | 2 | 150 | 3 | 500000 | 351190 | 345738 | 146998 | 0.4186 | 4 | 9000 | 3 | 47 | 52.2
1031 | 20260831 | 62 | 7 | 5 | 14 | 26 | 6 | 3 | 6 | Terminated | Deliver | Amber | 0.9583 | 0.6733 | 206728 | 197454 | 168251 | 279014 | 58264 | -29061 | 0.705 | 0.827 | 20260930 | 20270731 | 301 | 12 | 12 | 5 | 6 | 3 | 1048 | 824 | 864 | -224 | 7 | 1 | 118 | 2 | 500000 | 425595 | 348052 | 182412 | 0.4286 | 4 | 13000 | 4 | 49 | 59.5
1032 | 20241031 | 63 | 2 | 4 | 15 | 27 | 7 | 1 | 7 | Active | Initiate & Design | Green | 0.0833 | 0.0855 | 385315 | 29755 | 30213 | 411645 | -3189 | 2731 | 1.107 | 1.09 | 20250930 | 20250930 | 0 | 6 | 1 | 1 | 0 | 0 | 2174 | 2178 | 2194 | 4 | 7 | 1 | 106 | 2 | 500000 | 0 | 445690 | 0 |  | 0 | 0 | 6 | 88 | 96.9
1033 | 20241130 | 63 | 2 | 4 | 15 | 27 | 7 | 1 | 7 | Active | Initiate & Design | Green | 0.1667 | 0.15 | 385315 | 59938 | 51674 | 414856 | 2141 | 6123 | 0.964 | 1.119 | 20250930 | 20250930 | 8 | 6 | 1 | 1 | 0 | 0 | 2591 | 2616 | 2670 | 25 | 8 | 1 | 119 | 2 | 500000 | 0 | 442424 | 0 |  | 0 | 0 | 6 | 79 | 91.3
1034 | 20241231 | 63 | 2 | 4 | 15 | 27 | 7 | 1 | 7 | Active | Initiate & Design | Green | 0.25 | 0.2272 | 385315 | 90549 | 82754 | 418067 | 3005 | 4790 | 0.967 | 1.058 | 20250930 | 20250930 | 11 | 6 | 2 | 1 | 0 | 0 | 2949 | 2831 | 2779 | -118 | 8 | 1 | 119 | 2 | 500000 | 0 | 441870 | 0 |  | 0 | 0 | 6 | 81 | 88.4
1035 | 20250131 | 63 | 2 | 4 | 15 | 27 | 7 | 1 | 7 | Active | Initiate & Design | Green | 0.3333 | 0.2962 | 385315 | 121588 | 112288 | 421278 | 7458 | 1842 | 0.939 | 1.016 | 20250930 | 20251031 | 18 | 6 | 2 | 1 | 0 | 0 | 3223 | 2916 | 2945 | -307 | 8 | 1 | 119 | 2 | 500000 | 0 | 442572 | 0 |  | 0 | 0 | 4 | 75 | 84.5
1036 | 20250228 | 63 | 2 | 4 | 15 | 27 | 7 | 1 | 7 | Active | Deliver | Green | 0.4167 | 0.3635 | 385315 | 153056 | 137410 | 424489 | 12994 | 2652 | 0.915 | 1.019 | 20250930 | 20251031 | 26 | 6 | 3 | 1 | 1 | 0 | 3396 | 3213 | 3299 | -183 | 8 | 1 | 119 | 2 | 500000 | 0 | 458134 | 0 |  | 0 | 0 | 5 | 73 | 85.3
1037 | 20250331 | 63 | 2 | 4 | 15 | 27 | 7 | 1 | 7 | Active | Deliver | Green | 0.5 | 0.451 | 385315 | 184951 | 173607 | 427700 | 11174 | 170 | 0.94 | 1.001 | 20250930 | 20251031 | 24 | 6 | 3 | 2 | 0 | 0 | 3455 | 3370 | 3371 | -85 | 6 | 1 | 94 | 2 | 500000 | 0 | 457829 | 0 |  | 1 | 4000 | 6 | 78 | 86.4
1038 | 20250430 | 63 | 2 | 4 | 15 | 27 | 7 | 1 | 7 | Active | Deliver | Green | 0.5833 | 0.5318 | 385315 | 217275 | 212725 | 434020 | 12364 | -7814 | 0.943 | 0.963 | 20250930 | 20251031 | 26 | 6 | 4 | 3 | 1 | 0 | 3396 | 3156 | 3262 | -240 | 6 | 1 | 94 | 2 | 500000 | 0 | 440200 | 0 |  | 1 | 5000 | 3 | 71 | 83.3
1039 | 20250531 | 63 | 2 | 4 | 15 | 27 | 7 | 1 | 7 | Active | Deliver | Green | 0.6667 | 0.6058 | 385315 | 250027 | 244298 | 437899 | 16603 | -10874 | 0.934 | 0.955 | 20250930 | 20251031 | 30 | 6 | 4 | 2 | 1 | 0 | 3223 | 3102 | 2998 | -121 | 9 | 1 | 132 | 3 | 500000 | 0 | 455674 | 0 |  | 1 | 6000 | 4 | 69 | 84.1
1040 | 20250630 | 63 | 2 | 4 | 15 | 27 | 7 | 1 | 7 | Active | Deliver | Green | 0.75 | 0.6942 | 385315 | 283207 | 287326 | 443185 | 15721 | -19840 | 0.944 | 0.931 | 20250930 | 20251031 | 27 | 6 | 5 | 3 | 1 | 0 | 2949 | 2869 | 2759 | -80 | 7 | 1 | 106 | 2 | 500000 | 53571 | 444385 | 0 | 0 | 1 | 4000 | 4 | 72 | 83.4
1041 | 20250731 | 63 | 2 | 4 | 15 | 27 | 7 | 1 | 7 | Active | Deploy | Green | 0.8333 | 0.787 | 385315 | 316815 | 327836 | 446900 | 13572 | -24593 | 0.957 | 0.925 | 20250930 | 20251031 | 23 | 6 | 5 | 3 | 1 | 0 | 2591 | 2493 | 2430 | -98 | 4 | 1 | 69 | 1 | 500000 | 202381 | 447914 | 74383 | 0.3675 | 1 | 4000 | 4 | 76 | 83.7
1042 | 20250831 | 63 | 2 | 4 | 15 | 27 | 7 | 1 | 7 | Active | Deploy | Green | 0.9167 | 0.8596 | 385315 | 350851 | 367761 | 452179 | 19634 | -36544 | 0.944 | 0.901 | 20250930 | 20251031 | 28 | 6 | 6 | 4 | 1 | 0 | 2174 | 2013 | 1915 | -161 | 6 | 1 | 94 | 2 | 500000 | 351190 | 446891 | 191041 | 0.544 | 1 | 4000 | 4 | 71 | 81.4
1043 | 20250930 | 63 | 2 | 4 | 15 | 27 | 7 | 1 | 7 | Active | Deploy | Green | 1 | 0.9565 | 385315 | 385315 | 412144 | 455931 | 16761 | -43590 | 0.957 | 0.894 | 20250930 | 20251031 | 22 | 6 | 6 | 4 | 1 | 0 | 1727 | 1702 | 1762 | -25 | 5 | 1 | 81 | 1 | 500000 | 500000 | 459373 | 316352 | 0.6327 | 1 | 3000 | 3 | 71 | 83.7
1044 | 20251031 | 63 | 2 | 4 | 15 | 27 | 7 | 1 | 7 | Active | Deploy | Green | 1 | 0.9565 | 385315 | 385315 | 420909 | 460720 | 16761 | -52355 | 0.957 | 0.876 | 20250930 | 20251031 | 22 | 6 | 6 | 4 | 1 | 0 | 1727 | 1677 | 1745 | -50 | 4 | 1 | 69 | 1 | 500000 | 500000 | 448125 | 397784 | 0.7956 | 2 | 8000 | 2 | 72 | 82.1
1045 | 20251130 | 63 | 2 | 4 | 15 | 27 | 7 | 1 | 7 | Active | Deploy | Green | 1 | 0.9565 | 385315 | 385315 | 425588 | 464747 | 16761 | -57034 | 0.957 | 0.866 | 20250930 | 20251031 | 22 | 6 | 6 | 5 | 1 | 0 | 1727 | 1596 | 1621 | -131 | 5 | 0 | 63 | 1 | 500000 | 500000 | 458713 | 423771 | 0.8475 | 3 | 12000 | 3 | 78 | 89.4
1046 | 20251231 | 63 | 2 | 4 | 15 | 27 | 7 | 1 | 7 | Active | Deploy | Green | 1 | 0.9565 | 385315 | 385315 | 433048 | 469223 | 16761 | -64494 | 0.957 | 0.851 | 20250930 | 20251031 | 22 | 6 | 6 | 5 | 1 | 0 | 1727 | 1612 | 1624 | -115 | 6 | 1 | 94 | 2 | 500000 | 500000 | 448849 | 401947 | 0.8039 | 3 | 10000 | 2 | 70 | 80.5
1047 | 20260131 | 63 | 2 | 4 | 15 | 27 | 7 | 1 | 7 | Active | Deploy | Green | 1 | 0.9565 | 385315 | 385315 | 443248 | 474094 | 16761 | -74694 | 0.957 | 0.831 | 20250930 | 20251031 | 22 | 6 | 6 | 5 | 1 | 0 | 1727 | 1578 | 1658 | -149 | 6 | 1 | 94 | 2 | 500000 | 500000 | 449188 | 395206 | 0.7904 | 3 | 18000 | 4 | 66 | 79.4
1048 | 20260228 | 63 | 2 | 4 | 15 | 27 | 7 | 1 | 7 | Active | Deploy | Green | 1 | 0.9565 | 385315 | 385315 | 444622 | 474954 | 16761 | -76068 | 0.957 | 0.829 | 20250930 | 20251031 | 22 | 6 | 6 | 4 | 1 | 0 | 1727 | 1726 | 1743 | -1 | 6 | 1 | 94 | 2 | 500000 | 500000 | 445348 | 403791 | 0.8076 | 3 | 16000 | 2 | 70 | 81
1049 | 20260331 | 63 | 2 | 4 | 15 | 27 | 7 | 1 | 7 | Active | Deploy | Green | 1 | 0.9565 | 385315 | 385315 | 446327 | 475222 | 16761 | -77773 | 0.957 | 0.826 | 20250930 | 20251031 | 22 | 6 | 6 | 4 | 1 | 0 | 1727 | 1657 | 1743 | -70 | 6 | 1 | 94 | 2 | 500000 | 500000 | 455832 | 415037 | 0.8301 | 3 | 11000 | 4 | 68 | 80.6
1050 | 20260430 | 63 | 2 | 4 | 15 | 27 | 7 | 1 | 7 | Active | Deploy | Green | 1 | 0.9565 | 385315 | 385315 | 446327 | 475222 | 16761 | -77773 | 0.957 | 0.826 | 20250930 | 20251031 | 22 | 6 | 6 | 4 | 1 | 0 | 1727 | 1632 | 1574 | -95 | 4 | 1 | 69 | 1 | 500000 | 500000 | 449752 | 419083 | 0.8382 | 3 | 13000 | 2 | 67 | 79.9
1051 | 20260531 | 63 | 2 | 4 | 15 | 27 | 7 | 1 | 7 | Active | Deploy | Green | 1 | 0.9565 | 385315 | 385315 | 446327 | 475222 | 16761 | -77773 | 0.957 | 0.826 | 20250930 | 20251031 | 22 | 6 | 6 | 5 | 1 | 0 | 1727 | 1545 | 1590 | -182 | 4 | 1 | 69 | 1 | 500000 | 500000 | 443851 | 407953 | 0.8159 | 3 | 17000 | 3 | 71 | 78.5
1052 | 20260630 | 63 | 2 | 4 | 15 | 27 | 7 | 1 | 7 | Active | Deploy | Green | 1 | 0.9565 | 385315 | 385315 | 446327 | 475222 | 16761 | -77773 | 0.957 | 0.826 | 20250930 | 20251031 | 22 | 6 | 6 | 4 | 1 | 0 | 1727 | 1703 | 1684 | -24 | 6 | 1 | 94 | 2 | 500000 | 500000 | 446813 | 434503 | 0.869 | 3 | 13000 | 4 | 69 | 80.7
1053 | 20260731 | 63 | 2 | 4 | 15 | 27 | 7 | 1 | 7 | Active | Deploy | Green | 1 | 0.9565 | 385315 | 385315 | 446327 | 475222 | 16761 | -77773 | 0.957 | 0.826 | 20250930 | 20251031 | 22 | 6 | 6 | 5 | 1 | 0 | 1727 | 1601 | 1651 | -126 | 6 | 1 | 94 | 2 | 500000 | 500000 | 462393 | 405676 | 0.8114 | 3 | 11000 | 2 | 72 | 80.2
1054 | 20231031 | 64 | 7 | 5 | 16 | 28 | 8 | 1 | 8 | Completed | Completed | Green | 1 | 1 | 607453 | 607453 | 650689 | 650689 | 0 | -43236 | 1 | 0.934 | 20230430 | 20230430 | 0 | 6 | 6 | 5 | 0 | 0 | 2723 | 2698 | 2694 | -25 | 2 | 0 | 19 | 0 | 1600000 | 1600000 | 1616880 | 1606449 | 1.004 | 0 | 0 | 0 | 80 | 97.5
1055 | 20231031 | 65 | 10 | 7 | 17 | 29 | 1 | 2 | 1 | Active | Deliver | Green | 0.6 | 0.6918 | 1433336 | 832482 | 978525 | 1484936 | -159100 | 13057 | 1.191 | 1.013 | 20240430 | 20240430 | 0 | 8 | 5 | 4 | 0 | 0 | 12536 | 13028 | 12314 | 492 | 2 | 0 | 18 | 0 | 3400000 | 0 | 3620646 | 0 |  | 1 | 17000 | 3 | 89 | 100
1056 | 20231130 | 65 | 10 | 7 | 17 | 29 | 1 | 2 | 1 | Active | Deploy | Green | 0.6667 | 0.7523 | 1433336 | 930076 | 1081047 | 1488619 | -148223 | -2748 | 1.159 | 0.997 | 20240430 | 20240430 | 0 | 8 | 5 | 5 | 0 | 0 | 11990 | 12955 | 13097 | 965 | 2 | 0 | 18 | 0 | 3400000 | 0 | 3693496 | 0 |  | 1 | 14000 | 3 | 91 | 100
1057 | 20231231 | 65 | 10 | 7 | 17 | 29 | 1 | 2 | 1 | Active | Deploy | Green | 0.7333 | 0.8113 | 1433336 | 1028689 | 1167085 | 1491805 | -134176 | -4220 | 1.13 | 0.996 | 20240430 | 20240430 | 0 | 8 | 6 | 5 | 0 | 0 | 11200 | 11570 | 11753 | 370 | 3 | 0 | 27 | 0 | 3400000 | 161905 | 3597209 | 0 | 0 | 1 | 23000 | 1 | 88 | 100
1058 | 20240131 | 65 | 10 | 7 | 17 | 29 | 1 | 2 | 1 | Active | Deploy | Green | 0.8 | 0.8681 | 1433336 | 1128322 | 1277725 | 1501798 | -115957 | -33446 | 1.103 | 0.974 | 20240430 | 20240430 | 0 | 8 | 6 | 5 | 0 | 0 | 10202 | 11347 | 11220 | 1145 | 3 | 0 | 27 | 0 | 3400000 | 971429 | 3653382 | 241691 | 0.2488 | 1 | 17000 | 4 | 87 | 100
1059 | 20240229 | 65 | 10 | 7 | 17 | 29 | 1 | 2 | 1 | Active | Deploy | Green | 0.8667 | 0.9351 | 1433336 | 1228974 | 1384513 | 1506470 | -111338 | -44201 | 1.091 | 0.968 | 20240430 | 20240430 | 0 | 8 | 7 | 7 | 0 | 0 | 9039 | 10276 | 10080 | 1237 | 0 | 0 | 0 | 0 | 3400000 | 1780952 | 3738130 | 1079817 | 0.6063 | 1 | 12000 | 3 | 87 | 100
1060 | 20240331 | 65 | 10 | 7 | 17 | 29 | 1 | 2 | 1 | Completed | Completed | Green | 0.9333 | 1 | 1433336 | 1330645 | 1492812 | 1511833 | -102691 | -59476 | 1.077 | 0.96 | 20240430 | 20240430 | 0 | 8 | 7 | 6 | 0 | 0 | 7761 | 8594 | 8311 | 833 | 0 | 0 | 0 | 0 | 3400000 | 2590476 | 3675982 | 1807270 | 0.6977 | 1 | 18000 | 1 | 87 | 100
1061 | 20251031 | 66 | 10 | 7 | 18 | 30 | 2 | 3 | 2 | Active | Initiate & Design | Amber | 0.0476 | 0.0135 | 350385 | 15414 | 4110 | 361731 | 10684 | 620 | 0.307 | 1.153 | 20270630 | 20270731 | 27 | 11 | 1 | 0 | 1 | 0 | 1805 | 1372 | 1321 | -433 | 9 | 2 | 143 | 2 | 500000 | 0 | 462053 | 0 |  | 0 | 0 | 5 | 49 | 50.8
1062 | 20251130 | 66 | 10 | 7 | 18 | 30 | 2 | 3 | 2 | Active | Initiate & Design | Green | 0.0952 | 0.0436 | 350385 | 30955 | 11863 | 362565 | 15678 | 3414 | 0.494 | 1.289 | 20270630 | 20270731 | 43 | 11 | 1 | 0 | 1 | 0 | 2034 | 1647 | 1706 | -387 | 7 | 1 | 101 | 2 | 500000 | 0 | 467861 | 0 |  | 0 | 0 | 5 | 66 | 73.4
1063 | 20251231 | 66 | 10 | 7 | 18 | 30 | 2 | 3 | 2 | Active | Initiate & Design | Amber | 0.1429 | 0.0568 | 350385 | 46623 | 15812 | 363399 | 26721 | 4090 | 0.427 | 1.258 | 20270630 | 20270831 | 70 | 11 | 2 | 0 | 1 | 0 | 2252 | 1638 | 1574 | -614 | 10 | 1 | 136 | 3 | 500000 | 0 | 461483 | 0 |  | 0 | 0 | 4 | 61 | 67.1
1064 | 20260131 | 66 | 10 | 7 | 18 | 30 | 2 | 3 | 2 | Active | Initiate & Design | Green | 0.1905 | 0.1177 | 350385 | 62418 | 38787 | 364234 | 21178 | 2453 | 0.66 | 1.063 | 20270630 | 20270831 | 59 | 11 | 2 | 0 | 1 | 0 | 2455 | 1890 | 1967 | -565 | 7 | 1 | 101 | 2 | 500000 | 0 | 461189 | 0 |  | 0 | 0 | 6 | 68 | 71.7
1065 | 20260228 | 66 | 10 | 7 | 18 | 30 | 2 | 3 | 2 | Active | Initiate & Design | Green | 0.2381 | 0.1489 | 350385 | 78340 | 48735 | 365068 | 26168 | 3437 | 0.666 | 1.07 | 20270630 | 20270831 | 72 | 11 | 3 | 0 | 2 | 1 | 2639 | 2005 | 1988 | -634 | 7 | 0 | 83 | 2 | 500000 | 0 | 472964 | 0 |  | 0 | 0 | 4 | 70 | 80.6
1066 | 20260331 | 66 | 10 | 7 | 18 | 30 | 2 | 3 | 2 | Active | Initiate & Design | Green | 0.2857 | 0.2095 | 350385 | 94389 | 68813 | 365902 | 20983 | 4593 | 0.778 | 1.067 | 20270630 | 20270831 | 62 | 11 | 3 | 1 | 1 | 0 | 2799 | 2308 | 2346 | -491 | 7 | 0 | 83 | 2 | 500000 | 0 | 465896 | 0 |  | 0 | 0 | 5 | 74 | 86.6
1067 | 20260430 | 66 | 10 | 7 | 18 | 30 | 2 | 3 | 2 | Active | Initiate & Design | Green | 0.3333 | 0.2604 | 350385 | 110566 | 85535 | 366736 | 19326 | 5705 | 0.825 | 1.067 | 20270630 | 20270831 | 59 | 11 | 4 | 2 | 1 | 0 | 2931 | 2279 | 2228 | -652 | 6 | 1 | 89 | 2 | 500000 | 0 | 463288 | 0 |  | 0 | 0 | 4 | 73 | 79.5
1068 | 20260531 | 66 | 10 | 7 | 18 | 30 | 2 | 3 | 2 | Active | Initiate & Design | Green | 0.381 | 0.3049 | 350385 | 126870 | 101847 | 367571 | 20038 | 4985 | 0.842 | 1.049 | 20270630 | 20270831 | 62 | 11 | 4 | 3 | 1 | 0 | 3033 | 2334 | 2436 | -699 | 8 | 1 | 113 | 2 | 500000 | 0 | 478429 | 0 |  | 1 | 3000 | 3 | 74 | 80.3
1069 | 20260630 | 66 | 10 | 7 | 18 | 30 | 2 | 3 | 2 | Active | Deliver | Green | 0.4286 | 0.3517 | 350385 | 143300 | 118383 | 368405 | 20070 | 4847 | 0.86 | 1.041 | 20270630 | 20270831 | 62 | 11 | 5 | 3 | 1 | 0 | 3102 | 2508 | 2616 | -594 | 8 | 1 | 113 | 2 | 500000 | 0 | 472154 | 0 |  | 1 | 4000 | 6 | 68 | 81.4
1070 | 20260731 | 66 | 10 | 7 | 18 | 30 | 2 | 3 | 2 | Active | Deliver | Green | 0.4762 | 0.3795 | 350385 | 159858 | 129782 | 369239 | 26887 | 3189 | 0.832 | 1.025 | 20270630 | 20270930 | 79 | 11 | 5 | 3 | 2 | 1 | 3137 | 2612 | 2762 | -525 | 8 | 1 | 113 | 2 | 500000 | 0 | 458977 | 0 |  | 1 | 5000 | 2 | 71 | 79.3
1071 | 20260831 | 66 | 10 | 7 | 18 | 30 | 2 | 3 | 2 | Active | Deliver | Green | 0.5238 | 0.4061 | 350385 | 176543 | 139104 | 370073 | 34252 | 3187 | 0.806 | 1.023 | 20270630 | 20270930 | 95 | 11 | 6 | 3 | 2 | 1 | 3137 | 2609 | 2475 | -528 | 7 | 1 | 101 | 2 | 500000 | 0 | 481933 | 0 |  | 1 | 5000 | 4 | 68 | 79.4
1072 | 20260930 | 66 | 10 | 7 | 18 | 30 | 2 | 3 | 2 | Active | Deliver | Green | 0.5714 | 0.4499 | 350385 | 193355 | 157347 | 370908 | 35717 | 291 | 0.815 | 1.002 | 20270630 | 20270930 | 99 | 11 | 6 | 3 | 2 | 1 | 3102 | 2437 | 2448 | -665 | 7 | 1 | 101 | 2 | 500000 | 0 | 469284 | 0 |  | 1 | 4000 | 3 | 70 | 77.3
1073 | 20240630 | 67 | 5 | 5 | 19 | 31 | 3 | 3 | 3 | Active | Initiate & Design | Red | 0.0667 | 0.0114 | 617135 | 38070 | 9117 | 676708 | 31035 | -2082 | 0.185 | 0.773 | 20250831 | 20250930 | 33 | 8 | 1 | 0 | 1 | 0 | 3342 | 3104 | 2928 | -238 | 11 | 2 | 170 | 3 | 600000 | 0 | 567433 | 0 |  | 1 | 9000 | 5 | 29 | 36.3
1074 | 20240731 | 67 | 5 | 5 | 19 | 31 | 3 | 3 | 3 | Active | Initiate & Design | Green | 0.1333 | 0.0812 | 617135 | 76580 | 43211 | 648815 | 26469 | 6900 | 0.655 | 1.16 | 20250831 | 20250930 | 30 | 8 | 1 | 0 | 1 | 0 | 3892 | 3658 | 3456 | -234 | 9 | 2 | 145 | 2 | 600000 | 0 | 565362 | 0 |  | 1 | 8000 | 6 | 60 | 71.1
1075 | 20240831 | 67 | 5 | 5 | 19 | 31 | 3 | 3 | 3 | Active | Initiate & Design | Green | 0.2 | 0.142 | 617135 | 115528 | 78118 | 651695 | 27895 | 9515 | 0.759 | 1.122 | 20250831 | 20250930 | 34 | 8 | 2 | 0 | 1 | 0 | 4393 | 3898 | 4056 | -495 | 9 | 1 | 127 | 2 | 600000 | 0 | 564441 | 0 |  | 1 | 7000 | 5 | 67 | 81.3
1076 | 20240930 | 67 | 5 | 5 | 19 | 31 | 3 | 3 | 3 | Active | Initiate & Design | Green | 0.2667 | 0.2121 | 617135 | 154915 | 123105 | 654575 | 24021 | 7789 | 0.845 | 1.063 | 20250831 | 20250930 | 33 | 8 | 2 | 1 | 1 | 0 | 4822 | 4571 | 4454 | -251 | 8 | 2 | 133 | 2 | 600000 | 0 | 589241 | 0 |  | 1 | 9000 | 3 | 70 | 77.6
1077 | 20241031 | 67 | 5 | 5 | 19 | 31 | 3 | 3 | 3 | Active | Initiate & Design | Green | 0.3333 | 0.271 | 617135 | 194740 | 164113 | 657454 | 27496 | 3131 | 0.859 | 1.019 | 20250831 | 20250930 | 37 | 8 | 3 | 1 | 1 | 0 | 5162 | 4574 | 4533 | -588 | 7 | 1 | 103 | 2 | 600000 | 0 | 589321 | 0 |  | 1 | 8000 | 3 | 67 | 83.3
1078 | 20241130 | 67 | 5 | 5 | 19 | 31 | 3 | 3 | 3 | Active | Initiate & Design | Green | 0.4 | 0.3417 | 617135 | 235005 | 206044 | 660334 | 24130 | 4831 | 0.897 | 1.024 | 20250831 | 20250930 | 34 | 8 | 3 | 2 | 1 | 0 | 5398 | 5142 | 5409 | -256 | 8 | 1 | 115 | 2 | 600000 | 0 | 566371 | 0 |  | 1 | 10000 | 5 | 69 | 85.6
1079 | 20241231 | 67 | 5 | 5 | 19 | 31 | 3 | 3 | 3 | Active | Deliver | Green | 0.4667 | 0.4062 | 617135 | 275708 | 250380 | 663214 | 25028 | 300 | 0.909 | 1.001 | 20250831 | 20250930 | 35 | 8 | 4 | 2 | 1 | 0 | 5518 | 5296 | 5466 | -222 | 7 | 1 | 103 | 2 | 600000 | 0 | 573645 | 0 |  | 1 | 7000 | 6 | 70 | 85.9
1080 | 20250131 | 67 | 5 | 5 | 19 | 31 | 3 | 3 | 3 | Active | Deliver | Green | 0.5333 | 0.4605 | 617135 | 316851 | 282922 | 666094 | 32660 | 1269 | 0.897 | 1.005 | 20250831 | 20250930 | 43 | 8 | 4 | 2 | 1 | 0 | 5518 | 4748 | 4913 | -770 | 6 | 1 | 91 | 2 | 600000 | 0 | 578161 | 0 |  | 1 | 8000 | 5 | 71 | 83.4
1081 | 20250228 | 67 | 5 | 5 | 19 | 31 | 3 | 3 | 3 | Active | Deliver | Green | 0.6 | 0.5215 | 617135 | 358432 | 323886 | 669842 | 36596 | -2050 | 0.898 | 0.994 | 20250831 | 20251031 | 46 | 8 | 5 | 3 | 1 | 0 | 5398 | 5054 | 5245 | -344 | 7 | 1 | 103 | 2 | 600000 | 0 | 563258 | 0 |  | 2 | 10000 | 4 | 76 | 84.1
1082 | 20250331 | 67 | 5 | 5 | 19 | 31 | 3 | 3 | 3 | Active | Deliver | Green | 0.6667 | 0.5698 | 617135 | 400452 | 356633 | 673757 | 48808 | -4989 | 0.878 | 0.986 | 20250831 | 20250930 | 23 | 8 | 5 | 3 | 1 | 0 | 5162 | 4706 | 4950 | -456 | 8 | 1 | 115 | 2 | 600000 | 0 | 581557 | 0 |  | 2 | 14000 | 6 | 68 | 83.2
1083 | 20250430 | 67 | 5 | 5 | 19 | 31 | 3 | 3 | 3 | Active | Deliver | Green | 0.7333 | 0.648 | 617135 | 442911 | 411927 | 678705 | 43008 | -12024 | 0.903 | 0.971 | 20250831 | 20250930 | 15 | 8 | 6 | 4 | 1 | 0 | 4822 | 4326 | 4330 | -496 | 6 | 1 | 91 | 2 | 600000 | 28571 | 569820 | 0 | 0 | 2 | 15000 | 4 | 68 | 82.9
1084 | 20250531 | 67 | 5 | 5 | 19 | 31 | 3 | 3 | 3 | Active | Deliver | Green | 0.8 | 0.7348 | 617135 | 485809 | 475521 | 683906 | 32338 | -22050 | 0.933 | 0.954 | 20250831 | 20250831 | 3 | 8 | 6 | 4 | 1 | 0 | 4393 | 4105 | 3946 | -288 | 6 | 1 | 91 | 2 | 600000 | 171429 | 576269 | 34892 | 0.2035 | 2 | 15000 | 5 | 76 | 84.8
1085 | 20250630 | 67 | 5 | 5 | 19 | 31 | 3 | 3 | 3 | Active | Deploy | Green | 0.8667 | 0.8111 | 617135 | 529145 | 530029 | 688041 | 28587 | -29471 | 0.946 | 0.944 | 20250831 | 20250831 | -2 | 8 | 7 | 5 | 1 | 0 | 3892 | 3517 | 3444 | -375 | 5 | 1 | 79 | 1 | 600000 | 314286 | 573559 | 149103 | 0.4744 | 2 | 13000 | 2 | 76 | 84.3
1086 | 20250731 | 67 | 5 | 5 | 19 | 31 | 3 | 3 | 3 | Active | Deploy | Green | 0.9333 | 0.9045 | 617135 | 572921 | 605146 | 693910 | 14722 | -46947 | 0.974 | 0.922 | 20250831 | 20250831 | -18 | 8 | 7 | 6 | 1 | 0 | 3342 | 3001 | 3059 | -341 | 6 | 0 | 73 | 2 | 600000 | 457143 | 583219 | 294062 | 0.6433 | 2 | 11000 | 3 | 80 | 93.1
1087 | 20250831 | 67 | 5 | 5 | 19 | 31 | 3 | 3 | 3 | Active | Deploy | Green | 1 | 0.9878 | 617135 | 617135 | 662736 | 697143 | 7529 | -53130 | 0.988 | 0.92 | 20250831 | 20250831 | -27 | 8 | 8 | 6 | 1 | 0 | 2766 | 2386 | 2274 | -380 | 3 | 0 | 36 | 1 | 600000 | 600000 | 567839 | 388391 | 0.6473 | 2 | 17000 | 2 | 78 | 92.1
1088 | 20250930 | 67 | 5 | 5 | 19 | 31 | 3 | 3 | 3 | Completed | Completed | Green | 1 | 1 | 617135 | 617135 | 683918 | 702392 | 0 | -66783 | 1 | 0.902 | 20250831 | 20250831 | -35 | 8 | 8 | 8 | 0 | 0 | 2766 | 2587 | 2562 | -179 | 4 | 0 | 49 | 1 | 600000 | 600000 | 571120 | 524529 | 0.8742 | 2 | 15000 | 2 | 79 | 93.8
1089 | 20231031 | 68 | 7 | 5 | 20 | 32 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.2083 | 0.2313 | 1313364 | 256288 | 283900 | 1345213 | -47493 | 19881 | 1.185 | 1.07 | 20250531 | 20250531 | 0 | 12 | 3 | 2 | 0 | 0 | 9472 | 9173 | 9806 | -299 | 4 | 0 | 41 | 1 | 1800000 | 0 | 1327596 | 0 |  | 0 | 0 | 4 | 83 | 100
1090 | 20231130 | 68 | 7 | 5 | 20 | 32 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.25 | 0.2681 | 1313364 | 308641 | 328177 | 1346855 | -43472 | 23936 | 1.141 | 1.073 | 20250531 | 20250531 | 0 | 12 | 3 | 3 | 0 | 0 | 10051 | 10477 | 10298 | 426 | 2 | 0 | 20 | 0 | 1800000 | 0 | 1365013 | 0 |  | 0 | 0 | 2 | 83 | 100
1091 | 20231231 | 68 | 7 | 5 | 20 | 32 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.2917 | 0.3226 | 1313364 | 361358 | 397908 | 1348496 | -62333 | 25783 | 1.172 | 1.065 | 20250531 | 20250531 | 0 | 12 | 4 | 4 | 0 | 0 | 10558 | 10556 | 11269 | -2 | 2 | 0 | 20 | 0 | 1800000 | 0 | 1309586 | 0 |  | 0 | 0 | 5 | 86 | 100
1092 | 20240131 | 68 | 7 | 5 | 20 | 32 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.3333 | 0.3499 | 1313364 | 414439 | 440935 | 1350138 | -45107 | 18611 | 1.109 | 1.042 | 20250531 | 20250531 | 0 | 12 | 4 | 3 | 0 | 0 | 10986 | 11117 | 11043 | 131 | 2 | 0 | 20 | 0 | 1800000 | 0 | 1345280 | 0 |  | 0 | 0 | 5 | 82 | 99.3
1093 | 20240229 | 68 | 7 | 5 | 20 | 32 | 4 | 2 | 4 | Active | Deliver | Green | 0.375 | 0.3671 | 1313364 | 467886 | 461042 | 1351780 | -14250 | 21094 | 1.03 | 1.046 | 20250531 | 20250531 | 7 | 12 | 5 | 4 | 0 | 0 | 11327 | 11168 | 11367 | -159 | 3 | 0 | 31 | 1 | 1800000 | 0 | 1307821 | 0 |  | 0 | 0 | 2 | 75 | 95
1094 | 20240331 | 68 | 7 | 5 | 20 | 32 | 4 | 2 | 4 | Active | Deliver | Green | 0.4167 | 0.4106 | 1313364 | 521697 | 520205 | 1353422 | -17570 | 19062 | 1.034 | 1.037 | 20250531 | 20250531 | 5 | 12 | 5 | 5 | 0 | 0 | 11574 | 12194 | 12232 | 620 | 3 | 0 | 31 | 1 | 1800000 | 0 | 1345249 | 0 |  | 0 | 0 | 5 | 73 | 95.7
1095 | 20240430 | 68 | 7 | 5 | 20 | 32 | 4 | 2 | 4 | Active | Deliver | Green | 0.4583 | 0.4421 | 1313364 | 575874 | 553469 | 1355063 | -4764 | 27169 | 1.008 | 1.049 | 20250531 | 20250531 | 14 | 12 | 6 | 5 | 0 | 0 | 11725 | 12067 | 12250 | 342 | 2 | 0 | 20 | 0 | 1800000 | 0 | 1393540 | 0 |  | 0 | 0 | 2 | 75 | 95.8
1096 | 20240531 | 68 | 7 | 5 | 20 | 32 | 4 | 2 | 4 | Active | Deliver | Green | 0.5 | 0.5108 | 1313364 | 630415 | 657538 | 1356705 | -40451 | 13328 | 1.064 | 1.02 | 20250531 | 20250531 | 0 | 12 | 6 | 6 | 0 | 0 | 11775 | 12413 | 12432 | 638 | 3 | 0 | 31 | 1 | 1800000 | 0 | 1387253 | 0 |  | 1 | 12000 | 2 | 74 | 97.2
1097 | 20240630 | 68 | 7 | 5 | 20 | 32 | 4 | 2 | 4 | Active | Deliver | Green | 0.5417 | 0.555 | 1313364 | 685321 | 705053 | 1358347 | -43596 | 23864 | 1.064 | 1.034 | 20250531 | 20250531 | 0 | 12 | 7 | 6 | 0 | 0 | 11725 | 11150 | 11514 | -575 | 4 | 1 | 59 | 1 | 1800000 | 0 | 1356924 | 0 |  | 1 | 13000 | 4 | 68 | 88.1
1098 | 20240731 | 68 | 7 | 5 | 20 | 32 | 4 | 2 | 4 | Active | Deliver | Green | 0.5833 | 0.6076 | 1313364 | 740591 | 791795 | 1359988 | -57409 | 6205 | 1.077 | 1.008 | 20250531 | 20250531 | 0 | 12 | 7 | 6 | 0 | 0 | 11574 | 11489 | 11742 | -85 | 2 | 0 | 20 | 0 | 1800000 | 0 | 1373267 | 0 |  | 1 | 18000 | 3 | 78 | 97
1099 | 20240831 | 68 | 7 | 5 | 20 | 32 | 4 | 2 | 4 | Active | Deliver | Green | 0.625 | 0.6595 | 1313364 | 796227 | 862067 | 1361630 | -69937 | 4097 | 1.088 | 1.005 | 20250531 | 20250531 | 0 | 12 | 8 | 8 | 0 | 0 | 11327 | 11552 | 11594 | 225 | 5 | 0 | 51 | 1 | 1800000 | 0 | 1382303 | 0 |  | 1 | 21000 | 2 | 78 | 97.6
1100 | 20240930 | 68 | 7 | 5 | 20 | 32 | 4 | 2 | 4 | Active | Deliver | Green | 0.6667 | 0.695 | 1313364 | 852227 | 903754 | 1363272 | -60561 | 9034 | 1.071 | 1.01 | 20250531 | 20250531 | 0 | 12 | 8 | 7 | 0 | 0 | 10986 | 10620 | 10329 | -366 | 4 | 0 | 41 | 1 | 1800000 | 0 | 1386118 | 0 |  | 1 | 19000 | 3 | 76 | 96.4
1101 | 20241031 | 68 | 7 | 5 | 20 | 32 | 4 | 2 | 4 | Active | Deliver | Green | 0.7083 | 0.7315 | 1313364 | 908593 | 972871 | 1368509 | -52133 | -12145 | 1.057 | 0.988 | 20250531 | 20250531 | 0 | 12 | 9 | 8 | 0 | 0 | 10558 | 10506 | 10101 | -52 | 4 | 0 | 41 | 1 | 1800000 | 0 | 1364058 | 0 |  | 1 | 14000 | 5 | 76 | 95.3
1102 | 20241130 | 68 | 7 | 5 | 20 | 32 | 4 | 2 | 4 | Active | Deploy | Green | 0.75 | 0.7588 | 1313364 | 965323 | 1006336 | 1369358 | -31258 | -9755 | 1.032 | 0.99 | 20250531 | 20250531 | 0 | 12 | 9 | 8 | 0 | 0 | 10051 | 10547 | 11219 | 496 | 3 | 0 | 31 | 1 | 1800000 | 192857 | 1373115 | 0 | 0 | 1 | 15000 | 3 | 74 | 94.5
1103 | 20241231 | 68 | 7 | 5 | 20 | 32 | 4 | 2 | 4 | Active | Deploy | Green | 0.7917 | 0.7943 | 1313364 | 1022417 | 1067301 | 1374719 | -20788 | -24096 | 1.02 | 0.977 | 20250531 | 20250531 | 0 | 12 | 10 | 9 | 0 | 0 | 9472 | 9091 | 8997 | -381 | 4 | 1 | 59 | 1 | 1800000 | 460714 | 1311709 | 49914 | 0.1083 | 1 | 11000 | 5 | 66 | 83.6
1104 | 20250131 | 68 | 7 | 5 | 20 | 32 | 4 | 2 | 4 | Active | Deploy | Green | 0.8333 | 0.8278 | 1313364 | 1079877 | 1117767 | 1377731 | -7326 | -30564 | 1.007 | 0.973 | 20250531 | 20250531 | 5 | 12 | 10 | 10 | 0 | 0 | 8831 | 9400 | 9246 | 569 | 0 | 0 | 0 | 0 | 1800000 | 728571 | 1382930 | 216616 | 0.2973 | 1 | 14000 | 3 | 70 | 92.9
1105 | 20250228 | 68 | 7 | 5 | 20 | 32 | 4 | 2 | 4 | Active | Deploy | Green | 0.875 | 0.8784 | 1313364 | 1137702 | 1188207 | 1379878 | -15957 | -34548 | 1.014 | 0.971 | 20250531 | 20250531 | 0 | 12 | 11 | 10 | 0 | 0 | 8141 | 8520 | 8731 | 379 | 2 | 0 | 20 | 0 | 1800000 | 996429 | 1322878 | 407200 | 0.4087 | 1 | 15000 | 2 | 71 | 92.2
1106 | 20250331 | 68 | 7 | 5 | 20 | 32 | 4 | 2 | 4 | Active | Deploy | Green | 0.9167 | 0.933 | 1313364 | 1195891 | 1271238 | 1383543 | -29478 | -45869 | 1.025 | 0.964 | 20250531 | 20250531 | 0 | 12 | 11 | 10 | 0 | 0 | 7411 | 7482 | 7227 | 71 | 3 | 0 | 31 | 1 | 1800000 | 1264286 | 1305846 | 520579 | 0.4118 | 1 | 13000 | 3 | 69 | 92.2
1107 | 20250430 | 68 | 7 | 5 | 20 | 32 | 4 | 2 | 4 | Active | Deploy | Green | 0.9583 | 0.9859 | 1313364 | 1254445 | 1348858 | 1386324 | -40401 | -54012 | 1.032 | 0.96 | 20250531 | 20250531 | 0 | 12 | 12 | 12 | 0 | 0 | 6656 | 6722 | 6965 | 66 | 0 | 0 | 0 | 0 | 1800000 | 1532143 | 1315063 | 765737 | 0.4998 | 1 | 16000 | 2 | 76 | 92.5
1108 | 20250531 | 68 | 7 | 5 | 20 | 32 | 4 | 2 | 4 | Completed | Completed | Green | 1 | 1 | 1313364 | 1313364 | 1381042 | 1390565 | 0 | -67678 | 1 | 0.951 | 20250531 | 20250531 | 0 | 12 | 12 | 12 | 0 | 0 | 5887 | 5994 | 5875 | 107 | 1 | 0 | 10 | 0 | 1800000 | 1800000 | 1310899 | 911831 | 0.5066 | 1 | 21000 | 1 | 74 | 90.7
1109 | 20231031 | 69 | 3 | 2 | 21 | 33 | 5 | 2 | 5 | Terminated | Deliver | Amber | 1 | 0.6501 | 1250770 | 1250770 | 1065777 | 1778800 | 437644 | -252651 | 0.65 | 0.763 | 20230731 | 20240131 | 185 | 6 | 6 | 1 | 4 | 2 | 5607 | 4889 | 4959 | -718 | 9 | 2 | 164 | 3 | 3100000 | 3100000 | 2181849 | 2166345 | 0.6988 | 4 | 41000 | 6 | 40 | 48.8
1110 | 20240930 | 70 | 9 | 8 | 22 | 34 | 6 | 3 | 6 | Active | Initiate & Design | Green | 0.0333 | 0.0068 | 988849 | 30413 | 480 | 1051476 | 23689 | 6244 | 0.222 | 14.068 | 20270228 | 20270331 | 32 | 15 | 1 | 0 | 1 | 0 | 4896 | 4638 | 4952 | -258 | 11 | 1 | 157 | 3 | 2700000 | 0 | 2391170 | 0 |  | 0 | 0 | 7 | 96 | 100
1111 | 20241031 | 70 | 9 | 8 | 22 | 34 | 6 | 3 | 6 | Active | Initiate & Design | Green | 0.0667 | 0.0593 | 988849 | 61001 | 48895 | 1054772 | 2362 | 9744 | 0.962 | 1.2 | 20270228 | 20270228 | 9 | 15 | 1 | 1 | 0 | 0 | 5354 | 5175 | 5235 | -179 | 8 | 1 | 119 | 2 | 2700000 | 0 | 2456185 | 0 |  | 1 | 9000 | 5 | 81 | 94
1112 | 20241130 | 70 | 9 | 8 | 22 | 34 | 6 | 3 | 6 | Active | Initiate & Design | Green | 0.1 | 0.0992 | 988849 | 91765 | 87934 | 1058068 | -6329 | 10160 | 1.069 | 1.115 | 20270228 | 20270228 | 1 | 15 | 2 | 2 | 0 | 0 | 5803 | 5428 | 5802 | -375 | 8 | 1 | 119 | 2 | 2700000 | 0 | 2382111 | 0 |  | 1 | 10000 | 3 | 88 | 94.4
1113 | 20241231 | 70 | 9 | 8 | 22 | 34 | 6 | 3 | 6 | Active | Initiate & Design | Green | 0.1333 | 0.1324 | 988849 | 122705 | 118653 | 1061365 | -8219 | 12271 | 1.067 | 1.103 | 20270228 | 20270228 | 1 | 15 | 2 | 1 | 0 | 0 | 6236 | 5860 | 5777 | -376 | 5 | 0 | 63 | 1 | 2700000 | 0 | 2451661 | 0 |  | 1 | 14000 | 4 | 88 | 100
1114 | 20250131 | 70 | 9 | 8 | 22 | 34 | 6 | 3 | 6 | Active | Initiate & Design | Green | 0.1667 | 0.1446 | 988849 | 153821 | 132269 | 1064661 | 10833 | 10719 | 0.929 | 1.081 | 20270228 | 20270331 | 27 | 15 | 3 | 1 | 1 | 0 | 6649 | 6331 | 6461 | -318 | 8 | 1 | 119 | 2 | 2700000 | 0 | 2441541 | 0 |  | 1 | 14000 | 5 | 80 | 87.9
1115 | 20250228 | 70 | 9 | 8 | 22 | 34 | 6 | 3 | 6 | Active | Initiate & Design | Green | 0.2 | 0.184 | 988849 | 185113 | 176830 | 1067957 | 3165 | 5118 | 0.983 | 1.029 | 20270228 | 20270331 | 19 | 15 | 3 | 2 | 0 | 0 | 7038 | 6581 | 6472 | -457 | 6 | 1 | 94 | 2 | 2700000 | 0 | 2486023 | 0 |  | 1 | 10000 | 5 | 79 | 88.6
1116 | 20250331 | 70 | 9 | 8 | 22 | 34 | 6 | 3 | 6 | Active | Initiate & Design | Green | 0.2333 | 0.1895 | 988849 | 216580 | 182200 | 1071253 | 29193 | 5187 | 0.865 | 1.029 | 20270228 | 20270430 | 53 | 15 | 4 | 2 | 1 | 0 | 7399 | 7145 | 7354 | -254 | 8 | 1 | 119 | 2 | 2700000 | 0 | 2472335 | 0 |  | 1 | 14000 | 5 | 69 | 83.8
1117 | 20250430 | 70 | 9 | 8 | 22 | 34 | 6 | 3 | 6 | Active | Initiate & Design | Green | 0.2667 | 0.212 | 988849 | 248223 | 197943 | 1074549 | 38587 | 11693 | 0.844 | 1.059 | 20270228 | 20270430 | 66 | 15 | 4 | 2 | 1 | 0 | 7727 | 6986 | 7262 | -741 | 7 | 1 | 106 | 2 | 2700000 | 0 | 2443998 | 0 |  | 1 | 10000 | 6 | 74 | 82.3
1118 | 20250531 | 70 | 9 | 8 | 22 | 34 | 6 | 3 | 6 | Active | Initiate & Design | Green | 0.3 | 0.2541 | 988849 | 280042 | 248688 | 1077845 | 28775 | 2579 | 0.897 | 1.01 | 20270228 | 20270430 | 55 | 15 | 5 | 4 | 1 | 0 | 8019 | 7580 | 8097 | -439 | 7 | 2 | 124 | 2 | 2700000 | 0 | 2373841 | 0 |  | 1 | 15000 | 3 | 71 | 75.1
1119 | 20250630 | 70 | 9 | 8 | 22 | 34 | 6 | 3 | 6 | Active | Initiate & Design | Green | 0.3333 | 0.2947 | 988849 | 312037 | 284319 | 1081142 | 20623 | 7095 | 0.934 | 1.025 | 20270228 | 20270430 | 47 | 15 | 5 | 3 | 1 | 0 | 8272 | 7458 | 7135 | -814 | 8 | 1 | 119 | 2 | 2700000 | 0 | 2486187 | 0 |  | 1 | 8000 | 4 | 73 | 85.5
1120 | 20250731 | 70 | 9 | 8 | 22 | 34 | 6 | 3 | 6 | Active | Initiate & Design | Green | 0.3667 | 0.332 | 988849 | 344207 | 319813 | 1084438 | 15909 | 8485 | 0.954 | 1.026 | 20270228 | 20270331 | 42 | 15 | 6 | 4 | 1 | 0 | 8482 | 8262 | 8316 | -220 | 6 | 1 | 94 | 2 | 2700000 | 0 | 2480666 | 0 |  | 1 | 13000 | 7 | 74 | 88
1121 | 20250831 | 70 | 9 | 8 | 22 | 34 | 6 | 3 | 6 | Active | Deliver | Green | 0.4 | 0.3761 | 988849 | 376554 | 370163 | 1087734 | 4648 | 1743 | 0.988 | 1.005 | 20270228 | 20270331 | 30 | 15 | 6 | 4 | 1 | 0 | 8649 | 8298 | 7808 | -351 | 6 | 1 | 94 | 2 | 2700000 | 0 | 2437494 | 0 |  | 1 | 12000 | 4 | 77 | 88
1122 | 20250930 | 70 | 9 | 8 | 22 | 34 | 6 | 3 | 6 | Active | Deliver | Green | 0.4333 | 0.4077 | 988849 | 409076 | 405800 | 1092445 | 5922 | -2646 | 0.986 | 0.993 | 20270228 | 20270331 | 31 | 15 | 7 | 5 | 1 | 0 | 8769 | 8803 | 8378 | 34 | 8 | 1 | 119 | 2 | 2700000 | 0 | 2473022 | 0 |  | 1 | 10000 | 6 | 74 | 88.8
1123 | 20251031 | 70 | 9 | 8 | 22 | 34 | 6 | 3 | 6 | Active | Deliver | Green | 0.4667 | 0.4512 | 988849 | 441774 | 444922 | 1094326 | -4395 | 1247 | 1.01 | 1.003 | 20270228 | 20270331 | 19 | 15 | 7 | 6 | 0 | 0 | 8841 | 8263 | 8146 | -578 | 5 | 0 | 63 | 1 | 2700000 | 0 | 2489241 | 0 |  | 1 | 11000 | 3 | 86 | 96.9
1124 | 20251130 | 70 | 9 | 8 | 22 | 34 | 6 | 3 | 6 | Active | Deliver | Green | 0.5 | 0.4516 | 988849 | 474648 | 456584 | 1102383 | 28084 | -10020 | 0.941 | 0.978 | 20270228 | 20270430 | 59 | 15 | 8 | 7 | 1 | 0 | 8866 | 8541 | 8174 | -325 | 8 | 1 | 119 | 2 | 2700000 | 0 | 2380900 | 0 |  | 1 | 14000 | 4 | 74 | 84.5
1125 | 20251231 | 70 | 9 | 8 | 22 | 34 | 6 | 3 | 6 | Active | Deliver | Green | 0.5333 | 0.4689 | 988849 | 507697 | 464578 | 1101323 | 44026 | -907 | 0.913 | 0.998 | 20270228 | 20270531 | 78 | 15 | 8 | 5 | 2 | 1 | 8841 | 8692 | 8810 | -149 | 7 | 1 | 106 | 2 | 2700000 | 0 | 2465044 | 0 |  | 1 | 9000 | 3 | 71 | 85.2
1126 | 20260131 | 70 | 9 | 8 | 22 | 34 | 6 | 3 | 6 | Active | Deliver | Green | 0.5667 | 0.5109 | 988849 | 540922 | 518322 | 1109721 | 35719 | -13119 | 0.934 | 0.975 | 20270228 | 20270430 | 67 | 15 | 9 | 6 | 2 | 1 | 8769 | 7965 | 7799 | -804 | 6 | 1 | 94 | 2 | 2700000 | 0 | 2406293 | 0 |  | 1 | 12000 | 4 | 77 | 83.1
1127 | 20260228 | 70 | 9 | 8 | 22 | 34 | 6 | 3 | 6 | Active | Deliver | Green | 0.6 | 0.5374 | 988849 | 574323 | 543659 | 1112422 | 42916 | -12252 | 0.925 | 0.977 | 20270228 | 20270531 | 75 | 15 | 9 | 6 | 2 | 1 | 8649 | 8326 | 8556 | -323 | 7 | 1 | 106 | 2 | 2700000 | 0 | 2474631 | 0 |  | 1 | 9000 | 5 | 73 | 84.7
1128 | 20260331 | 70 | 9 | 8 | 22 | 34 | 6 | 3 | 6 | Active | Deliver | Green | 0.6333 | 0.5792 | 988849 | 607900 | 588394 | 1116589 | 35159 | -15653 | 0.942 | 0.973 | 20270228 | 20270430 | 66 | 15 | 10 | 8 | 2 | 1 | 8482 | 8214 | 8225 | -268 | 7 | 1 | 106 | 2 | 2700000 | 0 | 2490229 | 0 |  | 1 | 11000 | 3 | 77 | 85.6
1129 | 20260430 | 70 | 9 | 8 | 22 | 34 | 6 | 3 | 6 | Active | Deliver | Green | 0.6667 | 0.6119 | 988849 | 641653 | 635737 | 1124586 | 36576 | -30660 | 0.943 | 0.952 | 20270228 | 20270430 | 66 | 15 | 10 | 7 | 2 | 1 | 8272 | 7932 | 7576 | -340 | 8 | 1 | 119 | 2 | 2700000 | 0 | 2462231 | 0 |  | 1 | 9000 | 6 | 73 | 84.4
1130 | 20260531 | 70 | 9 | 8 | 22 | 34 | 6 | 3 | 6 | Active | Deliver | Green | 0.7 | 0.6716 | 988849 | 675582 | 702111 | 1129159 | 11471 | -38000 | 0.983 | 0.946 | 20270228 | 20270331 | 35 | 15 | 11 | 10 | 1 | 0 | 8019 | 7638 | 7627 | -381 | 8 | 1 | 119 | 2 | 2700000 | 0 | 2439182 | 0 |  | 1 | 11000 | 6 | 74 | 85.6
1131 | 20260630 | 70 | 9 | 8 | 22 | 34 | 6 | 3 | 6 | Active | Deliver | Green | 0.7333 | 0.7073 | 988849 | 709686 | 746802 | 1134514 | 10273 | -47389 | 0.985 | 0.936 | 20270228 | 20270331 | 31 | 15 | 11 | 9 | 1 | 0 | 7727 | 7429 | 7240 | -298 | 8 | 1 | 119 | 2 | 2700000 | 128571 | 2407686 | 0 | 0 | 1 | 11000 | 4 | 72 | 85.2
1132 | 20260731 | 70 | 9 | 8 | 22 | 34 | 6 | 3 | 6 | Active | Deliver | Green | 0.7667 | 0.713 | 988849 | 743966 | 746802 | 1136142 | 38917 | -41753 | 0.948 | 0.944 | 20270228 | 20270430 | 65 | 15 | 12 | 10 | 2 | 1 | 7399 | 6823 | 6647 | -576 | 6 | 1 | 94 | 2 | 2700000 | 450000 | 2415680 | 0 | 0 | 2 | 23000 | 5 | 70 | 83
1133 | 20260831 | 70 | 9 | 8 | 22 | 34 | 6 | 3 | 6 | Active | Deliver | Green | 0.8 | 0.7387 | 988849 | 778422 | 781644 | 1141532 | 47959 | -51181 | 0.938 | 0.935 | 20270228 | 20270430 | 74 | 15 | 12 | 9 | 2 | 1 | 7038 | 6596 | 7048 | -442 | 6 | 0 | 76 | 2 | 2700000 | 771429 | 2432692 | 160775 | 0.2084 | 2 | 17000 | 6 | 77 | 90.8
1134 | 20260930 | 70 | 9 | 8 | 22 | 34 | 6 | 3 | 6 | Active | Deploy | Green | 0.8333 | 0.7538 | 988849 | 813054 | 804152 | 1146488 | 67660 | -58758 | 0.917 | 0.927 | 20270228 | 20270531 | 97 | 15 | 13 | 9 | 3 | 1 | 6649 | 6570 | 6393 | -79 | 6 | 1 | 94 | 2 | 2700000 | 1092857 | 2475383 | 389785 | 0.3567 | 2 | 16000 | 3 | 74 | 83.1
1135 | 20231031 | 71 | 5 | 5 | 23 | 35 | 7 | 2 | 7 | Active | Deliver | Green | 0.4 | 0.4317 | 418856 | 159500 | 171518 | 423045 | -21320 | 9302 | 1.134 | 1.054 | 20250430 | 20250430 | 0 | 15 | 6 | 6 | 0 | 0 | 3663 | 3611 | 3442 | -52 | 3 | 0 | 29 | 1 | 1100000 | 0 | 1135144 | 0 |  | 0 | 0 | 4 | 89 | 100
1136 | 20231130 | 71 | 5 | 5 | 23 | 35 | 7 | 2 | 7 | Active | Deliver | Green | 0.4333 | 0.4659 | 418856 | 173276 | 186804 | 423184 | -21869 | 8341 | 1.126 | 1.045 | 20250430 | 20250430 | 0 | 15 | 7 | 6 | 0 | 0 | 3714 | 3820 | 3817 | 106 | 2 | 0 | 19 | 0 | 1100000 | 0 | 1117768 | 0 |  | 1 | 5000 | 3 | 90 | 100
1137 | 20231231 | 71 | 5 | 5 | 23 | 35 | 7 | 2 | 7 | Active | Deliver | Green | 0.4667 | 0.4883 | 418856 | 187126 | 194281 | 423324 | -17401 | 10246 | 1.093 | 1.053 | 20250430 | 20250430 | 0 | 15 | 7 | 6 | 0 | 0 | 3745 | 4019 | 4278 | 274 | 1 | 0 | 10 | 0 | 1100000 | 0 | 1100125 | 0 |  | 1 | 4000 | 1 | 90 | 100
1138 | 20240131 | 71 | 5 | 5 | 23 | 35 | 7 | 2 | 7 | Active | Deliver | Green | 0.5 | 0.4883 | 418856 | 201051 | 196160 | 423463 | -3476 | 8367 | 1.017 | 1.043 | 20250430 | 20250430 | 12 | 15 | 8 | 8 | 0 | 0 | 3755 | 4049 | 4208 | 294 | 3 | 0 | 29 | 1 | 1100000 | 0 | 1143643 | 0 |  | 1 | 5000 | 5 | 82 | 100
1139 | 20240229 | 71 | 5 | 5 | 23 | 35 | 7 | 2 | 7 | Active | Deliver | Green | 0.5333 | 0.5233 | 418856 | 215050 | 211946 | 423603 | -4137 | 7241 | 1.019 | 1.034 | 20250430 | 20250430 | 10 | 15 | 8 | 7 | 0 | 0 | 3745 | 3890 | 3748 | 145 | 2 | 0 | 19 | 0 | 1100000 | 0 | 1133747 | 0 |  | 1 | 4000 | 4 | 82 | 100
1140 | 20240331 | 71 | 5 | 5 | 23 | 35 | 7 | 2 | 7 | Active | Deliver | Green | 0.5667 | 0.5685 | 418856 | 229124 | 229561 | 423743 | -8996 | 8559 | 1.039 | 1.037 | 20250430 | 20250430 | 0 | 15 | 9 | 8 | 0 | 0 | 3714 | 3638 | 3831 | -76 | 2 | 0 | 19 | 0 | 1100000 | 0 | 1115436 | 0 |  | 1 | 4000 | 3 | 85 | 100
1141 | 20240430 | 71 | 5 | 5 | 23 | 35 | 7 | 2 | 7 | Active | Deliver | Green | 0.6 | 0.5988 | 418856 | 243272 | 243892 | 423882 | -7539 | 6919 | 1.031 | 1.028 | 20250430 | 20250430 | 1 | 15 | 9 | 8 | 0 | 0 | 3663 | 3564 | 3520 | -99 | 2 | 0 | 19 | 0 | 1100000 | 0 | 1128675 | 0 |  | 1 | 6000 | 5 | 88 | 100
1142 | 20240531 | 71 | 5 | 5 | 23 | 35 | 7 | 2 | 7 | Active | Deliver | Green | 0.6333 | 0.6386 | 418856 | 257494 | 262507 | 424022 | -9987 | 4974 | 1.039 | 1.019 | 20250430 | 20250430 | 0 | 15 | 10 | 9 | 0 | 0 | 3593 | 3696 | 3849 | 103 | 2 | 0 | 19 | 0 | 1100000 | 0 | 1097365 | 0 |  | 1 | 5000 | 3 | 81 | 100
1143 | 20240630 | 71 | 5 | 5 | 23 | 35 | 7 | 2 | 7 | Active | Deliver | Green | 0.6667 | 0.6948 | 418856 | 271791 | 285682 | 424162 | -19230 | 5339 | 1.071 | 1.019 | 20250430 | 20250430 | 0 | 15 | 10 | 9 | 0 | 0 | 3504 | 3770 | 3944 | 266 | 1 | 0 | 10 | 0 | 1100000 | 0 | 1117346 | 0 |  | 1 | 5000 | 3 | 86 | 100
1144 | 20240731 | 71 | 5 | 5 | 23 | 35 | 7 | 2 | 7 | Active | Deliver | Green | 0.7 | 0.7371 | 418856 | 286162 | 308337 | 424301 | -22577 | 402 | 1.079 | 1.001 | 20250430 | 20250430 | 0 | 15 | 11 | 10 | 0 | 0 | 3397 | 3311 | 3384 | -86 | 3 | 0 | 29 | 1 | 1100000 | 0 | 1136692 | 0 |  | 1 | 7000 | 3 | 87 | 100
1145 | 20240831 | 71 | 5 | 5 | 23 | 35 | 7 | 2 | 7 | Active | Deploy | Green | 0.7333 | 0.7643 | 418856 | 300608 | 318060 | 424441 | -19524 | 2072 | 1.065 | 1.006 | 20250430 | 20250430 | 0 | 15 | 11 | 11 | 0 | 0 | 3273 | 3253 | 3426 | -20 | 2 | 0 | 19 | 0 | 1100000 | 52381 | 1144727 | 0 | 0 | 1 | 5000 | 4 | 84 | 100
1146 | 20240930 | 71 | 5 | 5 | 23 | 35 | 7 | 2 | 7 | Active | Deploy | Green | 0.7667 | 0.7893 | 418856 | 315129 | 328362 | 424580 | -15474 | 2241 | 1.049 | 1.007 | 20250430 | 20250430 | 0 | 15 | 12 | 12 | 0 | 0 | 3134 | 3289 | 3293 | 155 | 2 | 0 | 19 | 0 | 1100000 | 183333 | 1096839 | 0 | 0 | 1 | 4000 | 2 | 87 | 100
1147 | 20241031 | 71 | 5 | 5 | 23 | 35 | 7 | 2 | 7 | Active | Deploy | Green | 0.8 | 0.805 | 418856 | 329723 | 337735 | 424874 | -7456 | -556 | 1.023 | 0.998 | 20250430 | 20250430 | 0 | 15 | 12 | 11 | 0 | 0 | 2981 | 3144 | 3113 | 163 | 2 | 0 | 19 | 0 | 1100000 | 314286 | 1104780 | 71113 | 0.2263 | 1 | 6000 | 2 | 83 | 100
1148 | 20241130 | 71 | 5 | 5 | 23 | 35 | 7 | 2 | 7 | Active | Deploy | Green | 0.8333 | 0.8321 | 418856 | 344393 | 352912 | 426000 | -4137 | -4382 | 1.012 | 0.988 | 20250430 | 20250430 | 1 | 15 | 13 | 13 | 0 | 0 | 2816 | 2806 | 2730 | -10 | 0 | 0 | 0 | 0 | 1100000 | 445238 | 1105584 | 183913 | 0.4131 | 1 | 4000 | 0 | 81 | 100
1149 | 20241231 | 71 | 5 | 5 | 23 | 35 | 7 | 2 | 7 | Active | Deploy | Green | 0.8667 | 0.874 | 418856 | 359136 | 369532 | 425863 | -6944 | -3452 | 1.019 | 0.991 | 20250430 | 20250430 | 0 | 15 | 13 | 13 | 0 | 0 | 2641 | 2783 | 2721 | 142 | 2 | 0 | 19 | 0 | 1100000 | 576190 | 1118173 | 281042 | 0.4878 | 1 | 4000 | 2 | 86 | 100
1150 | 20250131 | 71 | 5 | 5 | 23 | 35 | 7 | 2 | 7 | Active | Deploy | Green | 0.9 | 0.9078 | 418856 | 373955 | 386221 | 426568 | -6282 | -5984 | 1.017 | 0.984 | 20250430 | 20250430 | 0 | 15 | 14 | 13 | 0 | 0 | 2458 | 2412 | 2455 | -46 | 1 | 0 | 10 | 0 | 1100000 | 707143 | 1140016 | 423313 | 0.5986 | 1 | 6000 | 2 | 79 | 99.8
1151 | 20250228 | 71 | 5 | 5 | 23 | 35 | 7 | 2 | 7 | Active | Deploy | Green | 0.9333 | 0.9371 | 418856 | 388847 | 403781 | 427855 | -3663 | -11271 | 1.009 | 0.972 | 20250430 | 20250430 | 0 | 15 | 14 | 13 | 0 | 0 | 2268 | 2327 | 2240 | 59 | 1 | 0 | 10 | 0 | 1100000 | 838095 | 1118058 | 571413 | 0.6818 | 1 | 6000 | 2 | 82 | 99.4
1152 | 20250331 | 71 | 5 | 5 | 23 | 35 | 7 | 2 | 7 | Active | Deploy | Green | 0.9667 | 0.9927 | 418856 | 403814 | 425422 | 427500 | -11984 | -9624 | 1.03 | 0.977 | 20250430 | 20250430 | 0 | 15 | 15 | 14 | 0 | 0 | 2074 | 2080 | 2060 | 6 | 2 | 0 | 19 | 0 | 1100000 | 969048 | 1142264 | 648777 | 0.6695 | 1 | 4000 | 2 | 81 | 100
1153 | 20250430 | 71 | 5 | 5 | 23 | 35 | 7 | 2 | 7 | Completed | Completed | Green | 1 | 1 | 418856 | 418856 | 430662 | 430662 | 0 | -11806 | 1 | 0.973 | 20250430 | 20250430 | 0 | 15 | 15 | 15 | 0 | 0 | 1878 | 1825 | 1800 | -53 | 2 | 0 | 19 | 0 | 1100000 | 1100000 | 1133782 | 737328 | 0.6703 | 1 | 5000 | 1 | 77 | 98.4
1154 | 20240630 | 72 | 6 | 4 | 24 | 36 | 8 | 3 | 8 | Active | Initiate & Design | Green | 0.0556 | 0.0981 | 915461 | 47016 | 80214 | 933465 | -42791 | 9593 | 1.911 | 1.12 | 20251130 | 20251130 | 0 | 9 | 1 | 1 | 0 | 0 | 4816 | 5077 | 4841 | 261 | 0 | 0 | 0 | 0 | 1700000 | 0 | 1857127 | 0 |  | 0 | 0 | 4 | 96 | 100
1155 | 20240731 | 72 | 6 | 4 | 24 | 36 | 8 | 3 | 8 | Active | Initiate & Design | Green | 0.1111 | 0.1665 | 915461 | 94485 | 143861 | 934991 | -57939 | 8563 | 1.613 | 1.059 | 20251130 | 20251130 | 0 | 9 | 1 | 1 | 0 | 0 | 5507 | 5965 | 5770 | 458 | 0 | 0 | 0 | 0 | 1700000 | 0 | 1833469 | 0 |  | 0 | 0 | 3 | 96 | 100
1156 | 20240831 | 72 | 6 | 4 | 24 | 36 | 8 | 3 | 8 | Active | Initiate & Design | Green | 0.1667 | 0.2268 | 915461 | 142405 | 195566 | 936517 | -65222 | 12061 | 1.458 | 1.062 | 20251130 | 20251130 | 0 | 9 | 2 | 2 | 0 | 0 | 6156 | 6351 | 6506 | 195 | 1 | 0 | 9 | 0 | 1700000 | 0 | 1875257 | 0 |  | 0 | 0 | 1 | 96 | 100
1157 | 20240930 | 72 | 6 | 4 | 24 | 36 | 8 | 3 | 8 | Active | Initiate & Design | Green | 0.2222 | 0.2596 | 915461 | 190778 | 214973 | 938042 | -46876 | 22681 | 1.246 | 1.105 | 20251130 | 20251130 | 0 | 9 | 2 | 1 | 0 | 0 | 6742 | 6987 | 6895 | 245 | 0 | 0 | 0 | 0 | 1700000 | 0 | 1867896 | 0 |  | 0 | 0 | 4 | 96 | 100
1158 | 20241031 | 72 | 6 | 4 | 24 | 36 | 8 | 3 | 8 | Active | Initiate & Design | Green | 0.2778 | 0.3054 | 915461 | 239602 | 266081 | 939568 | -39980 | 13501 | 1.167 | 1.051 | 20251130 | 20251130 | 0 | 9 | 3 | 3 | 0 | 0 | 7247 | 7937 | 8455 | 690 | 3 | 0 | 27 | 0 | 1700000 | 0 | 1848387 | 0 |  | 0 | 0 | 5 | 93 | 100
1159 | 20241130 | 72 | 6 | 4 | 24 | 36 | 8 | 3 | 8 | Active | Deliver | Green | 0.3333 | 0.3734 | 915461 | 288879 | 325641 | 941094 | -52954 | 16192 | 1.183 | 1.05 | 20251130 | 20251130 | 0 | 9 | 3 | 2 | 0 | 0 | 7658 | 8273 | 8035 | 615 | 2 | 0 | 18 | 0 | 1700000 | 0 | 1838178 | 0 |  | 1 | 13000 | 2 | 95 | 100
1160 | 20241231 | 72 | 6 | 4 | 24 | 36 | 8 | 3 | 8 | Active | Deliver | Green | 0.3889 | 0.425 | 915461 | 338608 | 376862 | 942620 | -50463 | 12209 | 1.149 | 1.032 | 20251130 | 20251130 | 0 | 9 | 4 | 3 | 0 | 0 | 7960 | 8199 | 7732 | 239 | 1 | 0 | 9 | 0 | 1700000 | 0 | 1869302 | 0 |  | 1 | 10000 | 1 | 89 | 100
1161 | 20250131 | 72 | 6 | 4 | 24 | 36 | 8 | 3 | 8 | Active | Deliver | Green | 0.4444 | 0.49 | 915461 | 388788 | 427298 | 944145 | -59788 | 21278 | 1.154 | 1.05 | 20251130 | 20251130 | 0 | 9 | 4 | 3 | 0 | 0 | 8145 | 9009 | 9611 | 864 | 3 | 0 | 27 | 0 | 1700000 | 0 | 1860330 | 0 |  | 1 | 14000 | 3 | 90 | 100
1162 | 20250228 | 72 | 6 | 4 | 24 | 36 | 8 | 3 | 8 | Active | Deliver | Green | 0.5 | 0.5499 | 915461 | 439421 | 497299 | 945671 | -63991 | 6113 | 1.146 | 1.012 | 20251130 | 20251130 | 0 | 9 | 5 | 5 | 0 | 0 | 8208 | 8795 | 8906 | 587 | 2 | 0 | 18 | 0 | 1700000 | 0 | 1865117 | 0 |  | 1 | 10000 | 1 | 92 | 100
1163 | 20250331 | 72 | 6 | 4 | 24 | 36 | 8 | 3 | 8 | Active | Deliver | Green | 0.5556 | 0.6273 | 915461 | 490506 | 564288 | 947197 | -83763 | 9981 | 1.171 | 1.018 | 20251130 | 20251130 | 0 | 9 | 5 | 4 | 0 | 0 | 8145 | 9241 | 8928 | 1096 | 2 | 0 | 18 | 0 | 1700000 | 0 | 1797678 | 0 |  | 1 | 7000 | 3 | 86 | 100
1164 | 20250430 | 72 | 6 | 4 | 24 | 36 | 8 | 3 | 8 | Active | Deliver | Green | 0.6111 | 0.691 | 915461 | 542043 | 632223 | 948723 | -90541 | 361 | 1.167 | 1.001 | 20251130 | 20251130 | 0 | 9 | 6 | 6 | 0 | 0 | 7960 | 8714 | 8999 | 754 | 0 | 0 | 0 | 0 | 1700000 | 0 | 1816385 | 0 |  | 1 | 12000 | 1 | 92 | 100
1165 | 20250531 | 72 | 6 | 4 | 24 | 36 | 8 | 3 | 8 | Active | Deploy | Green | 0.6667 | 0.7642 | 915461 | 594032 | 698244 | 950249 | -105563 | 1351 | 1.178 | 1.002 | 20251130 | 20251130 | 0 | 9 | 6 | 5 | 0 | 0 | 7658 | 8683 | 9012 | 1025 | 2 | 0 | 18 | 0 | 1700000 | 0 | 1873376 | 0 |  | 1 | 14000 | 5 | 92 | 100
1166 | 20250630 | 72 | 6 | 4 | 24 | 36 | 8 | 3 | 8 | Active | Deploy | Green | 0.7222 | 0.8114 | 915461 | 646474 | 745392 | 952462 | -96331 | -2587 | 1.149 | 0.997 | 20251130 | 20251130 | 0 | 9 | 7 | 6 | 0 | 0 | 7247 | 7878 | 8398 | 631 | 3 | 0 | 27 | 0 | 1700000 | 13492 | 1804982 | 0 | 0 | 1 | 11000 | 3 | 92 | 100
1167 | 20250731 | 72 | 6 | 4 | 24 | 36 | 8 | 3 | 8 | Active | Deploy | Green | 0.7778 | 0.8437 | 915461 | 699367 | 784028 | 956283 | -73007 | -11654 | 1.104 | 0.985 | 20251130 | 20251130 | 0 | 9 | 7 | 7 | 0 | 0 | 6742 | 7685 | 8090 | 943 | 2 | 0 | 18 | 0 | 1700000 | 350794 | 1800436 | 0 | 0 | 1 | 8000 | 1 | 85 | 100
1168 | 20250831 | 72 | 6 | 4 | 24 | 36 | 8 | 3 | 8 | Active | Deploy | Green | 0.8333 | 0.9118 | 915461 | 752712 | 858593 | 960435 | -82005 | -23876 | 1.109 | 0.972 | 20251130 | 20251130 | 0 | 9 | 8 | 8 | 0 | 0 | 6156 | 6658 | 6707 | 502 | 1 | 0 | 9 | 0 | 1700000 | 688095 | 1872970 | 326852 | 0.475 | 1 | 13000 | 1 | 87 | 100
1169 | 20250930 | 72 | 6 | 4 | 24 | 36 | 8 | 3 | 8 | Active | Deploy | Green | 0.8889 | 0.9616 | 915461 | 806510 | 915706 | 964147 | -73797 | -35399 | 1.091 | 0.961 | 20251130 | 20251130 | 0 | 9 | 8 | 7 | 0 | 0 | 5507 | 5799 | 5511 | 292 | 0 | 0 | 0 | 0 | 1700000 | 1025397 | 1808285 | 652389 | 0.6362 | 1 | 9000 | 1 | 84 | 100
1170 | 20251031 | 72 | 6 | 4 | 24 | 36 | 8 | 3 | 8 | Completed | Completed | Green | 0.9444 | 1 | 915461 | 860759 | 947758 | 964740 | -54702 | -32297 | 1.064 | 0.966 | 20251130 | 20251130 | 0 | 9 | 9 | 9 | 0 | 0 | 4816 | 5146 | 5463 | 330 | 0 | 0 | 0 | 0 | 1700000 | 1362698 | 1808527 | 913244 | 0.6702 | 1 | 10000 | 2 | 84 | 100
1171 | 20250630 | 73 | 7 | 5 | 1 | 25 | 1 | 2 | 1 | Active | Initiate & Design | Amber | 0.0667 | 0.0395 | 553088 | 34119 | 22598 | 575700 | 12272 | -751 | 0.64 | 0.966 | 20260831 | 20260930 | 15 | 8 | 1 | 0 | 1 | 0 | 2995 | 2341 | 2386 | -654 | 8 | 1 | 113 | 2 | 700000 | 0 | 654777 | 0 |  | 0 | 0 | 3 | 63 | 68
1172 | 20250731 | 73 | 7 | 5 | 1 | 25 | 1 | 2 | 1 | Active | Initiate & Design | Green | 0.1333 | 0.0848 | 553088 | 68632 | 45172 | 573368 | 21730 | 1730 | 0.683 | 1.038 | 20260831 | 20260930 | 28 | 8 | 1 | 0 | 1 | 0 | 3488 | 2597 | 2457 | -891 | 8 | 1 | 113 | 2 | 700000 | 0 | 659679 | 0 |  | 1 | 9000 | 3 | 61 | 71.8
1173 | 20250831 | 73 | 7 | 5 | 1 | 25 | 1 | 2 | 1 | Active | Initiate & Design | Green | 0.2 | 0.1367 | 553088 | 103538 | 67863 | 575212 | 27931 | 7744 | 0.73 | 1.114 | 20260831 | 20260930 | 36 | 8 | 2 | 0 | 1 | 0 | 3937 | 2982 | 3034 | -955 | 8 | 1 | 113 | 2 | 700000 | 0 | 665701 | 0 |  | 1 | 5000 | 4 | 71 | 77.2
1174 | 20250930 | 73 | 7 | 5 | 1 | 25 | 1 | 2 | 1 | Active | Initiate & Design | Green | 0.2667 | 0.1771 | 553088 | 138837 | 92424 | 577055 | 40885 | 5528 | 0.705 | 1.06 | 20260831 | 20261031 | 52 | 8 | 2 | 1 | 1 | 0 | 4322 | 3359 | 3338 | -963 | 6 | 1 | 89 | 2 | 700000 | 0 | 671983 | 0 |  | 1 | 5000 | 3 | 65 | 74.8
1175 | 20251031 | 73 | 7 | 5 | 1 | 25 | 1 | 2 | 1 | Active | Initiate & Design | Green | 0.3333 | 0.2318 | 553088 | 174530 | 118863 | 578899 | 46324 | 9343 | 0.734 | 1.078 | 20260831 | 20261031 | 59 | 8 | 3 | 2 | 1 | 0 | 4627 | 3431 | 3292 | -1196 | 8 | 1 | 113 | 2 | 700000 | 0 | 661740 | 0 |  | 1 | 6000 | 6 | 69 | 75.6
1176 | 20251130 | 73 | 7 | 5 | 1 | 25 | 1 | 2 | 1 | Active | Initiate & Design | Green | 0.4 | 0.2839 | 553088 | 210616 | 149433 | 580742 | 53594 | 7589 | 0.745 | 1.051 | 20260831 | 20261031 | 67 | 8 | 3 | 1 | 1 | 0 | 4837 | 3641 | 3587 | -1196 | 6 | 1 | 89 | 2 | 700000 | 0 | 657974 | 0 |  | 1 | 7000 | 3 | 66 | 75.2
1177 | 20251231 | 73 | 7 | 5 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Green | 0.4667 | 0.3509 | 553088 | 247095 | 190583 | 582586 | 53016 | 3496 | 0.785 | 1.018 | 20260831 | 20261031 | 67 | 8 | 4 | 1 | 2 | 1 | 4945 | 4006 | 3943 | -939 | 7 | 1 | 101 | 2 | 700000 | 0 | 650078 | 0 |  | 1 | 8000 | 4 | 64 | 76.8
1178 | 20260131 | 73 | 7 | 5 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Green | 0.5333 | 0.4377 | 553088 | 283968 | 239691 | 584430 | 41881 | 2396 | 0.853 | 1.01 | 20260831 | 20261031 | 55 | 8 | 4 | 3 | 1 | 0 | 4945 | 3986 | 4232 | -959 | 7 | 1 | 101 | 2 | 700000 | 0 | 670641 | 0 |  | 1 | 7000 | 5 | 68 | 80.3
1179 | 20260228 | 73 | 7 | 5 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Green | 0.6 | 0.5059 | 553088 | 321234 | 282473 | 587427 | 41427 | -2666 | 0.871 | 0.991 | 20260831 | 20261031 | 54 | 8 | 5 | 3 | 1 | 0 | 4837 | 3694 | 3560 | -1143 | 8 | 1 | 113 | 2 | 700000 | 0 | 651712 | 0 |  | 1 | 9000 | 3 | 71 | 78.7
1180 | 20260331 | 73 | 7 | 5 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Green | 0.6667 | 0.5733 | 553088 | 358893 | 317120 | 588140 | 41808 | -35 | 0.883 | 1 | 20260831 | 20261031 | 54 | 8 | 5 | 3 | 1 | 0 | 4627 | 3506 | 3665 | -1121 | 7 | 1 | 101 | 2 | 700000 | 0 | 646312 | 0 |  | 1 | 8000 | 5 | 75 | 79.3
1181 | 20260430 | 73 | 7 | 5 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Green | 0.7333 | 0.613 | 553088 | 396945 | 345250 | 592153 | 57902 | -6207 | 0.854 | 0.982 | 20260831 | 20261031 | 70 | 8 | 6 | 3 | 2 | 1 | 4322 | 3609 | 3465 | -713 | 8 | 1 | 113 | 2 | 700000 | 33333 | 642039 | 0 | 0 | 1 | 7000 | 4 | 71 | 78.9
1182 | 20260531 | 73 | 7 | 5 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Green | 0.8 | 0.6824 | 553088 | 435391 | 387355 | 594920 | 57964 | -9928 | 0.867 | 0.974 | 20260831 | 20261031 | 68 | 8 | 6 | 4 | 2 | 1 | 3937 | 3204 | 3111 | -733 | 7 | 1 | 101 | 2 | 700000 | 200000 | 663630 | 42623 | 0.2131 | 1 | 7000 | 6 | 67 | 79.6
1183 | 20260630 | 73 | 7 | 5 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Green | 0.8667 | 0.7171 | 553088 | 474230 | 417269 | 599666 | 77611 | -20650 | 0.836 | 0.951 | 20260831 | 20261130 | 86 | 8 | 7 | 4 | 2 | 1 | 3488 | 2535 | 2710 | -953 | 4 | 1 | 65 | 1 | 700000 | 366667 | 651720 | 179160 | 0.4886 | 2 | 11000 | 4 | 65 | 75
1184 | 20260731 | 73 | 7 | 5 | 1 | 25 | 1 | 2 | 1 | Active | Deploy | Green | 0.9333 | 0.7833 | 553088 | 513462 | 458657 | 602232 | 80228 | -25423 | 0.844 | 0.945 | 20260831 | 20261130 | 88 | 8 | 7 | 4 | 2 | 1 | 2995 | 2406 | 2377 | -589 | 4 | 1 | 65 | 1 | 700000 | 533333 | 667551 | 340382 | 0.6382 | 2 | 14000 | 3 | 68 | 77.4
1185 | 20260831 | 73 | 7 | 5 | 1 | 25 | 1 | 2 | 1 | Active | Deploy | Green | 1 | 0.8484 | 553088 | 553088 | 499356 | 604677 | 83848 | -30116 | 0.848 | 0.94 | 20260831 | 20261130 | 88 | 8 | 8 | 6 | 2 | 1 | 2479 | 1805 | 1718 | -674 | 5 | 0 | 59 | 1 | 700000 | 700000 | 674929 | 431089 | 0.6158 | 2 | 18000 | 2 | 73 | 84.1
1186 | 20260930 | 73 | 7 | 5 | 1 | 25 | 1 | 2 | 1 | Active | Deploy | Green | 1 | 0.867 | 553088 | 553088 | 516198 | 607818 | 73561 | -36671 | 0.867 | 0.929 | 20260831 | 20261130 | 77 | 8 | 8 | 5 | 2 | 1 | 2479 | 2035 | 2133 | -444 | 3 | 0 | 36 | 1 | 700000 | 700000 | 668921 | 591000 | 0.8443 | 2 | 9000 | 2 | 70 | 86.3
1187 | 20251130 | 74 | 1 | 1 | 2 | 26 | 2 | 3 | 2 | Active | Initiate & Design | Green | 0.0333 | 0.024 | 591224 | 18183 | 16932 | 638672 | 3994 | -2743 | 0.779 | 0.837 | 20280430 | 20280430 | 10 | 15 | 1 | 1 | 0 | 0 | 2927 | 2631 | 2572 | -296 | 7 | 1 | 103 | 2 | 1300000 | 0 | 1228719 | 0 |  | 0 | 0 | 5 | 58 | 72.6
1188 | 20251231 | 74 | 1 | 1 | 2 | 26 | 2 | 3 | 2 | Active | Initiate & Design | Amber | 0.0667 | 0.0282 | 591224 | 36472 | 16932 | 620737 | 19799 | -259 | 0.457 | 0.985 | 20280430 | 20280630 | 46 | 15 | 1 | 0 | 1 | 0 | 3201 | 3045 | 3016 | -156 | 8 | 1 | 115 | 2 | 1300000 | 0 | 1239844 | 0 |  | 0 | 0 | 6 | 52 | 64.7
1189 | 20260131 | 74 | 1 | 1 | 2 | 26 | 2 | 3 | 2 | Active | Initiate & Design | Amber | 0.1 | 0.0411 | 591224 | 54866 | 21878 | 620194 | 30567 | 2421 | 0.443 | 1.111 | 20280430 | 20280630 | 70 | 15 | 2 | 1 | 1 | 0 | 3469 | 3251 | 3412 | -218 | 8 | 1 | 115 | 2 | 1300000 | 0 | 1257906 | 0 |  | 0 | 0 | 6 | 52 | 68.6
1190 | 20260228 | 74 | 1 | 1 | 2 | 26 | 2 | 3 | 2 | Active | Initiate & Design | Green | 0.1333 | 0.0777 | 591224 | 73364 | 43747 | 621573 | 27426 | 2191 | 0.626 | 1.05 | 20280430 | 20280630 | 66 | 15 | 2 | 0 | 1 | 0 | 3728 | 3483 | 3509 | -245 | 8 | 1 | 115 | 2 | 1300000 | 0 | 1261915 | 0 |  | 0 | 0 | 3 | 58 | 74.7
1191 | 20260331 | 74 | 1 | 1 | 2 | 26 | 2 | 3 | 2 | Active | Initiate & Design | Green | 0.1667 | 0.1079 | 591224 | 91968 | 59373 | 622953 | 28175 | 4420 | 0.694 | 1.074 | 20280430 | 20280630 | 70 | 15 | 3 | 0 | 2 | 1 | 3975 | 3881 | 3784 | -94 | 8 | 1 | 115 | 2 | 1300000 | 0 | 1266542 | 0 |  | 1 | 7000 | 3 | 65 | 79.6
1192 | 20260430 | 74 | 1 | 1 | 2 | 26 | 2 | 3 | 2 | Active | Initiate & Design | Green | 0.2 | 0.1376 | 591224 | 110677 | 78277 | 624333 | 29325 | 3075 | 0.735 | 1.04 | 20280430 | 20280630 | 73 | 15 | 3 | 1 | 1 | 0 | 4208 | 3832 | 3985 | -376 | 7 | 1 | 103 | 2 | 1300000 | 0 | 1262728 | 0 |  | 1 | 6000 | 6 | 70 | 78.7
1193 | 20260531 | 74 | 1 | 1 | 2 | 26 | 2 | 3 | 2 | Active | Initiate & Design | Green | 0.2333 | 0.1777 | 591224 | 129491 | 94863 | 625712 | 24430 | 10198 | 0.811 | 1.107 | 20280430 | 20280630 | 66 | 15 | 4 | 2 | 1 | 0 | 4424 | 3945 | 3959 | -479 | 8 | 1 | 115 | 2 | 1300000 | 0 | 1242623 | 0 |  | 1 | 9000 | 4 | 71 | 83.6
1194 | 20260630 | 74 | 1 | 1 | 2 | 26 | 2 | 3 | 2 | Active | Initiate & Design | Green | 0.2667 | 0.2276 | 591224 | 148410 | 130150 | 627092 | 13847 | 4413 | 0.907 | 1.034 | 20280430 | 20280630 | 46 | 15 | 4 | 3 | 1 | 0 | 4620 | 4375 | 4674 | -245 | 7 | 1 | 103 | 2 | 1300000 | 0 | 1255378 | 0 |  | 1 | 7000 | 5 | 78 | 86.9
1195 | 20260731 | 74 | 1 | 1 | 2 | 26 | 2 | 3 | 2 | Active | Initiate & Design | Green | 0.3 | 0.2647 | 591224 | 167435 | 151225 | 628471 | 10938 | 5272 | 0.935 | 1.035 | 20280430 | 20280531 | 42 | 15 | 5 | 3 | 1 | 0 | 4794 | 4330 | 4257 | -464 | 6 | 1 | 91 | 2 | 1300000 | 0 | 1250153 | 0 |  | 1 | 6000 | 5 | 71 | 87.1
1196 | 20260831 | 74 | 1 | 1 | 2 | 26 | 2 | 3 | 2 | Active | Initiate & Design | Green | 0.3333 | 0.2916 | 591224 | 186564 | 162311 | 629851 | 14163 | 10090 | 0.924 | 1.062 | 20280430 | 20280630 | 50 | 15 | 5 | 4 | 1 | 0 | 4946 | 4388 | 4193 | -558 | 5 | 1 | 79 | 1 | 1300000 | 0 | 1219372 | 0 |  | 1 | 5000 | 6 | 77 | 86.5
1197 | 20260930 | 74 | 1 | 1 | 2 | 26 | 2 | 3 | 2 | Active | Initiate & Design | Green | 0.3667 | 0.3015 | 591224 | 205799 | 169808 | 631230 | 27545 | 8446 | 0.866 | 1.05 | 20280430 | 20280731 | 77 | 15 | 6 | 3 | 2 | 1 | 5071 | 4719 | 4452 | -352 | 6 | 0 | 73 | 2 | 1300000 | 0 | 1276826 | 0 |  | 1 | 9000 | 5 | 75 | 93.7
1198 | 20240430 | 75 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.0417 | 0.0509 | 327974 | 12618 | 13388 | 334287 | -4076 | 3306 | 1.323 | 1.247 | 20260331 | 20260331 | 0 | 12 | 1 | 0 | 0 | 0 | 1662 | 1685 | 1588 | 23 | 1 | 0 | 10 | 0 | 800000 | 0 | 607789 | 0 |  | 0 | 0 | 4 | 96 | 100
1199 | 20240531 | 75 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.0833 | 0.0732 | 327974 | 25327 | 23557 | 334697 | 1319 | 451 | 0.947 | 1.019 | 20260331 | 20260331 | 8 | 12 | 1 | 0 | 0 | 0 | 1851 | 1896 | 1801 | 45 | 5 | 0 | 51 | 1 | 800000 | 0 | 604159 | 0 |  | 0 | 0 | 2 | 73 | 91.4
1200 | 20240630 | 75 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.125 | 0.1071 | 327974 | 38127 | 30420 | 335107 | 3001 | 4706 | 0.921 | 1.154 | 20260331 | 20260430 | 15 | 12 | 2 | 2 | 0 | 0 | 2033 | 2016 | 1915 | -17 | 5 | 1 | 69 | 1 | 800000 | 0 | 580872 | 0 |  | 0 | 0 | 5 | 70 | 86
1201 | 20240731 | 75 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.1667 | 0.1437 | 327974 | 51018 | 44446 | 335517 | 3888 | 2684 | 0.924 | 1.061 | 20260331 | 20260430 | 20 | 12 | 2 | 2 | 0 | 0 | 2205 | 2287 | 2295 | 82 | 6 | 0 | 61 | 1 | 800000 | 0 | 587118 | 0 |  | 1 | 4000 | 3 | 75 | 91.3
1202 | 20240831 | 75 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.2083 | 0.2123 | 327974 | 64000 | 62394 | 335927 | -5629 | 7235 | 1.088 | 1.116 | 20260331 | 20260331 | 0 | 12 | 3 | 3 | 0 | 0 | 2365 | 2275 | 2416 | -90 | 4 | 0 | 41 | 1 | 800000 | 0 | 607655 | 0 |  | 1 | 5000 | 2 | 80 | 100
1203 | 20240930 | 75 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.25 | 0.2519 | 327974 | 77074 | 75897 | 336337 | -5543 | 6720 | 1.072 | 1.089 | 20260331 | 20260331 | 0 | 12 | 3 | 2 | 0 | 0 | 2510 | 2580 | 2587 | 70 | 3 | 0 | 31 | 1 | 800000 | 0 | 592934 | 0 |  | 1 | 4000 | 4 | 76 | 99.1
1204 | 20241031 | 75 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.2917 | 0.3084 | 327974 | 90238 | 95649 | 336747 | -10909 | 5498 | 1.121 | 1.058 | 20260331 | 20260331 | 0 | 12 | 4 | 4 | 0 | 0 | 2637 | 2531 | 2406 | -106 | 3 | 0 | 31 | 1 | 800000 | 0 | 592275 | 0 |  | 1 | 3000 | 2 | 81 | 99.3
1205 | 20241130 | 75 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Deliver | Green | 0.3333 | 0.3526 | 327974 | 103494 | 107828 | 337157 | -12150 | 7816 | 1.117 | 1.072 | 20260331 | 20260331 | 0 | 12 | 4 | 3 | 0 | 0 | 2743 | 2607 | 2674 | -136 | 4 | 0 | 41 | 1 | 800000 | 0 | 591173 | 0 |  | 1 | 5000 | 2 | 81 | 99.4
1206 | 20241231 | 75 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Deliver | Green | 0.375 | 0.4024 | 327974 | 116841 | 125005 | 337567 | -15136 | 6972 | 1.129 | 1.056 | 20260331 | 20260331 | 0 | 12 | 5 | 5 | 0 | 0 | 2829 | 3007 | 2948 | 178 | 4 | 0 | 41 | 1 | 800000 | 0 | 606362 | 0 |  | 1 | 5000 | 3 | 81 | 100
1207 | 20250131 | 75 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Deliver | Green | 0.4167 | 0.4391 | 327974 | 130279 | 140511 | 337977 | -13734 | 3502 | 1.105 | 1.025 | 20260331 | 20260331 | 0 | 12 | 5 | 5 | 0 | 0 | 2890 | 2972 | 2946 | 82 | 3 | 0 | 31 | 1 | 800000 | 0 | 587207 | 0 |  | 1 | 3000 | 5 | 80 | 98.2
1208 | 20250228 | 75 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Deliver | Green | 0.4583 | 0.4642 | 327974 | 143807 | 146728 | 338387 | -8439 | 5518 | 1.059 | 1.038 | 20260331 | 20260331 | 0 | 12 | 6 | 5 | 0 | 0 | 2928 | 3071 | 2977 | 143 | 5 | 0 | 51 | 1 | 800000 | 0 | 609257 | 0 |  | 1 | 5000 | 5 | 73 | 97.3
1209 | 20250331 | 75 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Deliver | Green | 0.5 | 0.5025 | 327974 | 157428 | 159698 | 338797 | -7379 | 5109 | 1.047 | 1.032 | 20260331 | 20260331 | 0 | 12 | 6 | 5 | 0 | 0 | 2940 | 2956 | 3018 | 16 | 4 | 1 | 59 | 1 | 800000 | 0 | 587897 | 0 |  | 1 | 3000 | 5 | 74 | 87.8
1210 | 20250430 | 75 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Deliver | Green | 0.5417 | 0.5376 | 327974 | 171139 | 170870 | 339207 | -5180 | 5449 | 1.03 | 1.032 | 20260331 | 20260331 | 4 | 12 | 7 | 6 | 0 | 0 | 2928 | 2996 | 2838 | 68 | 2 | 0 | 20 | 0 | 800000 | 0 | 611973 | 0 |  | 1 | 3000 | 5 | 72 | 95.9
1211 | 20250531 | 75 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Deliver | Green | 0.5833 | 0.5808 | 327974 | 184941 | 189563 | 339617 | -5546 | 924 | 1.03 | 1.005 | 20260331 | 20260331 | 2 | 12 | 7 | 7 | 0 | 0 | 2890 | 2809 | 2909 | -81 | 3 | 0 | 31 | 1 | 800000 | 0 | 606659 | 0 |  | 1 | 5000 | 3 | 74 | 94.1
1212 | 20250630 | 75 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Deliver | Green | 0.625 | 0.6334 | 327974 | 198834 | 206658 | 340027 | -8905 | 1081 | 1.045 | 1.005 | 20260331 | 20260331 | 0 | 12 | 8 | 7 | 0 | 0 | 2829 | 2870 | 3052 | 41 | 3 | 1 | 49 | 1 | 800000 | 0 | 611143 | 0 |  | 1 | 4000 | 2 | 68 | 87.6
1213 | 20250731 | 75 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Deliver | Green | 0.6667 | 0.6876 | 327974 | 212819 | 223275 | 340437 | -12696 | 2240 | 1.06 | 1.01 | 20260331 | 20260331 | 0 | 12 | 8 | 7 | 0 | 0 | 2743 | 2817 | 2910 | 74 | 4 | 0 | 41 | 1 | 800000 | 0 | 614204 | 0 |  | 1 | 3000 | 2 | 78 | 96.5
1214 | 20250831 | 75 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Deliver | Green | 0.7083 | 0.7417 | 327974 | 226894 | 243834 | 341014 | -16364 | -576 | 1.072 | 0.998 | 20260331 | 20260331 | 0 | 12 | 9 | 9 | 0 | 0 | 2637 | 2638 | 2638 | 1 | 4 | 1 | 59 | 1 | 800000 | 0 | 599065 | 0 |  | 1 | 4000 | 4 | 71 | 88.1
1215 | 20250930 | 75 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Deploy | Green | 0.75 | 0.7839 | 327974 | 241061 | 258454 | 341637 | -16038 | -1355 | 1.067 | 0.995 | 20260331 | 20260331 | 0 | 12 | 9 | 9 | 0 | 0 | 2510 | 2629 | 2487 | 119 | 3 | 0 | 31 | 1 | 800000 | 85714 | 601596 | 0 | 0 | 1 | 4000 | 3 | 74 | 95.9
1216 | 20251031 | 75 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Deploy | Green | 0.7917 | 0.797 | 327974 | 255319 | 264605 | 342539 | -6076 | -3210 | 1.024 | 0.988 | 20260331 | 20260331 | 0 | 12 | 10 | 10 | 0 | 0 | 2365 | 2317 | 2391 | -48 | 3 | 0 | 31 | 1 | 800000 | 204762 | 614919 | 23237 | 0.1135 | 1 | 4000 | 4 | 77 | 93.7
1217 | 20251130 | 75 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Deploy | Green | 0.8333 | 0.8353 | 327974 | 269668 | 281683 | 344057 | -4289 | -7726 | 1.016 | 0.973 | 20260331 | 20260331 | 0 | 12 | 10 | 9 | 0 | 0 | 2205 | 2222 | 2260 | 17 | 2 | 0 | 20 | 0 | 800000 | 323810 | 585439 | 91193 | 0.2816 | 1 | 5000 | 1 | 74 | 92.2
1218 | 20251231 | 75 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Deploy | Green | 0.875 | 0.8657 | 327974 | 284107 | 290894 | 344217 | 180 | -6967 | 0.999 | 0.976 | 20260331 | 20260331 | 8 | 12 | 11 | 10 | 0 | 0 | 2033 | 2115 | 2197 | 82 | 3 | 1 | 49 | 1 | 800000 | 442857 | 612712 | 184901 | 0.4175 | 1 | 5000 | 0 | 66 | 84.6
1219 | 20260131 | 75 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Deploy | Green | 0.9167 | 0.9035 | 327974 | 298639 | 306641 | 345328 | 2314 | -10316 | 0.992 | 0.966 | 20260331 | 20260331 | 12 | 12 | 11 | 11 | 0 | 0 | 1851 | 1975 | 1928 | 124 | 2 | 0 | 20 | 0 | 800000 | 561905 | 593485 | 254050 | 0.4521 | 1 | 4000 | 2 | 68 | 91.2
1220 | 20260228 | 75 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Deploy | Green | 0.9583 | 0.9645 | 327974 | 313261 | 330577 | 346418 | -3070 | -14246 | 1.01 | 0.957 | 20260331 | 20260331 | 0 | 12 | 12 | 12 | 0 | 0 | 1662 | 1598 | 1691 | -64 | 2 | 0 | 20 | 0 | 800000 | 680952 | 616111 | 323209 | 0.4746 | 1 | 5000 | 0 | 70 | 91.6
1221 | 20260331 | 75 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Completed | Completed | Green | 1 | 1 | 327974 | 327974 | 345970 | 347470 | 0 | -17996 | 1 | 0.948 | 20260331 | 20260331 | 0 | 12 | 12 | 11 | 0 | 0 | 1470 | 1476 | 1474 | 6 | 3 | 1 | 49 | 1 | 800000 | 800000 | 585228 | 408229 | 0.5103 | 1 | 3000 | 1 | 69 | 82.7
1222 | 20240531 | 76 | 5 | 5 | 4 | 28 | 4 | 3 | 4 | Active | Initiate & Design | Red | 0.0417 | 0 | 1167336 | 44910 | 0 | 1317144 | 44910 | 0 | 0 | 1 | 20260430 | 20260531 | 44 | 12 | 1 | 0 | 1 | 1 | 5916 | 5058 | 4934 | -858 | 13 | 3 | 239 | 4 | 900000 | 0 | 631594 | 0 |  | 0 | 0 | 6 | 24 | 19.5
1223 | 20240630 | 76 | 5 | 5 | 4 | 28 | 4 | 3 | 4 | Active | Initiate & Design | Red | 0.0833 | 0 | 1167336 | 90144 | 5263 | 1583686 | 90144 | -5263 | 0 | 0 | 20260430 | 20260731 | 88 | 12 | 1 | 0 | 1 | 1 | 6587 | 5514 | 5872 | -1073 | 13 | 3 | 239 | 4 | 900000 | 0 | 617246 | 0 |  | 0 | 0 | 7 | 24 | 0
1224 | 20240731 | 76 | 5 | 5 | 4 | 28 | 4 | 3 | 4 | Active | Initiate & Design | Red | 0.125 | 0.0146 | 1167336 | 135703 | 16901 | 1336600 | 118660 | 142 | 0.126 | 1.01 | 20260430 | 20260831 | 116 | 12 | 2 | 0 | 1 | 1 | 7235 | 6272 | 6502 | -963 | 12 | 3 | 225 | 4 | 900000 | 0 | 641446 | 0 |  | 1 | 12000 | 7 | 24 | 26
1225 | 20240831 | 76 | 5 | 5 | 4 | 28 | 4 | 3 | 4 | Active | Initiate & Design | Red | 0.1667 | 0.0342 | 1167336 | 181586 | 31264 | 1346328 | 141663 | 8659 | 0.22 | 1.277 | 20260430 | 20260930 | 139 | 12 | 2 | 1 | 1 | 1 | 7849 | 6139 | 6316 | -1710 | 14 | 3 | 253 | 5 | 900000 | 0 | 623041 | 0 |  | 1 | 12000 | 7 | 35 | 37.2
1226 | 20240930 | 76 | 5 | 5 | 4 | 28 | 4 | 3 | 4 | Active | Initiate & Design | Amber | 0.2083 | 0.0956 | 1167336 | 227793 | 109688 | 1356055 | 116196 | 1909 | 0.49 | 1.017 | 20260430 | 20260831 | 119 | 12 | 3 | 0 | 2 | 1 | 8418 | 7031 | 6865 | -1387 | 12 | 2 | 207 | 4 | 900000 | 0 | 646443 | 0 |  | 1 | 12000 | 5 | 42 | 50.1
1227 | 20241031 | 76 | 5 | 5 | 4 | 28 | 4 | 3 | 4 | Active | Initiate & Design | Red | 0.25 | 0.1219 | 1167336 | 274324 | 134572 | 1365783 | 132026 | 7726 | 0.519 | 1.058 | 20260430 | 20260930 | 135 | 12 | 3 | 0 | 2 | 1 | 8933 | 7622 | 7307 | -1311 | 12 | 3 | 225 | 4 | 900000 | 0 | 628116 | 0 |  | 1 | 12000 | 8 | 37 | 44.7
1228 | 20241130 | 76 | 5 | 5 | 4 | 28 | 4 | 3 | 4 | Active | Initiate & Design | Amber | 0.2917 | 0.1583 | 1167336 | 321180 | 181722 | 1375511 | 136391 | 3067 | 0.575 | 1.017 | 20260430 | 20260930 | 141 | 12 | 4 | 0 | 3 | 2 | 9384 | 7482 | 7660 | -1902 | 10 | 2 | 178 | 3 | 900000 | 0 | 646894 | 0 |  | 1 | 11000 | 4 | 48 | 53.2
1229 | 20241231 | 76 | 5 | 5 | 4 | 28 | 4 | 3 | 4 | Active | Initiate & Design | Amber | 0.3333 | 0.1905 | 1167336 | 368359 | 214838 | 1385239 | 145981 | 7540 | 0.604 | 1.035 | 20260430 | 20260930 | 151 | 12 | 4 | 1 | 3 | 2 | 9765 | 7720 | 7712 | -2045 | 11 | 2 | 193 | 4 | 900000 | 0 | 644617 | 0 |  | 1 | 16000 | 7 | 49 | 54.8
1230 | 20250131 | 76 | 5 | 5 | 4 | 28 | 4 | 3 | 4 | Active | Initiate & Design | Red | 0.375 | 0.2217 | 1167336 | 415863 | 263190 | 1399306 | 157065 | -4392 | 0.622 | 0.983 | 20260430 | 20260930 | 161 | 12 | 5 | 1 | 3 | 2 | 10067 | 7704 | 7330 | -2363 | 11 | 3 | 211 | 4 | 900000 | 0 | 641670 | 0 |  | 1 | 17000 | 7 | 43 | 45.2
1231 | 20250228 | 76 | 5 | 5 | 4 | 28 | 4 | 3 | 4 | Active | Initiate & Design | Amber | 0.4167 | 0.2435 | 1167336 | 463692 | 294924 | 1414031 | 179446 | -10678 | 0.613 | 0.964 | 20260430 | 20261031 | 184 | 12 | 5 | 2 | 3 | 2 | 10287 | 8782 | 9108 | -1505 | 11 | 2 | 193 | 4 | 900000 | 0 | 616425 | 0 |  | 1 | 15000 | 4 | 46 | 53.3
1232 | 20250331 | 76 | 5 | 5 | 4 | 28 | 4 | 3 | 4 | Active | Initiate & Design | Amber | 0.4583 | 0.2746 | 1167336 | 511844 | 342574 | 1430966 | 191294 | -22024 | 0.626 | 0.936 | 20260430 | 20261031 | 194 | 12 | 6 | 1 | 4 | 2 | 10421 | 8030 | 8144 | -2391 | 11 | 2 | 193 | 4 | 900000 | 0 | 613439 | 0 |  | 1 | 14000 | 4 | 48 | 51
1233 | 20250430 | 76 | 5 | 5 | 4 | 28 | 4 | 3 | 4 | Active | Initiate & Design | Red | 0.5 | 0.3013 | 1167336 | 560321 | 368434 | 1435792 | 208603 | -16716 | 0.628 | 0.955 | 20260430 | 20261130 | 210 | 12 | 6 | 2 | 4 | 2 | 10466 | 9031 | 9642 | -1435 | 10 | 3 | 196 | 3 | 900000 | 0 | 625239 | 0 |  | 2 | 20000 | 5 | 38 | 46.1
1234 | 20250531 | 76 | 5 | 5 | 4 | 28 | 4 | 3 | 4 | Active | Initiate & Design | Red | 0.5417 | 0.3408 | 1167336 | 609122 | 425017 | 1450306 | 211294 | -27189 | 0.653 | 0.936 | 20260430 | 20261130 | 213 | 12 | 7 | 3 | 4 | 2 | 10421 | 8546 | 8040 | -1875 | 10 | 3 | 196 | 3 | 900000 | 0 | 640015 | 0 |  | 2 | 37000 | 5 | 39 | 46.1
1235 | 20250630 | 76 | 5 | 5 | 4 | 28 | 4 | 3 | 4 | Active | Deliver | Amber | 0.5833 | 0.3838 | 1167336 | 658248 | 481719 | 1461579 | 210224 | -33695 | 0.681 | 0.93 | 20260430 | 20261130 | 211 | 12 | 7 | 3 | 4 | 2 | 10287 | 8317 | 8049 | -1970 | 10 | 2 | 178 | 3 | 900000 | 0 | 617807 | 0 |  | 2 | 35000 | 7 | 46 | 54.2
1236 | 20250731 | 76 | 5 | 5 | 4 | 28 | 4 | 3 | 4 | Active | Deliver | Amber | 0.625 | 0.4354 | 1167336 | 707697 | 555159 | 1475022 | 199439 | -46901 | 0.718 | 0.916 | 20260430 | 20261130 | 201 | 12 | 8 | 4 | 4 | 2 | 10067 | 8723 | 8607 | -1344 | 9 | 2 | 164 | 3 | 900000 | 0 | 628868 | 0 |  | 2 | 19000 | 7 | 48 | 57
1237 | 20250831 | 76 | 5 | 5 | 4 | 28 | 4 | 3 | 4 | Active | Deliver | Amber | 0.6667 | 0.4582 | 1167336 | 757471 | 591479 | 1487643 | 222598 | -56606 | 0.706 | 0.904 | 20260430 | 20261130 | 220 | 12 | 8 | 4 | 4 | 2 | 9765 | 8043 | 8120 | -1722 | 11 | 2 | 193 | 4 | 900000 | 0 | 628727 | 0 |  | 2 | 29000 | 5 | 46 | 55.1
1238 | 20250930 | 76 | 5 | 5 | 4 | 28 | 4 | 3 | 4 | Active | Deliver | Red | 0.7083 | 0.4989 | 1167336 | 807570 | 648110 | 1498823 | 225186 | -65726 | 0.721 | 0.899 | 20260430 | 20261130 | 222 | 12 | 9 | 4 | 5 | 3 | 9384 | 7178 | 6898 | -2206 | 11 | 3 | 211 | 4 | 900000 | 0 | 649720 | 0 |  | 3 | 46000 | 4 | 40 | 46.9
1239 | 20251031 | 76 | 5 | 5 | 4 | 28 | 4 | 3 | 4 | Active | Deliver | Amber | 0.75 | 0.5033 | 1167336 | 857992 | 669777 | 1514077 | 270472 | -82257 | 0.685 | 0.877 | 20260430 | 20270131 | 261 | 12 | 9 | 3 | 5 | 3 | 8933 | 7628 | 7766 | -1305 | 11 | 2 | 193 | 4 | 900000 | 96429 | 649695 | 0 | 0 | 3 | 42000 | 6 | 42 | 54.5
1240 | 20251130 | 76 | 5 | 5 | 4 | 28 | 4 | 3 | 4 | Active | Deliver | Amber | 0.7917 | 0.5416 | 1167336 | 908739 | 723592 | 1524672 | 276510 | -91363 | 0.696 | 0.874 | 20260430 | 20270131 | 264 | 12 | 10 | 4 | 6 | 3 | 8418 | 7126 | 7390 | -1292 | 12 | 2 | 207 | 4 | 900000 | 230357 | 615669 | 22745 | 0.0987 | 3 | 43000 | 7 | 44 | 53.7
1241 | 20251231 | 76 | 5 | 5 | 4 | 28 | 4 | 3 | 4 | Active | Deliver | Amber | 0.8333 | 0.5592 | 1167336 | 959810 | 763700 | 1539275 | 307036 | -110926 | 0.68 | 0.855 | 20260430 | 20270228 | 289 | 12 | 10 | 3 | 6 | 3 | 7849 | 6164 | 6123 | -1685 | 8 | 2 | 150 | 3 | 900000 | 364286 | 614513 | 98509 | 0.2704 | 3 | 38000 | 6 | 45 | 50.9
1242 | 20260131 | 76 | 5 | 5 | 4 | 28 | 4 | 3 | 4 | Active | Deliver | Amber | 0.875 | 0.5845 | 1167336 | 1011205 | 813713 | 1553180 | 328897 | -131405 | 0.675 | 0.838 | 20260430 | 20270228 | 307 | 12 | 11 | 4 | 6 | 3 | 7235 | 5662 | 5604 | -1573 | 9 | 2 | 164 | 3 | 900000 | 498214 | 633063 | 184013 | 0.3693 | 3 | 55000 | 2 | 45 | 50.6
1243 | 20260228 | 76 | 5 | 5 | 4 | 28 | 4 | 3 | 4 | Active | Deliver | Amber | 0.9167 | 0.6375 | 1167336 | 1062924 | 895593 | 1564851 | 318747 | -151416 | 0.7 | 0.831 | 20260430 | 20270228 | 295 | 12 | 11 | 5 | 6 | 3 | 6587 | 5479 | 5515 | -1108 | 8 | 2 | 150 | 3 | 900000 | 632143 | 639771 | 260207 | 0.4116 | 3 | 42000 | 3 | 43 | 52.8
1244 | 20260331 | 76 | 5 | 5 | 4 | 28 | 4 | 3 | 4 | Active | Deliver | Amber | 0.9583 | 0.6742 | 1167336 | 1114968 | 949347 | 1575059 | 327950 | -162329 | 0.706 | 0.829 | 20260430 | 20270228 | 301 | 12 | 12 | 6 | 6 | 3 | 5916 | 4537 | 4797 | -1379 | 9 | 2 | 164 | 3 | 900000 | 766071 | 638489 | 346231 | 0.452 | 4 | 66000 | 3 | 46 | 51.5
1245 | 20260430 | 76 | 5 | 5 | 4 | 28 | 4 | 3 | 4 | Active | Deliver | Amber | 1 | 0.7168 | 1167336 | 1167336 | 1021866 | 1587419 | 330590 | -185120 | 0.717 | 0.819 | 20260430 | 20270228 | 299 | 12 | 12 | 6 | 6 | 3 | 5233 | 4113 | 4085 | -1120 | 9 | 2 | 164 | 3 | 900000 | 900000 | 631809 | 438064 | 0.4867 | 4 | 50000 | 2 | 43 | 51.9
1246 | 20260531 | 76 | 5 | 5 | 4 | 28 | 4 | 3 | 4 | Active | Deliver | Amber | 1 | 0.7168 | 1167336 | 1167336 | 1033533 | 1599521 | 330590 | -196787 | 0.717 | 0.81 | 20260430 | 20270228 | 299 | 12 | 12 | 5 | 6 | 3 | 5233 | 4015 | 4081 | -1218 | 9 | 2 | 164 | 3 | 900000 | 900000 | 624181 | 488471 | 0.5427 | 4 | 58000 | 5 | 46 | 50.9
1247 | 20260630 | 76 | 5 | 5 | 4 | 28 | 4 | 3 | 4 | Active | Deliver | Amber | 1 | 0.7168 | 1167336 | 1167336 | 1046340 | 1611793 | 330590 | -209594 | 0.717 | 0.8 | 20260430 | 20270228 | 299 | 12 | 12 | 5 | 6 | 3 | 5233 | 4307 | 4327 | -926 | 7 | 2 | 136 | 2 | 900000 | 900000 | 626569 | 574339 | 0.6382 | 4 | 56000 | 5 | 42 | 51.8
1248 | 20260731 | 76 | 5 | 5 | 4 | 28 | 4 | 3 | 4 | Active | Deliver | Amber | 1 | 0.7168 | 1167336 | 1167336 | 1052641 | 1622751 | 330590 | -215895 | 0.717 | 0.795 | 20260430 | 20270228 | 299 | 12 | 12 | 5 | 6 | 3 | 5233 | 3988 | 4027 | -1245 | 10 | 2 | 178 | 3 | 900000 | 900000 | 620150 | 610477 | 0.6783 | 4 | 50000 | 5 | 41 | 50.1
1249 | 20260831 | 76 | 5 | 5 | 4 | 28 | 4 | 3 | 4 | Active | Deliver | Amber | 1 | 0.7168 | 1167336 | 1167336 | 1077767 | 1637237 | 330590 | -241021 | 0.717 | 0.776 | 20260430 | 20270228 | 299 | 12 | 12 | 5 | 6 | 3 | 5233 | 4591 | 4658 | -642 | 7 | 2 | 136 | 2 | 900000 | 900000 | 628147 | 622240 | 0.6914 | 4 | 69000 | 4 | 46 | 52.3
1250 | 20260930 | 76 | 5 | 5 | 4 | 28 | 4 | 3 | 4 | Active | Deliver | Amber | 1 | 0.7168 | 1167336 | 1167336 | 1082802 | 1647892 | 330590 | -246056 | 0.717 | 0.773 | 20260430 | 20270228 | 299 | 12 | 12 | 6 | 6 | 3 | 5233 | 4126 | 4081 | -1107 | 7 | 2 | 136 | 2 | 900000 | 900000 | 608748 | 540908 | 0.601 | 4 | 41000 | 2 | 43 | 49.6
1251 | 20240930 | 77 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Initiate & Design | Amber | 0.0476 | 0.0109 | 896234 | 39426 | 8830 | 954276 | 29657 | 939 | 0.248 | 1.105 | 20260531 | 20260630 | 31 | 11 | 1 | 0 | 1 | 0 | 4616 | 4362 | 4563 | -254 | 12 | 2 | 188 | 3 | 2600000 | 0 | 2367426 | 0 |  | 0 | 0 | 4 | 45 | 50.1
1252 | 20241031 | 77 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.0952 | 0.0621 | 896234 | 79177 | 52328 | 958544 | 23521 | 3328 | 0.703 | 1.063 | 20260531 | 20260630 | 28 | 11 | 1 | 0 | 1 | 0 | 5202 | 4810 | 5096 | -392 | 7 | 1 | 106 | 2 | 2600000 | 0 | 2294909 | 0 |  | 0 | 0 | 7 | 67 | 75.9
1253 | 20241130 | 77 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.1429 | 0.109 | 896234 | 119254 | 93266 | 962811 | 21564 | 4424 | 0.819 | 1.047 | 20260531 | 20260630 | 28 | 11 | 2 | 1 | 1 | 0 | 5761 | 5543 | 5356 | -218 | 7 | 1 | 106 | 2 | 2600000 | 0 | 2290006 | 0 |  | 0 | 0 | 6 | 73 | 81.3
1254 | 20241231 | 77 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.1905 | 0.1621 | 896234 | 159656 | 142070 | 967079 | 14376 | 3210 | 0.91 | 1.023 | 20260531 | 20260630 | 24 | 11 | 2 | 2 | 0 | 0 | 6281 | 5695 | 5948 | -586 | 8 | 1 | 119 | 2 | 2600000 | 0 | 2381455 | 0 |  | 1 | 12000 | 3 | 75 | 84.3
1255 | 20250131 | 77 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.2381 | 0.2176 | 896234 | 200382 | 187820 | 971347 | 5361 | 7201 | 0.973 | 1.038 | 20260531 | 20260630 | 18 | 11 | 3 | 3 | 0 | 0 | 6750 | 6148 | 6349 | -602 | 8 | 1 | 119 | 2 | 2600000 | 0 | 2316244 | 0 |  | 1 | 12000 | 5 | 78 | 87.1
1256 | 20250228 | 77 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.2857 | 0.2675 | 896234 | 241434 | 234604 | 975615 | 1691 | 5139 | 0.993 | 1.022 | 20260531 | 20260630 | 15 | 11 | 3 | 3 | 0 | 0 | 7159 | 6938 | 6855 | -221 | 6 | 1 | 94 | 2 | 2600000 | 0 | 2353917 | 0 |  | 1 | 8000 | 4 | 75 | 89.1
1257 | 20250331 | 77 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Initiate & Design | Green | 0.3333 | 0.3044 | 896234 | 282812 | 263149 | 979883 | 9998 | 9665 | 0.965 | 1.037 | 20260531 | 20260630 | 24 | 11 | 4 | 4 | 0 | 0 | 7497 | 7199 | 7153 | -298 | 7 | 1 | 106 | 2 | 2600000 | 0 | 2313951 | 0 |  | 1 | 12000 | 6 | 76 | 87.7
1258 | 20250430 | 77 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.381 | 0.3568 | 896234 | 324514 | 315512 | 984150 | 4738 | 4264 | 0.985 | 1.013 | 20260531 | 20260630 | 20 | 11 | 4 | 4 | 0 | 0 | 7757 | 7771 | 7810 | 14 | 6 | 1 | 94 | 2 | 2600000 | 0 | 2344655 | 0 |  | 1 | 10000 | 5 | 81 | 89.1
1259 | 20250531 | 77 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.4286 | 0.3857 | 896234 | 366541 | 344520 | 988418 | 20864 | 1157 | 0.943 | 1.003 | 20260531 | 20260630 | 36 | 11 | 5 | 3 | 1 | 0 | 7934 | 7476 | 7591 | -458 | 8 | 1 | 119 | 2 | 2600000 | 0 | 2357722 | 0 |  | 1 | 12000 | 5 | 71 | 85.7
1260 | 20250630 | 77 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.4762 | 0.4173 | 896234 | 408894 | 377148 | 994314 | 34896 | -3150 | 0.915 | 0.992 | 20260531 | 20260731 | 50 | 11 | 5 | 4 | 1 | 0 | 8024 | 7435 | 7071 | -589 | 8 | 1 | 119 | 2 | 2600000 | 0 | 2327700 | 0 |  | 1 | 10000 | 3 | 76 | 83.3
1261 | 20250731 | 77 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.5238 | 0.4637 | 896234 | 451572 | 417832 | 998020 | 35988 | -2248 | 0.92 | 0.995 | 20260531 | 20260731 | 51 | 11 | 6 | 4 | 1 | 0 | 8024 | 7406 | 7693 | -618 | 6 | 1 | 94 | 2 | 2600000 | 0 | 2293581 | 0 |  | 1 | 10000 | 7 | 77 | 83.2
1262 | 20250831 | 77 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.5714 | 0.5099 | 896234 | 494575 | 469549 | 1006507 | 37585 | -12559 | 0.924 | 0.973 | 20260531 | 20260731 | 53 | 11 | 6 | 5 | 1 | 0 | 7934 | 7282 | 7447 | -652 | 6 | 1 | 94 | 2 | 2600000 | 0 | 2375919 | 0 |  | 1 | 10000 | 5 | 73 | 83.4
1263 | 20250930 | 77 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.619 | 0.5648 | 896234 | 537903 | 526106 | 1012938 | 31710 | -19913 | 0.941 | 0.962 | 20260531 | 20260731 | 46 | 11 | 7 | 5 | 1 | 0 | 7757 | 7554 | 7748 | -203 | 8 | 1 | 119 | 2 | 2600000 | 0 | 2294177 | 0 |  | 1 | 10000 | 7 | 72 | 84.2
1264 | 20251031 | 77 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.6667 | 0.639 | 896234 | 581556 | 603142 | 1019713 | 8862 | -30448 | 0.985 | 0.95 | 20260531 | 20260630 | 23 | 11 | 7 | 6 | 1 | 0 | 7497 | 6865 | 6754 | -632 | 7 | 1 | 106 | 2 | 2600000 | 0 | 2345457 | 0 |  | 1 | 9000 | 6 | 78 | 85
1265 | 20251130 | 77 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.7143 | 0.6699 | 896234 | 625535 | 638926 | 1025921 | 25148 | -38539 | 0.96 | 0.94 | 20260531 | 20260630 | 38 | 11 | 8 | 7 | 1 | 0 | 7159 | 7128 | 7330 | -31 | 7 | 1 | 106 | 2 | 2600000 | 0 | 2355369 | 0 |  | 1 | 9000 | 4 | 77 | 85.3
1266 | 20251231 | 77 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.7619 | 0.7209 | 896234 | 669838 | 691793 | 1031308 | 23743 | -45698 | 0.965 | 0.934 | 20260531 | 20260630 | 35 | 11 | 8 | 6 | 1 | 0 | 6750 | 6097 | 6043 | -653 | 8 | 2 | 137 | 2 | 2600000 | 389116 | 2276136 | 0 | 0 | 2 | 26000 | 5 | 72 | 74.5
1267 | 20260131 | 77 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deliver | Green | 0.8095 | 0.7454 | 896234 | 714467 | 714202 | 1035304 | 46414 | -46149 | 0.935 | 0.935 | 20260531 | 20260731 | 54 | 11 | 9 | 6 | 2 | 1 | 6281 | 6263 | 6028 | -18 | 6 | 1 | 94 | 2 | 2600000 | 831293 | 2344524 | 210716 | 0.2535 | 2 | 25000 | 2 | 69 | 84
1268 | 20260228 | 77 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deploy | Green | 0.8571 | 0.7952 | 896234 | 759421 | 776571 | 1043057 | 46736 | -63886 | 0.938 | 0.918 | 20260531 | 20260731 | 53 | 11 | 9 | 8 | 1 | 0 | 5761 | 5414 | 5371 | -347 | 4 | 0 | 51 | 1 | 2600000 | 1273469 | 2398182 | 611558 | 0.4802 | 2 | 21000 | 4 | 75 | 90.8
1269 | 20260331 | 77 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deploy | Green | 0.9048 | 0.8283 | 896234 | 804700 | 816059 | 1048895 | 62349 | -73708 | 0.923 | 0.91 | 20260531 | 20260731 | 65 | 11 | 10 | 8 | 2 | 1 | 5202 | 4714 | 4908 | -488 | 6 | 1 | 94 | 2 | 2600000 | 1715646 | 2305588 | 883119 | 0.5147 | 2 | 28000 | 3 | 73 | 80.1
1270 | 20260430 | 77 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deploy | Green | 0.9524 | 0.8768 | 896234 | 850305 | 872802 | 1055019 | 64487 | -86984 | 0.924 | 0.9 | 20260531 | 20260731 | 65 | 11 | 10 | 8 | 2 | 1 | 4616 | 4209 | 4462 | -407 | 6 | 1 | 94 | 2 | 2600000 | 2157823 | 2281208 | 1165207 | 0.54 | 2 | 24000 | 3 | 66 | 79.7
1271 | 20260531 | 77 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deploy | Green | 1 | 0.9323 | 896234 | 896234 | 932835 | 1060191 | 60675 | -97276 | 0.932 | 0.896 | 20260531 | 20260731 | 58 | 11 | 11 | 9 | 2 | 1 | 4018 | 4046 | 3814 | 28 | 6 | 1 | 94 | 2 | 2600000 | 2600000 | 2349406 | 1611269 | 0.6197 | 2 | 28000 | 2 | 71 | 82.6
1272 | 20260630 | 77 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deploy | Green | 1 | 0.9433 | 896234 | 896234 | 957293 | 1066944 | 50816 | -111875 | 0.943 | 0.883 | 20260531 | 20260731 | 49 | 11 | 11 | 8 | 2 | 1 | 4018 | 3992 | 4155 | -26 | 5 | 1 | 81 | 1 | 2600000 | 2600000 | 2391426 | 1964618 | 0.7556 | 2 | 26000 | 3 | 67 | 83
1273 | 20260731 | 77 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deploy | Green | 1 | 0.9433 | 896234 | 896234 | 961192 | 1071918 | 50816 | -115774 | 0.943 | 0.88 | 20260531 | 20260731 | 49 | 11 | 11 | 9 | 2 | 1 | 4018 | 4020 | 3894 | 2 | 6 | 1 | 94 | 2 | 2600000 | 2600000 | 2357665 | 2108468 | 0.8109 | 2 | 26000 | 3 | 71 | 82.6
1274 | 20260831 | 77 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deploy | Green | 1 | 0.9433 | 896234 | 896234 | 979325 | 1079397 | 50816 | -133907 | 0.943 | 0.863 | 20260531 | 20260731 | 49 | 11 | 11 | 9 | 2 | 1 | 4018 | 3954 | 4223 | -64 | 5 | 1 | 81 | 1 | 2600000 | 2600000 | 2383107 | 2115339 | 0.8136 | 3 | 30000 | 2 | 72 | 82
1275 | 20260930 | 77 | 1 | 1 | 5 | 29 | 5 | 2 | 5 | Active | Deploy | Green | 1 | 0.9433 | 896234 | 896234 | 992164 | 1085868 | 50816 | -146746 | 0.943 | 0.852 | 20260531 | 20260731 | 49 | 11 | 11 | 9 | 2 | 1 | 4018 | 3682 | 3666 | -336 | 5 | 1 | 81 | 1 | 2600000 | 2600000 | 2288623 | 2241866 | 0.8623 | 3 | 38000 | 1 | 72 | 79.1
1276 | 20240930 | 78 | 7 | 5 | 6 | 30 | 6 | 3 | 6 | Active | Initiate & Design | Green | 0.0833 | 0.0718 | 1211768 | 93575 | 78236 | 1220048 | 6570 | 8769 | 0.93 | 1.112 | 20250831 | 20250831 | 4 | 6 | 1 | 0 | 0 | 0 | 6838 | 6691 | 6756 | -147 | 4 | 0 | 38 | 1 | 1900000 | 0 | 1902273 | 0 |  | 0 | 0 | 1 | 83 | 100
1277 | 20241031 | 78 | 7 | 5 | 6 | 30 | 6 | 3 | 6 | Active | Initiate & Design | Green | 0.1667 | 0.1643 | 1211768 | 188497 | 185524 | 1221058 | -10596 | 13569 | 1.056 | 1.073 | 20250831 | 20250831 | 1 | 6 | 1 | 1 | 0 | 0 | 8148 | 8268 | 8575 | 120 | 1 | 0 | 10 | 0 | 1900000 | 0 | 1894423 | 0 |  | 0 | 0 | 2 | 88 | 100
1278 | 20241130 | 78 | 7 | 5 | 6 | 30 | 6 | 3 | 6 | Active | Initiate & Design | Green | 0.25 | 0.2707 | 1211768 | 284765 | 314743 | 1222068 | -43261 | 13283 | 1.152 | 1.042 | 20250831 | 20250831 | 0 | 6 | 2 | 1 | 0 | 0 | 9273 | 9463 | 9762 | 190 | 1 | 0 | 10 | 0 | 1900000 | 0 | 1951486 | 0 |  | 0 | 0 | 4 | 93 | 100
1279 | 20241231 | 78 | 7 | 5 | 6 | 30 | 6 | 3 | 6 | Active | Initiate & Design | Green | 0.3333 | 0.3425 | 1211768 | 382380 | 391237 | 1223078 | -32651 | 23794 | 1.085 | 1.061 | 20250831 | 20250831 | 0 | 6 | 2 | 2 | 0 | 0 | 10136 | 10246 | 9907 | 110 | 3 | 0 | 29 | 1 | 1900000 | 0 | 1957033 | 0 |  | 0 | 0 | 1 | 91 | 100
1280 | 20250131 | 78 | 7 | 5 | 6 | 30 | 6 | 3 | 6 | Active | Deliver | Green | 0.4167 | 0.4419 | 1211768 | 481341 | 502739 | 1224088 | -54139 | 32741 | 1.113 | 1.065 | 20250831 | 20250831 | 0 | 6 | 3 | 2 | 0 | 0 | 10679 | 10829 | 11431 | 150 | 1 | 0 | 10 | 0 | 1900000 | 0 | 1979598 | 0 |  | 0 | 0 | 2 | 88 | 100
1281 | 20250228 | 78 | 7 | 5 | 6 | 30 | 6 | 3 | 6 | Active | Deliver | Green | 0.5 | 0.5209 | 1211768 | 581649 | 601417 | 1225097 | -49561 | 29793 | 1.085 | 1.05 | 20250831 | 20250831 | 0 | 6 | 3 | 3 | 0 | 0 | 10864 | 11515 | 10930 | 651 | 3 | 0 | 29 | 1 | 1900000 | 0 | 1962279 | 0 |  | 0 | 0 | 2 | 88 | 100
1282 | 20250331 | 78 | 7 | 5 | 6 | 30 | 6 | 3 | 6 | Active | Deliver | Green | 0.5833 | 0.5848 | 1211768 | 683303 | 696522 | 1226107 | -25339 | 12120 | 1.037 | 1.017 | 20250831 | 20250831 | 0 | 6 | 4 | 3 | 0 | 0 | 10679 | 11004 | 10624 | 325 | 3 | 0 | 29 | 1 | 1900000 | 0 | 1905395 | 0 |  | 0 | 0 | 4 | 84 | 100
1283 | 20250430 | 78 | 7 | 5 | 6 | 30 | 6 | 3 | 6 | Active | Deliver | Green | 0.6667 | 0.6779 | 1211768 | 786303 | 805238 | 1227117 | -35155 | 16220 | 1.045 | 1.02 | 20250831 | 20250831 | 0 | 6 | 4 | 3 | 0 | 0 | 10136 | 10357 | 10405 | 221 | 2 | 0 | 19 | 0 | 1900000 | 0 | 1966974 | 0 |  | 1 | 18000 | 5 | 83 | 100
1284 | 20250531 | 78 | 7 | 5 | 6 | 30 | 6 | 3 | 6 | Active | Deploy | Green | 0.75 | 0.7513 | 1211768 | 890649 | 905674 | 1228127 | -19752 | 4727 | 1.022 | 1.005 | 20250831 | 20250831 | 0 | 6 | 5 | 5 | 0 | 0 | 9273 | 9171 | 8923 | -102 | 2 | 0 | 19 | 0 | 1900000 | 203571 | 1967484 | 0 | 0 | 1 | 15000 | 3 | 82 | 100
1285 | 20250630 | 78 | 7 | 5 | 6 | 30 | 6 | 3 | 6 | Active | Deploy | Green | 0.8333 | 0.8211 | 1211768 | 996343 | 995219 | 1229214 | 1360 | -236 | 0.999 | 1 | 20250831 | 20250831 | 4 | 6 | 5 | 4 | 0 | 0 | 8148 | 7855 | 8089 | -293 | 1 | 0 | 10 | 0 | 1900000 | 769048 | 1907367 | 304047 | 0.3954 | 1 | 19000 | 0 | 81 | 99.1
1286 | 20250731 | 78 | 7 | 5 | 6 | 30 | 6 | 3 | 6 | Active | Deploy | Green | 0.9167 | 0.9135 | 1211768 | 1103382 | 1132462 | 1236144 | -3568 | -25512 | 1.003 | 0.978 | 20250831 | 20250831 | 1 | 6 | 6 | 5 | 0 | 0 | 6838 | 7367 | 7834 | 529 | 1 | 0 | 10 | 0 | 1900000 | 1334524 | 1983283 | 797827 | 0.5978 | 1 | 16000 | 0 | 82 | 99.4
1287 | 20250831 | 78 | 7 | 5 | 6 | 30 | 6 | 3 | 6 | Completed | Completed | Green | 1 | 1 | 1211768 | 1211768 | 1252448 | 1252448 | 0 | -40680 | 1 | 0.968 | 20250831 | 20250831 | 0 | 6 | 6 | 5 | 0 | 0 | 5432 | 5363 | 5133 | -69 | 1 | 0 | 10 | 0 | 1900000 | 1900000 | 1935682 | 1401483 | 0.7376 | 1 | 12000 | 2 | 80 | 98.6
1288 | 20251031 | 79 | 10 | 7 | 7 | 31 | 7 | 3 | 7 | Active | Initiate & Design | Green | 0.0667 | 0.0898 | 1227062 | 75696 | 107249 | 1251603 | -34494 | 2941 | 1.456 | 1.028 | 20261231 | 20261231 | 0 | 8 | 1 | 1 | 0 | 0 | 6644 | 7458 | 7457 | 814 | 1 | 0 | 9 | 0 | 3400000 | 0 | 3628611 | 0 |  | 0 | 0 | 7 | 96 | 100
1289 | 20251130 | 79 | 10 | 7 | 7 | 31 | 7 | 3 | 7 | Active | Initiate & Design | Green | 0.1333 | 0.158 | 1227062 | 152265 | 174560 | 1254057 | -41611 | 19316 | 1.274 | 1.111 | 20261231 | 20261231 | 0 | 8 | 1 | 0 | 0 | 0 | 7738 | 8559 | 8446 | 821 | 1 | 0 | 9 | 0 | 3400000 | 0 | 3591219 | 0 |  | 0 | 0 | 5 | 96 | 100
1290 | 20251231 | 79 | 10 | 7 | 7 | 31 | 7 | 3 | 7 | Active | Initiate & Design | Green | 0.2 | 0.2493 | 1227062 | 229706 | 280023 | 1256511 | -76201 | 25884 | 1.331 | 1.092 | 20261231 | 20261231 | 0 | 8 | 2 | 2 | 0 | 0 | 8734 | 8927 | 8650 | 193 | 0 | 0 | 0 | 0 | 3400000 | 0 | 3674636 | 0 |  | 0 | 0 | 8 | 96 | 100
1291 | 20260131 | 79 | 10 | 7 | 7 | 31 | 7 | 3 | 7 | Active | Initiate & Design | Green | 0.2667 | 0.3358 | 1227062 | 308020 | 394052 | 1258966 | -104027 | 17995 | 1.338 | 1.046 | 20261231 | 20261231 | 0 | 8 | 2 | 2 | 0 | 0 | 9588 | 10738 | 10144 | 1150 | 1 | 0 | 9 | 0 | 3400000 | 0 | 3590475 | 0 |  | 0 | 0 | 5 | 96 | 100
1292 | 20260228 | 79 | 10 | 7 | 7 | 31 | 7 | 3 | 7 | Active | Deliver | Green | 0.3333 | 0.3917 | 1227062 | 387206 | 458620 | 1261420 | -93434 | 22020 | 1.241 | 1.048 | 20261231 | 20261231 | 0 | 8 | 3 | 2 | 0 | 0 | 10264 | 11510 | 12143 | 1246 | 1 | 0 | 9 | 0 | 3400000 | 0 | 3742751 | 0 |  | 0 | 0 | 4 | 94 | 100
1293 | 20260331 | 79 | 10 | 7 | 7 | 31 | 7 | 3 | 7 | Active | Deliver | Green | 0.4 | 0.464 | 1227062 | 467265 | 553743 | 1263874 | -102092 | 15614 | 1.218 | 1.028 | 20261231 | 20261231 | 0 | 8 | 3 | 2 | 0 | 0 | 10732 | 11424 | 11845 | 692 | 3 | 0 | 27 | 0 | 3400000 | 0 | 3709851 | 0 |  | 1 | 19000 | 5 | 95 | 100
1294 | 20260430 | 79 | 10 | 7 | 7 | 31 | 7 | 3 | 7 | Active | Deliver | Green | 0.4667 | 0.5067 | 1227062 | 548197 | 601185 | 1266328 | -73555 | 20567 | 1.134 | 1.034 | 20261231 | 20261231 | 0 | 8 | 4 | 3 | 0 | 0 | 10971 | 11268 | 11878 | 297 | 2 | 0 | 18 | 0 | 3400000 | 0 | 3654346 | 0 |  | 1 | 12000 | 7 | 87 | 100
1295 | 20260531 | 79 | 10 | 7 | 7 | 31 | 7 | 3 | 7 | Active | Deliver | Green | 0.5333 | 0.5844 | 1227062 | 630001 | 705936 | 1268782 | -87094 | 11159 | 1.138 | 1.016 | 20261231 | 20261231 | 0 | 8 | 4 | 3 | 0 | 0 | 10971 | 11330 | 11062 | 359 | 1 | 0 | 9 | 0 | 3400000 | 0 | 3608243 | 0 |  | 1 | 16000 | 4 | 87 | 100
1296 | 20260630 | 79 | 10 | 7 | 7 | 31 | 7 | 3 | 7 | Active | Deliver | Green | 0.6 | 0.6515 | 1227062 | 712678 | 792308 | 1271236 | -86753 | 7123 | 1.122 | 1.009 | 20261231 | 20261231 | 0 | 8 | 5 | 5 | 0 | 0 | 10732 | 11783 | 11995 | 1051 | 3 | 0 | 27 | 0 | 3400000 | 0 | 3647588 | 0 |  | 1 | 18000 | 5 | 90 | 100
1297 | 20260731 | 79 | 10 | 7 | 7 | 31 | 7 | 3 | 7 | Active | Deliver | Green | 0.6667 | 0.7402 | 1227062 | 796227 | 903328 | 1273690 | -112044 | 4943 | 1.141 | 1.006 | 20261231 | 20261231 | 0 | 8 | 5 | 5 | 0 | 0 | 10264 | 11258 | 10637 | 994 | 3 | 0 | 27 | 0 | 3400000 | 0 | 3614402 | 0 |  | 1 | 12000 | 8 | 89 | 100
1298 | 20260831 | 79 | 10 | 7 | 7 | 31 | 7 | 3 | 7 | Active | Deploy | Green | 0.7333 | 0.802 | 1227062 | 880649 | 999378 | 1280285 | -103455 | -15274 | 1.117 | 0.985 | 20261231 | 20261231 | 0 | 8 | 6 | 6 | 0 | 0 | 9588 | 10369 | 10243 | 781 | 1 | 0 | 9 | 0 | 3400000 | 161905 | 3713045 | 0 | 0 | 1 | 19000 | 4 | 83 | 100
1299 | 20260930 | 79 | 10 | 7 | 7 | 31 | 7 | 3 | 7 | Active | Deploy | Green | 0.8 | 0.9011 | 1227062 | 965943 | 1128686 | 1284105 | -139763 | -22980 | 1.145 | 0.98 | 20261231 | 20261231 | 0 | 8 | 6 | 5 | 0 | 0 | 8734 | 9945 | 10229 | 1211 | 3 | 0 | 27 | 0 | 3400000 | 971429 | 3636474 | 229502 | 0.2363 | 1 | 15000 | 6 | 90 | 100
1300 | 20250630 | 80 | 7 | 5 | 8 | 32 | 8 | 1 | 8 | Active | Initiate & Design | Red | 0.0333 | 0 | 848953 | 26110 | 0 | 875837 | 26110 | 0 | 0 | 1 | 20271130 | 20271231 | 39 | 15 | 1 | 0 | 1 | 0 | 4203 | 3108 | 3273 | -1095 | 12 | 1 | 160 | 3 | 2000000 | 0 | 1899872 | 0 |  | 0 | 0 | 3 | 34 | 39.9
1301 | 20250731 | 80 | 7 | 5 | 8 | 32 | 8 | 1 | 8 | Active | Initiate & Design | Amber | 0.0667 | 0.0219 | 848953 | 52371 | 13829 | 877251 | 33779 | 4763 | 0.355 | 1.345 | 20271130 | 20280131 | 52 | 15 | 1 | 0 | 1 | 0 | 4597 | 3831 | 3863 | -766 | 10 | 2 | 154 | 3 | 2000000 | 0 | 1857382 | 0 |  | 0 | 0 | 3 | 51 | 61.4
1302 | 20250831 | 80 | 7 | 5 | 8 | 32 | 8 | 1 | 8 | Active | Initiate & Design | Green | 0.1 | 0.0638 | 848953 | 78783 | 44741 | 878666 | 24620 | 9422 | 0.688 | 1.211 | 20271130 | 20271231 | 43 | 15 | 2 | 1 | 1 | 0 | 4982 | 3646 | 3817 | -1336 | 7 | 1 | 101 | 2 | 2000000 | 0 | 1830139 | 0 |  | 0 | 0 | 5 | 70 | 77
1303 | 20250930 | 80 | 7 | 5 | 8 | 32 | 8 | 1 | 8 | Active | Initiate & Design | Green | 0.1333 | 0.0932 | 848953 | 105346 | 69582 | 880081 | 26224 | 9540 | 0.751 | 1.137 | 20271130 | 20280131 | 46 | 15 | 2 | 0 | 1 | 0 | 5354 | 4276 | 4079 | -1078 | 6 | 1 | 89 | 2 | 2000000 | 0 | 1896783 | 0 |  | 1 | 7000 | 3 | 74 | 79.7
1304 | 20251031 | 80 | 7 | 5 | 8 | 32 | 8 | 1 | 8 | Active | Initiate & Design | Green | 0.1667 | 0.1005 | 848953 | 132059 | 80484 | 881496 | 46739 | 4836 | 0.646 | 1.06 | 20271130 | 20280229 | 77 | 15 | 3 | 0 | 2 | 1 | 5708 | 4178 | 4238 | -1530 | 8 | 1 | 113 | 2 | 2000000 | 0 | 1854776 | 0 |  | 1 | 13000 | 4 | 66 | 70.2
1305 | 20251130 | 80 | 7 | 5 | 8 | 32 | 8 | 1 | 8 | Active | Initiate & Design | Green | 0.2 | 0.1355 | 848953 | 158924 | 108547 | 882911 | 43891 | 6486 | 0.724 | 1.06 | 20271130 | 20280229 | 75 | 15 | 3 | 1 | 1 | 0 | 6043 | 4834 | 4797 | -1209 | 7 | 1 | 101 | 2 | 2000000 | 0 | 1844008 | 0 |  | 1 | 9000 | 5 | 71 | 75.1
1306 | 20251231 | 80 | 7 | 5 | 8 | 32 | 8 | 1 | 8 | Active | Initiate & Design | Green | 0.2333 | 0.139 | 848953 | 185940 | 108547 | 884326 | 67936 | 9457 | 0.635 | 1.087 | 20271130 | 20280331 | 109 | 15 | 4 | 2 | 2 | 1 | 6352 | 4814 | 4804 | -1538 | 9 | 1 | 125 | 2 | 2000000 | 0 | 1850719 | 0 |  | 1 | 13000 | 4 | 61 | 71.2
1307 | 20260131 | 80 | 7 | 5 | 8 | 32 | 8 | 1 | 8 | Active | Initiate & Design | Green | 0.2667 | 0.1744 | 848953 | 213106 | 141826 | 885741 | 65049 | 6231 | 0.695 | 1.044 | 20271130 | 20280331 | 107 | 15 | 4 | 1 | 2 | 1 | 6634 | 5515 | 5796 | -1119 | 6 | 1 | 89 | 2 | 2000000 | 0 | 1890248 | 0 |  | 1 | 13000 | 6 | 69 | 74.5
1308 | 20260228 | 80 | 7 | 5 | 8 | 32 | 8 | 1 | 8 | Active | Initiate & Design | Green | 0.3 | 0.2219 | 848953 | 240423 | 185221 | 887156 | 52040 | 3162 | 0.783 | 1.017 | 20271130 | 20280229 | 90 | 15 | 5 | 3 | 2 | 1 | 6884 | 5217 | 5151 | -1667 | 8 | 1 | 113 | 2 | 2000000 | 0 | 1919020 | 0 |  | 1 | 11000 | 6 | 66 | 76.4
1309 | 20260331 | 80 | 7 | 5 | 8 | 32 | 8 | 1 | 8 | Active | Initiate & Design | Green | 0.3333 | 0.2526 | 848953 | 267892 | 211035 | 888571 | 53446 | 3411 | 0.801 | 1.016 | 20271130 | 20280229 | 94 | 15 | 5 | 3 | 2 | 1 | 7101 | 5563 | 5460 | -1538 | 6 | 1 | 89 | 2 | 2000000 | 0 | 1886601 | 0 |  | 1 | 11000 | 5 | 72 | 77.2
1310 | 20260430 | 80 | 7 | 5 | 8 | 32 | 8 | 1 | 8 | Active | Initiate & Design | Green | 0.3667 | 0.2884 | 848953 | 295511 | 239422 | 889986 | 50673 | 5416 | 0.829 | 1.023 | 20271130 | 20280229 | 90 | 15 | 6 | 3 | 2 | 1 | 7282 | 5575 | 5721 | -1707 | 7 | 1 | 101 | 2 | 2000000 | 0 | 1909255 | 0 |  | 1 | 7000 | 3 | 71 | 78.7
1311 | 20260531 | 80 | 7 | 5 | 8 | 32 | 8 | 1 | 8 | Active | Initiate & Design | Green | 0.4 | 0.3397 | 848953 | 323281 | 277857 | 891401 | 34892 | 10532 | 0.892 | 1.038 | 20271130 | 20280131 | 70 | 15 | 6 | 4 | 1 | 0 | 7425 | 5566 | 5773 | -1859 | 7 | 1 | 101 | 2 | 2000000 | 0 | 1878843 | 0 |  | 1 | 11000 | 6 | 74 | 81.3
1312 | 20260630 | 80 | 7 | 5 | 8 | 32 | 8 | 1 | 8 | Active | Deliver | Green | 0.4333 | 0.3531 | 848953 | 351202 | 291861 | 892816 | 51437 | 7904 | 0.854 | 1.027 | 20271130 | 20280229 | 93 | 15 | 7 | 4 | 2 | 1 | 7528 | 5828 | 5996 | -1700 | 5 | 1 | 77 | 1 | 2000000 | 0 | 1891191 | 0 |  | 1 | 12000 | 5 | 71 | 79.9
1313 | 20260731 | 80 | 7 | 5 | 8 | 32 | 8 | 1 | 8 | Active | Deliver | Green | 0.4667 | 0.3834 | 848953 | 379274 | 316934 | 894230 | 53785 | 8555 | 0.858 | 1.027 | 20271130 | 20280229 | 97 | 15 | 7 | 4 | 2 | 1 | 7590 | 6343 | 6335 | -1247 | 8 | 1 | 113 | 2 | 2000000 | 0 | 1864518 | 0 |  | 1 | 13000 | 4 | 73 | 81.1
1314 | 20260831 | 80 | 7 | 5 | 8 | 32 | 8 | 1 | 8 | Active | Deliver | Green | 0.5 | 0.3834 | 848953 | 407497 | 318527 | 895645 | 82008 | 6962 | 0.799 | 1.022 | 20271130 | 20280430 | 135 | 15 | 8 | 4 | 3 | 1 | 7611 | 5640 | 5846 | -1971 | 8 | 1 | 113 | 2 | 2000000 | 0 | 1867305 | 0 |  | 1 | 9000 | 6 | 67 | 76.2
1315 | 20260930 | 80 | 7 | 5 | 8 | 32 | 8 | 1 | 8 | Active | Deliver | Green | 0.5333 | 0.421 | 848953 | 435871 | 352116 | 897060 | 78462 | 5293 | 0.82 | 1.015 | 20271130 | 20280331 | 130 | 15 | 8 | 4 | 3 | 1 | 7590 | 6061 | 6382 | -1529 | 7 | 1 | 101 | 2 | 2000000 | 0 | 1903993 | 0 |  | 1 | 12000 | 4 | 68 | 78.7
1316 | 20231231 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Initiate & Design | Amber | 0.0333 | 0.0133 | 961045 | 29557 | 10075 | 1003651 | 16775 | 2707 | 0.431 | 1.265 | 20260531 | 20260630 | 24 | 15 | 1 | 0 | 1 | 0 | 4758 | 4407 | 4659 | -351 | 8 | 2 | 133 | 2 | 800000 | 0 | 773488 | 0 |  | 0 | 0 | 6 | 52 | 65.1
1317 | 20240131 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.0667 | 0.0577 | 961045 | 59286 | 45102 | 1005894 | 3834 | 10350 | 0.936 | 1.23 | 20260531 | 20260531 | 10 | 15 | 1 | 1 | 0 | 0 | 5204 | 4832 | 4599 | -372 | 5 | 1 | 79 | 1 | 800000 | 0 | 774143 | 0 |  | 0 | 0 | 5 | 81 | 94.7
1318 | 20240229 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.1 | 0.0783 | 961045 | 89185 | 66908 | 1008136 | 13935 | 8342 | 0.844 | 1.125 | 20260531 | 20260630 | 26 | 15 | 2 | 0 | 1 | 0 | 5639 | 5497 | 5751 | -142 | 7 | 1 | 103 | 2 | 800000 | 0 | 752965 | 0 |  | 0 | 0 | 3 | 74 | 87.1
1319 | 20240331 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.1333 | 0.095 | 961045 | 119255 | 90389 | 1010379 | 27956 | 910 | 0.766 | 1.01 | 20260531 | 20260731 | 46 | 15 | 2 | 1 | 1 | 0 | 6060 | 5566 | 5248 | -494 | 6 | 1 | 91 | 2 | 800000 | 0 | 786821 | 0 |  | 0 | 0 | 7 | 67 | 79.5
1320 | 20240430 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.1667 | 0.1032 | 961045 | 149496 | 98615 | 1012621 | 50316 | 565 | 0.664 | 1.006 | 20260531 | 20260831 | 75 | 15 | 3 | 1 | 2 | 1 | 6462 | 5987 | 5800 | -475 | 9 | 1 | 127 | 2 | 800000 | 0 | 786228 | 0 |  | 0 | 0 | 6 | 66 | 75
1321 | 20240531 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.2 | 0.1214 | 961045 | 179908 | 116093 | 1014864 | 63237 | 578 | 0.649 | 1.005 | 20260531 | 20260831 | 93 | 15 | 3 | 0 | 2 | 1 | 6840 | 6680 | 6311 | -160 | 8 | 1 | 115 | 2 | 800000 | 0 | 759253 | 0 |  | 0 | 0 | 5 | 65 | 74.4
1322 | 20240630 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.2333 | 0.1572 | 961045 | 210490 | 142985 | 1017106 | 59414 | 8091 | 0.718 | 1.057 | 20260531 | 20260831 | 89 | 15 | 4 | 1 | 2 | 1 | 7191 | 6907 | 6979 | -284 | 9 | 1 | 127 | 2 | 800000 | 0 | 773934 | 0 |  | 1 | 10000 | 6 | 67 | 79.5
1323 | 20240731 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.2667 | 0.1913 | 961045 | 241244 | 178429 | 1019348 | 57396 | 5419 | 0.762 | 1.03 | 20260531 | 20260831 | 89 | 15 | 4 | 1 | 2 | 1 | 7510 | 7118 | 7022 | -392 | 8 | 1 | 115 | 2 | 800000 | 0 | 776155 | 0 |  | 1 | 15000 | 6 | 70 | 80.4
1324 | 20240831 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.3 | 0.2481 | 961045 | 272168 | 224704 | 1021591 | 33733 | 13731 | 0.876 | 1.061 | 20260531 | 20260731 | 62 | 15 | 5 | 3 | 1 | 0 | 7793 | 7420 | 7095 | -373 | 6 | 1 | 91 | 2 | 800000 | 0 | 758106 | 0 |  | 1 | 9000 | 4 | 77 | 86.1
1325 | 20240930 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.3333 | 0.2885 | 961045 | 303263 | 271202 | 1023833 | 26002 | 6059 | 0.914 | 1.022 | 20260531 | 20260731 | 52 | 15 | 5 | 3 | 1 | 0 | 8039 | 7542 | 7374 | -497 | 6 | 1 | 91 | 2 | 800000 | 0 | 774177 | 0 |  | 1 | 8000 | 4 | 72 | 86.6
1326 | 20241031 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.3667 | 0.3221 | 961045 | 334529 | 300691 | 1026076 | 24976 | 8862 | 0.925 | 1.03 | 20260531 | 20260731 | 52 | 15 | 6 | 4 | 1 | 0 | 8244 | 7403 | 7730 | -841 | 6 | 1 | 91 | 2 | 800000 | 0 | 766901 | 0 |  | 1 | 12000 | 5 | 74 | 86.3
1327 | 20241130 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Deliver | Green | 0.4 | 0.3574 | 961045 | 365966 | 332438 | 1028318 | 22489 | 11039 | 0.939 | 1.033 | 20260531 | 20260731 | 50 | 15 | 6 | 5 | 1 | 0 | 8405 | 7482 | 7789 | -923 | 8 | 2 | 133 | 2 | 800000 | 0 | 755791 | 0 |  | 1 | 15000 | 6 | 74 | 78.4
1328 | 20241231 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Deliver | Green | 0.4333 | 0.358 | 961045 | 397574 | 335902 | 1030561 | 53520 | 8152 | 0.865 | 1.024 | 20260531 | 20260831 | 89 | 15 | 7 | 5 | 2 | 1 | 8522 | 8120 | 8132 | -402 | 7 | 1 | 103 | 2 | 800000 | 0 | 768320 | 0 |  | 1 | 11000 | 4 | 71 | 84.6
1329 | 20250131 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Deliver | Green | 0.4667 | 0.3944 | 961045 | 429352 | 374051 | 1032803 | 50316 | 4985 | 0.883 | 1.013 | 20260531 | 20260831 | 85 | 15 | 7 | 4 | 2 | 1 | 8593 | 8036 | 8424 | -557 | 7 | 1 | 103 | 2 | 800000 | 0 | 781994 | 0 |  | 1 | 12000 | 6 | 69 | 85.1
1330 | 20250228 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Deliver | Green | 0.5 | 0.4148 | 961045 | 461302 | 389066 | 1035045 | 62661 | 9575 | 0.864 | 1.025 | 20260531 | 20260831 | 101 | 15 | 8 | 6 | 2 | 1 | 8616 | 7790 | 7539 | -826 | 8 | 2 | 133 | 2 | 800000 | 0 | 770613 | 0 |  | 1 | 15000 | 3 | 70 | 75.6
1331 | 20250331 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Deliver | Green | 0.5333 | 0.4304 | 961045 | 493422 | 420403 | 1040712 | 79788 | -6769 | 0.838 | 0.984 | 20260531 | 20260930 | 122 | 15 | 8 | 5 | 2 | 1 | 8593 | 7735 | 7281 | -858 | 8 | 1 | 115 | 2 | 800000 | 0 | 755551 | 0 |  | 1 | 8000 | 5 | 68 | 80.4
1332 | 20250430 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Deliver | Green | 0.5667 | 0.4835 | 961045 | 525713 | 465230 | 1039773 | 61048 | -565 | 0.884 | 0.999 | 20260531 | 20260831 | 98 | 15 | 9 | 7 | 2 | 1 | 8522 | 7668 | 7778 | -854 | 8 | 1 | 115 | 2 | 800000 | 0 | 779209 | 0 |  | 1 | 15000 | 3 | 72 | 83.8
1333 | 20250531 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Deliver | Green | 0.6 | 0.5176 | 961045 | 558175 | 508024 | 1046170 | 60738 | -10587 | 0.891 | 0.979 | 20260531 | 20260831 | 97 | 15 | 9 | 7 | 2 | 1 | 8405 | 8220 | 8245 | -185 | 7 | 1 | 103 | 2 | 800000 | 0 | 750266 | 0 |  | 2 | 18000 | 6 | 72 | 84.2
1334 | 20250630 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Deliver | Green | 0.6333 | 0.5559 | 961045 | 590808 | 550048 | 1050096 | 56563 | -15803 | 0.904 | 0.971 | 20260531 | 20260831 | 92 | 15 | 10 | 7 | 2 | 1 | 8244 | 7934 | 7815 | -310 | 6 | 1 | 91 | 2 | 800000 | 0 | 768643 | 0 |  | 2 | 25000 | 6 | 71 | 84.8
1335 | 20250731 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Deliver | Green | 0.6667 | 0.5999 | 961045 | 623611 | 594561 | 1052655 | 47080 | -18030 | 0.925 | 0.97 | 20260531 | 20260630 | 44 | 15 | 10 | 7 | 2 | 1 | 8039 | 7168 | 7225 | -871 | 7 | 1 | 103 | 2 | 800000 | 0 | 775934 | 0 |  | 2 | 17000 | 6 | 74 | 84.3
1336 | 20250831 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Deliver | Green | 0.7 | 0.638 | 961045 | 656586 | 626172 | 1052911 | 43439 | -13025 | 0.934 | 0.979 | 20260531 | 20260630 | 38 | 15 | 11 | 9 | 2 | 1 | 7793 | 6923 | 7218 | -870 | 5 | 0 | 61 | 1 | 800000 | 0 | 785612 | 0 |  | 2 | 18000 | 6 | 81 | 93.3
1337 | 20250930 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Deliver | Green | 0.7333 | 0.6687 | 961045 | 689731 | 672841 | 1060218 | 47080 | -30190 | 0.932 | 0.955 | 20260531 | 20260630 | 41 | 15 | 11 | 9 | 2 | 1 | 7510 | 7050 | 6744 | -460 | 6 | 1 | 91 | 2 | 800000 | 38095 | 755465 | 0 | 0 | 2 | 29000 | 4 | 74 | 84.5
1338 | 20251031 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Deliver | Green | 0.7667 | 0.6973 | 961045 | 723048 | 693570 | 1060131 | 52911 | -23433 | 0.927 | 0.966 | 20260531 | 20260731 | 46 | 15 | 12 | 10 | 2 | 1 | 7191 | 6422 | 6761 | -769 | 5 | 0 | 61 | 1 | 800000 | 133333 | 758612 | 0 | 0 | 2 | 23000 | 3 | 76 | 91.7
1339 | 20251130 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Deliver | Green | 0.8 | 0.7207 | 961045 | 756535 | 726830 | 1065179 | 63910 | -34205 | 0.916 | 0.953 | 20260531 | 20260731 | 58 | 15 | 12 | 9 | 2 | 1 | 6840 | 6595 | 6727 | -245 | 7 | 1 | 103 | 2 | 800000 | 228571 | 752957 | 44593 | 0.1951 | 2 | 24000 | 3 | 76 | 84.1
1340 | 20251231 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Deploy | Green | 0.8333 | 0.76 | 961045 | 790193 | 768993 | 1068080 | 59799 | -38599 | 0.924 | 0.95 | 20260531 | 20260731 | 52 | 15 | 13 | 10 | 2 | 1 | 6462 | 5736 | 5794 | -726 | 5 | 0 | 61 | 1 | 800000 | 323810 | 762855 | 132017 | 0.4077 | 2 | 17000 | 2 | 80 | 91.1
1341 | 20260131 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Deploy | Green | 0.8667 | 0.8178 | 961045 | 824021 | 835677 | 1072299 | 38078 | -49734 | 0.954 | 0.94 | 20260531 | 20260630 | 23 | 15 | 13 | 11 | 2 | 1 | 6060 | 5930 | 6188 | -130 | 5 | 1 | 79 | 1 | 800000 | 419048 | 771505 | 209076 | 0.4989 | 2 | 18000 | 2 | 72 | 86.4
1342 | 20260228 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Deploy | Green | 0.9 | 0.8535 | 961045 | 858021 | 873017 | 1074736 | 37769 | -52765 | 0.956 | 0.94 | 20260531 | 20260630 | 20 | 15 | 14 | 11 | 2 | 1 | 5639 | 4947 | 4703 | -692 | 4 | 1 | 67 | 1 | 800000 | 514286 | 769106 | 304854 | 0.5928 | 2 | 28000 | 2 | 75 | 84.1
1343 | 20260331 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Deploy | Green | 0.9333 | 0.9238 | 961045 | 892191 | 949929 | 1078029 | 4378 | -62116 | 0.995 | 0.935 | 20260531 | 20260531 | -23 | 15 | 14 | 12 | 1 | 0 | 5204 | 4632 | 4588 | -572 | 4 | 0 | 49 | 1 | 800000 | 609524 | 759896 | 372976 | 0.6119 | 2 | 20000 | 4 | 78 | 93.7
1344 | 20260430 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Deploy | Green | 0.9667 | 0.9556 | 961045 | 926533 | 989869 | 1081706 | 8158 | -71494 | 0.991 | 0.928 | 20260531 | 20260531 | -22 | 15 | 15 | 14 | 1 | 0 | 4758 | 4306 | 4456 | -452 | 3 | 1 | 54 | 1 | 800000 | 704762 | 784001 | 483476 | 0.686 | 2 | 16000 | 1 | 75 | 86.4
1345 | 20260531 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Deploy | Green | 1 | 0.9909 | 961045 | 961045 | 1037964 | 1086137 | 8746 | -85665 | 0.991 | 0.917 | 20260531 | 20260531 | -25 | 15 | 15 | 14 | 1 | 0 | 4308 | 4185 | 4157 | -123 | 4 | 0 | 49 | 1 | 800000 | 800000 | 750491 | 545474 | 0.6818 | 2 | 27000 | 4 | 76 | 94.3
1346 | 20260630 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Deploy | Green | 1 | 0.9909 | 961045 | 961045 | 1051883 | 1090946 | 8746 | -99584 | 0.991 | 0.905 | 20260531 | 20260531 | -25 | 15 | 15 | 13 | 1 | 0 | 4308 | 3938 | 3987 | -370 | 3 | 0 | 36 | 1 | 800000 | 800000 | 759909 | 612318 | 0.7654 | 2 | 19000 | 4 | 76 | 93
1347 | 20260731 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Deploy | Green | 1 | 0.9909 | 961045 | 961045 | 1058981 | 1094472 | 8746 | -106682 | 0.991 | 0.899 | 20260531 | 20260531 | -25 | 15 | 15 | 13 | 1 | 0 | 4308 | 3783 | 3768 | -525 | 3 | 0 | 36 | 1 | 800000 | 800000 | 759085 | 683283 | 0.8541 | 2 | 20000 | 4 | 78 | 91.9
1348 | 20260831 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Deploy | Green | 1 | 0.9909 | 961045 | 961045 | 1061553 | 1097175 | 8746 | -109254 | 0.991 | 0.897 | 20260531 | 20260531 | -25 | 15 | 15 | 14 | 1 | 0 | 4308 | 3976 | 4248 | -332 | 5 | 1 | 79 | 1 | 800000 | 800000 | 766986 | 747849 | 0.9348 | 2 | 18000 | 3 | 74 | 85.1
1349 | 20260930 | 81 | 2 | 4 | 9 | 33 | 1 | 3 | 1 | Active | Deploy | Green | 1 | 0.9909 | 961045 | 961045 | 1062076 | 1099511 | 8746 | -109777 | 0.991 | 0.897 | 20260531 | 20260531 | -25 | 15 | 15 | 13 | 1 | 0 | 4308 | 4187 | 4019 | -121 | 3 | 0 | 36 | 1 | 800000 | 800000 | 773828 | 720647 | 0.9008 | 2 | 25000 | 3 | 78 | 94.4
1350 | 20231031 | 82 | 4 | 3 | 10 | 34 | 2 | 3 | 2 | Active | Deploy | Green | 0.75 | 0.7779 | 1412906 | 1038486 | 1112793 | 1473955 | -60614 | -13693 | 1.058 | 0.988 | 20240131 | 20240131 | 0 | 6 | 5 | 5 | 0 | 0 | 10812 | 10338 | 10764 | -474 | 4 | 0 | 41 | 1 | 1400000 | 150000 | 1020585 | 0 | 0 | 0 | 0 | 2 | 75 | 93.6
1351 | 20231130 | 82 | 4 | 3 | 10 | 34 | 2 | 3 | 2 | Active | Deploy | Green | 0.8333 | 0.8512 | 1412906 | 1161723 | 1235167 | 1481857 | -40943 | -32501 | 1.035 | 0.974 | 20240131 | 20240131 | 0 | 6 | 5 | 4 | 0 | 0 | 9501 | 9769 | 9684 | 268 | 2 | 0 | 20 | 0 | 1400000 | 566667 | 1083014 | 188333 | 0.3324 | 1 | 21000 | 0 | 73 | 94.3
1352 | 20231231 | 82 | 4 | 3 | 10 | 34 | 2 | 3 | 2 | Active | Deploy | Green | 0.9167 | 0.9398 | 1412906 | 1286529 | 1367529 | 1486204 | -41320 | -39680 | 1.032 | 0.971 | 20240131 | 20240131 | 0 | 6 | 6 | 5 | 0 | 0 | 7973 | 8328 | 8097 | 355 | 2 | 0 | 20 | 0 | 1400000 | 983333 | 1039935 | 429785 | 0.4371 | 1 | 22000 | 0 | 74 | 93.2
1353 | 20240131 | 82 | 4 | 3 | 10 | 34 | 2 | 3 | 2 | Completed | Completed | Green | 1 | 1 | 1412906 | 1412906 | 1493984 | 1497595 | 0 | -81078 | 1 | 0.946 | 20240131 | 20240131 | 0 | 6 | 6 | 5 | 0 | 0 | 6334 | 6684 | 6961 | 350 | 3 | 0 | 31 | 1 | 1400000 | 1400000 | 1074158 | 706763 | 0.5048 | 1 | 12000 | 0 | 74 | 91.6
1354 | 20240831 | 83 | 9 | 8 | 11 | 35 | 3 | 3 | 3 | Active | Initiate & Design | Red | 0.0556 | 0 | 991440 | 50918 | 4905 | 1339546 | 50918 | -4905 | 0 | 0 | 20260131 | 20260228 | 44 | 9 | 1 | 0 | 1 | 1 | 5216 | 4542 | 4307 | -674 | 15 | 4 | 286 | 5 | 3000000 | 0 | 2134706 | 0 |  | 1 | 13000 | 8 | 24 | 0
1355 | 20240930 | 83 | 9 | 8 | 11 | 35 | 3 | 3 | 3 | Active | Initiate & Design | Red | 0.1111 | 0.0064 | 991440 | 102326 | 8281 | 1184361 | 95981 | -1936 | 0.062 | 0.762 | 20260131 | 20260430 | 84 | 9 | 1 | 0 | 1 | 1 | 5964 | 4648 | 4881 | -1316 | 14 | 4 | 271 | 5 | 3000000 | 0 | 2163097 | 0 |  | 1 | 16000 | 8 | 24 | 4.8
1356 | 20241031 | 83 | 9 | 8 | 11 | 35 | 3 | 3 | 3 | Active | Initiate & Design | Red | 0.1667 | 0.0467 | 991440 | 154224 | 45881 | 1143461 | 107924 | 419 | 0.3 | 1.009 | 20260131 | 20260430 | 95 | 9 | 2 | 0 | 1 | 1 | 6667 | 5160 | 5203 | -1507 | 12 | 3 | 225 | 4 | 3000000 | 0 | 2150667 | 0 |  | 1 | 9000 | 6 | 26 | 31.9
1357 | 20241130 | 83 | 9 | 8 | 11 | 35 | 3 | 3 | 3 | Active | Initiate & Design | Red | 0.2222 | 0.072 | 991440 | 206611 | 69933 | 1154477 | 135227 | 1451 | 0.346 | 1.021 | 20260131 | 20260531 | 119 | 9 | 2 | 1 | 1 | 1 | 7301 | 6093 | 6008 | -1208 | 13 | 3 | 239 | 4 | 3000000 | 0 | 2069153 | 0 |  | 1 | 13000 | 7 | 28 | 35
1358 | 20241231 | 83 | 9 | 8 | 11 | 35 | 3 | 3 | 3 | Active | Initiate & Design | Red | 0.2778 | 0.1155 | 991440 | 259488 | 111754 | 1165493 | 144977 | 2757 | 0.441 | 1.024 | 20260131 | 20260531 | 129 | 9 | 3 | 1 | 2 | 1 | 7849 | 6555 | 6294 | -1294 | 12 | 3 | 225 | 4 | 3000000 | 0 | 2034327 | 0 |  | 1 | 9000 | 5 | 38 | 39.1
1359 | 20250131 | 83 | 9 | 8 | 11 | 35 | 3 | 3 | 3 | Active | Initiate & Design | Red | 0.3333 | 0.1791 | 991440 | 312854 | 172530 | 1176509 | 135287 | 5037 | 0.567 | 1.029 | 20260131 | 20260531 | 122 | 9 | 3 | 1 | 2 | 1 | 8293 | 7199 | 6790 | -1094 | 10 | 3 | 196 | 3 | 3000000 | 0 | 2146748 | 0 |  | 1 | 11000 | 4 | 37 | 46.7
1360 | 20250228 | 83 | 9 | 8 | 11 | 35 | 3 | 3 | 3 | Active | Initiate & Design | Red | 0.3889 | 0.2283 | 991440 | 366710 | 236097 | 1196570 | 140364 | -9751 | 0.617 | 0.959 | 20260131 | 20260531 | 128 | 9 | 4 | 0 | 3 | 2 | 8621 | 6984 | 7437 | -1637 | 12 | 3 | 225 | 4 | 3000000 | 0 | 2138645 | 0 |  | 1 | 8000 | 6 | 42 | 45.1
1361 | 20250331 | 83 | 9 | 8 | 11 | 35 | 3 | 3 | 3 | Active | Initiate & Design | Amber | 0.4444 | 0.2904 | 991440 | 421056 | 300209 | 1207471 | 133142 | -12295 | 0.684 | 0.959 | 20260131 | 20260531 | 122 | 9 | 4 | 1 | 2 | 1 | 8821 | 7726 | 7440 | -1095 | 12 | 2 | 207 | 4 | 3000000 | 0 | 2028999 | 0 |  | 2 | 22000 | 7 | 50 | 56.5
1362 | 20250430 | 83 | 9 | 8 | 11 | 35 | 3 | 3 | 3 | Active | Initiate & Design | Amber | 0.5 | 0.3432 | 991440 | 475891 | 357532 | 1220102 | 135629 | -17270 | 0.715 | 0.952 | 20260131 | 20260531 | 125 | 9 | 5 | 1 | 3 | 2 | 8889 | 7200 | 6984 | -1689 | 10 | 2 | 178 | 3 | 3000000 | 0 | 2111722 | 0 |  | 2 | 32000 | 7 | 48 | 57
1363 | 20250531 | 83 | 9 | 8 | 11 | 35 | 3 | 3 | 3 | Active | Deliver | Amber | 0.5556 | 0.3805 | 991440 | 531216 | 407553 | 1236801 | 153973 | -30310 | 0.71 | 0.926 | 20260131 | 20260630 | 139 | 9 | 5 | 2 | 3 | 2 | 8821 | 7060 | 6992 | -1761 | 9 | 2 | 164 | 3 | 3000000 | 0 | 2108951 | 0 |  | 2 | 26000 | 8 | 45 | 55.6
1364 | 20250630 | 83 | 9 | 8 | 11 | 35 | 3 | 3 | 3 | Active | Deliver | Red | 0.6111 | 0.4151 | 991440 | 587030 | 450171 | 1250323 | 175483 | -38624 | 0.701 | 0.914 | 20260131 | 20260630 | 156 | 9 | 6 | 2 | 3 | 2 | 8621 | 7407 | 7397 | -1214 | 10 | 3 | 196 | 3 | 3000000 | 0 | 2073316 | 0 |  | 2 | 21000 | 6 | 42 | 47.8
1365 | 20250731 | 83 | 9 | 8 | 11 | 35 | 3 | 3 | 3 | Active | Deliver | Red | 0.6667 | 0.432 | 991440 | 643334 | 474438 | 1263810 | 215032 | -46136 | 0.666 | 0.903 | 20260131 | 20260731 | 186 | 9 | 6 | 2 | 4 | 2 | 8293 | 6463 | 6873 | -1830 | 12 | 3 | 225 | 4 | 3000000 | 0 | 2147815 | 0 |  | 2 | 19000 | 6 | 37 | 44.7
1366 | 20250831 | 83 | 9 | 8 | 11 | 35 | 3 | 3 | 3 | Active | Deliver | Red | 0.7222 | 0.4615 | 991440 | 700128 | 522580 | 1280767 | 242578 | -65030 | 0.654 | 0.876 | 20260131 | 20260831 | 207 | 9 | 7 | 2 | 4 | 2 | 7849 | 6750 | 6563 | -1099 | 11 | 3 | 211 | 4 | 3000000 | 23810 | 2026774 | 0 | 0 | 2 | 17000 | 7 | 34 | 43.9
1367 | 20250930 | 83 | 9 | 8 | 11 | 35 | 3 | 3 | 3 | Active | Deliver | Amber | 0.7778 | 0.5093 | 991440 | 757411 | 585910 | 1294775 | 252471 | -80970 | 0.667 | 0.862 | 20260131 | 20260831 | 213 | 9 | 7 | 2 | 4 | 2 | 7301 | 5773 | 5520 | -1528 | 10 | 2 | 178 | 3 | 3000000 | 619048 | 2029320 | 0 | 0 | 3 | 40000 | 5 | 44 | 50.5
1368 | 20251031 | 83 | 9 | 8 | 11 | 35 | 3 | 3 | 3 | Active | Deliver | Amber | 0.8333 | 0.5596 | 991440 | 815184 | 653622 | 1308612 | 260374 | -98812 | 0.681 | 0.849 | 20260131 | 20260831 | 217 | 9 | 8 | 2 | 5 | 3 | 6667 | 5093 | 5096 | -1574 | 8 | 2 | 150 | 3 | 3000000 | 1214286 | 2025543 | 313320 | 0.258 | 3 | 26000 | 4 | 45 | 50.1
1369 | 20251130 | 83 | 9 | 8 | 11 | 35 | 3 | 3 | 3 | Active | Deliver | Amber | 0.8889 | 0.6095 | 991440 | 873446 | 722805 | 1322432 | 269163 | -118522 | 0.692 | 0.836 | 20260131 | 20260831 | 222 | 9 | 8 | 4 | 4 | 2 | 5964 | 4705 | 4668 | -1259 | 7 | 2 | 136 | 2 | 3000000 | 1809524 | 2071402 | 740001 | 0.4089 | 3 | 29000 | 4 | 46 | 51.1
1370 | 20251231 | 83 | 9 | 8 | 11 | 35 | 3 | 3 | 3 | Active | Deliver | Amber | 0.9444 | 0.666 | 991440 | 932198 | 802815 | 1336418 | 271899 | -142516 | 0.708 | 0.822 | 20260131 | 20260831 | 220 | 9 | 9 | 4 | 5 | 3 | 5216 | 4424 | 4656 | -792 | 7 | 1 | 118 | 2 | 3000000 | 2404762 | 2104424 | 1115347 | 0.4638 | 3 | 28000 | 5 | 48 | 61
1371 | 20260131 | 83 | 9 | 8 | 11 | 35 | 3 | 3 | 3 | Active | Deliver | Amber | 1 | 0.7144 | 991440 | 991440 | 860036 | 1347193 | 283155 | -151751 | 0.714 | 0.824 | 20260131 | 20260930 | 226 | 9 | 9 | 3 | 5 | 3 | 4444 | 3618 | 3867 | -826 | 9 | 2 | 164 | 3 | 3000000 | 3000000 | 2133513 | 1408219 | 0.4694 | 3 | 30000 | 6 | 40 | 52.8
1372 | 20260228 | 83 | 9 | 8 | 11 | 35 | 3 | 3 | 3 | Active | Deliver | Amber | 1 | 0.7144 | 991440 | 991440 | 879615 | 1362207 | 283155 | -171330 | 0.714 | 0.805 | 20260131 | 20260930 | 226 | 9 | 9 | 3 | 5 | 3 | 4444 | 3800 | 3993 | -644 | 8 | 2 | 150 | 3 | 3000000 | 3000000 | 2104421 | 1808412 | 0.6028 | 3 | 24000 | 2 | 45 | 52.8
1373 | 20260331 | 83 | 9 | 8 | 11 | 35 | 3 | 3 | 3 | Active | Deliver | Amber | 1 | 0.7144 | 991440 | 991440 | 896612 | 1376553 | 283155 | -188327 | 0.714 | 0.79 | 20260131 | 20260930 | 226 | 9 | 9 | 4 | 5 | 3 | 4444 | 3795 | 4023 | -649 | 9 | 2 | 164 | 3 | 3000000 | 3000000 | 2151753 | 1950657 | 0.6502 | 3 | 47000 | 5 | 44 | 52.7
1374 | 20260430 | 83 | 9 | 8 | 11 | 35 | 3 | 3 | 3 | Active | Deliver | Amber | 1 | 0.7144 | 991440 | 991440 | 912675 | 1390601 | 283155 | -204390 | 0.714 | 0.776 | 20260131 | 20260930 | 226 | 9 | 9 | 3 | 5 | 3 | 4444 | 3420 | 3368 | -1024 | 7 | 2 | 136 | 2 | 3000000 | 3000000 | 2138337 | 2012197 | 0.6707 | 4 | 40000 | 3 | 44 | 50.2
1375 | 20260531 | 83 | 9 | 8 | 11 | 35 | 3 | 3 | 3 | Active | Deliver | Red | 1 | 0.7144 | 991440 | 991440 | 929293 | 1404644 | 283155 | -221008 | 0.714 | 0.762 | 20260131 | 20260930 | 226 | 9 | 9 | 4 | 5 | 3 | 4444 | 3488 | 3327 | -956 | 10 | 3 | 196 | 3 | 3000000 | 3000000 | 2029093 | 1914193 | 0.6381 | 4 | 55000 | 3 | 37 | 41
1376 | 20260630 | 83 | 9 | 8 | 11 | 35 | 3 | 3 | 3 | Active | Deliver | Amber | 1 | 0.7144 | 991440 | 991440 | 938446 | 1417281 | 283155 | -230161 | 0.714 | 0.755 | 20260131 | 20260930 | 226 | 9 | 9 | 3 | 5 | 3 | 4444 | 3393 | 3511 | -1051 | 8 | 1 | 132 | 3 | 3000000 | 3000000 | 2059076 | 1797033 | 0.599 | 4 | 59000 | 4 | 48 | 56.6
1377 | 20260731 | 83 | 9 | 8 | 11 | 35 | 3 | 3 | 3 | Active | Deliver | Red | 1 | 0.7144 | 991440 | 991440 | 957369 | 1431551 | 283155 | -249084 | 0.714 | 0.74 | 20260131 | 20260930 | 226 | 9 | 9 | 3 | 5 | 3 | 4444 | 3873 | 4128 | -571 | 10 | 3 | 196 | 3 | 3000000 | 3000000 | 2063555 | 1798480 | 0.5995 | 4 | 33000 | 6 | 38 | 42.5
1378 | 20260831 | 83 | 9 | 8 | 11 | 35 | 3 | 3 | 3 | Active | Deliver | Amber | 1 | 0.7144 | 991440 | 991440 | 957369 | 1434856 | 283155 | -249084 | 0.714 | 0.74 | 20260131 | 20260930 | 226 | 9 | 9 | 4 | 5 | 3 | 4444 | 3882 | 3749 | -562 | 7 | 2 | 136 | 2 | 3000000 | 3000000 | 2025778 | 1768823 | 0.5896 | 4 | 48000 | 3 | 40 | 50.2
1379 | 20260930 | 83 | 9 | 8 | 11 | 35 | 3 | 3 | 3 | Active | Deliver | Amber | 1 | 0.7144 | 991440 | 991440 | 957369 | 1434856 | 283155 | -249084 | 0.714 | 0.74 | 20260131 | 20260930 | 226 | 9 | 9 | 3 | 5 | 3 | 4444 | 3401 | 3478 | -1043 | 8 | 2 | 150 | 3 | 3000000 | 3000000 | 2147786 | 2030803 | 0.6769 | 5 | 46000 | 3 | 42 | 48.9
1380 | 20241231 | 84 | 8 | 6 | 12 | 36 | 4 | 2 | 4 | Active | Initiate & Design | Red | 0.0476 | 0.0195 | 483705 | 21279 | 11968 | 537483 | 11847 | -2536 | 0.444 | 0.789 | 20260831 | 20260930 | 24 | 11 | 1 | 0 | 1 | 0 | 2492 | 2267 | 2360 | -225 | 10 | 2 | 162 | 3 | 500000 | 0 | 443543 | 0 |  | 0 | 0 | 4 | 36 | 46.4
1381 | 20250131 | 84 | 8 | 6 | 12 | 36 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.0952 | 0.0589 | 483705 | 42733 | 25199 | 517334 | 14243 | 3291 | 0.667 | 1.131 | 20260831 | 20260930 | 31 | 11 | 1 | 0 | 1 | 0 | 2807 | 2741 | 2650 | -66 | 8 | 1 | 119 | 2 | 500000 | 0 | 438043 | 0 |  | 0 | 0 | 5 | 67 | 77.6
1382 | 20250228 | 84 | 8 | 6 | 12 | 36 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.1429 | 0.1128 | 483705 | 64362 | 48398 | 519637 | 9800 | 6164 | 0.848 | 1.128 | 20260831 | 20260930 | 26 | 11 | 2 | 0 | 1 | 0 | 3109 | 2978 | 2982 | -131 | 7 | 1 | 106 | 2 | 500000 | 0 | 446630 | 0 |  | 0 | 0 | 4 | 76 | 85.7
1383 | 20250331 | 84 | 8 | 6 | 12 | 36 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.1905 | 0.1548 | 483705 | 86167 | 71112 | 521941 | 11289 | 3766 | 0.869 | 1.053 | 20260831 | 20260930 | 30 | 11 | 2 | 0 | 1 | 0 | 3390 | 3193 | 3193 | -197 | 9 | 2 | 150 | 3 | 500000 | 0 | 450976 | 0 |  | 0 | 0 | 5 | 65 | 75.9
1384 | 20250430 | 84 | 8 | 6 | 12 | 36 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.2381 | 0.2067 | 483705 | 108148 | 98188 | 524244 | 8166 | 1794 | 0.925 | 1.018 | 20260831 | 20260930 | 27 | 11 | 3 | 2 | 1 | 0 | 3643 | 3479 | 3508 | -164 | 6 | 1 | 94 | 2 | 500000 | 0 | 447268 | 0 |  | 0 | 0 | 5 | 78 | 85.3
1385 | 20250531 | 84 | 8 | 6 | 12 | 36 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.2857 | 0.2502 | 483705 | 130304 | 115097 | 526547 | 9281 | 5926 | 0.929 | 1.052 | 20260831 | 20260930 | 30 | 11 | 3 | 1 | 1 | 0 | 3864 | 3489 | 3624 | -375 | 6 | 1 | 94 | 2 | 500000 | 0 | 450196 | 0 |  | 1 | 5000 | 5 | 79 | 85.7
1386 | 20250630 | 84 | 8 | 6 | 12 | 36 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.3333 | 0.3154 | 483705 | 152636 | 144800 | 528851 | 75 | 7761 | 0.999 | 1.054 | 20260831 | 20260930 | 15 | 11 | 4 | 3 | 0 | 0 | 4046 | 3789 | 4011 | -257 | 8 | 1 | 119 | 2 | 500000 | 0 | 450367 | 0 |  | 1 | 7000 | 6 | 78 | 89.7
1387 | 20250731 | 84 | 8 | 6 | 12 | 36 | 4 | 2 | 4 | Active | Deliver | Green | 0.381 | 0.3571 | 483705 | 175143 | 170048 | 531154 | 2412 | 2683 | 0.986 | 1.016 | 20260831 | 20260930 | 20 | 11 | 4 | 3 | 0 | 0 | 4187 | 3933 | 3830 | -254 | 8 | 2 | 137 | 2 | 500000 | 0 | 438634 | 0 |  | 1 | 5000 | 4 | 75 | 79.2
1388 | 20250831 | 84 | 8 | 6 | 12 | 36 | 4 | 2 | 4 | Active | Deliver | Green | 0.4286 | 0.4131 | 483705 | 197825 | 200168 | 533632 | -1994 | -349 | 1.01 | 0.998 | 20260831 | 20260831 | 13 | 11 | 5 | 4 | 0 | 0 | 4282 | 3880 | 3876 | -402 | 7 | 1 | 106 | 2 | 500000 | 0 | 454317 | 0 |  | 1 | 6000 | 6 | 80 | 87.8
1389 | 20250930 | 84 | 8 | 6 | 12 | 36 | 4 | 2 | 4 | Active | Deliver | Green | 0.4762 | 0.4431 | 483705 | 220684 | 214838 | 536006 | 6354 | -508 | 0.971 | 0.998 | 20260831 | 20260930 | 28 | 11 | 5 | 3 | 1 | 0 | 4331 | 3943 | 4205 | -388 | 6 | 1 | 94 | 2 | 500000 | 0 | 444103 | 0 |  | 1 | 7000 | 6 | 79 | 85.5
1390 | 20251031 | 84 | 8 | 6 | 12 | 36 | 4 | 2 | 4 | Active | Deliver | Green | 0.5238 | 0.4661 | 483705 | 243717 | 225452 | 538064 | 18262 | 3 | 0.925 | 1 | 20260831 | 20261031 | 49 | 11 | 6 | 4 | 1 | 0 | 4331 | 4081 | 4078 | -250 | 7 | 1 | 106 | 2 | 500000 | 0 | 448125 | 0 |  | 2 | 15000 | 7 | 76 | 84.5
1391 | 20251130 | 84 | 8 | 6 | 12 | 36 | 4 | 2 | 4 | Active | Deliver | Green | 0.5714 | 0.5067 | 483705 | 266926 | 250926 | 542842 | 21833 | -5833 | 0.918 | 0.977 | 20260831 | 20261031 | 55 | 11 | 6 | 4 | 1 | 0 | 4282 | 3981 | 4053 | -301 | 6 | 1 | 94 | 2 | 500000 | 0 | 458024 | 0 |  | 2 | 11000 | 4 | 69 | 83.6
1392 | 20251231 | 84 | 8 | 6 | 12 | 36 | 4 | 2 | 4 | Active | Deliver | Green | 0.619 | 0.5619 | 483705 | 290311 | 283362 | 547023 | 18517 | -11568 | 0.936 | 0.959 | 20260831 | 20261031 | 49 | 11 | 7 | 5 | 1 | 0 | 4187 | 4162 | 4433 | -25 | 7 | 1 | 106 | 2 | 500000 | 0 | 454857 | 0 |  | 2 | 9000 | 3 | 74 | 85
1393 | 20260131 | 84 | 8 | 6 | 12 | 36 | 4 | 2 | 4 | Active | Deliver | Green | 0.6667 | 0.6054 | 483705 | 313871 | 306671 | 549776 | 21036 | -13836 | 0.933 | 0.955 | 20260831 | 20261031 | 53 | 11 | 7 | 6 | 1 | 0 | 4046 | 3809 | 3831 | -237 | 7 | 1 | 106 | 2 | 500000 | 0 | 451240 | 0 |  | 2 | 13000 | 5 | 73 | 83.4
1394 | 20260228 | 84 | 8 | 6 | 12 | 36 | 4 | 2 | 4 | Active | Deliver | Green | 0.7143 | 0.6663 | 483705 | 337606 | 343698 | 553905 | 15313 | -21405 | 0.955 | 0.938 | 20260831 | 20260930 | 40 | 11 | 8 | 6 | 1 | 0 | 3864 | 3660 | 3789 | -204 | 8 | 2 | 137 | 2 | 500000 | 0 | 445771 | 0 |  | 2 | 10000 | 3 | 65 | 75.6
1395 | 20260331 | 84 | 8 | 6 | 12 | 36 | 4 | 2 | 4 | Active | Deliver | Green | 0.7619 | 0.7304 | 483705 | 361517 | 374083 | 555489 | 8219 | -20785 | 0.977 | 0.944 | 20260831 | 20260930 | 27 | 11 | 8 | 6 | 1 | 0 | 3643 | 3315 | 3544 | -328 | 7 | 1 | 106 | 2 | 500000 | 74830 | 446901 | 0 | 0 | 2 | 11000 | 6 | 74 | 84.1
1396 | 20260430 | 84 | 8 | 6 | 12 | 36 | 4 | 2 | 4 | Active | Deploy | Green | 0.8095 | 0.7668 | 483705 | 385604 | 398660 | 559298 | 14699 | -27755 | 0.962 | 0.93 | 20260831 | 20260930 | 36 | 11 | 9 | 7 | 1 | 0 | 3390 | 3121 | 3175 | -269 | 5 | 1 | 81 | 1 | 500000 | 159864 | 450812 | 40368 | 0.2525 | 2 | 8000 | 4 | 76 | 83.3
1397 | 20260531 | 84 | 8 | 6 | 12 | 36 | 4 | 2 | 4 | Active | Deploy | Green | 0.8571 | 0.8005 | 483705 | 409866 | 423294 | 563258 | 22660 | -36088 | 0.945 | 0.915 | 20260831 | 20261031 | 49 | 11 | 9 | 7 | 1 | 0 | 3109 | 2872 | 2993 | -237 | 4 | 1 | 69 | 1 | 500000 | 244898 | 451520 | 105655 | 0.4314 | 2 | 11000 | 1 | 70 | 82.1
1398 | 20260630 | 84 | 8 | 6 | 12 | 36 | 4 | 2 | 4 | Active | Deploy | Green | 0.9048 | 0.8445 | 483705 | 434303 | 449058 | 566101 | 25814 | -40569 | 0.941 | 0.91 | 20260831 | 20261031 | 51 | 11 | 10 | 8 | 2 | 1 | 2807 | 2754 | 2786 | -53 | 5 | 1 | 81 | 1 | 500000 | 329932 | 452796 | 175445 | 0.5318 | 2 | 13000 | 2 | 74 | 83.1
1399 | 20260731 | 84 | 8 | 6 | 12 | 36 | 4 | 2 | 4 | Active | Deploy | Green | 0.9524 | 0.8769 | 483705 | 458916 | 471595 | 569494 | 34755 | -47434 | 0.924 | 0.899 | 20260831 | 20261031 | 65 | 11 | 10 | 7 | 2 | 1 | 2492 | 2249 | 2401 | -243 | 4 | 0 | 51 | 1 | 500000 | 414966 | 460366 | 258458 | 0.6228 | 2 | 14000 | 5 | 77 | 88.7
1400 | 20260831 | 84 | 8 | 6 | 12 | 36 | 4 | 2 | 4 | Active | Deploy | Green | 1 | 0.9225 | 483705 | 483705 | 499036 | 572361 | 37487 | -52818 | 0.922 | 0.894 | 20260831 | 20261031 | 66 | 11 | 11 | 8 | 2 | 1 | 2168 | 1981 | 1871 | -187 | 5 | 1 | 81 | 1 | 500000 | 500000 | 457406 | 331320 | 0.6626 | 2 | 9000 | 3 | 69 | 80.5
1401 | 20260930 | 84 | 8 | 6 | 12 | 36 | 4 | 2 | 4 | Active | Deploy | Green | 1 | 0.9225 | 483705 | 483705 | 504678 | 575729 | 37487 | -58460 | 0.922 | 0.884 | 20260831 | 20261031 | 66 | 11 | 11 | 9 | 2 | 1 | 2168 | 2167 | 2052 | -1 | 4 | 0 | 51 | 1 | 500000 | 500000 | 438942 | 390919 | 0.7818 | 2 | 11000 | 4 | 76 | 89
1402 | 20231031 | 85 | 2 | 4 | 13 | 25 | 5 | 1 | 5 | Active | Initiate & Design | Green | 0.0952 | 0.0771 | 260196 | 22987 | 18231 | 262005 | 2926 | 1830 | 0.873 | 1.101 | 20250531 | 20250531 | 12 | 11 | 1 | 1 | 0 | 0 | 1510 | 1512 | 1533 | 2 | 4 | 0 | 38 | 1 | 700000 | 0 | 713175 | 0 |  | 0 | 0 | 3 | 76 | 97.8
1403 | 20231130 | 85 | 2 | 4 | 13 | 25 | 5 | 1 | 5 | Active | Initiate & Design | Green | 0.1429 | 0.1348 | 260196 | 34622 | 31022 | 262129 | -452 | 4052 | 1.013 | 1.13 | 20250531 | 20250531 | 6 | 11 | 2 | 1 | 0 | 0 | 1672 | 1676 | 1730 | 4 | 4 | 0 | 38 | 1 | 700000 | 0 | 717358 | 0 |  | 0 | 0 | 2 | 85 | 100
1404 | 20231231 | 85 | 2 | 4 | 13 | 25 | 5 | 1 | 5 | Active | Initiate & Design | Green | 0.1905 | 0.1921 | 260196 | 46351 | 48176 | 262253 | -3633 | 1808 | 1.079 | 1.038 | 20250531 | 20250531 | 0 | 11 | 2 | 1 | 0 | 0 | 1823 | 1771 | 1835 | -52 | 3 | 0 | 29 | 1 | 700000 | 0 | 728164 | 0 |  | 0 | 0 | 1 | 83 | 100
1405 | 20240131 | 85 | 2 | 4 | 13 | 25 | 5 | 1 | 5 | Active | Initiate & Design | Green | 0.2381 | 0.2388 | 260196 | 58175 | 56456 | 262377 | -3960 | 5679 | 1.068 | 1.1 | 20250531 | 20250531 | 0 | 11 | 3 | 2 | 0 | 0 | 1960 | 1940 | 1957 | -20 | 3 | 0 | 29 | 1 | 700000 | 0 | 708495 | 0 |  | 0 | 0 | 4 | 85 | 100
1406 | 20240229 | 85 | 2 | 4 | 13 | 25 | 5 | 1 | 5 | Active | Initiate & Design | Green | 0.2857 | 0.3133 | 260196 | 70094 | 76612 | 262501 | -11425 | 4907 | 1.163 | 1.064 | 20250531 | 20250531 | 0 | 11 | 3 | 3 | 0 | 0 | 2078 | 2070 | 2107 | -8 | 3 | 0 | 29 | 1 | 700000 | 0 | 717073 | 0 |  | 0 | 0 | 2 | 92 | 100
1407 | 20240331 | 85 | 2 | 4 | 13 | 25 | 5 | 1 | 5 | Active | Initiate & Design | Green | 0.3333 | 0.3468 | 260196 | 82106 | 86657 | 262624 | -8130 | 3579 | 1.099 | 1.041 | 20250531 | 20250531 | 0 | 11 | 4 | 4 | 0 | 0 | 2177 | 2196 | 2229 | 19 | 3 | 0 | 29 | 1 | 700000 | 0 | 730406 | 0 |  | 0 | 0 | 4 | 86 | 100
1408 | 20240430 | 85 | 2 | 4 | 13 | 25 | 5 | 1 | 5 | Active | Deliver | Green | 0.381 | 0.3975 | 260196 | 94213 | 98116 | 262748 | -9215 | 5312 | 1.098 | 1.054 | 20250531 | 20250531 | 0 | 11 | 4 | 4 | 0 | 0 | 2252 | 2345 | 2287 | 93 | 2 | 0 | 19 | 0 | 700000 | 0 | 726123 | 0 |  | 0 | 0 | 3 | 86 | 100
1409 | 20240531 | 85 | 2 | 4 | 13 | 25 | 5 | 1 | 5 | Active | Deliver | Green | 0.4286 | 0.4277 | 260196 | 106415 | 107247 | 262872 | -4871 | 4039 | 1.046 | 1.038 | 20250531 | 20250531 | 1 | 11 | 5 | 4 | 0 | 0 | 2304 | 2433 | 2437 | 129 | 1 | 0 | 10 | 0 | 700000 | 0 | 724337 | 0 |  | 0 | 0 | 3 | 89 | 100
1410 | 20240630 | 85 | 2 | 4 | 13 | 25 | 5 | 1 | 5 | Active | Deliver | Green | 0.4762 | 0.4727 | 260196 | 118711 | 117522 | 262996 | -4284 | 5473 | 1.036 | 1.047 | 20250531 | 20250531 | 2 | 11 | 5 | 4 | 0 | 0 | 2330 | 2311 | 2244 | -19 | 4 | 1 | 56 | 1 | 700000 | 0 | 697300 | 0 |  | 0 | 0 | 2 | 83 | 95
1411 | 20240731 | 85 | 2 | 4 | 13 | 25 | 5 | 1 | 5 | Active | Deliver | Green | 0.5238 | 0.5104 | 260196 | 131101 | 128022 | 263120 | -1703 | 4782 | 1.013 | 1.037 | 20250531 | 20250531 | 9 | 11 | 6 | 6 | 0 | 0 | 2330 | 2276 | 2403 | -54 | 2 | 0 | 19 | 0 | 700000 | 0 | 710740 | 0 |  | 0 | 0 | 2 | 82 | 100
1412 | 20240831 | 85 | 2 | 4 | 13 | 25 | 5 | 1 | 5 | Active | Deliver | Green | 0.5714 | 0.5746 | 260196 | 143586 | 145071 | 263244 | -5923 | 4438 | 1.041 | 1.031 | 20250531 | 20250531 | 0 | 11 | 6 | 5 | 0 | 0 | 2304 | 2261 | 2323 | -43 | 3 | 0 | 29 | 1 | 700000 | 0 | 729248 | 0 |  | 0 | 0 | 2 | 85 | 100
1413 | 20240930 | 85 | 2 | 4 | 13 | 25 | 5 | 1 | 5 | Active | Deliver | Green | 0.619 | 0.6259 | 260196 | 156165 | 158700 | 263368 | -6692 | 4157 | 1.043 | 1.026 | 20250531 | 20250531 | 0 | 11 | 7 | 6 | 0 | 0 | 2252 | 2281 | 2191 | 29 | 3 | 0 | 29 | 1 | 700000 | 0 | 711026 | 0 |  | 0 | 0 | 3 | 86 | 100
1414 | 20241031 | 85 | 2 | 4 | 13 | 25 | 5 | 1 | 5 | Active | Deliver | Green | 0.6667 | 0.6833 | 260196 | 168838 | 175392 | 263492 | -8954 | 2400 | 1.053 | 1.014 | 20250531 | 20250531 | 0 | 11 | 7 | 6 | 0 | 0 | 2177 | 2124 | 2217 | -53 | 3 | 0 | 29 | 1 | 700000 | 0 | 703680 | 0 |  | 0 | 0 | 3 | 88 | 100
1415 | 20241130 | 85 | 2 | 4 | 13 | 25 | 5 | 1 | 5 | Active | Deliver | Green | 0.7143 | 0.7343 | 260196 | 181606 | 191608 | 263778 | -9456 | -546 | 1.052 | 0.997 | 20250531 | 20250531 | 0 | 11 | 8 | 7 | 0 | 0 | 2078 | 2135 | 2185 | 57 | 4 | 0 | 38 | 1 | 700000 | 0 | 718326 | 0 |  | 0 | 0 | 3 | 82 | 100
1416 | 20241231 | 85 | 2 | 4 | 13 | 25 | 5 | 1 | 5 | Active | Deploy | Green | 0.7619 | 0.7821 | 260196 | 194468 | 202853 | 263740 | -9031 | 646 | 1.046 | 1.003 | 20250531 | 20250531 | 0 | 11 | 8 | 8 | 0 | 0 | 1960 | 2059 | 2051 | 99 | 4 | 0 | 38 | 1 | 700000 | 104762 | 708114 | 0 | 0 | 0 | 0 | 5 | 86 | 100
1417 | 20250131 | 85 | 2 | 4 | 13 | 25 | 5 | 1 | 5 | Active | Deploy | Green | 0.8095 | 0.8441 | 260196 | 207425 | 221591 | 264367 | -12206 | -1960 | 1.059 | 0.991 | 20250531 | 20250531 | 0 | 11 | 9 | 9 | 0 | 0 | 1823 | 1854 | 1976 | 31 | 1 | 0 | 10 | 0 | 700000 | 223810 | 699187 | 66268 | 0.2961 | 0 | 0 | 0 | 87 | 100
1418 | 20250228 | 85 | 2 | 4 | 13 | 25 | 5 | 1 | 5 | Active | Deploy | Green | 0.8571 | 0.863 | 260196 | 220476 | 227008 | 264605 | -4073 | -2459 | 1.019 | 0.989 | 20250531 | 20250531 | 0 | 11 | 9 | 9 | 0 | 0 | 1672 | 1789 | 1851 | 117 | 0 | 0 | 0 | 0 | 700000 | 342857 | 721051 | 182655 | 0.5327 | 0 | 0 | 0 | 84 | 100
1419 | 20250331 | 85 | 2 | 4 | 13 | 25 | 5 | 1 | 5 | Active | Deploy | Green | 0.9048 | 0.9063 | 260196 | 233622 | 238537 | 264764 | -2194 | -2721 | 1.009 | 0.989 | 20250531 | 20250531 | 0 | 11 | 10 | 10 | 0 | 0 | 1510 | 1458 | 1522 | -52 | 0 | 0 | 0 | 0 | 700000 | 461905 | 717266 | 273760 | 0.5927 | 1 | 3000 | 0 | 79 | 99.3
1420 | 20250430 | 85 | 2 | 4 | 13 | 25 | 5 | 1 | 5 | Active | Deploy | Green | 0.9524 | 0.9501 | 260196 | 246862 | 254492 | 265873 | -350 | -7280 | 1.001 | 0.971 | 20250531 | 20250531 | 1 | 11 | 10 | 9 | 0 | 0 | 1340 | 1329 | 1406 | -11 | 0 | 0 | 0 | 0 | 700000 | 580952 | 708278 | 401184 | 0.6906 | 1 | 3000 | 1 | 78 | 98.9
1421 | 20250531 | 85 | 2 | 4 | 13 | 25 | 5 | 1 | 5 | Active | Deploy | Green | 1 | 0.9864 | 260196 | 260196 | 265296 | 266223 | 3539 | -8639 | 0.986 | 0.967 | 20250531 | 20250531 | 10 | 11 | 11 | 10 | 0 | 0 | 1166 | 1201 | 1169 | 35 | 1 | 0 | 10 | 0 | 700000 | 700000 | 712287 | 477868 | 0.6827 | 1 | 3000 | 2 | 83 | 98.2
1422 | 20250630 | 85 | 2 | 4 | 13 | 25 | 5 | 1 | 5 | Completed | Completed | Green | 1 | 1 | 260196 | 260196 | 268878 | 268878 | 0 | -8682 | 1 | 0.968 | 20250531 | 20250531 | 0 | 11 | 11 | 11 | 0 | 0 | 1166 | 1122 | 1199 | -44 | 0 | 0 | 0 | 0 | 700000 | 700000 | 697340 | 611682 | 0.8738 | 1 | 4000 | 1 | 79 | 97.9
1423 | 20240131 | 86 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Initiate & Design | Green | 0.0476 | 0.0704 | 1198982 | 52744 | 80915 | 1222277 | -31664 | 3493 | 1.601 | 1.043 | 20250930 | 20250930 | 0 | 11 | 1 | 0 | 0 | 0 | 6176 | 6552 | 6824 | 376 | 0 | 0 | 0 | 0 | 1800000 | 0 | 1940276 | 0 |  | 0 | 0 | 3 | 96 | 100
1424 | 20240229 | 86 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Initiate & Design | Green | 0.0952 | 0.1056 | 1198982 | 105924 | 114668 | 1223989 | -20688 | 11944 | 1.195 | 1.104 | 20250930 | 20250930 | 0 | 11 | 1 | 1 | 0 | 0 | 6959 | 7817 | 7613 | 858 | 1 | 0 | 9 | 0 | 1800000 | 0 | 1965158 | 0 |  | 0 | 0 | 3 | 91 | 100
1425 | 20240331 | 86 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Initiate & Design | Green | 0.1429 | 0.1766 | 1198982 | 159538 | 194902 | 1225702 | -52202 | 16838 | 1.327 | 1.086 | 20250930 | 20250930 | 0 | 11 | 2 | 1 | 0 | 0 | 7707 | 8253 | 8383 | 546 | 1 | 0 | 9 | 0 | 1800000 | 0 | 1970314 | 0 |  | 0 | 0 | 2 | 96 | 100
1426 | 20240430 | 86 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Initiate & Design | Green | 0.1905 | 0.2281 | 1198982 | 213587 | 258191 | 1227415 | -59901 | 15297 | 1.28 | 1.059 | 20250930 | 20250930 | 0 | 11 | 2 | 1 | 0 | 0 | 8402 | 9016 | 8535 | 614 | 2 | 0 | 18 | 0 | 1800000 | 0 | 1973467 | 0 |  | 0 | 0 | 3 | 96 | 100
1427 | 20240531 | 86 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Initiate & Design | Green | 0.2381 | 0.281 | 1198982 | 268072 | 322648 | 1229128 | -68842 | 14266 | 1.257 | 1.044 | 20250930 | 20250930 | 0 | 11 | 3 | 2 | 0 | 0 | 9031 | 10038 | 10685 | 1007 | 0 | 0 | 0 | 0 | 1800000 | 0 | 1921573 | 0 |  | 0 | 0 | 1 | 94 | 100
1428 | 20240630 | 86 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Initiate & Design | Green | 0.2857 | 0.3416 | 1198982 | 322991 | 394743 | 1230841 | -86581 | 14829 | 1.268 | 1.038 | 20250930 | 20250930 | 0 | 11 | 3 | 3 | 0 | 0 | 9577 | 10837 | 10504 | 1260 | 0 | 0 | 0 | 0 | 1800000 | 0 | 1961781 | 0 |  | 0 | 0 | 4 | 96 | 100
1429 | 20240731 | 86 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deliver | Green | 0.3333 | 0.3829 | 1198982 | 378345 | 437964 | 1232553 | -80745 | 21126 | 1.213 | 1.048 | 20250930 | 20250930 | 0 | 11 | 4 | 3 | 0 | 0 | 10029 | 10274 | 10248 | 245 | 1 | 0 | 9 | 0 | 1800000 | 0 | 1903403 | 0 |  | 0 | 0 | 1 | 96 | 100
1430 | 20240831 | 86 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deliver | Green | 0.381 | 0.4316 | 1198982 | 434135 | 487878 | 1234266 | -83346 | 29603 | 1.192 | 1.061 | 20250930 | 20250930 | 0 | 11 | 4 | 3 | 0 | 0 | 10378 | 11424 | 11535 | 1046 | 2 | 0 | 18 | 0 | 1800000 | 0 | 1911817 | 0 |  | 0 | 0 | 4 | 92 | 100
1431 | 20240930 | 86 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deliver | Green | 0.4286 | 0.4644 | 1198982 | 490359 | 540126 | 1235979 | -66448 | 16681 | 1.135 | 1.031 | 20250930 | 20250930 | 0 | 11 | 5 | 4 | 0 | 0 | 10615 | 11199 | 11047 | 584 | 1 | 0 | 9 | 0 | 1800000 | 0 | 1944181 | 0 |  | 0 | 0 | 4 | 91 | 100
1432 | 20241031 | 86 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deliver | Green | 0.4762 | 0.5255 | 1198982 | 547019 | 619527 | 1237692 | -83046 | 10538 | 1.152 | 1.017 | 20250930 | 20250930 | 0 | 11 | 5 | 4 | 0 | 0 | 10734 | 11461 | 11241 | 727 | 2 | 0 | 18 | 0 | 1800000 | 0 | 1899429 | 0 |  | 0 | 0 | 2 | 88 | 100
1433 | 20241130 | 86 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deliver | Green | 0.5238 | 0.568 | 1198982 | 604113 | 662393 | 1239405 | -76909 | 18629 | 1.127 | 1.028 | 20250930 | 20250930 | 0 | 11 | 6 | 6 | 0 | 0 | 10734 | 11341 | 11758 | 607 | 3 | 0 | 27 | 0 | 1800000 | 0 | 1988698 | 0 |  | 0 | 0 | 3 | 87 | 100
1434 | 20241231 | 86 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deliver | Green | 0.5714 | 0.6233 | 1198982 | 661642 | 732227 | 1241118 | -85683 | 15098 | 1.129 | 1.021 | 20250930 | 20250930 | 0 | 11 | 6 | 5 | 0 | 0 | 10615 | 11246 | 11490 | 631 | 3 | 0 | 27 | 0 | 1800000 | 0 | 1947236 | 0 |  | 0 | 0 | 4 | 88 | 100
1435 | 20250131 | 86 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deliver | Green | 0.619 | 0.6799 | 1198982 | 719607 | 801490 | 1242830 | -95581 | 13698 | 1.133 | 1.017 | 20250930 | 20250930 | 0 | 11 | 7 | 6 | 0 | 0 | 10378 | 11231 | 11952 | 853 | 3 | 0 | 27 | 0 | 1800000 | 0 | 1905932 | 0 |  | 0 | 0 | 2 | 90 | 100
1436 | 20250228 | 86 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deliver | Green | 0.6667 | 0.7479 | 1198982 | 778006 | 894343 | 1244543 | -118713 | 2376 | 1.153 | 1.003 | 20250930 | 20250930 | 0 | 11 | 7 | 7 | 0 | 0 | 10029 | 10760 | 10491 | 731 | 3 | 0 | 27 | 0 | 1800000 | 0 | 1954375 | 0 |  | 1 | 15000 | 2 | 86 | 100
1437 | 20250331 | 86 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deploy | Green | 0.7143 | 0.8138 | 1198982 | 836840 | 976707 | 1246529 | -138892 | -975 | 1.166 | 0.999 | 20250930 | 20250930 | 0 | 11 | 8 | 8 | 0 | 0 | 9577 | 9904 | 9972 | 327 | 0 | 0 | 0 | 0 | 1800000 | 0 | 1930579 | 0 |  | 1 | 13000 | 3 | 87 | 100
1438 | 20250430 | 86 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deploy | Green | 0.7619 | 0.8585 | 1198982 | 896110 | 1049134 | 1252936 | -133216 | -19808 | 1.149 | 0.981 | 20250930 | 20250930 | 0 | 11 | 8 | 8 | 0 | 0 | 9031 | 10021 | 10411 | 990 | 1 | 0 | 9 | 0 | 1800000 | 269388 | 1929498 | 0 | 0 | 1 | 18000 | 3 | 87 | 100
1439 | 20250531 | 86 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deploy | Green | 0.8095 | 0.892 | 1198982 | 955814 | 1089448 | 1254513 | -113678 | -19956 | 1.119 | 0.982 | 20250930 | 20250930 | 0 | 11 | 9 | 9 | 0 | 0 | 8402 | 9222 | 8889 | 820 | 1 | 0 | 9 | 0 | 1800000 | 575510 | 1971272 | 184388 | 0.3204 | 1 | 18000 | 2 | 86 | 100
1440 | 20250630 | 86 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deploy | Green | 0.8571 | 0.94 | 1198982 | 1015954 | 1154924 | 1257752 | -111089 | -27881 | 1.109 | 0.976 | 20250930 | 20250930 | 0 | 11 | 9 | 8 | 0 | 0 | 7707 | 7892 | 8281 | 185 | 0 | 0 | 0 | 0 | 1800000 | 881633 | 1974494 | 476281 | 0.5402 | 1 | 18000 | 1 | 84 | 100
1441 | 20250731 | 86 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Active | Deploy | Green | 0.9048 | 0.9733 | 1198982 | 1076528 | 1211110 | 1262727 | -90441 | -44141 | 1.084 | 0.964 | 20250930 | 20250930 | 0 | 11 | 10 | 9 | 0 | 0 | 6959 | 7120 | 7261 | 161 | 0 | 0 | 0 | 0 | 1800000 | 1187755 | 1904277 | 729823 | 0.6145 | 1 | 16000 | 0 | 83 | 100
1442 | 20250831 | 86 | 3 | 2 | 14 | 26 | 6 | 2 | 6 | Completed | Completed | Green | 0.9524 | 1 | 1198982 | 1137538 | 1252658 | 1266123 | -61444 | -53676 | 1.054 | 0.957 | 20250930 | 20250930 | 0 | 11 | 10 | 9 | 0 | 0 | 6176 | 6366 | 6203 | 190 | 0 | 0 | 0 | 0 | 1800000 | 1493878 | 1928823 | 1039293 | 0.6957 | 1 | 10000 | 0 | 86 | 100
1443 | 20250430 | 87 | 9 | 8 | 15 | 27 | 7 | 1 | 7 | Active | Initiate & Design | Red | 0.0667 | 0.0083 | 356174 | 21972 | 4757 | 397772 | 19016 | -1801 | 0.134 | 0.621 | 20260630 | 20260731 | 33 | 8 | 1 | 0 | 1 | 0 | 1929 | 1390 | 1407 | -539 | 10 | 2 | 154 | 3 | 600000 | 0 | 570757 | 0 |  | 0 | 0 | 3 | 24 | 24.3
1444 | 20250531 | 87 | 9 | 8 | 15 | 27 | 7 | 1 | 7 | Active | Initiate & Design | Green | 0.1333 | 0.075 | 356174 | 44197 | 25547 | 369234 | 17484 | 1166 | 0.605 | 1.046 | 20260630 | 20260731 | 33 | 8 | 1 | 0 | 1 | 0 | 2246 | 1882 | 1824 | -364 | 9 | 1 | 125 | 2 | 600000 | 0 | 567953 | 0 |  | 0 | 0 | 2 | 59 | 70.8
1445 | 20250630 | 87 | 9 | 8 | 15 | 27 | 7 | 1 | 7 | Active | Initiate & Design | Green | 0.2 | 0.1441 | 356174 | 66676 | 46589 | 370421 | 15351 | 4736 | 0.77 | 1.101 | 20260630 | 20260731 | 32 | 8 | 2 | 1 | 1 | 0 | 2535 | 1969 | 1977 | -566 | 8 | 1 | 113 | 2 | 600000 | 0 | 555742 | 0 |  | 0 | 0 | 4 | 72 | 78.2
1446 | 20250731 | 87 | 9 | 8 | 15 | 27 | 7 | 1 | 7 | Active | Initiate & Design | Green | 0.2667 | 0.2087 | 356174 | 89408 | 72008 | 371608 | 15074 | 2326 | 0.831 | 1.032 | 20260630 | 20260731 | 33 | 8 | 2 | 0 | 1 | 0 | 2783 | 2240 | 2375 | -543 | 6 | 1 | 89 | 2 | 600000 | 0 | 564823 | 0 |  | 0 | 0 | 5 | 71 | 79.6
1447 | 20250831 | 87 | 9 | 8 | 15 | 27 | 7 | 1 | 7 | Active | Initiate & Design | Green | 0.3333 | 0.2751 | 356174 | 112393 | 92873 | 372795 | 14410 | 5110 | 0.872 | 1.055 | 20260630 | 20260731 | 33 | 8 | 3 | 1 | 1 | 0 | 2979 | 2424 | 2452 | -555 | 7 | 1 | 101 | 2 | 600000 | 0 | 551001 | 0 |  | 0 | 0 | 4 | 71 | 81.8
1448 | 20250930 | 87 | 9 | 8 | 15 | 27 | 7 | 1 | 7 | Active | Initiate & Design | Green | 0.4 | 0.3184 | 356174 | 135631 | 111713 | 373983 | 22225 | 1693 | 0.836 | 1.015 | 20260630 | 20260831 | 48 | 8 | 3 | 1 | 1 | 0 | 3115 | 2360 | 2443 | -755 | 6 | 1 | 89 | 2 | 600000 | 0 | 572408 | 0 |  | 1 | 5000 | 5 | 66 | 78.5
1449 | 20251031 | 87 | 9 | 8 | 15 | 27 | 7 | 1 | 7 | Active | Deliver | Green | 0.4667 | 0.3704 | 356174 | 159123 | 127432 | 375170 | 27196 | 4495 | 0.829 | 1.035 | 20260630 | 20260831 | 55 | 8 | 4 | 3 | 1 | 0 | 3185 | 2648 | 2569 | -537 | 7 | 1 | 101 | 2 | 600000 | 0 | 560242 | 0 |  | 1 | 5000 | 4 | 74 | 80
1450 | 20251130 | 87 | 9 | 8 | 15 | 27 | 7 | 1 | 7 | Active | Deliver | Amber | 0.5333 | 0.407 | 356174 | 182868 | 145655 | 376732 | 37905 | -692 | 0.793 | 0.995 | 20260630 | 20260831 | 73 | 8 | 4 | 3 | 1 | 0 | 3185 | 2590 | 2659 | -595 | 8 | 2 | 131 | 2 | 600000 | 0 | 577445 | 0 |  | 1 | 4000 | 5 | 59 | 69.3
1451 | 20251231 | 87 | 9 | 8 | 15 | 27 | 7 | 1 | 7 | Active | Deliver | Green | 0.6 | 0.4579 | 356174 | 206866 | 164068 | 378009 | 43774 | -976 | 0.788 | 0.994 | 20260630 | 20260930 | 82 | 8 | 5 | 2 | 2 | 1 | 3115 | 2574 | 2463 | -541 | 6 | 1 | 89 | 2 | 600000 | 0 | 555611 | 0 |  | 1 | 3000 | 3 | 65 | 76.4
1452 | 20260131 | 87 | 9 | 8 | 15 | 27 | 7 | 1 | 7 | Active | Deliver | Green | 0.6667 | 0.5175 | 356174 | 231117 | 184740 | 378905 | 46797 | -420 | 0.798 | 0.998 | 20260630 | 20260930 | 86 | 8 | 5 | 2 | 2 | 1 | 2979 | 2205 | 2227 | -774 | 7 | 0 | 83 | 2 | 600000 | 0 | 578601 | 0 |  | 1 | 5000 | 4 | 75 | 84.1
1453 | 20260228 | 87 | 9 | 8 | 15 | 27 | 7 | 1 | 7 | Active | Deliver | Green | 0.7333 | 0.5868 | 356174 | 255622 | 212230 | 381114 | 46619 | -3227 | 0.818 | 0.985 | 20260630 | 20260930 | 85 | 8 | 6 | 3 | 2 | 1 | 2783 | 2180 | 2164 | -603 | 8 | 1 | 113 | 2 | 600000 | 28571 | 549243 | 0 | 0 | 1 | 5000 | 6 | 69 | 76.1
1454 | 20260331 | 87 | 9 | 8 | 15 | 27 | 7 | 1 | 7 | Active | Deliver | Green | 0.8 | 0.6726 | 356174 | 280380 | 248351 | 383878 | 40817 | -8788 | 0.854 | 0.965 | 20260630 | 20260831 | 73 | 8 | 6 | 3 | 2 | 1 | 2535 | 1974 | 2059 | -561 | 6 | 0 | 71 | 2 | 600000 | 171429 | 564760 | 34177 | 0.1994 | 1 | 3000 | 4 | 77 | 85.7
1455 | 20260430 | 87 | 9 | 8 | 15 | 27 | 7 | 1 | 7 | Active | Deploy | Green | 0.8667 | 0.7557 | 356174 | 305392 | 279627 | 385230 | 36231 | -10466 | 0.881 | 0.963 | 20260630 | 20260831 | 64 | 8 | 7 | 4 | 2 | 1 | 2246 | 1681 | 1701 | -565 | 6 | 0 | 71 | 2 | 600000 | 314286 | 559538 | 150626 | 0.4793 | 1 | 3000 | 1 | 76 | 85.9
1456 | 20260531 | 87 | 9 | 8 | 15 | 27 | 7 | 1 | 7 | Active | Deploy | Green | 0.9333 | 0.8283 | 356174 | 330656 | 311419 | 387607 | 35637 | -16400 | 0.892 | 0.947 | 20260630 | 20260831 | 61 | 8 | 7 | 4 | 2 | 1 | 1929 | 1526 | 1541 | -403 | 4 | 1 | 65 | 1 | 600000 | 457143 | 552758 | 277407 | 0.6068 | 2 | 7000 | 4 | 68 | 78.5
1457 | 20260630 | 87 | 9 | 8 | 15 | 27 | 7 | 1 | 7 | Active | Deploy | Green | 1 | 0.8977 | 356174 | 356174 | 341879 | 389746 | 36437 | -22142 | 0.898 | 0.935 | 20260630 | 20260831 | 59 | 8 | 8 | 6 | 2 | 1 | 1597 | 1150 | 1156 | -447 | 4 | 0 | 47 | 1 | 600000 | 600000 | 568327 | 403806 | 0.673 | 2 | 7000 | 4 | 79 | 85.5
1458 | 20260731 | 87 | 9 | 8 | 15 | 27 | 7 | 1 | 7 | Active | Deploy | Green | 1 | 0.8977 | 356174 | 356174 | 347231 | 392063 | 36437 | -27494 | 0.898 | 0.921 | 20260630 | 20260831 | 59 | 8 | 8 | 6 | 2 | 1 | 1597 | 1205 | 1216 | -392 | 4 | 1 | 65 | 1 | 600000 | 600000 | 564751 | 470155 | 0.7836 | 2 | 6000 | 2 | 72 | 77.6
1459 | 20260831 | 87 | 9 | 8 | 15 | 27 | 7 | 1 | 7 | Active | Deploy | Green | 1 | 0.8977 | 356174 | 356174 | 352064 | 394240 | 36437 | -32327 | 0.898 | 0.908 | 20260630 | 20260831 | 59 | 8 | 8 | 5 | 2 | 1 | 1597 | 1309 | 1293 | -288 | 4 | 0 | 47 | 1 | 600000 | 600000 | 562125 | 549401 | 0.9157 | 2 | 10000 | 4 | 78 | 86.4
1460 | 20260930 | 87 | 9 | 8 | 15 | 27 | 7 | 1 | 7 | Active | Deploy | Green | 1 | 0.8977 | 356174 | 356174 | 352715 | 395559 | 36437 | -32978 | 0.898 | 0.906 | 20260630 | 20260831 | 59 | 8 | 8 | 5 | 2 | 1 | 1597 | 1315 | 1358 | -282 | 5 | 1 | 77 | 1 | 600000 | 600000 | 554453 | 497832 | 0.8297 | 2 | 8000 | 1 | 72 | 78.1
1461 | 20231031 | 88 | 4 | 3 | 16 | 28 | 8 | 3 | 8 | Active | Deliver | Green | 0.4333 | 0.3924 | 330265 | 136627 | 125653 | 354154 | 7031 | 3943 | 0.949 | 1.031 | 20250331 | 20250531 | 49 | 15 | 7 | 5 | 1 | 0 | 2929 | 2523 | 2680 | -406 | 8 | 1 | 115 | 2 | 600000 | 0 | 585452 | 0 |  | 0 | 0 | 6 | 75 | 87.1
1462 | 20231130 | 88 | 4 | 3 | 16 | 28 | 8 | 3 | 8 | Active | Deliver | Green | 0.4667 | 0.3943 | 330265 | 147548 | 128636 | 354925 | 17325 | 1587 | 0.883 | 1.012 | 20250331 | 20250630 | 85 | 15 | 7 | 4 | 2 | 1 | 2953 | 2877 | 2988 | -76 | 7 | 1 | 103 | 2 | 600000 | 0 | 564988 | 0 |  | 0 | 0 | 5 | 74 | 85
1463 | 20231231 | 88 | 4 | 3 | 16 | 28 | 8 | 3 | 8 | Active | Deliver | Green | 0.5 | 0.434 | 330265 | 158527 | 144160 | 356118 | 15192 | -825 | 0.904 | 0.994 | 20250331 | 20250630 | 77 | 15 | 8 | 6 | 2 | 1 | 2961 | 2662 | 2753 | -299 | 7 | 1 | 103 | 2 | 600000 | 0 | 585830 | 0 |  | 1 | 4000 | 6 | 71 | 84.6
1464 | 20240131 | 88 | 4 | 3 | 16 | 28 | 8 | 3 | 8 | Active | Deliver | Green | 0.5333 | 0.4484 | 330265 | 169565 | 148452 | 356637 | 21474 | -361 | 0.873 | 0.998 | 20250331 | 20250630 | 100 | 15 | 8 | 5 | 2 | 1 | 2953 | 2628 | 2648 | -325 | 6 | 0 | 73 | 2 | 600000 | 0 | 580321 | 0 |  | 1 | 4000 | 4 | 74 | 90.9
1465 | 20240229 | 88 | 4 | 3 | 16 | 28 | 8 | 3 | 8 | Active | Deliver | Green | 0.5667 | 0.4789 | 330265 | 180662 | 158379 | 357338 | 22498 | -215 | 0.875 | 0.999 | 20250331 | 20250630 | 104 | 15 | 9 | 7 | 2 | 1 | 2929 | 2585 | 2753 | -344 | 6 | 1 | 91 | 2 | 600000 | 0 | 582210 | 0 |  | 1 | 4000 | 4 | 71 | 82.9
1466 | 20240331 | 88 | 4 | 3 | 16 | 28 | 8 | 3 | 8 | Active | Deliver | Green | 0.6 | 0.4908 | 330265 | 191818 | 164869 | 359231 | 29724 | -2775 | 0.845 | 0.983 | 20250331 | 20250731 | 129 | 15 | 9 | 6 | 3 | 1 | 2889 | 2657 | 2568 | -232 | 8 | 1 | 115 | 2 | 600000 | 0 | 563729 | 0 |  | 1 | 5000 | 5 | 73 | 81
1467 | 20240430 | 88 | 4 | 3 | 16 | 28 | 8 | 3 | 8 | Active | Deliver | Green | 0.6333 | 0.5339 | 330265 | 203032 | 180049 | 360274 | 26704 | -3721 | 0.869 | 0.979 | 20250331 | 20250731 | 117 | 15 | 10 | 6 | 3 | 1 | 2833 | 2488 | 2457 | -345 | 6 | 1 | 91 | 2 | 600000 | 0 | 580287 | 0 |  | 1 | 4000 | 6 | 69 | 81.8
1468 | 20240531 | 88 | 4 | 3 | 16 | 28 | 8 | 3 | 8 | Active | Deliver | Green | 0.6667 | 0.5861 | 330265 | 214305 | 196733 | 360714 | 20737 | -3165 | 0.903 | 0.984 | 20250331 | 20250531 | 59 | 15 | 10 | 7 | 2 | 1 | 2763 | 2485 | 2388 | -278 | 5 | 1 | 79 | 1 | 600000 | 0 | 571730 | 0 |  | 1 | 3000 | 3 | 74 | 83.6
1469 | 20240630 | 88 | 4 | 3 | 16 | 28 | 8 | 3 | 8 | Active | Deliver | Green | 0.7 | 0.6436 | 330265 | 225637 | 220716 | 363008 | 13078 | -8157 | 0.942 | 0.963 | 20250331 | 20250430 | 32 | 15 | 11 | 9 | 2 | 1 | 2678 | 2465 | 2593 | -213 | 6 | 1 | 91 | 2 | 600000 | 0 | 573157 | 0 |  | 1 | 3000 | 4 | 74 | 85.1
1470 | 20240731 | 88 | 4 | 3 | 16 | 28 | 8 | 3 | 8 | Active | Deliver | Green | 0.7333 | 0.6754 | 330265 | 237028 | 231987 | 363887 | 13967 | -8926 | 0.941 | 0.962 | 20250331 | 20250430 | 33 | 15 | 11 | 8 | 2 | 1 | 2581 | 2277 | 2292 | -304 | 6 | 1 | 91 | 2 | 600000 | 28571 | 576795 | 0 | 0 | 1 | 4000 | 4 | 74 | 84.3
1471 | 20240831 | 88 | 4 | 3 | 16 | 28 | 8 | 3 | 8 | Active | Deliver | Green | 0.7667 | 0.7124 | 330265 | 248477 | 246753 | 365242 | 13196 | -11472 | 0.947 | 0.953 | 20250331 | 20250430 | 29 | 15 | 12 | 10 | 2 | 1 | 2471 | 2200 | 2071 | -271 | 6 | 0 | 73 | 2 | 600000 | 100000 | 579061 | 0 | 0 | 1 | 4000 | 6 | 78 | 92.6
1472 | 20240930 | 88 | 4 | 3 | 16 | 28 | 8 | 3 | 8 | Active | Deliver | Green | 0.8 | 0.7455 | 330265 | 259985 | 260799 | 366697 | 13772 | -14586 | 0.947 | 0.944 | 20250331 | 20250430 | 29 | 15 | 12 | 10 | 2 | 1 | 2351 | 2097 | 2192 | -254 | 8 | 1 | 115 | 2 | 600000 | 171429 | 564415 | 33654 | 0.1963 | 1 | 4000 | 5 | 77 | 83.6
1473 | 20241031 | 88 | 4 | 3 | 16 | 28 | 8 | 3 | 8 | Active | Deploy | Green | 0.8333 | 0.7753 | 330265 | 271551 | 270519 | 367288 | 15497 | -14465 | 0.943 | 0.947 | 20250331 | 20250430 | 33 | 15 | 13 | 11 | 2 | 1 | 2221 | 2103 | 2083 | -118 | 5 | 0 | 61 | 1 | 600000 | 242857 | 589321 | 93840 | 0.3864 | 1 | 4000 | 4 | 81 | 93.9
1474 | 20241130 | 88 | 4 | 3 | 16 | 28 | 8 | 3 | 8 | Active | Deploy | Green | 0.8667 | 0.7952 | 330265 | 283177 | 281617 | 369076 | 20550 | -18990 | 0.927 | 0.933 | 20250331 | 20250531 | 49 | 15 | 13 | 11 | 2 | 1 | 2083 | 1838 | 1939 | -245 | 5 | 0 | 61 | 1 | 600000 | 314286 | 571932 | 152384 | 0.4849 | 2 | 7000 | 3 | 76 | 90.5
1475 | 20241231 | 88 | 4 | 3 | 16 | 28 | 8 | 3 | 8 | Active | Deploy | Green | 0.9 | 0.8445 | 330265 | 294861 | 298188 | 369637 | 15952 | -19279 | 0.946 | 0.935 | 20250331 | 20250430 | 31 | 15 | 14 | 11 | 2 | 1 | 1938 | 1895 | 2014 | -43 | 3 | 0 | 36 | 1 | 600000 | 385714 | 563926 | 215760 | 0.5594 | 2 | 10000 | 3 | 80 | 93.1
1476 | 20250131 | 88 | 4 | 3 | 16 | 28 | 8 | 3 | 8 | Active | Deploy | Green | 0.9333 | 0.8808 | 330265 | 306603 | 312543 | 370749 | 15706 | -21646 | 0.949 | 0.931 | 20250331 | 20250430 | 27 | 15 | 14 | 12 | 2 | 1 | 1788 | 1686 | 1611 | -102 | 4 | 1 | 67 | 1 | 600000 | 457143 | 575504 | 265668 | 0.5811 | 2 | 7000 | 2 | 75 | 84.9
1477 | 20250228 | 88 | 4 | 3 | 16 | 28 | 8 | 3 | 8 | Active | Deploy | Green | 0.9667 | 0.9455 | 330265 | 318405 | 340602 | 372529 | 6139 | -28336 | 0.981 | 0.917 | 20250331 | 20250331 | -10 | 15 | 15 | 14 | 1 | 0 | 1635 | 1425 | 1390 | -210 | 5 | 0 | 61 | 1 | 600000 | 528571 | 579463 | 316746 | 0.5992 | 2 | 9000 | 3 | 81 | 92.4
1478 | 20250331 | 88 | 4 | 3 | 16 | 28 | 8 | 3 | 8 | Active | Deploy | Green | 1 | 0.9996 | 330265 | 330265 | 361629 | 373583 | 132 | -31496 | 1 | 0.913 | 20250331 | 20250331 | -35 | 15 | 15 | 13 | 1 | 0 | 1480 | 1377 | 1346 | -103 | 5 | 1 | 79 | 1 | 600000 | 600000 | 589892 | 403968 | 0.6733 | 2 | 6000 | 3 | 71 | 86.9
1479 | 20250430 | 88 | 4 | 3 | 16 | 28 | 8 | 3 | 8 | Active | Deploy | Green | 1 | 0.9996 | 330265 | 330265 | 363073 | 374617 | 132 | -32940 | 1 | 0.909 | 20250331 | 20250331 | -35 | 15 | 15 | 13 | 1 | 0 | 1480 | 1424 | 1341 | -56 | 4 | 0 | 49 | 1 | 600000 | 600000 | 579014 | 464306 | 0.7738 | 2 | 7000 | 3 | 78 | 95
1480 | 20250531 | 88 | 4 | 3 | 16 | 28 | 8 | 3 | 8 | Active | Deploy | Green | 1 | 0.9996 | 330265 | 330265 | 365957 | 375908 | 132 | -35824 | 1 | 0.902 | 20250331 | 20250331 | -35 | 15 | 15 | 14 | 1 | 0 | 1480 | 1285 | 1306 | -195 | 5 | 1 | 79 | 1 | 600000 | 600000 | 580944 | 548156 | 0.9136 | 2 | 7000 | 2 | 71 | 84.8
1481 | 20250630 | 88 | 4 | 3 | 16 | 28 | 8 | 3 | 8 | Active | Deploy | Green | 1 | 0.9996 | 330265 | 330265 | 366533 | 376782 | 132 | -36400 | 1 | 0.901 | 20250331 | 20250331 | -35 | 15 | 15 | 13 | 1 | 0 | 1480 | 1373 | 1326 | -107 | 4 | 0 | 49 | 1 | 600000 | 600000 | 568208 | 513872 | 0.8565 | 2 | 10000 | 1 | 79 | 93.4
1482 | 20250731 | 88 | 4 | 3 | 16 | 28 | 8 | 3 | 8 | Active | Deploy | Green | 1 | 0.9996 | 330265 | 330265 | 369596 | 378095 | 132 | -39463 | 1 | 0.893 | 20250331 | 20250331 | -35 | 15 | 15 | 14 | 1 | 0 | 1480 | 1418 | 1406 | -62 | 4 | 1 | 67 | 1 | 600000 | 600000 | 586928 | 558859 | 0.9314 | 2 | 10000 | 2 | 74 | 86.7
1483 | 20250831 | 88 | 4 | 3 | 16 | 28 | 8 | 3 | 8 | Active | Deploy | Green | 1 | 0.9996 | 330265 | 330265 | 369596 | 378865 | 132 | -39463 | 1 | 0.893 | 20250331 | 20250331 | -35 | 15 | 15 | 13 | 1 | 0 | 1480 | 1277 | 1260 | -203 | 5 | 1 | 79 | 1 | 600000 | 600000 | 582690 | 542386 | 0.904 | 2 | 5000 | 4 | 76 | 84.4
1484 | 20250930 | 88 | 4 | 3 | 16 | 28 | 8 | 3 | 8 | Active | Deploy | Green | 1 | 0.9996 | 330265 | 330265 | 375880 | 380721 | 132 | -45747 | 1 | 0.878 | 20250331 | 20250331 | -35 | 15 | 15 | 13 | 1 | 0 | 1480 | 1395 | 1424 | -85 | 4 | 1 | 67 | 1 | 600000 | 600000 | 571761 | 499014 | 0.8317 | 2 | 5000 | 3 | 69 | 85.1
1485 | 20251031 | 88 | 4 | 3 | 16 | 28 | 8 | 3 | 8 | Completed | Completed | Green | 1 | 1 | 330265 | 330265 | 375880 | 381467 | 0 | -45615 | 1 | 0.879 | 20250331 | 20250331 | -35 | 15 | 15 | 14 | 1 | 0 | 1480 | 1286 | 1324 | -194 | 4 | 0 | 49 | 1 | 600000 | 600000 | 571616 | 519292 | 0.8655 | 2 | 9000 | 3 | 82 | 91.5
1486 | 20240630 | 89 | 9 | 8 | 17 | 29 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.0476 | 0.0541 | 1159794 | 51020 | 65488 | 1192940 | -11725 | -2743 | 1.23 | 0.958 | 20260228 | 20260228 | 0 | 11 | 1 | 1 | 0 | 0 | 5974 | 6227 | 6413 | 253 | 4 | 0 | 41 | 1 | 1300000 | 0 | 994384 | 0 |  | 0 | 0 | 3 | 82 | 100
1487 | 20240731 | 89 | 9 | 8 | 17 | 29 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.0952 | 0.1058 | 1159794 | 102462 | 113289 | 1183984 | -20244 | 9417 | 1.197 | 1.083 | 20260228 | 20260228 | 0 | 11 | 1 | 1 | 0 | 0 | 6732 | 7084 | 7209 | 352 | 4 | 0 | 41 | 1 | 1300000 | 0 | 976043 | 0 |  | 1 | 9000 | 4 | 84 | 100
1488 | 20240831 | 89 | 9 | 8 | 17 | 29 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.1429 | 0.1601 | 1159794 | 154324 | 166165 | 1185641 | -31359 | 19518 | 1.203 | 1.118 | 20260228 | 20260228 | 0 | 11 | 2 | 1 | 0 | 0 | 7455 | 7708 | 7603 | 253 | 3 | 0 | 31 | 1 | 1300000 | 0 | 1003481 | 0 |  | 1 | 12000 | 4 | 89 | 100
1489 | 20240930 | 89 | 9 | 8 | 17 | 29 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.1905 | 0.1981 | 1159794 | 206606 | 210830 | 1187298 | -23149 | 18925 | 1.112 | 1.09 | 20260228 | 20260228 | 0 | 11 | 2 | 2 | 0 | 0 | 8128 | 8556 | 8803 | 428 | 4 | 0 | 41 | 1 | 1300000 | 0 | 975656 | 0 |  | 1 | 18000 | 2 | 83 | 100
1490 | 20241031 | 89 | 9 | 8 | 17 | 29 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.2381 | 0.247 | 1159794 | 259310 | 271566 | 1188955 | -27159 | 14903 | 1.105 | 1.055 | 20260228 | 20260228 | 0 | 11 | 3 | 2 | 0 | 0 | 8735 | 8368 | 8450 | -367 | 4 | 0 | 41 | 1 | 1300000 | 0 | 964207 | 0 |  | 1 | 14000 | 3 | 78 | 98.5
1491 | 20241130 | 89 | 9 | 8 | 17 | 29 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.2857 | 0.2786 | 1159794 | 312434 | 311454 | 1190611 | -10685 | 11665 | 1.034 | 1.038 | 20260228 | 20260228 | 5 | 11 | 3 | 3 | 0 | 0 | 9264 | 9730 | 9485 | 466 | 3 | 0 | 31 | 1 | 1300000 | 0 | 996467 | 0 |  | 1 | 17000 | 5 | 74 | 96.3
1492 | 20241231 | 89 | 9 | 8 | 17 | 29 | 1 | 3 | 1 | Active | Initiate & Design | Green | 0.3333 | 0.3259 | 1159794 | 365979 | 361867 | 1192268 | -11998 | 16110 | 1.033 | 1.045 | 20260228 | 20260228 | 6 | 11 | 4 | 3 | 0 | 0 | 9702 | 10111 | 10244 | 409 | 2 | 0 | 20 | 0 | 1300000 | 0 | 970295 | 0 |  | 1 | 14000 | 3 | 74 | 95.9
1493 | 20250131 | 89 | 9 | 8 | 17 | 29 | 1 | 3 | 1 | Active | Deliver | Green | 0.381 | 0.3607 | 1159794 | 419945 | 407084 | 1193925 | 1607 | 11254 | 0.996 | 1.028 | 20260228 | 20260331 | 15 | 11 | 4 | 4 | 0 | 0 | 10039 | 10352 | 10924 | 313 | 3 | 0 | 31 | 1 | 1300000 | 0 | 952685 | 0 |  | 1 | 10000 | 2 | 70 | 93.3
1494 | 20250228 | 89 | 9 | 8 | 17 | 29 | 1 | 3 | 1 | Active | Deliver | Green | 0.4286 | 0.4313 | 1159794 | 474332 | 484162 | 1195582 | -25887 | 16057 | 1.055 | 1.033 | 20260228 | 20260228 | 0 | 11 | 5 | 5 | 0 | 0 | 10268 | 10124 | 9562 | -144 | 5 | 0 | 51 | 1 | 1300000 | 0 | 995538 | 0 |  | 1 | 10000 | 5 | 80 | 96.8
1495 | 20250331 | 89 | 9 | 8 | 17 | 29 | 1 | 3 | 1 | Active | Deliver | Green | 0.4762 | 0.4997 | 1159794 | 529140 | 569387 | 1197239 | -50409 | 10162 | 1.095 | 1.018 | 20260228 | 20260228 | 0 | 11 | 5 | 4 | 0 | 0 | 10384 | 10763 | 11177 | 379 | 5 | 0 | 51 | 1 | 1300000 | 0 | 995730 | 0 |  | 1 | 13000 | 5 | 79 | 98.4
1496 | 20250430 | 89 | 9 | 8 | 17 | 29 | 1 | 3 | 1 | Active | Deliver | Green | 0.5238 | 0.5478 | 1159794 | 584368 | 624382 | 1198896 | -50967 | 10953 | 1.087 | 1.018 | 20260228 | 20260228 | 0 | 11 | 6 | 6 | 0 | 0 | 10384 | 10265 | 9987 | -119 | 3 | 0 | 31 | 1 | 1300000 | 0 | 946196 | 0 |  | 1 | 15000 | 4 | 75 | 96.7
1497 | 20250531 | 89 | 9 | 8 | 17 | 29 | 1 | 3 | 1 | Active | Deliver | Green | 0.5714 | 0.6033 | 1159794 | 640017 | 691676 | 1200552 | -59687 | 8028 | 1.093 | 1.012 | 20260228 | 20260228 | 0 | 11 | 6 | 5 | 0 | 0 | 10268 | 10346 | 9752 | 78 | 5 | 0 | 51 | 1 | 1300000 | 0 | 993525 | 0 |  | 1 | 11000 | 5 | 79 | 98
1498 | 20250630 | 89 | 9 | 8 | 17 | 29 | 1 | 3 | 1 | Active | Deliver | Green | 0.619 | 0.6536 | 1159794 | 696087 | 748399 | 1202209 | -61954 | 9642 | 1.089 | 1.013 | 20260228 | 20260228 | 0 | 11 | 7 | 7 | 0 | 0 | 10039 | 9814 | 10472 | -225 | 4 | 0 | 41 | 1 | 1300000 | 0 | 973541 | 0 |  | 1 | 18000 | 4 | 81 | 96.9
1499 | 20250731 | 89 | 9 | 8 | 17 | 29 | 1 | 3 | 1 | Active | Deliver | Green | 0.6667 | 0.6709 | 1159794 | 752577 | 771436 | 1203866 | -25529 | 6670 | 1.034 | 1.009 | 20260228 | 20260228 | 0 | 11 | 7 | 7 | 0 | 0 | 9702 | 10062 | 9496 | 360 | 3 | 0 | 31 | 1 | 1300000 | 0 | 1001674 | 0 |  | 1 | 18000 | 3 | 72 | 95.4
1500 | 20250831 | 89 | 9 | 8 | 17 | 29 | 1 | 3 | 1 | Active | Deliver | Green | 0.7143 | 0.7128 | 1159794 | 809489 | 838396 | 1209066 | -17212 | -11695 | 1.021 | 0.986 | 20260228 | 20260228 | 1 | 11 | 8 | 8 | 0 | 0 | 9264 | 9319 | 9688 | 55 | 2 | 0 | 20 | 0 | 1300000 | 0 | 968915 | 0 |  | 1 | 13000 | 1 | 73 | 93.3
1501 | 20250930 | 89 | 9 | 8 | 17 | 29 | 1 | 3 | 1 | Active | Deploy | Green | 0.7619 | 0.7557 | 1159794 | 866821 | 891796 | 1211580 | -9635 | -15340 | 1.011 | 0.983 | 20260228 | 20260228 | 5 | 11 | 8 | 8 | 0 | 0 | 8735 | 9263 | 9466 | 528 | 2 | 0 | 20 | 0 | 1300000 | 194558 | 962468 | 0 | 0 | 1 | 16000 | 3 | 71 | 92.6
1502 | 20251031 | 89 | 9 | 8 | 17 | 29 | 1 | 3 | 1 | Active | Deploy | Green | 0.8095 | 0.8049 | 1159794 | 924574 | 955925 | 1214809 | -8944 | -22407 | 1.01 | 0.977 | 20260228 | 20260228 | 4 | 11 | 9 | 8 | 0 | 0 | 8128 | 7933 | 7760 | -195 | 2 | 0 | 20 | 0 | 1300000 | 415646 | 999148 | 87191 | 0.2098 | 1 | 16000 | 2 | 69 | 92.6
1503 | 20251130 | 89 | 9 | 8 | 17 | 29 | 1 | 3 | 1 | Active | Deploy | Green | 0.8571 | 0.8687 | 1159794 | 982748 | 1030713 | 1216249 | -24765 | -23200 | 1.025 | 0.977 | 20260228 | 20260228 | 0 | 11 | 9 | 9 | 0 | 0 | 7455 | 7131 | 7482 | -324 | 3 | 0 | 31 | 1 | 1300000 | 636735 | 996342 | 226603 | 0.3559 | 1 | 16000 | 2 | 75 | 92.8
1504 | 20251231 | 89 | 9 | 8 | 17 | 29 | 1 | 3 | 1 | Active | Deploy | Green | 0.9048 | 0.915 | 1159794 | 1041342 | 1101228 | 1221414 | -19870 | -40016 | 1.019 | 0.964 | 20260228 | 20260228 | 0 | 11 | 10 | 10 | 0 | 0 | 6732 | 7200 | 7178 | 468 | 3 | 0 | 31 | 1 | 1300000 | 857823 | 969071 | 397978 | 0.4639 | 1 | 12000 | 2 | 70 | 92.5
1505 | 20260131 | 89 | 9 | 8 | 17 | 29 | 1 | 3 | 1 | Active | Deploy | Green | 0.9524 | 0.9671 | 1159794 | 1100358 | 1177343 | 1225886 | -21279 | -55706 | 1.019 | 0.953 | 20260228 | 20260228 | 0 | 11 | 10 | 9 | 0 | 0 | 5974 | 6148 | 5886 | 174 | 1 | 0 | 10 | 0 | 1300000 | 1078912 | 998675 | 542041 | 0.5024 | 1 | 11000 | 0 | 76 | 92.7
1506 | 20260228 | 89 | 9 | 8 | 17 | 29 | 1 | 3 | 1 | Completed | Completed | Green | 1 | 1 | 1159794 | 1159794 | 1224071 | 1228863 | 0 | -64277 | 1 | 0.947 | 20260228 | 20260228 | 0 | 11 | 11 | 10 | 0 | 0 | 5199 | 5187 | 5357 | -12 | 3 | 1 | 49 | 1 | 1300000 | 1300000 | 943074 | 634371 | 0.488 | 1 | 12000 | 3 | 64 | 82.4
1507 | 20231031 | 90 | 3 | 2 | 18 | 30 | 2 | 3 | 2 | Active | Initiate & Design | Red | 0.4 | 0.21 | 2076375 | 790684 | 447106 | 2502909 | 354645 | -11067 | 0.552 | 0.975 | 20240731 | 20241130 | 125 | 8 | 3 | 1 | 2 | 1 | 18160 | 14176 | 13917 | -3984 | 12 | 3 | 225 | 4 | 2500000 | 0 | 1748526 | 0 |  | 2 | 61000 | 11 | 40 | 41.7
1508 | 20231130 | 90 | 3 | 2 | 18 | 30 | 2 | 3 | 2 | Active | Initiate & Design | Amber | 0.4667 | 0.2787 | 2076375 | 927632 | 593907 | 2530983 | 348946 | -15221 | 0.624 | 0.975 | 20240731 | 20241130 | 125 | 8 | 4 | 1 | 3 | 2 | 18565 | 14378 | 13853 | -4187 | 11 | 2 | 193 | 4 | 2500000 | 0 | 1777794 | 0 |  | 2 | 43000 | 9 | 45 | 53.1
1509 | 20231231 | 90 | 3 | 2 | 18 | 30 | 2 | 3 | 2 | Active | Initiate & Design | Amber | 0.5333 | 0.3385 | 2076375 | 1066057 | 762524 | 2582754 | 363204 | -59671 | 0.659 | 0.922 | 20240731 | 20241130 | 129 | 8 | 4 | 1 | 2 | 1 | 18565 | 15201 | 14577 | -3364 | 11 | 2 | 193 | 4 | 2500000 | 0 | 1752186 | 0 |  | 2 | 53000 | 8 | 43 | 53.6
1510 | 20240131 | 90 | 3 | 2 | 18 | 30 | 2 | 3 | 2 | Active | Deliver | Amber | 0.6 | 0.3893 | 2076375 | 1205959 | 865932 | 2605061 | 397626 | -57599 | 0.67 | 0.934 | 20240731 | 20241231 | 139 | 8 | 5 | 2 | 3 | 2 | 18160 | 14626 | 14872 | -3534 | 9 | 2 | 164 | 3 | 2500000 | 0 | 1793272 | 0 |  | 2 | 61000 | 9 | 48 | 54.6
1511 | 20240229 | 90 | 3 | 2 | 18 | 30 | 2 | 3 | 2 | Active | Deliver | Amber | 0.6667 | 0.4479 | 2076375 | 1347337 | 1020036 | 2642730 | 417329 | -90028 | 0.69 | 0.912 | 20240731 | 20241231 | 144 | 8 | 5 | 2 | 3 | 2 | 17369 | 14345 | 13587 | -3024 | 9 | 2 | 164 | 3 | 2500000 | 0 | 1793438 | 0 |  | 2 | 59000 | 9 | 45 | 55.2
1512 | 20240331 | 90 | 3 | 2 | 18 | 30 | 2 | 3 | 2 | Active | Deliver | Amber | 0.7333 | 0.5014 | 2076375 | 1490191 | 1168172 | 2679799 | 449097 | -127078 | 0.699 | 0.891 | 20240731 | 20241231 | 153 | 8 | 6 | 2 | 3 | 2 | 16225 | 13906 | 14054 | -2319 | 9 | 2 | 164 | 3 | 2500000 | 119048 | 1717808 | 0 | 0 | 2 | 50000 | 9 | 43 | 54.7
1513 | 20240430 | 90 | 3 | 2 | 18 | 30 | 2 | 3 | 2 | Active | Deliver | Red | 0.8 | 0.5616 | 2076375 | 1634522 | 1348392 | 2719525 | 468430 | -182300 | 0.713 | 0.865 | 20240731 | 20241231 | 157 | 8 | 6 | 2 | 3 | 2 | 14779 | 12328 | 12155 | -2451 | 11 | 3 | 211 | 4 | 2500000 | 714286 | 1753438 | 115396 | 0.1616 | 2 | 52000 | 7 | 41 | 46.4
1514 | 20240531 | 90 | 3 | 2 | 18 | 30 | 2 | 3 | 2 | Active | Deliver | Amber | 0.8667 | 0.6126 | 2076375 | 1780330 | 1488701 | 2751972 | 508343 | -216714 | 0.714 | 0.854 | 20240731 | 20250131 | 167 | 8 | 7 | 3 | 4 | 2 | 13094 | 10666 | 10167 | -2428 | 7 | 2 | 136 | 2 | 2500000 | 1309524 | 1689049 | 459257 | 0.3507 | 2 | 56000 | 5 | 45 | 52.9
1515 | 20240630 | 90 | 3 | 2 | 18 | 30 | 2 | 3 | 2 | Active | Deliver | Amber | 0.9333 | 0.6372 | 2076375 | 1927614 | 1602065 | 2792690 | 604548 | -278999 | 0.686 | 0.826 | 20240731 | 20250228 | 195 | 8 | 7 | 2 | 4 | 2 | 11243 | 9643 | 9141 | -1600 | 8 | 2 | 150 | 3 | 2500000 | 1904762 | 1692302 | 808756 | 0.4246 | 3 | 78000 | 5 | 45 | 51.6
1516 | 20240731 | 90 | 3 | 2 | 18 | 30 | 2 | 3 | 2 | Active | Deliver | Amber | 1 | 0.6831 | 2076375 | 2076375 | 1742600 | 2825796 | 658003 | -324228 | 0.683 | 0.814 | 20240731 | 20250228 | 210 | 8 | 8 | 2 | 5 | 3 | 9308 | 8066 | 7679 | -1242 | 7 | 2 | 136 | 2 | 2500000 | 2500000 | 1783258 | 1276101 | 0.5104 | 3 | 79000 | 9 | 43 | 52.3
1517 | 20240831 | 90 | 3 | 2 | 18 | 30 | 2 | 3 | 2 | Active | Deliver | Amber | 1 | 0.6831 | 2076375 | 2076375 | 1783353 | 2861978 | 658003 | -364981 | 0.683 | 0.795 | 20240731 | 20250228 | 210 | 8 | 8 | 2 | 5 | 3 | 9308 | 7832 | 7817 | -1476 | 8 | 2 | 150 | 3 | 2500000 | 2500000 | 1709068 | 1541685 | 0.6167 | 3 | 75000 | 7 | 42 | 50.2
1518 | 20240930 | 90 | 3 | 2 | 18 | 30 | 2 | 3 | 2 | Active | Deliver | Amber | 1 | 0.6831 | 2076375 | 2076375 | 1803757 | 2893773 | 658003 | -385385 | 0.683 | 0.786 | 20240731 | 20250228 | 210 | 8 | 8 | 2 | 5 | 3 | 9308 | 7771 | 7564 | -1537 | 9 | 2 | 164 | 3 | 2500000 | 2500000 | 1801885 | 1645172 | 0.6581 | 3 | 52000 | 8 | 40 | 50.8
1519 | 20241031 | 90 | 3 | 2 | 18 | 30 | 2 | 3 | 2 | Active | Deliver | Amber | 1 | 0.6831 | 2076375 | 2076375 | 1827569 | 2926138 | 658003 | -409197 | 0.683 | 0.776 | 20240731 | 20250228 | 210 | 8 | 8 | 2 | 5 | 3 | 9308 | 7661 | 7506 | -1647 | 8 | 2 | 150 | 3 | 2500000 | 2500000 | 1732608 | 1588264 | 0.6353 | 3 | 56000 | 9 | 44 | 49.4
1520 | 20241130 | 90 | 3 | 2 | 18 | 30 | 2 | 3 | 2 | Active | Deliver | Amber | 1 | 0.6831 | 2076375 | 2076375 | 1866496 | 2961218 | 658003 | -448124 | 0.683 | 0.76 | 20240731 | 20250228 | 210 | 8 | 8 | 3 | 5 | 3 | 9308 | 7395 | 7123 | -1913 | 7 | 1 | 118 | 2 | 2500000 | 2500000 | 1696915 | 1674171 | 0.6697 | 4 | 103000 | 9 | 42 | 55.8
1521 | 20241231 | 90 | 3 | 2 | 18 | 30 | 2 | 3 | 2 | Active | Deliver | Red | 1 | 0.6831 | 2076375 | 2076375 | 1903538 | 2995658 | 658003 | -485166 | 0.683 | 0.745 | 20240731 | 20250228 | 210 | 8 | 8 | 2 | 5 | 3 | 9308 | 7426 | 7828 | -1882 | 8 | 2 | 150 | 3 | 2500000 | 2500000 | 1726310 | 1610305 | 0.6441 | 4 | 69000 | 9 | 37 | 47.7
1522 | 20250131 | 90 | 3 | 2 | 18 | 30 | 2 | 3 | 2 | Active | Deliver | Amber | 1 | 0.6831 | 2076375 | 2076375 | 1918018 | 3005149 | 658003 | -499646 | 0.683 | 0.74 | 20240731 | 20250228 | 210 | 8 | 8 | 3 | 5 | 3 | 9308 | 8086 | 8068 | -1222 | 10 | 2 | 178 | 3 | 2500000 | 2500000 | 1764700 | 1690773 | 0.6763 | 4 | 67000 | 7 | 40 | 49.5
1523 | 20250228 | 90 | 3 | 2 | 18 | 30 | 2 | 3 | 2 | Active | Deliver | Red | 1 | 0.6831 | 2076375 | 2076375 | 1918018 | 3005149 | 658003 | -499646 | 0.683 | 0.74 | 20240731 | 20250228 | 210 | 8 | 8 | 2 | 5 | 3 | 9308 | 7092 | 7261 | -2216 | 9 | 2 | 164 | 3 | 2500000 | 2500000 | 1807988 | 1650392 | 0.6602 | 4 | 97000 | 7 | 38 | 47.6
1524 | 20250331 | 90 | 3 | 2 | 18 | 30 | 2 | 3 | 2 | Active | Deliver | Red | 1 | 0.6831 | 2076375 | 2076375 | 1918018 | 3005149 | 658003 | -499646 | 0.683 | 0.74 | 20240731 | 20250228 | 210 | 8 | 8 | 2 | 5 | 3 | 9308 | 7152 | 7118 | -2156 | 7 | 2 | 136 | 2 | 2500000 | 2500000 | 1806964 | 1602770 | 0.6411 | 4 | 118000 | 8 | 40 | 47.8
1525 | 20250430 | 90 | 3 | 2 | 18 | 30 | 2 | 3 | 2 | Active | Deliver | Red | 1 | 0.6831 | 2076375 | 2076375 | 1918018 | 3005149 | 658003 | -499646 | 0.683 | 0.74 | 20240731 | 20250228 | 210 | 8 | 8 | 3 | 5 | 3 | 9308 | 7522 | 7519 | -1786 | 8 | 2 | 150 | 3 | 2500000 | 2500000 | 1704612 | 1664003 | 0.6656 | 4 | 83000 | 8 | 42 | 47.5
1526 | 20250531 | 90 | 3 | 2 | 18 | 30 | 2 | 3 | 2 | Active | Deliver | Amber | 1 | 0.6831 | 2076375 | 2076375 | 1918018 | 3005149 | 658003 | -499646 | 0.683 | 0.74 | 20240731 | 20250228 | 210 | 8 | 8 | 2 | 5 | 3 | 9308 | 7906 | 7891 | -1402 | 9 | 2 | 164 | 3 | 2500000 | 2500000 | 1703398 | 1517843 | 0.6071 | 5 | 143000 | 8 | 41 | 48.4
1527 | 20231031 | 91 | 9 | 8 | 19 | 31 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.2667 | 0.2147 | 130549 | 32771 | 25980 | 141863 | 4742 | 2049 | 0.855 | 1.079 | 20240930 | 20241031 | 31 | 8 | 2 | 1 | 1 | 0 | 1020 | 909 | 894 | -111 | 7 | 1 | 106 | 2 | 200000 | 0 | 177938 | 0 |  | 0 | 0 | 4 | 75 | 82.7
1528 | 20231130 | 91 | 9 | 8 | 19 | 31 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.3333 | 0.2943 | 130549 | 41195 | 37444 | 142734 | 2774 | 977 | 0.932 | 1.026 | 20240930 | 20241031 | 24 | 8 | 3 | 2 | 1 | 0 | 1092 | 990 | 996 | -102 | 6 | 1 | 94 | 2 | 200000 | 0 | 184143 | 0 |  | 1 | 2000 | 4 | 78 | 85.6
1529 | 20231231 | 91 | 9 | 8 | 19 | 31 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.4 | 0.3434 | 130549 | 49713 | 44855 | 143620 | 4882 | -24 | 0.902 | 0.999 | 20240930 | 20241031 | 34 | 8 | 3 | 2 | 1 | 0 | 1142 | 1048 | 994 | -94 | 8 | 1 | 119 | 2 | 200000 | 0 | 183426 | 0 |  | 1 | 1000 | 4 | 74 | 83.4
1530 | 20240131 | 91 | 9 | 8 | 19 | 31 | 3 | 2 | 3 | Active | Deliver | Green | 0.4667 | 0.4259 | 130549 | 58323 | 55340 | 144474 | 2722 | 261 | 0.953 | 1.005 | 20240930 | 20241031 | 24 | 8 | 4 | 2 | 1 | 0 | 1167 | 1108 | 1061 | -59 | 7 | 1 | 106 | 2 | 200000 | 0 | 184849 | 0 |  | 1 | 1000 | 3 | 78 | 86.8
1531 | 20240229 | 91 | 9 | 8 | 19 | 31 | 3 | 2 | 3 | Active | Deliver | Green | 0.5333 | 0.5019 | 130549 | 67027 | 67416 | 146150 | 1504 | -1893 | 0.978 | 0.972 | 20240930 | 20241031 | 19 | 8 | 4 | 3 | 0 | 0 | 1167 | 1176 | 1180 | 9 | 6 | 1 | 94 | 2 | 200000 | 0 | 181369 | 0 |  | 2 | 2000 | 6 | 72 | 87.4
1532 | 20240331 | 91 | 9 | 8 | 19 | 31 | 3 | 2 | 3 | Active | Deliver | Green | 0.6 | 0.5729 | 130549 | 75823 | 76510 | 146860 | 1031 | -1718 | 0.986 | 0.978 | 20240930 | 20241031 | 16 | 8 | 5 | 5 | 0 | 0 | 1142 | 1121 | 1066 | -21 | 6 | 1 | 94 | 2 | 200000 | 0 | 181141 | 0 |  | 2 | 3000 | 7 | 73 | 87.6
1533 | 20240430 | 91 | 9 | 8 | 19 | 31 | 3 | 2 | 3 | Active | Deliver | Green | 0.6667 | 0.6455 | 130549 | 84712 | 88008 | 148304 | 443 | -3739 | 0.995 | 0.958 | 20240930 | 20240930 | 13 | 8 | 5 | 4 | 0 | 0 | 1092 | 1007 | 1072 | -85 | 7 | 1 | 106 | 2 | 200000 | 0 | 176238 | 0 |  | 2 | 2000 | 5 | 77 | 85.2
1534 | 20240531 | 91 | 9 | 8 | 19 | 31 | 3 | 2 | 3 | Active | Deliver | Green | 0.7333 | 0.6937 | 130549 | 93694 | 96066 | 149602 | 3132 | -5504 | 0.967 | 0.943 | 20240930 | 20241031 | 24 | 8 | 6 | 5 | 1 | 0 | 1020 | 940 | 923 | -80 | 8 | 1 | 119 | 2 | 200000 | 9524 | 177979 | 0 | 0 | 2 | 2000 | 3 | 75 | 83.7
1535 | 20240630 | 91 | 9 | 8 | 19 | 31 | 3 | 2 | 3 | Active | Deploy | Green | 0.8 | 0.7512 | 130549 | 102768 | 104595 | 150617 | 4700 | -6527 | 0.954 | 0.938 | 20240930 | 20241031 | 30 | 8 | 6 | 4 | 1 | 0 | 929 | 872 | 839 | -57 | 6 | 1 | 94 | 2 | 200000 | 57143 | 178350 | 10455 | 0.183 | 2 | 3000 | 4 | 77 | 83.4
1536 | 20240731 | 91 | 9 | 8 | 19 | 31 | 3 | 2 | 3 | Active | Deploy | Green | 0.8667 | 0.8013 | 130549 | 111936 | 113239 | 151884 | 7327 | -8630 | 0.935 | 0.924 | 20240930 | 20241031 | 39 | 8 | 7 | 5 | 1 | 0 | 823 | 762 | 804 | -61 | 6 | 1 | 94 | 2 | 200000 | 104762 | 177893 | 49467 | 0.4722 | 2 | 4000 | 3 | 74 | 81.7
1537 | 20240831 | 91 | 9 | 8 | 19 | 31 | 3 | 2 | 3 | Active | Deploy | Green | 0.9333 | 0.8417 | 130549 | 121196 | 122551 | 153535 | 11313 | -12668 | 0.907 | 0.897 | 20240930 | 20241130 | 55 | 8 | 7 | 6 | 1 | 0 | 707 | 649 | 653 | -58 | 4 | 1 | 69 | 1 | 200000 | 152381 | 182476 | 87578 | 0.5747 | 2 | 4000 | 4 | 67 | 79.9
1538 | 20240930 | 91 | 9 | 8 | 19 | 31 | 3 | 2 | 3 | Active | Deploy | Green | 1 | 0.9059 | 130549 | 130549 | 133606 | 154734 | 12285 | -15342 | 0.906 | 0.885 | 20240930 | 20241130 | 57 | 8 | 8 | 6 | 2 | 1 | 585 | 565 | 560 | -20 | 4 | 1 | 69 | 1 | 200000 | 200000 | 181046 | 115720 | 0.5786 | 2 | 3000 | 4 | 72 | 80.3
1539 | 20241031 | 91 | 9 | 8 | 19 | 31 | 3 | 2 | 3 | Active | Deploy | Green | 1 | 0.9152 | 130549 | 130549 | 135390 | 155682 | 11071 | -15912 | 0.915 | 0.883 | 20240930 | 20241130 | 51 | 8 | 8 | 6 | 2 | 1 | 585 | 551 | 583 | -34 | 4 | 1 | 69 | 1 | 200000 | 200000 | 180024 | 150118 | 0.7506 | 2 | 2000 | 1 | 69 | 80
1540 | 20241130 | 91 | 9 | 8 | 19 | 31 | 3 | 2 | 3 | Active | Deploy | Green | 1 | 0.9218 | 130549 | 130549 | 139342 | 157094 | 10209 | -19002 | 0.922 | 0.864 | 20240930 | 20241130 | 47 | 8 | 8 | 6 | 1 | 0 | 585 | 576 | 570 | -9 | 5 | 0 | 63 | 1 | 200000 | 200000 | 181581 | 171834 | 0.8592 | 2 | 3000 | 2 | 73 | 88.8
1541 | 20241231 | 91 | 9 | 8 | 19 | 31 | 3 | 2 | 3 | Active | Deploy | Green | 1 | 0.9308 | 130549 | 130549 | 141876 | 158170 | 9034 | -20361 | 0.931 | 0.856 | 20240930 | 20241031 | 42 | 8 | 8 | 7 | 1 | 0 | 585 | 570 | 560 | -15 | 6 | 1 | 94 | 2 | 200000 | 200000 | 181268 | 158176 | 0.7909 | 3 | 4000 | 1 | 66 | 80.7
1542 | 20250131 | 91 | 9 | 8 | 19 | 31 | 3 | 2 | 3 | Active | Deploy | Green | 1 | 0.9308 | 130549 | 130549 | 144318 | 159457 | 9034 | -22803 | 0.931 | 0.842 | 20240930 | 20241031 | 42 | 8 | 8 | 6 | 1 | 0 | 585 | 523 | 546 | -62 | 5 | 1 | 81 | 1 | 200000 | 200000 | 177140 | 162273 | 0.8114 | 3 | 6000 | 4 | 65 | 77.8
1543 | 20250228 | 91 | 9 | 8 | 19 | 31 | 3 | 2 | 3 | Active | Deploy | Green | 1 | 0.9308 | 130549 | 130549 | 145960 | 160599 | 9034 | -24445 | 0.931 | 0.833 | 20240930 | 20241031 | 42 | 8 | 8 | 6 | 1 | 0 | 585 | 567 | 600 | -18 | 4 | 1 | 69 | 1 | 200000 | 200000 | 178212 | 157489 | 0.7874 | 3 | 6000 | 3 | 71 | 79.3
1544 | 20250331 | 91 | 9 | 8 | 19 | 31 | 3 | 2 | 3 | Active | Deploy | Green | 1 | 0.9308 | 130549 | 130549 | 145960 | 160817 | 9034 | -24445 | 0.931 | 0.833 | 20240930 | 20241031 | 42 | 8 | 8 | 6 | 1 | 0 | 585 | 541 | 546 | -44 | 6 | 1 | 94 | 2 | 200000 | 200000 | 175983 | 161745 | 0.8087 | 3 | 5000 | 1 | 65 | 78
1545 | 20250430 | 91 | 9 | 8 | 19 | 31 | 3 | 2 | 3 | Active | Deploy | Green | 1 | 0.9308 | 130549 | 130549 | 145960 | 160817 | 9034 | -24445 | 0.931 | 0.833 | 20240930 | 20241031 | 42 | 8 | 8 | 6 | 1 | 0 | 585 | 553 | 592 | -32 | 6 | 1 | 94 | 2 | 200000 | 200000 | 176062 | 161672 | 0.8084 | 3 | 4000 | 4 | 65 | 78.5
1546 | 20250531 | 91 | 9 | 8 | 19 | 31 | 3 | 2 | 3 | Active | Deploy | Green | 1 | 0.9308 | 130549 | 130549 | 147155 | 161011 | 9034 | -25640 | 0.931 | 0.826 | 20240930 | 20241031 | 42 | 8 | 8 | 6 | 1 | 0 | 585 | 569 | 571 | -16 | 4 | 0 | 51 | 1 | 200000 | 200000 | 184083 | 173335 | 0.8667 | 3 | 5000 | 1 | 76 | 88
1547 | 20250630 | 91 | 9 | 8 | 19 | 31 | 3 | 2 | 3 | Active | Deploy | Green | 1 | 0.9308 | 130549 | 130549 | 147155 | 161011 | 9034 | -25640 | 0.931 | 0.826 | 20240930 | 20241031 | 42 | 8 | 8 | 6 | 1 | 0 | 585 | 582 | 566 | -3 | 4 | 0 | 51 | 1 | 200000 | 200000 | 177443 | 166116 | 0.8306 | 3 | 6000 | 3 | 75 | 87.5
1548 | 20250731 | 91 | 9 | 8 | 19 | 31 | 3 | 2 | 3 | Active | Deploy | Green | 1 | 0.9308 | 130549 | 130549 | 147191 | 161017 | 9034 | -25676 | 0.931 | 0.826 | 20240930 | 20241031 | 42 | 8 | 8 | 7 | 1 | 0 | 585 | 522 | 525 | -63 | 4 | 1 | 69 | 1 | 200000 | 200000 | 176006 | 175081 | 0.8754 | 3 | 6000 | 1 | 71 | 77.1
1549 | 20250531 | 92 | 2 | 4 | 20 | 32 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.0667 | 0.0842 | 1339880 | 82656 | 110794 | 1348813 | -30162 | 2024 | 1.364 | 1.018 | 20260731 | 20260731 | 0 | 8 | 1 | 0 | 0 | 0 | 7255 | 7123 | 6802 | -132 | 0 | 0 | 0 | 0 | 3900000 | 0 | 3961220 | 0 |  | 0 | 0 | 5 | 96 | 100
1550 | 20250630 | 92 | 2 | 4 | 20 | 32 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.1333 | 0.1333 | 1339880 | 166264 | 169109 | 1349706 | -12342 | 9497 | 1.075 | 1.056 | 20260731 | 20260731 | 0 | 8 | 1 | 1 | 0 | 0 | 8449 | 8763 | 9189 | 314 | 3 | 0 | 29 | 1 | 3900000 | 0 | 3910029 | 0 |  | 0 | 0 | 4 | 88 | 100
1551 | 20250731 | 92 | 2 | 4 | 20 | 32 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.2 | 0.1909 | 1339880 | 250826 | 244970 | 1350599 | -4957 | 10813 | 1.02 | 1.044 | 20260731 | 20260731 | 4 | 8 | 2 | 1 | 0 | 0 | 9537 | 9287 | 9659 | -250 | 4 | 0 | 38 | 1 | 3900000 | 0 | 4013908 | 0 |  | 0 | 0 | 4 | 82 | 100
1552 | 20250831 | 92 | 2 | 4 | 20 | 32 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.2667 | 0.2564 | 1339880 | 336340 | 316882 | 1351492 | -7205 | 26663 | 1.021 | 1.084 | 20260731 | 20260731 | 6 | 8 | 2 | 2 | 0 | 0 | 10470 | 11187 | 11030 | 717 | 3 | 0 | 29 | 1 | 3900000 | 0 | 3932432 | 0 |  | 0 | 0 | 1 | 87 | 100
1553 | 20250930 | 92 | 2 | 4 | 20 | 32 | 4 | 2 | 4 | Active | Initiate & Design | Green | 0.3333 | 0.3247 | 1339880 | 422807 | 416986 | 1352386 | -12252 | 18073 | 1.029 | 1.043 | 20260731 | 20260731 | 4 | 8 | 3 | 2 | 0 | 0 | 11208 | 11234 | 10796 | 26 | 3 | 1 | 47 | 1 | 3900000 | 0 | 3974404 | 0 |  | 0 | 0 | 2 | 83 | 94.8
1554 | 20251031 | 92 | 2 | 4 | 20 | 32 | 4 | 2 | 4 | Active | Deliver | Green | 0.4 | 0.4079 | 1339880 | 510226 | 517091 | 1353279 | -36311 | 29446 | 1.071 | 1.057 | 20260731 | 20260731 | 0 | 8 | 3 | 2 | 0 | 0 | 11719 | 11273 | 11545 | -446 | 3 | 0 | 29 | 1 | 3900000 | 0 | 3918037 | 0 |  | 0 | 0 | 2 | 88 | 100
1555 | 20251130 | 92 | 2 | 4 | 20 | 32 | 4 | 2 | 4 | Active | Deliver | Green | 0.4667 | 0.4735 | 1339880 | 598599 | 607384 | 1354172 | -35834 | 27049 | 1.06 | 1.045 | 20260731 | 20260731 | 0 | 8 | 4 | 3 | 0 | 0 | 11980 | 12036 | 12010 | 56 | 3 | 0 | 29 | 1 | 3900000 | 0 | 3883198 | 0 |  | 1 | 19000 | 1 | 82 | 100
1556 | 20251231 | 92 | 2 | 4 | 20 | 32 | 4 | 2 | 4 | Active | Deliver | Green | 0.5333 | 0.5597 | 1339880 | 687924 | 720325 | 1355065 | -62007 | 29606 | 1.09 | 1.041 | 20260731 | 20260731 | 0 | 8 | 4 | 3 | 0 | 0 | 11980 | 12781 | 12158 | 801 | 3 | 0 | 29 | 1 | 3900000 | 0 | 3951639 | 0 |  | 1 | 11000 | 4 | 91 | 100
1557 | 20260131 | 92 | 2 | 4 | 20 | 32 | 4 | 2 | 4 | Active | Deliver | Green | 0.6 | 0.6388 | 1339880 | 778202 | 837961 | 1355959 | -77713 | 17954 | 1.1 | 1.021 | 20260731 | 20260731 | 0 | 8 | 5 | 5 | 0 | 0 | 11719 | 11867 | 11797 | 148 | 4 | 0 | 38 | 1 | 3900000 | 0 | 3994463 | 0 |  | 1 | 14000 | 2 | 87 | 100
1558 | 20260228 | 92 | 2 | 4 | 20 | 32 | 4 | 2 | 4 | Active | Deliver | Green | 0.6667 | 0.7023 | 1339880 | 869433 | 930060 | 1356852 | -71565 | 10938 | 1.082 | 1.012 | 20260731 | 20260731 | 0 | 8 | 5 | 5 | 0 | 0 | 11208 | 11626 | 11446 | 418 | 1 | 0 | 10 | 0 | 3900000 | 0 | 4018048 | 0 |  | 1 | 14000 | 5 | 86 | 100
1559 | 20260331 | 92 | 2 | 4 | 20 | 32 | 4 | 2 | 4 | Active | Deliver | Green | 0.7333 | 0.7411 | 1339880 | 961617 | 979524 | 1357745 | -31368 | 13461 | 1.033 | 1.014 | 20260731 | 20260731 | 0 | 8 | 6 | 6 | 0 | 0 | 10470 | 10996 | 11095 | 526 | 4 | 0 | 38 | 1 | 3900000 | 185714 | 4067888 | 0 | 0 | 1 | 21000 | 4 | 81 | 100
1560 | 20260430 | 92 | 2 | 4 | 20 | 32 | 4 | 2 | 4 | Active | Deploy | Green | 0.8 | 0.803 | 1339880 | 1054754 | 1078272 | 1359280 | -21170 | -2348 | 1.02 | 0.998 | 20260731 | 20260731 | 0 | 8 | 6 | 6 | 0 | 0 | 9537 | 9359 | 9615 | -178 | 3 | 0 | 29 | 1 | 3900000 | 1114286 | 3922540 | 254600 | 0.2285 | 1 | 19000 | 1 | 80 | 100
1561 | 20260531 | 92 | 2 | 4 | 20 | 32 | 4 | 2 | 4 | Active | Deploy | Green | 0.8667 | 0.8615 | 1339880 | 1148843 | 1161182 | 1361280 | -5464 | -6875 | 1.005 | 0.994 | 20260731 | 20260731 | 2 | 8 | 7 | 7 | 0 | 0 | 8449 | 8760 | 8306 | 311 | 1 | 0 | 10 | 0 | 3900000 | 2042857 | 3979444 | 1139665 | 0.5579 | 1 | 13000 | 2 | 83 | 100
1562 | 20260630 | 92 | 2 | 4 | 20 | 32 | 4 | 2 | 4 | Active | Deploy | Green | 0.9333 | 0.9303 | 1339880 | 1243885 | 1272528 | 1366448 | -2605 | -26038 | 1.002 | 0.98 | 20260731 | 20260731 | 1 | 8 | 7 | 7 | 0 | 0 | 7255 | 7682 | 7620 | 427 | 1 | 0 | 10 | 0 | 3900000 | 2971429 | 4047280 | 1997766 | 0.6723 | 1 | 17000 | 0 | 78 | 99.4
1563 | 20260731 | 92 | 2 | 4 | 20 | 32 | 4 | 2 | 4 | Completed | Completed | Green | 1 | 1 | 1339880 | 1339880 | 1386113 | 1386113 | 0 | -46233 | 1 | 0.967 | 20260731 | 20260731 | 0 | 8 | 8 | 7 | 0 | 0 | 6006 | 6432 | 6669 | 426 | 2 | 0 | 19 | 0 | 3900000 | 3900000 | 4021003 | 2695655 | 0.6912 | 1 | 20000 | 1 | 77 | 98.8
1564 | 20231031 | 93 | 6 | 4 | 21 | 33 | 5 | 2 | 5 | Active | Deliver | Green | 0.5556 | 0.6222 | 1318745 | 706587 | 796974 | 1364461 | -113936 | 23549 | 1.161 | 1.029 | 20240229 | 20240229 | 0 | 6 | 3 | 3 | 0 | 0 | 11733 | 12421 | 12885 | 688 | 1 | 0 | 9 | 0 | 1700000 | 0 | 1828486 | 0 |  | 0 | 0 | 3 | 87 | 100
1565 | 20231130 | 93 | 6 | 4 | 21 | 33 | 5 | 2 | 5 | Active | Deliver | Green | 0.6667 | 0.7412 | 1318745 | 855719 | 975544 | 1368857 | -121735 | 1910 | 1.142 | 1.002 | 20240229 | 20240229 | 0 | 6 | 4 | 4 | 0 | 0 | 11031 | 12349 | 11706 | 1318 | 1 | 0 | 9 | 0 | 1700000 | 0 | 1809449 | 0 |  | 1 | 15000 | 3 | 85 | 100
1566 | 20231231 | 93 | 6 | 4 | 21 | 33 | 5 | 2 | 5 | Active | Deploy | Green | 0.7778 | 0.8719 | 1318745 | 1007456 | 1166364 | 1377362 | -142358 | -16550 | 1.141 | 0.986 | 20240229 | 20240229 | 0 | 6 | 5 | 4 | 0 | 0 | 9712 | 10579 | 10730 | 867 | 3 | 0 | 27 | 0 | 1700000 | 350794 | 1872772 | 0 | 0 | 1 | 19000 | 3 | 89 | 100
1567 | 20240131 | 93 | 6 | 4 | 21 | 33 | 5 | 2 | 5 | Active | Deploy | Green | 0.8889 | 0.9855 | 1318745 | 1161798 | 1339795 | 1386340 | -137825 | -40172 | 1.119 | 0.97 | 20240229 | 20240229 | 0 | 6 | 5 | 4 | 0 | 0 | 7934 | 8254 | 7958 | 320 | 0 | 0 | 0 | 0 | 1700000 | 1025397 | 1824603 | 658526 | 0.6422 | 1 | 20000 | 2 | 90 | 100
1568 | 20240229 | 93 | 6 | 4 | 21 | 33 | 5 | 2 | 5 | Completed | Completed | Green | 1 | 1 | 1318745 | 1318745 | 1377701 | 1394460 | 0 | -58956 | 1 | 0.957 | 20240229 | 20240229 | 0 | 6 | 6 | 6 | 0 | 0 | 5912 | 6526 | 6297 | 614 | 0 | 0 | 0 | 0 | 1700000 | 1700000 | 1806161 | 1224137 | 0.7201 | 1 | 19000 | 0 | 80 | 98.5
1569 | 20231031 | 94 | 5 | 5 | 22 | 34 | 6 | 1 | 6 | Active | Initiate & Design | Amber | 0.0952 | 0.0223 | 905616 | 80006 | 18634 | 937097 | 59811 | 1561 | 0.252 | 1.083 | 20250531 | 20250731 | 59 | 11 | 1 | 0 | 1 | 0 | 5256 | 4088 | 4120 | -1168 | 9 | 1 | 125 | 2 | 2300000 | 0 | 2108880 | 0 |  | 0 | 0 | 5 | 46 | 54
1570 | 20231130 | 94 | 5 | 5 | 22 | 34 | 6 | 1 | 6 | Active | Initiate & Design | Amber | 0.1429 | 0.0584 | 905616 | 120502 | 53787 | 942466 | 67614 | -899 | 0.439 | 0.984 | 20250531 | 20250731 | 68 | 11 | 2 | 0 | 1 | 0 | 5821 | 4825 | 4890 | -996 | 9 | 1 | 125 | 2 | 2300000 | 0 | 2213152 | 0 |  | 1 | 8000 | 5 | 48 | 61.4
1571 | 20231231 | 94 | 5 | 5 | 22 | 34 | 6 | 1 | 6 | Active | Initiate & Design | Amber | 0.1905 | 0.1062 | 905616 | 161327 | 89359 | 941409 | 65151 | 6817 | 0.596 | 1.076 | 20250531 | 20250731 | 68 | 11 | 2 | 1 | 1 | 0 | 6347 | 4889 | 5145 | -1458 | 9 | 1 | 125 | 2 | 2300000 | 0 | 2148872 | 0 |  | 1 | 11000 | 5 | 61 | 69.6
1572 | 20240131 | 94 | 5 | 5 | 22 | 34 | 6 | 1 | 6 | Active | Initiate & Design | Green | 0.2381 | 0.1613 | 905616 | 202480 | 134186 | 943566 | 56404 | 11890 | 0.721 | 1.088 | 20250531 | 20250731 | 62 | 11 | 3 | 2 | 1 | 0 | 6821 | 5678 | 5950 | -1143 | 7 | 1 | 101 | 2 | 2300000 | 0 | 2182531 | 0 |  | 1 | 8000 | 4 | 71 | 77.4
1573 | 20240229 | 94 | 5 | 5 | 22 | 34 | 6 | 1 | 6 | Active | Initiate & Design | Green | 0.2857 | 0.2141 | 905616 | 243962 | 185853 | 945722 | 50070 | 8039 | 0.795 | 1.043 | 20250531 | 20250731 | 58 | 11 | 3 | 2 | 1 | 0 | 7234 | 5812 | 5928 | -1422 | 5 | 0 | 59 | 1 | 2300000 | 0 | 2151063 | 0 |  | 1 | 12000 | 6 | 78 | 86.1
1574 | 20240331 | 94 | 5 | 5 | 22 | 34 | 6 | 1 | 6 | Active | Initiate & Design | Green | 0.3333 | 0.2579 | 905616 | 285772 | 226654 | 947878 | 52214 | 6904 | 0.817 | 1.031 | 20250531 | 20250731 | 61 | 11 | 4 | 2 | 1 | 0 | 7575 | 6198 | 5931 | -1377 | 6 | 1 | 89 | 2 | 2300000 | 0 | 2197280 | 0 |  | 1 | 8000 | 6 | 73 | 79.6
1575 | 20240430 | 94 | 5 | 5 | 22 | 34 | 6 | 1 | 6 | Active | Initiate & Design | Green | 0.381 | 0.2989 | 905616 | 327911 | 266630 | 950034 | 57222 | 4059 | 0.825 | 1.015 | 20250531 | 20250731 | 67 | 11 | 4 | 2 | 1 | 0 | 7839 | 5654 | 6043 | -2185 | 7 | 1 | 101 | 2 | 2300000 | 0 | 2153416 | 0 |  | 1 | 8000 | 6 | 66 | 76.8
1576 | 20240531 | 94 | 5 | 5 | 22 | 34 | 6 | 1 | 6 | Active | Initiate & Design | Green | 0.4286 | 0.342 | 905616 | 370378 | 298030 | 952191 | 60657 | 11691 | 0.836 | 1.039 | 20250531 | 20250731 | 71 | 11 | 5 | 2 | 2 | 1 | 8018 | 5979 | 6325 | -2039 | 7 | 1 | 101 | 2 | 2300000 | 0 | 2121234 | 0 |  | 1 | 12000 | 6 | 74 | 78.2
1577 | 20240630 | 94 | 5 | 5 | 22 | 34 | 6 | 1 | 6 | Active | Deliver | Green | 0.4762 | 0.3713 | 905616 | 413174 | 331006 | 954347 | 76919 | 5249 | 0.814 | 1.016 | 20250531 | 20250831 | 85 | 11 | 5 | 2 | 2 | 1 | 8108 | 6433 | 6275 | -1675 | 7 | 1 | 101 | 2 | 2300000 | 0 | 2203587 | 0 |  | 1 | 14000 | 3 | 71 | 78.5
1578 | 20240731 | 94 | 5 | 5 | 22 | 34 | 6 | 1 | 6 | Active | Deliver | Green | 0.5238 | 0.4105 | 905616 | 456299 | 362707 | 956503 | 84544 | 9048 | 0.815 | 1.025 | 20250531 | 20250831 | 91 | 11 | 6 | 4 | 2 | 1 | 8108 | 5951 | 6192 | -2157 | 6 | 0 | 71 | 2 | 2300000 | 0 | 2106889 | 0 |  | 1 | 9000 | 4 | 71 | 84.3
1579 | 20240831 | 94 | 5 | 5 | 22 | 34 | 6 | 1 | 6 | Active | Deliver | Green | 0.5714 | 0.4388 | 905616 | 499752 | 396600 | 958659 | 102368 | 784 | 0.795 | 1.002 | 20250531 | 20250930 | 108 | 11 | 6 | 3 | 2 | 1 | 8018 | 5878 | 5832 | -2140 | 5 | 1 | 77 | 1 | 2300000 | 0 | 2168798 | 0 |  | 1 | 11000 | 4 | 65 | 75.4
1580 | 20240930 | 94 | 5 | 5 | 22 | 34 | 6 | 1 | 6 | Active | Deliver | Green | 0.619 | 0.4858 | 905616 | 543534 | 435196 | 960815 | 103586 | 4752 | 0.809 | 1.011 | 20250531 | 20250930 | 108 | 11 | 7 | 5 | 2 | 1 | 7839 | 6171 | 5869 | -1668 | 5 | 1 | 77 | 1 | 2300000 | 0 | 2200184 | 0 |  | 1 | 11000 | 3 | 65 | 77.9
1581 | 20241031 | 94 | 5 | 5 | 22 | 34 | 6 | 1 | 6 | Active | Deliver | Green | 0.6667 | 0.55 | 905616 | 587644 | 501117 | 964169 | 89555 | -3028 | 0.848 | 0.994 | 20250531 | 20250831 | 94 | 11 | 7 | 4 | 2 | 1 | 7575 | 6200 | 5985 | -1375 | 8 | 1 | 113 | 2 | 2300000 | 0 | 2138259 | 0 |  | 1 | 10000 | 3 | 66 | 79
1582 | 20241130 | 94 | 5 | 5 | 22 | 34 | 6 | 1 | 6 | Active | Deliver | Green | 0.7143 | 0.6123 | 905616 | 632083 | 572205 | 971278 | 77574 | -17696 | 0.877 | 0.969 | 20250531 | 20250831 | 82 | 11 | 8 | 6 | 2 | 1 | 7234 | 5419 | 5472 | -1815 | 7 | 0 | 83 | 2 | 2300000 | 0 | 2217878 | 0 |  | 1 | 13000 | 3 | 72 | 86.9
1583 | 20241231 | 94 | 5 | 5 | 22 | 34 | 6 | 1 | 6 | Active | Deliver | Green | 0.7619 | 0.654 | 905616 | 676850 | 607873 | 972409 | 84577 | -15600 | 0.875 | 0.974 | 20250531 | 20250831 | 88 | 11 | 8 | 5 | 2 | 1 | 6821 | 5725 | 5965 | -1096 | 8 | 1 | 113 | 2 | 2300000 | 344218 | 2182123 | 0 | 0 | 1 | 8000 | 6 | 70 | 80.5
1584 | 20250131 | 94 | 5 | 5 | 22 | 34 | 6 | 1 | 6 | Active | Deliver | Green | 0.8095 | 0.6843 | 905616 | 721946 | 646880 | 977814 | 102233 | -27167 | 0.858 | 0.958 | 20250531 | 20250831 | 102 | 11 | 9 | 6 | 2 | 1 | 6347 | 4991 | 4770 | -1356 | 5 | 1 | 77 | 1 | 2300000 | 735374 | 2112423 | 202309 | 0.2751 | 1 | 12000 | 1 | 66 | 77.2
1585 | 20250228 | 94 | 5 | 5 | 22 | 34 | 6 | 1 | 6 | Active | Deliver | Green | 0.8571 | 0.7347 | 905616 | 767371 | 696772 | 980573 | 102015 | -31416 | 0.867 | 0.955 | 20250531 | 20250831 | 99 | 11 | 9 | 7 | 2 | 1 | 5821 | 4597 | 4883 | -1224 | 6 | 1 | 89 | 2 | 2300000 | 1126531 | 2216638 | 518107 | 0.4599 | 1 | 9000 | 3 | 68 | 78.8
1586 | 20250331 | 94 | 5 | 5 | 22 | 34 | 6 | 1 | 6 | Active | Deploy | Green | 0.9048 | 0.7566 | 905616 | 813124 | 722962 | 984158 | 127935 | -37773 | 0.843 | 0.948 | 20250531 | 20250930 | 120 | 11 | 10 | 6 | 3 | 1 | 5256 | 4215 | 4266 | -1041 | 5 | 1 | 77 | 1 | 2300000 | 1517687 | 2142255 | 779257 | 0.5135 | 1 | 12000 | 2 | 72 | 76.8
1587 | 20250430 | 94 | 5 | 5 | 22 | 34 | 6 | 1 | 6 | Active | Deploy | Green | 0.9524 | 0.811 | 905616 | 859206 | 779214 | 987343 | 124751 | -44759 | 0.855 | 0.943 | 20250531 | 20250930 | 115 | 11 | 10 | 7 | 3 | 1 | 4665 | 3734 | 3785 | -931 | 3 | 1 | 54 | 1 | 2300000 | 1908844 | 2196052 | 1236509 | 0.6478 | 2 | 19000 | 4 | 66 | 77.8
1588 | 20250531 | 94 | 5 | 5 | 22 | 34 | 6 | 1 | 6 | Active | Deploy | Green | 1 | 0.8467 | 905616 | 905616 | 814469 | 989739 | 138831 | -47684 | 0.847 | 0.941 | 20250531 | 20250930 | 125 | 11 | 11 | 7 | 3 | 1 | 4060 | 2950 | 2956 | -1110 | 4 | 0 | 47 | 1 | 2300000 | 2300000 | 2142658 | 1523032 | 0.6622 | 2 | 19000 | 1 | 76 | 83.1
1589 | 20250630 | 94 | 5 | 5 | 22 | 34 | 6 | 1 | 6 | Active | Deploy | Green | 1 | 0.8665 | 905616 | 905616 | 848933 | 995285 | 120900 | -64217 | 0.867 | 0.924 | 20250531 | 20250930 | 108 | 11 | 11 | 8 | 3 | 1 | 4060 | 3379 | 3219 | -681 | 5 | 0 | 59 | 1 | 2300000 | 2300000 | 2115269 | 1768049 | 0.7687 | 2 | 17000 | 3 | 72 | 85.4
1590 | 20250731 | 94 | 5 | 5 | 22 | 34 | 6 | 1 | 6 | Active | Deploy | Green | 1 | 0.8674 | 905616 | 905616 | 851903 | 997898 | 120085 | -66372 | 0.867 | 0.922 | 20250531 | 20250930 | 108 | 11 | 11 | 8 | 3 | 1 | 4060 | 3258 | 3205 | -802 | 4 | 0 | 47 | 1 | 2300000 | 2300000 | 2207132 | 2164550 | 0.9411 | 2 | 28000 | 1 | 73 | 85.8
1591 | 20250831 | 94 | 5 | 5 | 22 | 34 | 6 | 1 | 6 | Active | Deploy | Green | 1 | 0.874 | 905616 | 905616 | 873411 | 1003221 | 114108 | -81903 | 0.874 | 0.906 | 20250531 | 20250831 | 102 | 11 | 11 | 7 | 3 | 1 | 4060 | 3167 | 3238 | -893 | 4 | 0 | 47 | 1 | 2300000 | 2300000 | 2152754 | 2010015 | 0.8739 | 2 | 25000 | 3 | 71 | 84.4
1592 | 20250930 | 94 | 5 | 5 | 22 | 34 | 6 | 1 | 6 | Active | Deploy | Green | 1 | 0.9006 | 905616 | 905616 | 896628 | 1004695 | 90018 | -81030 | 0.901 | 0.91 | 20250531 | 20250831 | 81 | 11 | 11 | 8 | 2 | 1 | 4060 | 3346 | 3370 | -714 | 5 | 0 | 59 | 1 | 2300000 | 2300000 | 2137605 | 1894135 | 0.8235 | 2 | 22000 | 1 | 74 | 86.5
1593 | 20251031 | 94 | 5 | 5 | 22 | 34 | 6 | 1 | 6 | Active | Deploy | Green | 1 | 0.9006 | 905616 | 905616 | 903461 | 1008222 | 90018 | -87863 | 0.901 | 0.903 | 20250531 | 20250831 | 81 | 11 | 11 | 9 | 2 | 1 | 4060 | 2943 | 3080 | -1117 | 6 | 1 | 89 | 2 | 2300000 | 2300000 | 2153094 | 2111744 | 0.9181 | 2 | 23000 | 3 | 72 | 76.3
1594 | 20251130 | 94 | 5 | 5 | 22 | 34 | 6 | 1 | 6 | Active | Deploy | Green | 1 | 0.9006 | 905616 | 905616 | 917788 | 1013186 | 90018 | -102190 | 0.901 | 0.889 | 20250531 | 20250831 | 81 | 11 | 11 | 8 | 2 | 1 | 4060 | 3090 | 3300 | -970 | 4 | 1 | 65 | 1 | 2300000 | 2300000 | 2137178 | 2052551 | 0.8924 | 2 | 27000 | 4 | 65 | 76.4
1595 | 20251231 | 94 | 5 | 5 | 22 | 34 | 6 | 1 | 6 | Active | Deploy | Green | 1 | 0.9006 | 905616 | 905616 | 917788 | 1015342 | 90018 | -102190 | 0.901 | 0.889 | 20250531 | 20250831 | 81 | 11 | 11 | 8 | 2 | 1 | 4060 | 3324 | 3229 | -736 | 5 | 0 | 59 | 1 | 2300000 | 2300000 | 2127498 | 1871609 | 0.8137 | 2 | 21000 | 1 | 76 | 85.5
1596 | 20260131 | 94 | 5 | 5 | 22 | 34 | 6 | 1 | 6 | Active | Deploy | Green | 1 | 0.9006 | 905616 | 905616 | 919416 | 1016411 | 90018 | -103818 | 0.901 | 0.887 | 20250531 | 20250831 | 81 | 11 | 11 | 8 | 2 | 1 | 4060 | 3151 | 2977 | -909 | 4 | 1 | 65 | 1 | 2300000 | 2300000 | 2197396 | 2191279 | 0.9527 | 2 | 25000 | 1 | 73 | 77.4
1597 | 20260228 | 94 | 5 | 5 | 22 | 34 | 6 | 1 | 6 | Active | Deploy | Green | 1 | 0.9006 | 905616 | 905616 | 926833 | 1017825 | 90018 | -111235 | 0.901 | 0.88 | 20250531 | 20250831 | 81 | 11 | 11 | 9 | 2 | 1 | 4060 | 3066 | 2975 | -994 | 3 | 0 | 36 | 1 | 2300000 | 2300000 | 2115656 | 2001889 | 0.8704 | 2 | 21000 | 1 | 77 | 83.7
1598 | 20260331 | 94 | 5 | 5 | 22 | 34 | 6 | 1 | 6 | Active | Deploy | Green | 1 | 0.9006 | 905616 | 905616 | 926833 | 1017825 | 90018 | -111235 | 0.901 | 0.88 | 20250531 | 20250831 | 81 | 11 | 11 | 9 | 2 | 1 | 4060 | 3041 | 3169 | -1019 | 6 | 0 | 71 | 2 | 2300000 | 2300000 | 2116688 | 1902167 | 0.827 | 2 | 18000 | 4 | 74 | 83.6
1599 | 20241130 | 95 | 10 | 7 | 23 | 35 | 7 | 3 | 7 | Active | Initiate & Design | Amber | 0.0667 | 0.0182 | 238114 | 14689 | 5723 | 261930 | 10355 | -1389 | 0.295 | 0.757 | 20260131 | 20260228 | 29 | 8 | 1 | 0 | 1 | 0 | 1289 | 1221 | 1273 | -68 | 8 | 1 | 115 | 2 | 600000 | 0 | 577662 | 0 |  | 1 | 3000 | 5 | 33 | 49.6
1600 | 20241231 | 95 | 10 | 7 | 23 | 35 | 7 | 3 | 7 | Active | Initiate & Design | Green | 0.1333 | 0.083 | 238114 | 29547 | 16650 | 250337 | 9784 | 3113 | 0.669 | 1.187 | 20260131 | 20260228 | 30 | 8 | 1 | 0 | 1 | 0 | 1502 | 1324 | 1295 | -178 | 8 | 1 | 115 | 2 | 600000 | 0 | 567289 | 0 |  | 1 | 3000 | 5 | 71 | 79.5
1601 | 20250131 | 95 | 10 | 7 | 23 | 35 | 7 | 3 | 7 | Active | Initiate & Design | Green | 0.2 | 0.1435 | 238114 | 44575 | 31432 | 251448 | 10406 | 2737 | 0.766 | 1.087 | 20260131 | 20260228 | 33 | 8 | 2 | 1 | 1 | 0 | 1695 | 1477 | 1479 | -218 | 6 | 1 | 91 | 2 | 600000 | 0 | 581859 | 0 |  | 1 | 3000 | 6 | 67 | 80.8
1602 | 20250228 | 95 | 10 | 7 | 23 | 35 | 7 | 3 | 7 | Active | Initiate & Design | Green | 0.2667 | 0.2268 | 238114 | 59772 | 49501 | 252560 | 5768 | 4503 | 0.903 | 1.091 | 20260131 | 20260228 | 24 | 8 | 2 | 1 | 0 | 0 | 1861 | 1663 | 1759 | -198 | 6 | 1 | 91 | 2 | 600000 | 0 | 569269 | 0 |  | 1 | 2000 | 4 | 78 | 87.1
1603 | 20250331 | 95 | 10 | 7 | 23 | 35 | 7 | 3 | 7 | Active | Initiate & Design | Green | 0.3333 | 0.285 | 238114 | 75138 | 65084 | 253671 | 7276 | 2778 | 0.903 | 1.043 | 20260131 | 20260228 | 29 | 8 | 3 | 1 | 1 | 0 | 1992 | 1835 | 1804 | -157 | 6 | 1 | 91 | 2 | 600000 | 0 | 561746 | 0 |  | 1 | 3000 | 3 | 77 | 85.6
1604 | 20250430 | 95 | 10 | 7 | 23 | 35 | 7 | 3 | 7 | Active | Initiate & Design | Green | 0.4 | 0.3499 | 238114 | 90674 | 80588 | 254782 | 7358 | 2728 | 0.919 | 1.034 | 20260131 | 20260228 | 30 | 8 | 3 | 1 | 1 | 0 | 2083 | 1910 | 1988 | -173 | 5 | 0 | 61 | 1 | 600000 | 0 | 568488 | 0 |  | 1 | 3000 | 5 | 79 | 94.2
1605 | 20250531 | 95 | 10 | 7 | 23 | 35 | 7 | 3 | 7 | Active | Deliver | Green | 0.4667 | 0.418 | 238114 | 106379 | 97482 | 255893 | 6847 | 2050 | 0.936 | 1.021 | 20260131 | 20260228 | 29 | 8 | 4 | 3 | 1 | 0 | 2129 | 1908 | 1889 | -221 | 7 | 1 | 103 | 2 | 600000 | 0 | 563369 | 0 |  | 1 | 4000 | 5 | 78 | 85.9
1606 | 20250630 | 95 | 10 | 7 | 23 | 35 | 7 | 3 | 7 | Active | Deliver | Green | 0.5333 | 0.4531 | 238114 | 122253 | 108704 | 257395 | 14364 | -815 | 0.883 | 0.993 | 20260131 | 20260331 | 47 | 8 | 4 | 2 | 1 | 0 | 2129 | 1918 | 1827 | -211 | 7 | 1 | 103 | 2 | 600000 | 0 | 563044 | 0 |  | 1 | 3000 | 5 | 72 | 82.5
1607 | 20250731 | 95 | 10 | 7 | 23 | 35 | 7 | 3 | 7 | Active | Deliver | Green | 0.6 | 0.5042 | 238114 | 138297 | 122997 | 259363 | 18240 | -2940 | 0.868 | 0.976 | 20260131 | 20260331 | 56 | 8 | 5 | 3 | 1 | 0 | 2083 | 1892 | 2012 | -191 | 7 | 1 | 103 | 2 | 600000 | 0 | 574639 | 0 |  | 1 | 2000 | 6 | 73 | 82
1608 | 20250831 | 95 | 10 | 7 | 23 | 35 | 7 | 3 | 7 | Active | Deliver | Green | 0.6667 | 0.5685 | 238114 | 154510 | 138803 | 260523 | 19142 | -3435 | 0.876 | 0.975 | 20260131 | 20260228 | 23 | 8 | 5 | 4 | 1 | 0 | 1992 | 1770 | 1747 | -222 | 6 | 0 | 73 | 2 | 600000 | 0 | 579764 | 0 |  | 1 | 3000 | 6 | 73 | 90.2
1609 | 20250930 | 95 | 10 | 7 | 23 | 35 | 7 | 3 | 7 | Active | Deliver | Green | 0.7333 | 0.6522 | 238114 | 170892 | 161071 | 262217 | 15594 | -5773 | 0.909 | 0.964 | 20260131 | 20260131 | 14 | 8 | 6 | 4 | 1 | 0 | 1861 | 1762 | 1688 | -99 | 7 | 1 | 103 | 2 | 600000 | 28571 | 581847 | 0 | 0 | 1 | 4000 | 5 | 70 | 84.6
1610 | 20251031 | 95 | 10 | 7 | 23 | 35 | 7 | 3 | 7 | Active | Deliver | Green | 0.8 | 0.7356 | 238114 | 187443 | 183019 | 263698 | 12286 | -7862 | 0.934 | 0.957 | 20260131 | 20260131 | 3 | 8 | 6 | 5 | 1 | 0 | 1695 | 1636 | 1684 | -59 | 5 | 1 | 79 | 1 | 600000 | 171429 | 584157 | 35613 | 0.2077 | 1 | 4000 | 3 | 76 | 86
1611 | 20251130 | 95 | 10 | 7 | 23 | 35 | 7 | 3 | 7 | Active | Deploy | Green | 0.8667 | 0.82 | 238114 | 204164 | 208485 | 265884 | 8911 | -13232 | 0.956 | 0.937 | 20260131 | 20260131 | -7 | 8 | 7 | 6 | 1 | 0 | 1502 | 1409 | 1405 | -93 | 5 | 1 | 79 | 1 | 600000 | 314286 | 571254 | 151939 | 0.4834 | 1 | 2000 | 4 | 74 | 85.1
1612 | 20251231 | 95 | 10 | 7 | 23 | 35 | 7 | 3 | 7 | Active | Deploy | Green | 0.9333 | 0.9073 | 238114 | 221054 | 233811 | 267651 | 5013 | -17770 | 0.977 | 0.924 | 20260131 | 20260131 | -19 | 8 | 7 | 5 | 1 | 0 | 1289 | 1134 | 1164 | -155 | 6 | 0 | 73 | 2 | 600000 | 457143 | 561253 | 249834 | 0.5465 | 2 | 5000 | 2 | 81 | 91.9
1613 | 20260131 | 95 | 10 | 7 | 23 | 35 | 7 | 3 | 7 | Active | Deploy | Green | 1 | 0.9994 | 238114 | 238114 | 260396 | 269296 | 143 | -22425 | 0.999 | 0.914 | 20260131 | 20260131 | -35 | 8 | 8 | 6 | 1 | 0 | 1067 | 946 | 923 | -121 | 5 | 1 | 79 | 1 | 600000 | 600000 | 569773 | 383336 | 0.6389 | 2 | 5000 | 2 | 78 | 85.1
1614 | 20260228 | 95 | 10 | 7 | 23 | 35 | 7 | 3 | 7 | Active | Deploy | Green | 1 | 0.9994 | 238114 | 238114 | 261409 | 270593 | 143 | -23438 | 0.999 | 0.91 | 20260131 | 20260131 | -35 | 8 | 8 | 6 | 1 | 0 | 1067 | 1003 | 974 | -64 | 4 | 1 | 67 | 1 | 600000 | 600000 | 564007 | 534541 | 0.8909 | 2 | 4000 | 2 | 73 | 85.8
1615 | 20260331 | 95 | 10 | 7 | 23 | 35 | 7 | 3 | 7 | Active | Deploy | Green | 1 | 0.9996 | 238114 | 238114 | 265423 | 272414 | 95 | -27404 | 1 | 0.897 | 20260131 | 20260131 | -35 | 8 | 8 | 7 | 1 | 0 | 1067 | 924 | 970 | -143 | 3 | 0 | 36 | 1 | 600000 | 600000 | 588393 | 527992 | 0.88 | 2 | 7000 | 2 | 75 | 92.9
1616 | 20260430 | 95 | 10 | 7 | 23 | 35 | 7 | 3 | 7 | Completed | Completed | Green | 1 | 1 | 238114 | 238114 | 267814 | 273926 | 0 | -29700 | 1 | 0.889 | 20260131 | 20260131 | -35 | 8 | 8 | 7 | 0 | 0 | 1067 | 1006 | 1025 | -61 | 3 | 0 | 36 | 1 | 600000 | 600000 | 587068 | 540386 | 0.9006 | 2 | 7000 | 1 | 75 | 94.3
1617 | 20240831 | 96 | 6 | 4 | 24 | 36 | 8 | 1 | 8 | Active | Initiate & Design | Green | 0.1111 | 0.1065 | 919708 | 94923 | 93940 | 939328 | -3026 | 4009 | 1.031 | 1.042 | 20250430 | 20250430 | 1 | 6 | 1 | 0 | 0 | 0 | 5533 | 5425 | 5767 | -108 | 3 | 0 | 31 | 1 | 2400000 | 0 | 1771025 | 0 |  | 0 | 0 | 2 | 76 | 95.1
1618 | 20240930 | 96 | 6 | 4 | 24 | 36 | 8 | 1 | 8 | Active | Initiate & Design | Green | 0.2222 | 0.2127 | 919708 | 191663 | 188930 | 942394 | -3959 | 6692 | 1.02 | 1.035 | 20250430 | 20250430 | 4 | 6 | 1 | 0 | 0 | 0 | 6773 | 6653 | 6764 | -120 | 5 | 0 | 51 | 1 | 2400000 | 0 | 1829734 | 0 |  | 0 | 0 | 2 | 76 | 95.1
1619 | 20241031 | 96 | 6 | 4 | 24 | 36 | 8 | 1 | 8 | Active | Initiate & Design | Green | 0.3333 | 0.3491 | 919708 | 290219 | 304686 | 945460 | -30851 | 16384 | 1.106 | 1.054 | 20250430 | 20250430 | 0 | 6 | 2 | 1 | 0 | 0 | 7693 | 7715 | 8119 | 22 | 3 | 0 | 31 | 1 | 2400000 | 0 | 1832084 | 0 |  | 0 | 0 | 2 | 83 | 100
1620 | 20241130 | 96 | 6 | 4 | 24 | 36 | 8 | 1 | 8 | Active | Deliver | Green | 0.4444 | 0.4574 | 919708 | 390592 | 403929 | 948526 | -30082 | 16745 | 1.077 | 1.042 | 20250430 | 20250430 | 0 | 6 | 3 | 3 | 0 | 0 | 8183 | 7866 | 8078 | -317 | 3 | 0 | 31 | 1 | 2400000 | 0 | 1813404 | 0 |  | 0 | 0 | 2 | 80 | 97.2
1621 | 20241231 | 96 | 6 | 4 | 24 | 36 | 8 | 1 | 8 | Active | Deliver | Green | 0.5556 | 0.5772 | 919708 | 492782 | 516121 | 951591 | -38073 | 14734 | 1.077 | 1.028 | 20250430 | 20250430 | 0 | 6 | 3 | 3 | 0 | 0 | 8183 | 8686 | 8634 | 503 | 4 | 0 | 41 | 1 | 2400000 | 0 | 1742943 | 0 |  | 0 | 0 | 5 | 78 | 96.8
1622 | 20250131 | 96 | 6 | 4 | 24 | 36 | 8 | 1 | 8 | Active | Deliver | Green | 0.6667 | 0.6894 | 919708 | 596788 | 632467 | 954657 | -37259 | 1580 | 1.062 | 1.003 | 20250430 | 20250430 | 0 | 6 | 4 | 4 | 0 | 0 | 7693 | 8127 | 7965 | 434 | 4 | 0 | 41 | 1 | 2400000 | 0 | 1828016 | 0 |  | 1 | 9000 | 5 | 79 | 96.2
1623 | 20250228 | 96 | 6 | 4 | 24 | 36 | 8 | 1 | 8 | Active | Deploy | Green | 0.7778 | 0.7929 | 919708 | 702611 | 735113 | 959346 | -26625 | -5877 | 1.038 | 0.992 | 20250430 | 20250430 | 0 | 6 | 5 | 5 | 0 | 0 | 6773 | 7119 | 6813 | 346 | 2 | 0 | 20 | 0 | 2400000 | 495238 | 1759151 | 0 | 0 | 1 | 10000 | 5 | 72 | 93.9
1624 | 20250331 | 96 | 6 | 4 | 24 | 36 | 8 | 1 | 8 | Active | Deploy | Green | 0.8889 | 0.8815 | 919708 | 810251 | 840054 | 967850 | -472 | -29331 | 1.001 | 0.965 | 20250430 | 20250430 | 2 | 6 | 5 | 5 | 0 | 0 | 5533 | 5651 | 5465 | 118 | 1 | 0 | 10 | 0 | 2400000 | 1447619 | 1834391 | 610853 | 0.422 | 1 | 14000 | 0 | 70 | 92.2
1625 | 20250430 | 96 | 6 | 4 | 24 | 36 | 8 | 1 | 8 | Completed | Completed | Green | 1 | 1 | 919708 | 919708 | 961563 | 972661 | 0 | -41855 | 1 | 0.956 | 20250430 | 20250430 | 0 | 6 | 6 | 5 | 0 | 0 | 4123 | 4365 | 4649 | 242 | 2 | 0 | 20 | 0 | 2400000 | 2400000 | 1769625 | 1294110 | 0.5392 | 1 | 14000 | 1 | 69 | 91.1
1626 | 20231031 | 97 | 10 | 7 | 1 | 25 | 1 | 2 | 1 | Active | Initiate & Design | Amber | 0.1667 | 0.0768 | 999025 | 155404 | 73763 | 1152209 | 78679 | 2962 | 0.493 | 1.04 | 20250131 | 20250331 | 72 | 9 | 2 | 0 | 1 | 1 | 6718 | 5706 | 5835 | -1012 | 10 | 2 | 178 | 3 | 2300000 | 0 | 1600810 | 0 |  | 0 | 0 | 4 | 40 | 50.8
1627 | 20231130 | 97 | 10 | 7 | 1 | 25 | 1 | 2 | 1 | Active | Initiate & Design | Amber | 0.2222 | 0.1196 | 999025 | 208192 | 121248 | 1166568 | 88709 | -1765 | 0.574 | 0.985 | 20250131 | 20250430 | 81 | 9 | 2 | 1 | 1 | 1 | 7357 | 5778 | 6096 | -1579 | 11 | 2 | 193 | 4 | 2300000 | 0 | 1581775 | 0 |  | 1 | 16000 | 7 | 41 | 50.8
1628 | 20231231 | 97 | 10 | 7 | 1 | 25 | 1 | 2 | 1 | Active | Initiate & Design | Red | 0.2778 | 0.1458 | 999025 | 261473 | 142241 | 1174409 | 115815 | 3417 | 0.557 | 1.024 | 20250131 | 20250430 | 104 | 9 | 3 | 1 | 2 | 1 | 7909 | 6688 | 7042 | -1221 | 12 | 3 | 225 | 4 | 2300000 | 0 | 1597316 | 0 |  | 1 | 13000 | 7 | 38 | 45
1629 | 20240131 | 97 | 10 | 7 | 1 | 25 | 1 | 2 | 1 | Active | Initiate & Design | Amber | 0.3333 | 0.1881 | 999025 | 315248 | 181087 | 1185510 | 127331 | 6830 | 0.596 | 1.038 | 20250131 | 20250531 | 115 | 9 | 3 | 1 | 2 | 1 | 8357 | 7084 | 7439 | -1273 | 10 | 2 | 178 | 3 | 2300000 | 0 | 1634818 | 0 |  | 1 | 8000 | 4 | 49 | 55.7
1630 | 20240229 | 97 | 10 | 7 | 1 | 25 | 1 | 2 | 1 | Active | Initiate & Design | Red | 0.3889 | 0.2162 | 999025 | 369516 | 217359 | 1197946 | 153527 | -1370 | 0.585 | 0.994 | 20250131 | 20250630 | 137 | 9 | 4 | 1 | 3 | 2 | 8687 | 6774 | 6786 | -1913 | 12 | 3 | 225 | 4 | 2300000 | 0 | 1592897 | 0 |  | 1 | 12000 | 8 | 36 | 43.6
1631 | 20240331 | 97 | 10 | 7 | 1 | 25 | 1 | 2 | 1 | Active | Initiate & Design | Red | 0.4444 | 0.252 | 999025 | 424277 | 267247 | 1220449 | 172523 | -15493 | 0.593 | 0.942 | 20250131 | 20250630 | 153 | 9 | 4 | 1 | 3 | 2 | 8889 | 7803 | 7924 | -1086 | 11 | 3 | 211 | 4 | 2300000 | 0 | 1659274 | 0 |  | 1 | 12000 | 6 | 34 | 45.2
1632 | 20240430 | 97 | 10 | 7 | 1 | 25 | 1 | 2 | 1 | Active | Initiate & Design | Amber | 0.5 | 0.3084 | 999025 | 479532 | 324432 | 1229876 | 171433 | -16333 | 0.642 | 0.95 | 20250131 | 20250630 | 151 | 9 | 5 | 1 | 3 | 2 | 8957 | 6995 | 6592 | -1962 | 10 | 2 | 178 | 3 | 2300000 | 0 | 1612443 | 0 |  | 1 | 12000 | 7 | 44 | 53
1633 | 20240531 | 97 | 10 | 7 | 1 | 25 | 1 | 2 | 1 | Active | Initiate & Design | Amber | 0.5556 | 0.3432 | 999025 | 535280 | 366399 | 1244012 | 192415 | -23534 | 0.641 | 0.936 | 20250131 | 20250731 | 169 | 9 | 5 | 1 | 3 | 2 | 8889 | 7177 | 6764 | -1712 | 11 | 2 | 193 | 4 | 2300000 | 0 | 1574863 | 0 |  | 2 | 22000 | 6 | 48 | 52.5
1634 | 20240630 | 97 | 10 | 7 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Red | 0.6111 | 0.3931 | 999025 | 591521 | 434112 | 1261980 | 198804 | -41395 | 0.664 | 0.905 | 20250131 | 20250731 | 173 | 9 | 6 | 1 | 4 | 2 | 8687 | 7551 | 7186 | -1136 | 11 | 3 | 211 | 4 | 2300000 | 0 | 1586596 | 0 |  | 2 | 20000 | 7 | 39 | 46
1635 | 20240731 | 97 | 10 | 7 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Amber | 0.6667 | 0.4468 | 999025 | 648256 | 494247 | 1273397 | 201892 | -47883 | 0.689 | 0.903 | 20250131 | 20250731 | 175 | 9 | 6 | 2 | 3 | 2 | 8357 | 7233 | 7154 | -1124 | 9 | 2 | 164 | 3 | 2300000 | 0 | 1661340 | 0 |  | 2 | 19000 | 7 | 44 | 55.9
1636 | 20240831 | 97 | 10 | 7 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Amber | 0.7222 | 0.4925 | 999025 | 705484 | 551018 | 1286750 | 213464 | -58998 | 0.697 | 0.893 | 20250131 | 20250731 | 182 | 9 | 7 | 2 | 4 | 2 | 7909 | 6050 | 6166 | -1859 | 9 | 2 | 164 | 3 | 2300000 | 18254 | 1657764 | 0 | 0 | 3 | 30000 | 5 | 48 | 53.6
1637 | 20240930 | 97 | 10 | 7 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Amber | 0.7778 | 0.5454 | 999025 | 763206 | 619525 | 1300813 | 218338 | -74657 | 0.714 | 0.879 | 20250131 | 20250731 | 185 | 9 | 7 | 2 | 4 | 2 | 7357 | 5818 | 5919 | -1539 | 10 | 2 | 178 | 3 | 2300000 | 474603 | 1626309 | 0 | 0 | 3 | 40000 | 5 | 48 | 54.1
1638 | 20241031 | 97 | 10 | 7 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Amber | 0.8333 | 0.5638 | 999025 | 821421 | 651938 | 1315326 | 258171 | -88688 | 0.686 | 0.864 | 20250131 | 20250831 | 214 | 9 | 8 | 2 | 5 | 3 | 6718 | 5527 | 5521 | -1191 | 8 | 2 | 150 | 3 | 2300000 | 930952 | 1569129 | 261690 | 0.2811 | 3 | 38000 | 4 | 42 | 52.3
1639 | 20241130 | 97 | 10 | 7 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Amber | 0.8889 | 0.6001 | 999025 | 880129 | 707282 | 1329986 | 280614 | -107767 | 0.681 | 0.848 | 20250131 | 20250930 | 229 | 9 | 8 | 2 | 5 | 3 | 6010 | 5062 | 5169 | -948 | 8 | 2 | 150 | 3 | 2300000 | 1387302 | 1620835 | 518450 | 0.3737 | 3 | 48000 | 3 | 47 | 52.6
1640 | 20241231 | 97 | 10 | 7 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Amber | 0.9444 | 0.6311 | 999025 | 939330 | 754163 | 1343654 | 308845 | -123678 | 0.671 | 0.836 | 20250131 | 20250930 | 248 | 9 | 9 | 3 | 5 | 3 | 5256 | 4605 | 4342 | -651 | 9 | 2 | 164 | 3 | 2300000 | 1843651 | 1564872 | 776448 | 0.4211 | 3 | 43000 | 6 | 44 | 51.8
1641 | 20250131 | 97 | 10 | 7 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Amber | 1 | 0.6774 | 999025 | 999025 | 834256 | 1360205 | 322285 | -157516 | 0.677 | 0.811 | 20250131 | 20251031 | 255 | 9 | 9 | 4 | 5 | 3 | 4478 | 3722 | 3687 | -756 | 9 | 2 | 164 | 3 | 2300000 | 2300000 | 1612602 | 1070263 | 0.4653 | 3 | 36000 | 5 | 44 | 50.8
1642 | 20250228 | 97 | 10 | 7 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Amber | 1 | 0.6859 | 999025 | 999025 | 849762 | 1372367 | 313794 | -164531 | 0.686 | 0.806 | 20250131 | 20250930 | 250 | 9 | 9 | 3 | 5 | 3 | 4478 | 3783 | 3793 | -695 | 8 | 1 | 132 | 3 | 2300000 | 2300000 | 1614233 | 1457162 | 0.6335 | 4 | 33000 | 4 | 51 | 59.3
1643 | 20250331 | 97 | 10 | 7 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Amber | 1 | 0.6859 | 999025 | 999025 | 871785 | 1387945 | 313794 | -186554 | 0.686 | 0.786 | 20250131 | 20250930 | 250 | 9 | 9 | 3 | 5 | 3 | 4478 | 3904 | 4047 | -574 | 9 | 2 | 164 | 3 | 2300000 | 2300000 | 1563083 | 1420721 | 0.6177 | 4 | 64000 | 4 | 44 | 50.6
1644 | 20250430 | 97 | 10 | 7 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Amber | 1 | 0.6859 | 999025 | 999025 | 883698 | 1401374 | 313794 | -198467 | 0.686 | 0.775 | 20250131 | 20250930 | 250 | 9 | 9 | 3 | 5 | 3 | 4478 | 3780 | 3912 | -698 | 9 | 2 | 164 | 3 | 2300000 | 2300000 | 1581929 | 1385932 | 0.6026 | 4 | 52000 | 2 | 39 | 49.8
1645 | 20250531 | 97 | 10 | 7 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Amber | 1 | 0.6859 | 999025 | 999025 | 895470 | 1414715 | 313794 | -210239 | 0.686 | 0.765 | 20250131 | 20250930 | 250 | 9 | 9 | 3 | 5 | 3 | 4478 | 3620 | 3405 | -858 | 8 | 1 | 132 | 3 | 2300000 | 2300000 | 1570587 | 1419537 | 0.6172 | 4 | 42000 | 5 | 49 | 56.6
1646 | 20250630 | 97 | 10 | 7 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Amber | 1 | 0.6859 | 999025 | 999025 | 911804 | 1428828 | 313794 | -226573 | 0.686 | 0.752 | 20250131 | 20250930 | 250 | 9 | 9 | 4 | 5 | 3 | 4478 | 3937 | 3995 | -541 | 8 | 2 | 150 | 3 | 2300000 | 2300000 | 1596127 | 1439616 | 0.6259 | 4 | 57000 | 3 | 44 | 49.9
1647 | 20250731 | 97 | 10 | 7 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Amber | 1 | 0.6859 | 999025 | 999025 | 915615 | 1440615 | 313794 | -230384 | 0.686 | 0.748 | 20250131 | 20250930 | 250 | 9 | 9 | 3 | 5 | 3 | 4478 | 3777 | 3629 | -701 | 8 | 2 | 150 | 3 | 2300000 | 2300000 | 1594913 | 1425842 | 0.6199 | 5 | 73000 | 6 | 42 | 49
1648 | 20250831 | 97 | 10 | 7 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Amber | 1 | 0.6859 | 999025 | 999025 | 924501 | 1445527 | 313794 | -239270 | 0.686 | 0.741 | 20250131 | 20250930 | 250 | 9 | 9 | 3 | 5 | 3 | 4478 | 3528 | 3702 | -950 | 9 | 2 | 164 | 3 | 2300000 | 2300000 | 1653744 | 1464140 | 0.6366 | 5 | 77000 | 2 | 37 | 48.3
1649 | 20250930 | 97 | 10 | 7 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Red | 1 | 0.6859 | 999025 | 999025 | 927264 | 1446012 | 313794 | -242033 | 0.686 | 0.739 | 20250131 | 20250930 | 250 | 9 | 9 | 3 | 5 | 3 | 4478 | 3546 | 3446 | -932 | 10 | 2 | 178 | 3 | 2300000 | 2300000 | 1588712 | 1487216 | 0.6466 | 5 | 79000 | 4 | 41 | 47.5
1650 | 20251031 | 97 | 10 | 7 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Red | 1 | 0.6859 | 999025 | 999025 | 927264 | 1446012 | 313794 | -242033 | 0.686 | 0.739 | 20250131 | 20250930 | 250 | 9 | 9 | 3 | 5 | 3 | 4478 | 3521 | 3398 | -957 | 9 | 2 | 164 | 3 | 2300000 | 2300000 | 1624588 | 1453640 | 0.632 | 5 | 51000 | 4 | 37 | 47.8
1651 | 20251130 | 97 | 10 | 7 | 1 | 25 | 1 | 2 | 1 | Active | Deliver | Amber | 1 | 0.6859 | 999025 | 999025 | 927264 | 1446012 | 313794 | -242033 | 0.686 | 0.739 | 20250131 | 20250930 | 250 | 9 | 9 | 3 | 5 | 3 | 4478 | 3931 | 3766 | -547 | 7 | 2 | 136 | 2 | 2300000 | 2300000 | 1555365 | 1364185 | 0.5931 | 5 | 44000 | 2 | 42 | 49
1652 | 20251231 | 98 | 4 | 3 | 2 | 26 | 2 | 2 | 2 | Active | Initiate & Design | Amber | 0.0333 | 0.0056 | 1261115 | 38786 | 4810 | 1340986 | 31724 | 2252 | 0.182 | 1.471 | 20280531 | 20280630 | 34 | 15 | 1 | 0 | 1 | 0 | 6244 | 5737 | 6041 | -507 | 12 | 2 | 188 | 3 | 3200000 | 0 | 2806017 | 0 |  | 0 | 0 | 7 | 52 | 58.5
1653 | 20260131 | 98 | 4 | 3 | 2 | 26 | 2 | 2 | 2 | Active | Initiate & Design | Green | 0.0667 | 0.0642 | 1261115 | 77797 | 77184 | 1345189 | -3167 | 3780 | 1.041 | 1.05 | 20280531 | 20280531 | 3 | 15 | 1 | 0 | 0 | 0 | 6829 | 6360 | 6694 | -469 | 7 | 1 | 106 | 2 | 3200000 | 0 | 2880431 | 0 |  | 0 | 0 | 8 | 80 | 91.3
1654 | 20260228 | 98 | 4 | 3 | 2 | 26 | 2 | 2 | 2 | Active | Initiate & Design | Green | 0.1 | 0.0862 | 1261115 | 117031 | 106307 | 1349393 | 8323 | 2401 | 0.929 | 1.023 | 20280531 | 20280630 | 16 | 15 | 2 | 2 | 0 | 0 | 7400 | 7107 | 7053 | -293 | 8 | 2 | 137 | 2 | 3200000 | 0 | 2956254 | 0 |  | 0 | 0 | 8 | 69 | 78.6
1655 | 20260331 | 98 | 4 | 3 | 2 | 26 | 2 | 2 | 2 | Active | Initiate & Design | Green | 0.1333 | 0.1108 | 1261115 | 156490 | 126273 | 1353597 | 16758 | 13459 | 0.893 | 1.106 | 20280531 | 20280630 | 27 | 15 | 2 | 2 | 0 | 0 | 7953 | 7432 | 7671 | -521 | 8 | 1 | 119 | 2 | 3200000 | 0 | 2889830 | 0 |  | 0 | 0 | 8 | 76 | 86.7
1656 | 20260430 | 98 | 4 | 3 | 2 | 26 | 2 | 2 | 2 | Active | Initiate & Design | Green | 0.1667 | 0.1554 | 1261115 | 196173 | 183547 | 1357800 | 196 | 12430 | 0.999 | 1.068 | 20280531 | 20280531 | 13 | 15 | 3 | 2 | 0 | 0 | 8480 | 8250 | 8081 | -230 | 8 | 2 | 137 | 2 | 3200000 | 0 | 2911242 | 0 |  | 0 | 0 | 7 | 78 | 83.2
1657 | 20260531 | 98 | 4 | 3 | 2 | 26 | 2 | 2 | 2 | Active | Initiate & Design | Green | 0.2 | 0.1747 | 1261115 | 236081 | 214196 | 1362004 | 15764 | 6121 | 0.933 | 1.028 | 20280531 | 20280630 | 31 | 15 | 3 | 1 | 1 | 0 | 8976 | 8913 | 9473 | -63 | 6 | 1 | 94 | 2 | 3200000 | 0 | 2904769 | 0 |  | 0 | 0 | 8 | 75 | 87.2
1658 | 20260630 | 98 | 4 | 3 | 2 | 26 | 2 | 2 | 2 | Active | Initiate & Design | Green | 0.2333 | 0.1766 | 1261115 | 276212 | 214196 | 1366208 | 53499 | 8517 | 0.806 | 1.04 | 20280531 | 20280731 | 69 | 15 | 4 | 2 | 1 | 0 | 9436 | 8742 | 8907 | -694 | 9 | 2 | 150 | 3 | 3200000 | 0 | 2858361 | 0 |  | 1 | 14000 | 8 | 63 | 72.1
1659 | 20260731 | 98 | 4 | 3 | 2 | 26 | 2 | 2 | 2 | Active | Initiate & Design | Green | 0.2667 | 0.2166 | 1261115 | 316568 | 268960 | 1370412 | 43410 | 4198 | 0.863 | 1.016 | 20280531 | 20280731 | 61 | 15 | 4 | 3 | 1 | 0 | 9854 | 9826 | 9272 | -28 | 7 | 1 | 106 | 2 | 3200000 | 0 | 2832677 | 0 |  | 1 | 12000 | 8 | 74 | 83.1
1660 | 20260831 | 98 | 4 | 3 | 2 | 26 | 2 | 2 | 2 | Active | Initiate & Design | Green | 0.3 | 0.2534 | 1261115 | 357148 | 316105 | 1374615 | 37581 | 3462 | 0.895 | 1.011 | 20280531 | 20280731 | 57 | 15 | 5 | 4 | 1 | 0 | 10227 | 10060 | 10503 | -167 | 7 | 1 | 106 | 2 | 3200000 | 0 | 2851601 | 0 |  | 1 | 14000 | 8 | 74 | 84.2
1661 | 20260930 | 98 | 4 | 3 | 2 | 26 | 2 | 2 | 2 | Active | Initiate & Design | Green | 0.3333 | 0.2943 | 1261115 | 397952 | 352422 | 1378819 | 26806 | 18724 | 0.933 | 1.053 | 20280531 | 20280731 | 47 | 15 | 5 | 3 | 1 | 0 | 10549 | 10151 | 10007 | -398 | 6 | 1 | 94 | 2 | 3200000 | 0 | 2827767 | 0 |  | 1 | 15000 | 6 | 75 | 86.7
1662 | 20240930 | 99 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.0476 | 0.0681 | 210445 | 9258 | 12184 | 211808 | -5073 | 2147 | 1.549 | 1.177 | 20260531 | 20260531 | 0 | 11 | 1 | 0 | 0 | 0 | 1084 | 1052 | 1113 | -32 | 0 | 0 | 0 | 0 | 600000 | 0 | 609149 | 0 |  | 0 | 0 | 2 | 96 | 100
1663 | 20241031 | 99 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.0952 | 0.1274 | 210445 | 18592 | 25293 | 211908 | -8219 | 1518 | 1.442 | 1.06 | 20260531 | 20260531 | 0 | 11 | 1 | 1 | 0 | 0 | 1221 | 1222 | 1285 | 1 | 0 | 0 | 0 | 0 | 600000 | 0 | 624024 | 0 |  | 0 | 0 | 4 | 96 | 100
1664 | 20241130 | 99 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.1429 | 0.1571 | 210445 | 28002 | 29388 | 212008 | -5059 | 3673 | 1.181 | 1.125 | 20260531 | 20260531 | 0 | 11 | 2 | 1 | 0 | 0 | 1353 | 1391 | 1322 | 38 | 2 | 0 | 19 | 0 | 600000 | 0 | 625855 | 0 |  | 0 | 0 | 5 | 95 | 100
1665 | 20241231 | 99 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.1905 | 0.1968 | 210445 | 37489 | 38360 | 212109 | -3927 | 3056 | 1.105 | 1.08 | 20260531 | 20260531 | 0 | 11 | 2 | 2 | 0 | 0 | 1475 | 1477 | 1414 | 2 | 4 | 0 | 38 | 1 | 600000 | 0 | 612792 | 0 |  | 0 | 0 | 1 | 91 | 100
1666 | 20250131 | 99 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.2381 | 0.2405 | 210445 | 47052 | 47973 | 212209 | -3560 | 2639 | 1.076 | 1.055 | 20260531 | 20260531 | 0 | 11 | 3 | 2 | 0 | 0 | 1585 | 1527 | 1598 | -58 | 3 | 0 | 29 | 1 | 600000 | 0 | 601794 | 0 |  | 0 | 0 | 4 | 84 | 100
1667 | 20250228 | 99 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.2857 | 0.269 | 210445 | 56691 | 53891 | 212309 | 81 | 2719 | 0.998 | 1.05 | 20260531 | 20260531 | 12 | 11 | 3 | 3 | 0 | 0 | 1681 | 1705 | 1611 | 24 | 3 | 0 | 29 | 1 | 600000 | 0 | 606545 | 0 |  | 0 | 0 | 2 | 86 | 100
1668 | 20250331 | 99 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Initiate & Design | Green | 0.3333 | 0.3213 | 210445 | 66407 | 64435 | 212409 | -1209 | 3181 | 1.018 | 1.049 | 20260531 | 20260531 | 9 | 11 | 4 | 3 | 0 | 0 | 1760 | 1894 | 1992 | 134 | 2 | 0 | 19 | 0 | 600000 | 0 | 605939 | 0 |  | 0 | 0 | 4 | 84 | 100
1669 | 20250430 | 99 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Deliver | Green | 0.381 | 0.3731 | 210445 | 76199 | 73783 | 212509 | -2318 | 4734 | 1.03 | 1.064 | 20260531 | 20260531 | 6 | 11 | 4 | 3 | 0 | 0 | 1822 | 1789 | 1861 | -33 | 2 | 0 | 19 | 0 | 600000 | 0 | 622556 | 0 |  | 0 | 0 | 4 | 88 | 100
1670 | 20250531 | 99 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Deliver | Green | 0.4286 | 0.4305 | 210445 | 86068 | 87595 | 212610 | -4529 | 3002 | 1.053 | 1.034 | 20260531 | 20260531 | 0 | 11 | 5 | 4 | 0 | 0 | 1863 | 1928 | 1870 | 65 | 3 | 0 | 29 | 1 | 600000 | 0 | 623578 | 0 |  | 0 | 0 | 5 | 88 | 100
1671 | 20250630 | 99 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Deliver | Green | 0.4762 | 0.4968 | 210445 | 96013 | 99975 | 212710 | -8536 | 4574 | 1.089 | 1.046 | 20260531 | 20260531 | 0 | 11 | 5 | 5 | 0 | 0 | 1884 | 1969 | 1864 | 85 | 2 | 0 | 19 | 0 | 600000 | 0 | 624596 | 0 |  | 0 | 0 | 3 | 90 | 100
1672 | 20250731 | 99 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Deliver | Green | 0.5238 | 0.5465 | 210445 | 106034 | 111434 | 212810 | -8974 | 3574 | 1.085 | 1.032 | 20260531 | 20260531 | 0 | 11 | 6 | 6 | 0 | 0 | 1884 | 2028 | 2008 | 144 | 3 | 0 | 29 | 1 | 600000 | 0 | 611684 | 0 |  | 0 | 0 | 4 | 90 | 100
1673 | 20250831 | 99 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Deliver | Green | 0.5714 | 0.6004 | 210445 | 116131 | 123744 | 212910 | -10220 | 2607 | 1.088 | 1.021 | 20260531 | 20260531 | 0 | 11 | 6 | 5 | 0 | 0 | 1863 | 1824 | 1867 | -39 | 3 | 0 | 29 | 1 | 600000 | 0 | 605311 | 0 |  | 0 | 0 | 3 | 89 | 100
1674 | 20250930 | 99 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Deliver | Green | 0.619 | 0.6417 | 210445 | 126305 | 132936 | 213010 | -8738 | 2107 | 1.069 | 1.016 | 20260531 | 20260531 | 0 | 11 | 7 | 7 | 0 | 0 | 1822 | 1951 | 2067 | 129 | 2 | 0 | 19 | 0 | 600000 | 0 | 616311 | 0 |  | 0 | 0 | 1 | 84 | 100
1675 | 20251031 | 99 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Deliver | Green | 0.6667 | 0.666 | 210445 | 136555 | 137114 | 213111 | -3601 | 3042 | 1.026 | 1.022 | 20260531 | 20260531 | 0 | 11 | 7 | 7 | 0 | 0 | 1760 | 1822 | 1748 | 62 | 4 | 0 | 38 | 1 | 600000 | 0 | 610501 | 0 |  | 0 | 0 | 1 | 88 | 100
1676 | 20251130 | 99 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Deliver | Green | 0.7143 | 0.7149 | 210445 | 146882 | 147815 | 213211 | -3565 | 2632 | 1.024 | 1.018 | 20260531 | 20260531 | 0 | 11 | 8 | 8 | 0 | 0 | 1681 | 1663 | 1654 | -18 | 3 | 0 | 29 | 1 | 600000 | 0 | 620359 | 0 |  | 0 | 0 | 5 | 86 | 100
1677 | 20251231 | 99 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Deploy | Green | 0.7619 | 0.7614 | 210445 | 157285 | 160106 | 213311 | -2948 | 127 | 1.019 | 1.001 | 20260531 | 20260531 | 0 | 11 | 8 | 8 | 0 | 0 | 1585 | 1669 | 1598 | 84 | 3 | 0 | 29 | 1 | 600000 | 89796 | 624013 | 0 | 0 | 0 | 0 | 4 | 80 | 100
1678 | 20260131 | 99 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Deploy | Green | 0.8095 | 0.8201 | 210445 | 167764 | 174126 | 213820 | -4822 | -1540 | 1.029 | 0.991 | 20260531 | 20260531 | 0 | 11 | 9 | 8 | 0 | 0 | 1475 | 1437 | 1530 | -38 | 0 | 0 | 0 | 0 | 600000 | 191837 | 624338 | 55796 | 0.2909 | 0 | 0 | 0 | 80 | 100
1679 | 20260228 | 99 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Deploy | Green | 0.8571 | 0.8836 | 210445 | 178320 | 188200 | 214064 | -7629 | -2251 | 1.043 | 0.988 | 20260531 | 20260531 | 0 | 11 | 9 | 9 | 0 | 0 | 1353 | 1436 | 1467 | 83 | 1 | 0 | 10 | 0 | 600000 | 293878 | 609093 | 153005 | 0.5206 | 0 | 0 | 0 | 82 | 100
1680 | 20260331 | 99 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Deploy | Green | 0.9048 | 0.9274 | 210445 | 188952 | 197242 | 214099 | -6215 | -2075 | 1.033 | 0.989 | 20260531 | 20260531 | 0 | 11 | 10 | 9 | 0 | 0 | 1221 | 1251 | 1295 | 30 | 0 | 0 | 0 | 0 | 600000 | 395918 | 601362 | 224657 | 0.5674 | 0 | 0 | 0 | 83 | 100
1681 | 20260430 | 99 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Active | Deploy | Green | 0.9524 | 0.9821 | 210445 | 199660 | 211389 | 214745 | -7018 | -4711 | 1.035 | 0.978 | 20260531 | 20260531 | 0 | 11 | 10 | 10 | 0 | 0 | 1084 | 1060 | 1027 | -24 | 2 | 0 | 19 | 0 | 600000 | 497959 | 616284 | 313459 | 0.6295 | 0 | 0 | 0 | 83 | 100
1682 | 20260531 | 99 | 4 | 3 | 3 | 27 | 3 | 2 | 3 | Completed | Completed | Green | 1 | 1 | 210445 | 210445 | 215655 | 215655 | 0 | -5210 | 1 | 0.976 | 20260531 | 20260531 | 0 | 11 | 11 | 10 | 0 | 0 | 943 | 911 | 954 | -32 | 2 | 0 | 19 | 0 | 600000 | 600000 | 614836 | 439669 | 0.7328 | 1 | 2000 | 0 | 81 | 98.4
1683 | 20250331 | 100 | 5 | 5 | 4 | 28 | 4 | 1 | 4 | Active | Initiate & Design | Green | 0.0667 | 0.1148 | 892844 | 55079 | 92940 | 910701 | -47419 | 9558 | 1.861 | 1.103 | 20260531 | 20260531 | 0 | 8 | 1 | 0 | 0 | 0 | 4835 | 5139 | 4932 | 304 | 0 | 0 | 0 | 0 | 900000 | 0 | 963300 | 0 |  | 1 | 10000 | 3 | 96 | 100
1684 | 20250430 | 100 | 5 | 5 | 4 | 28 | 4 | 1 | 4 | Active | Initiate & Design | Green | 0.1333 | 0.172 | 892844 | 110792 | 136850 | 912487 | -42777 | 16719 | 1.386 | 1.122 | 20260531 | 20260531 | 0 | 8 | 1 | 0 | 0 | 0 | 5630 | 6031 | 6007 | 401 | 1 | 0 | 9 | 0 | 900000 | 0 | 972936 | 0 |  | 1 | 8000 | 4 | 96 | 100
1685 | 20250531 | 100 | 5 | 5 | 4 | 28 | 4 | 1 | 4 | Active | Initiate & Design | Green | 0.2 | 0.2519 | 892844 | 167140 | 206858 | 914272 | -57767 | 18049 | 1.346 | 1.087 | 20260531 | 20260531 | 0 | 8 | 2 | 1 | 0 | 0 | 6355 | 6484 | 6532 | 129 | 0 | 0 | 0 | 0 | 900000 | 0 | 968372 | 0 |  | 1 | 9000 | 4 | 96 | 100
1686 | 20250630 | 100 | 5 | 5 | 4 | 28 | 4 | 1 | 4 | Active | Initiate & Design | Green | 0.2667 | 0.3007 | 892844 | 224124 | 254967 | 916058 | -44354 | 13511 | 1.198 | 1.053 | 20260531 | 20260531 | 0 | 8 | 2 | 1 | 0 | 0 | 6977 | 7500 | 7080 | 523 | 0 | 0 | 0 | 0 | 900000 | 0 | 952790 | 0 |  | 1 | 14000 | 4 | 94 | 100
1687 | 20250731 | 100 | 5 | 5 | 4 | 28 | 4 | 1 | 4 | Active | Deliver | Green | 0.3333 | 0.3671 | 892844 | 281742 | 316932 | 917844 | -46021 | 10831 | 1.163 | 1.034 | 20260531 | 20260531 | 0 | 8 | 3 | 2 | 0 | 0 | 7469 | 8246 | 8032 | 777 | 2 | 0 | 18 | 0 | 900000 | 0 | 989831 | 0 |  | 1 | 11000 | 4 | 94 | 100
1688 | 20250831 | 100 | 5 | 5 | 4 | 28 | 4 | 1 | 4 | Active | Deliver | Green | 0.4 | 0.4423 | 892844 | 339995 | 374844 | 919629 | -54910 | 20061 | 1.161 | 1.053 | 20260531 | 20260531 | 0 | 8 | 3 | 2 | 0 | 0 | 7809 | 8383 | 8697 | 574 | 1 | 0 | 9 | 0 | 900000 | 0 | 964149 | 0 |  | 1 | 12000 | 4 | 93 | 100
1689 | 20250930 | 100 | 5 | 5 | 4 | 28 | 4 | 1 | 4 | Active | Deliver | Green | 0.4667 | 0.5142 | 892844 | 398883 | 444422 | 921415 | -60217 | 14678 | 1.151 | 1.033 | 20260531 | 20260531 | 0 | 8 | 4 | 4 | 0 | 0 | 7983 | 8767 | 8301 | 784 | 2 | 0 | 18 | 0 | 900000 | 0 | 964639 | 0 |  | 1 | 8000 | 1 | 88 | 100
1690 | 20251031 | 100 | 5 | 5 | 4 | 28 | 4 | 1 | 4 | Active | Deliver | Green | 0.5333 | 0.5877 | 892844 | 458406 | 514273 | 923201 | -66318 | 10451 | 1.145 | 1.02 | 20260531 | 20260531 | 0 | 8 | 4 | 3 | 0 | 0 | 7983 | 8980 | 9227 | 997 | 1 | 0 | 9 | 0 | 900000 | 0 | 957284 | 0 |  | 1 | 7000 | 4 | 88 | 100
1691 | 20251130 | 100 | 5 | 5 | 4 | 28 | 4 | 1 | 4 | Active | Deliver | Green | 0.6 | 0.6867 | 892844 | 518564 | 606580 | 924986 | -94552 | 6536 | 1.182 | 1.011 | 20260531 | 20260531 | 0 | 8 | 5 | 4 | 0 | 0 | 7809 | 8841 | 8863 | 1032 | 1 | 0 | 9 | 0 | 900000 | 0 | 972430 | 0 |  | 1 | 12000 | 4 | 91 | 100
1692 | 20251231 | 100 | 5 | 5 | 4 | 28 | 4 | 1 | 4 | Active | Deploy | Green | 0.6667 | 0.7527 | 892844 | 579357 | 674840 | 927594 | -92687 | -2796 | 1.16 | 0.996 | 20260531 | 20260531 | 0 | 8 | 5 | 5 | 0 | 0 | 7469 | 8150 | 7694 | 681 | 2 | 0 | 18 | 0 | 900000 | 0 | 965227 | 0 |  | 1 | 9000 | 3 | 88 | 100
1693 | 20260131 | 100 | 5 | 5 | 4 | 28 | 4 | 1 | 4 | Active | Deploy | Green | 0.7333 | 0.8298 | 892844 | 640784 | 744603 | 929535 | -100098 | -3721 | 1.156 | 0.995 | 20260531 | 20260531 | 0 | 8 | 6 | 5 | 0 | 0 | 6977 | 7755 | 7571 | 778 | 2 | 0 | 18 | 0 | 900000 | 42857 | 988441 | 0 | 0 | 1 | 9000 | 1 | 85 | 100
1694 | 20260228 | 100 | 5 | 5 | 4 | 28 | 4 | 1 | 4 | Active | Deploy | Green | 0.8 | 0.8756 | 892844 | 702847 | 803343 | 935618 | -78927 | -21569 | 1.112 | 0.973 | 20260531 | 20260531 | 0 | 8 | 6 | 5 | 0 | 0 | 6355 | 6915 | 6620 | 560 | 1 | 0 | 9 | 0 | 900000 | 257143 | 958798 | 56564 | 0.22 | 1 | 10000 | 3 | 88 | 100
1695 | 20260331 | 100 | 5 | 5 | 4 | 28 | 4 | 1 | 4 | Active | Deploy | Green | 0.8667 | 0.9532 | 892844 | 765544 | 873113 | 937094 | -85515 | -22054 | 1.112 | 0.975 | 20260531 | 20260531 | 0 | 8 | 7 | 6 | 0 | 0 | 5630 | 6236 | 6378 | 606 | 0 | 0 | 0 | 0 | 900000 | 471429 | 962041 | 264048 | 0.5601 | 1 | 12000 | 0 | 84 | 100
1696 | 20260430 | 100 | 5 | 5 | 4 | 28 | 4 | 1 | 4 | Completed | Completed | Green | 0.9333 | 1 | 892844 | 828877 | 929268 | 941614 | -63967 | -36424 | 1.077 | 0.961 | 20260531 | 20260531 | 0 | 8 | 7 | 6 | 0 | 0 | 4835 | 5341 | 5082 | 506 | 0 | 0 | 0 | 0 | 900000 | 685714 | 960192 | 434041 | 0.633 | 1 | 12000 | 0 | 85 | 100

## DimDate
DateKey | Date | Year | MonthNumber | MonthName | Quarter | FiscalYear | FiscalYearLabel | IsWeekend
20231001 | 2023-10-01 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 1
20231002 | 2023-10-02 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 0
20231003 | 2023-10-03 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 0
20231004 | 2023-10-04 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 0
20231005 | 2023-10-05 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 0
20231006 | 2023-10-06 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 0
20231007 | 2023-10-07 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 1
20231008 | 2023-10-08 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 1
20231009 | 2023-10-09 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 0
20231010 | 2023-10-10 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 0
20231011 | 2023-10-11 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 0
20231012 | 2023-10-12 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 0
20231013 | 2023-10-13 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 0
20231014 | 2023-10-14 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 1
20231015 | 2023-10-15 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 1
20231016 | 2023-10-16 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 0
20231017 | 2023-10-17 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 0
20231018 | 2023-10-18 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 0
20231019 | 2023-10-19 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 0
20231020 | 2023-10-20 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 0
20231021 | 2023-10-21 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 1
20231022 | 2023-10-22 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 1
20231023 | 2023-10-23 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 0
20231024 | 2023-10-24 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 0
20231025 | 2023-10-25 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 0
20231026 | 2023-10-26 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 0
20231027 | 2023-10-27 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 0
20231028 | 2023-10-28 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 1
20231029 | 2023-10-29 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 1
20231030 | 2023-10-30 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 0
20231031 | 2023-10-31 | 2023 | 10 | October | Q4 | 2024 | FY2024 | 0
20231101 | 2023-11-01 | 2023 | 11 | November | Q4 | 2024 | FY2024 | 0
20231102 | 2023-11-02 | 2023 | 11 | November | Q4 | 2024 | FY2024 | 0
20231103 | 2023-11-03 | 2023 | 11 | November | Q4 | 2024 | FY2024 | 0
20231104 | 2023-11-04 | 2023 | 11 | November | Q4 | 2024 | FY2024 | 1
20231105 | 2023-11-05 | 2023 | 11 | November | Q4 | 2024 | FY2024 | 1
20231106 | 2023-11-06 | 2023 | 11 | November | Q4 | 2024 | FY2024 | 0
20231107 | 2023-11-07 | 2023 | 11 | November | Q4 | 2024 | FY2024 | 0
20231108 | 2023-11-08 | 2023 | 11 | November | Q4 | 2024 | FY2024 | 0
20231109 | 2023-11-09 | 2023 | 11 | November | Q4 | 2024 | FY2024 | 0
20231110 | 2023-11-10 | 2023 | 11 | November | Q4 | 2024 | FY2024 | 0
20231111 | 2023-11-11 | 2023 | 11 | November | Q4 | 2024 | FY2024 | 1
20231112 | 2023-11-12 | 2023 | 11 | November | Q4 | 2024 | FY2024 | 1
20231113 | 2023-11-13 | 2023 | 11 | November | Q4 | 2024 | FY2024 | 0
20231114 | 2023-11-14 | 2023 | 11 | November | Q4 | 2024 | FY2024 | 0
20231115 | 2023-11-15 | 2023 | 11 | November | Q4 | 2024 | FY2024 | 0
20231116 | 2023-11-16 | 2023 | 11 | November | Q4 | 2024 | FY2024 | 0
20231117 | 2023-11-17 | 2023 | 11 | November | Q4 | 2024 | FY2024 | 0
20231118 | 2023-11-18 | 2023 | 11 | November | Q4 | 2024 | FY2024 | 1
20231119 | 2023-11-19 | 2023 | 11 | November | Q4 | 2024 | FY2024 | 1
20231120 | 2023-11-20 | 2023 | 11 | November | Q4 | 2024 | FY2024 | 0
20231121 | 2023-11-21 | 2023 | 11 | November | Q4 | 2024 | FY2024 | 0
20231122 | 2023-11-22 | 2023 | 11 | November | Q4 | 2024 | FY2024 | 0
20231123 | 2023-11-23 | 2023 | 11 | November | Q4 | 2024 | FY2024 | 0
20231124 | 2023-11-24 | 2023 | 11 | November | Q4 | 2024 | FY2024 | 0
20231125 | 2023-11-25 | 2023 | 11 | November | Q4 | 2024 | FY2024 | 1
20231126 | 2023-11-26 | 2023 | 11 | November | Q4 | 2024 | FY2024 | 1
20231127 | 2023-11-27 | 2023 | 11 | November | Q4 | 2024 | FY2024 | 0
20231128 | 2023-11-28 | 2023 | 11 | November | Q4 | 2024 | FY2024 | 0
20231129 | 2023-11-29 | 2023 | 11 | November | Q4 | 2024 | FY2024 | 0
20231130 | 2023-11-30 | 2023 | 11 | November | Q4 | 2024 | FY2024 | 0
20231201 | 2023-12-01 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 0
20231202 | 2023-12-02 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 1
20231203 | 2023-12-03 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 1
20231204 | 2023-12-04 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 0
20231205 | 2023-12-05 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 0
20231206 | 2023-12-06 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 0
20231207 | 2023-12-07 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 0
20231208 | 2023-12-08 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 0
20231209 | 2023-12-09 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 1
20231210 | 2023-12-10 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 1
20231211 | 2023-12-11 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 0
20231212 | 2023-12-12 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 0
20231213 | 2023-12-13 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 0
20231214 | 2023-12-14 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 0
20231215 | 2023-12-15 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 0
20231216 | 2023-12-16 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 1
20231217 | 2023-12-17 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 1
20231218 | 2023-12-18 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 0
20231219 | 2023-12-19 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 0
20231220 | 2023-12-20 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 0
20231221 | 2023-12-21 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 0
20231222 | 2023-12-22 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 0
20231223 | 2023-12-23 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 1
20231224 | 2023-12-24 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 1
20231225 | 2023-12-25 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 0
20231226 | 2023-12-26 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 0
20231227 | 2023-12-27 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 0
20231228 | 2023-12-28 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 0
20231229 | 2023-12-29 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 0
20231230 | 2023-12-30 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 1
20231231 | 2023-12-31 | 2023 | 12 | December | Q4 | 2024 | FY2024 | 1
20240101 | 2024-01-01 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 0
20240102 | 2024-01-02 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 0
20240103 | 2024-01-03 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 0
20240104 | 2024-01-04 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 0
20240105 | 2024-01-05 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 0
20240106 | 2024-01-06 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 1
20240107 | 2024-01-07 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 1
20240108 | 2024-01-08 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 0
20240109 | 2024-01-09 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 0
20240110 | 2024-01-10 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 0
20240111 | 2024-01-11 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 0
20240112 | 2024-01-12 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 0
20240113 | 2024-01-13 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 1
20240114 | 2024-01-14 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 1
20240115 | 2024-01-15 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 0
20240116 | 2024-01-16 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 0
20240117 | 2024-01-17 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 0
20240118 | 2024-01-18 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 0
20240119 | 2024-01-19 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 0
20240120 | 2024-01-20 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 1
20240121 | 2024-01-21 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 1
20240122 | 2024-01-22 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 0
20240123 | 2024-01-23 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 0
20240124 | 2024-01-24 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 0
20240125 | 2024-01-25 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 0
20240126 | 2024-01-26 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 0
20240127 | 2024-01-27 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 1
20240128 | 2024-01-28 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 1
20240129 | 2024-01-29 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 0
20240130 | 2024-01-30 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 0
20240131 | 2024-01-31 | 2024 | 1 | January | Q1 | 2024 | FY2024 | 0
20240201 | 2024-02-01 | 2024 | 2 | February | Q1 | 2024 | FY2024 | 0
20240202 | 2024-02-02 | 2024 | 2 | February | Q1 | 2024 | FY2024 | 0
20240203 | 2024-02-03 | 2024 | 2 | February | Q1 | 2024 | FY2024 | 1
20240204 | 2024-02-04 | 2024 | 2 | February | Q1 | 2024 | FY2024 | 1
20240205 | 2024-02-05 | 2024 | 2 | February | Q1 | 2024 | FY2024 | 0
20240206 | 2024-02-06 | 2024 | 2 | February | Q1 | 2024 | FY2024 | 0
20240207 | 2024-02-07 | 2024 | 2 | February | Q1 | 2024 | FY2024 | 0
20240208 | 2024-02-08 | 2024 | 2 | February | Q1 | 2024 | FY2024 | 0
20240209 | 2024-02-09 | 2024 | 2 | February | Q1 | 2024 | FY2024 | 0
20240210 | 2024-02-10 | 2024 | 2 | February | Q1 | 2024 | FY2024 | 1
20240211 | 2024-02-11 | 2024 | 2 | February | Q1 | 2024 | FY2024 | 1
20240212 | 2024-02-12 | 2024 | 2 | February | Q1 | 2024 | FY2024 | 0
20240213 | 2024-02-13 | 2024 | 2 | February | Q1 | 2024 | FY2024 | 0
20240214 | 2024-02-14 | 2024 | 2 | February | Q1 | 2024 | FY2024 | 0
20240215 | 2024-02-15 | 2024 | 2 | February | Q1 | 2024 | FY2024 | 0
20240216 | 2024-02-16 | 2024 | 2 | February | Q1 | 2024 | FY2024 | 0
20240217 | 2024-02-17 | 2024 | 2 | February | Q1 | 2024 | FY2024 | 1
20240218 | 2024-02-18 | 2024 | 2 | February | Q1 | 2024 | FY2024 | 1
20240219 | 2024-02-19 | 2024 | 2 | February | Q1 | 2024 | FY2024 | 0
20240220 | 2024-02-20 | 2024 | 2 | February | Q1 | 2024 | FY2024 | 0
20240221 | 2024-02-21 | 2024 | 2 | February | Q1 | 2024 | FY2024 | 0
20240222 | 2024-02-22 | 2024 | 2 | February | Q1 | 2024 | FY2024 | 0
20240223 | 2024-02-23 | 2024 | 2 | February | Q1 | 2024 | FY2024 | 0
20240224 | 2024-02-24 | 2024 | 2 | February | Q1 | 2024 | FY2024 | 1
20240225 | 2024-02-25 | 2024 | 2 | February | Q1 | 2024 | FY2024 | 1
20240226 | 2024-02-26 | 2024 | 2 | February | Q1 | 2024 | FY2024 | 0
20240227 | 2024-02-27 | 2024 | 2 | February | Q1 | 2024 | FY2024 | 0
20240228 | 2024-02-28 | 2024 | 2 | February | Q1 | 2024 | FY2024 | 0
20240229 | 2024-02-29 | 2024 | 2 | February | Q1 | 2024 | FY2024 | 0
20240301 | 2024-03-01 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 0
20240302 | 2024-03-02 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 1
20240303 | 2024-03-03 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 1
20240304 | 2024-03-04 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 0
20240305 | 2024-03-05 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 0
20240306 | 2024-03-06 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 0
20240307 | 2024-03-07 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 0
20240308 | 2024-03-08 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 0
20240309 | 2024-03-09 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 1
20240310 | 2024-03-10 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 1
20240311 | 2024-03-11 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 0
20240312 | 2024-03-12 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 0
20240313 | 2024-03-13 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 0
20240314 | 2024-03-14 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 0
20240315 | 2024-03-15 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 0
20240316 | 2024-03-16 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 1
20240317 | 2024-03-17 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 1
20240318 | 2024-03-18 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 0
20240319 | 2024-03-19 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 0
20240320 | 2024-03-20 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 0
20240321 | 2024-03-21 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 0
20240322 | 2024-03-22 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 0
20240323 | 2024-03-23 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 1
20240324 | 2024-03-24 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 1
20240325 | 2024-03-25 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 0
20240326 | 2024-03-26 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 0
20240327 | 2024-03-27 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 0
20240328 | 2024-03-28 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 0
20240329 | 2024-03-29 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 0
20240330 | 2024-03-30 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 1
20240331 | 2024-03-31 | 2024 | 3 | March | Q1 | 2024 | FY2024 | 1
20240401 | 2024-04-01 | 2024 | 4 | April | Q2 | 2025 | FY2025 | 0
20240402 | 2024-04-02 | 2024 | 4 | April | Q2 | 2025 | FY2025 | 0
20240403 | 2024-04-03 | 2024 | 4 | April | Q2 | 2025 | FY2025 | 0
20240404 | 2024-04-04 | 2024 | 4 | April | Q2 | 2025 | FY2025 | 0
20240405 | 2024-04-05 | 2024 | 4 | April | Q2 | 2025 | FY2025 | 0
20240406 | 2024-04-06 | 2024 | 4 | April | Q2 | 2025 | FY2025 | 1
20240407 | 2024-04-07 | 2024 | 4 | April | Q2 | 2025 | FY2025 | 1
20240408 | 2024-04-08 | 2024 | 4 | April | Q2 | 2025 | FY2025 | 0
20240409 | 2024-04-09 | 2024 | 4 | April | Q2 | 2025 | FY2025 | 0
20240410 | 2024-04-10 | 2024 | 4 | April | Q2 | 2025 | FY2025 | 0
20240411 | 2024-04-11 | 2024 | 4 | April | Q2 | 2025 | FY2025 | 0
20240412 | 2024-04-12 | 2024 | 4 | April | Q2 | 2025 | FY2025 | 0
20240413 | 2024-04-13 | 2024 | 4 | April | Q2 | 2025 | FY2025 | 1
20240414 | 2024-04-14 | 2024 | 4 | April | Q2 | 2025 | FY2025 | 1
20240415 | 2024-04-15 | 2024 | 4 | April | Q2 | 2025 | FY2025 | 0
20240416 | 2024-04-16 | 2024 | 4 | April | Q2 | 2025 | FY2025 | 0
20240417 | 2024-04-17 | 2024 | 4 | April | Q2 | 2025 | FY2025 | 0
20240418 | 2024-04-18 | 2024 | 4 | April | Q2 | 2025 | FY2025 | 0
20240419 | 2024-04-19 | 2024 | 4 | April | Q2 | 2025 | FY2025 | 0
20240420 | 2024-04-20 | 2024 | 4 | April | Q2 | 2025 | FY2025 | 1
20240421 | 2024-04-21 | 2024 | 4 | April | Q2 | 2025 | FY2025 | 1
20240422 | 2024-04-22 | 2024 | 4 | April | Q2 | 2025 | FY2025 | 0
20240423 | 2024-04-23 | 2024 | 4 | April | Q2 | 2025 | FY2025 | 0
20240424 | 2024-04-24 | 2024 | 4 | April | Q2 | 2025 | FY2025 | 0
20240425 | 2024-04-25 | 2024 | 4 | April | Q2 | 2025 | FY2025 | 0
20240426 | 2024-04-26 | 2024 | 4 | April | Q2 | 2025 | FY2025 | 0
20240427 | 2024-04-27 | 2024 | 4 | April | Q2 | 2025 | FY2025 | 1
20240428 | 2024-04-28 | 2024 | 4 | April | Q2 | 2025 | FY2025 | 1
20240429 | 2024-04-29 | 2024 | 4 | April | Q2 | 2025 | FY2025 | 0
20240430 | 2024-04-30 | 2024 | 4 | April | Q2 | 2025 | FY2025 | 0
20240501 | 2024-05-01 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 0
20240502 | 2024-05-02 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 0
20240503 | 2024-05-03 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 0
20240504 | 2024-05-04 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 1
20240505 | 2024-05-05 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 1
20240506 | 2024-05-06 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 0
20240507 | 2024-05-07 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 0
20240508 | 2024-05-08 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 0
20240509 | 2024-05-09 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 0
20240510 | 2024-05-10 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 0
20240511 | 2024-05-11 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 1
20240512 | 2024-05-12 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 1
20240513 | 2024-05-13 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 0
20240514 | 2024-05-14 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 0
20240515 | 2024-05-15 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 0
20240516 | 2024-05-16 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 0
20240517 | 2024-05-17 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 0
20240518 | 2024-05-18 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 1
20240519 | 2024-05-19 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 1
20240520 | 2024-05-20 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 0
20240521 | 2024-05-21 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 0
20240522 | 2024-05-22 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 0
20240523 | 2024-05-23 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 0
20240524 | 2024-05-24 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 0
20240525 | 2024-05-25 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 1
20240526 | 2024-05-26 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 1
20240527 | 2024-05-27 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 0
20240528 | 2024-05-28 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 0
20240529 | 2024-05-29 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 0
20240530 | 2024-05-30 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 0
20240531 | 2024-05-31 | 2024 | 5 | May | Q2 | 2025 | FY2025 | 0
20240601 | 2024-06-01 | 2024 | 6 | June | Q2 | 2025 | FY2025 | 1
20240602 | 2024-06-02 | 2024 | 6 | June | Q2 | 2025 | FY2025 | 1
20240603 | 2024-06-03 | 2024 | 6 | June | Q2 | 2025 | FY2025 | 0
20240604 | 2024-06-04 | 2024 | 6 | June | Q2 | 2025 | FY2025 | 0
20240605 | 2024-06-05 | 2024 | 6 | June | Q2 | 2025 | FY2025 | 0
20240606 | 2024-06-06 | 2024 | 6 | June | Q2 | 2025 | FY2025 | 0
20240607 | 2024-06-07 | 2024 | 6 | June | Q2 | 2025 | FY2025 | 0
20240608 | 2024-06-08 | 2024 | 6 | June | Q2 | 2025 | FY2025 | 1
20240609 | 2024-06-09 | 2024 | 6 | June | Q2 | 2025 | FY2025 | 1
20240610 | 2024-06-10 | 2024 | 6 | June | Q2 | 2025 | FY2025 | 0
20240611 | 2024-06-11 | 2024 | 6 | June | Q2 | 2025 | FY2025 | 0
20240612 | 2024-06-12 | 2024 | 6 | June | Q2 | 2025 | FY2025 | 0
20240613 | 2024-06-13 | 2024 | 6 | June | Q2 | 2025 | FY2025 | 0
20240614 | 2024-06-14 | 2024 | 6 | June | Q2 | 2025 | FY2025 | 0
20240615 | 2024-06-15 | 2024 | 6 | June | Q2 | 2025 | FY2025 | 1
20240616 | 2024-06-16 | 2024 | 6 | June | Q2 | 2025 | FY2025 | 1
20240617 | 2024-06-17 | 2024 | 6 | June | Q2 | 2025 | FY2025 | 0
20240618 | 2024-06-18 | 2024 | 6 | June | Q2 | 2025 | FY2025 | 0
20240619 | 2024-06-19 | 2024 | 6 | June | Q2 | 2025 | FY2025 | 0
20240620 | 2024-06-20 | 2024 | 6 | June | Q2 | 2025 | FY2025 | 0
20240621 | 2024-06-21 | 2024 | 6 | June | Q2 | 2025 | FY2025 | 0
20240622 | 2024-06-22 | 2024 | 6 | June | Q2 | 2025 | FY2025 | 1
20240623 | 2024-06-23 | 2024 | 6 | June | Q2 | 2025 | FY2025 | 1
20240624 | 2024-06-24 | 2024 | 6 | June | Q2 | 2025 | FY2025 | 0
20240625 | 2024-06-25 | 2024 | 6 | June | Q2 | 2025 | FY2025 | 0
20240626 | 2024-06-26 | 2024 | 6 | June | Q2 | 2025 | FY2025 | 0
20240627 | 2024-06-27 | 2024 | 6 | June | Q2 | 2025 | FY2025 | 0
20240628 | 2024-06-28 | 2024 | 6 | June | Q2 | 2025 | FY2025 | 0
20240629 | 2024-06-29 | 2024 | 6 | June | Q2 | 2025 | FY2025 | 1
20240630 | 2024-06-30 | 2024 | 6 | June | Q2 | 2025 | FY2025 | 1
20240701 | 2024-07-01 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 0
20240702 | 2024-07-02 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 0
20240703 | 2024-07-03 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 0
20240704 | 2024-07-04 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 0
20240705 | 2024-07-05 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 0
20240706 | 2024-07-06 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 1
20240707 | 2024-07-07 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 1
20240708 | 2024-07-08 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 0
20240709 | 2024-07-09 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 0
20240710 | 2024-07-10 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 0
20240711 | 2024-07-11 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 0
20240712 | 2024-07-12 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 0
20240713 | 2024-07-13 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 1
20240714 | 2024-07-14 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 1
20240715 | 2024-07-15 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 0
20240716 | 2024-07-16 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 0
20240717 | 2024-07-17 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 0
20240718 | 2024-07-18 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 0
20240719 | 2024-07-19 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 0
20240720 | 2024-07-20 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 1
20240721 | 2024-07-21 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 1
20240722 | 2024-07-22 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 0
20240723 | 2024-07-23 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 0
20240724 | 2024-07-24 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 0
20240725 | 2024-07-25 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 0
20240726 | 2024-07-26 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 0
20240727 | 2024-07-27 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 1
20240728 | 2024-07-28 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 1
20240729 | 2024-07-29 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 0
20240730 | 2024-07-30 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 0
20240731 | 2024-07-31 | 2024 | 7 | July | Q3 | 2025 | FY2025 | 0
20240801 | 2024-08-01 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 0
20240802 | 2024-08-02 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 0
20240803 | 2024-08-03 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 1
20240804 | 2024-08-04 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 1
20240805 | 2024-08-05 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 0
20240806 | 2024-08-06 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 0
20240807 | 2024-08-07 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 0
20240808 | 2024-08-08 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 0
20240809 | 2024-08-09 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 0
20240810 | 2024-08-10 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 1
20240811 | 2024-08-11 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 1
20240812 | 2024-08-12 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 0
20240813 | 2024-08-13 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 0
20240814 | 2024-08-14 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 0
20240815 | 2024-08-15 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 0
20240816 | 2024-08-16 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 0
20240817 | 2024-08-17 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 1
20240818 | 2024-08-18 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 1
20240819 | 2024-08-19 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 0
20240820 | 2024-08-20 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 0
20240821 | 2024-08-21 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 0
20240822 | 2024-08-22 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 0
20240823 | 2024-08-23 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 0
20240824 | 2024-08-24 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 1
20240825 | 2024-08-25 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 1
20240826 | 2024-08-26 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 0
20240827 | 2024-08-27 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 0
20240828 | 2024-08-28 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 0
20240829 | 2024-08-29 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 0
20240830 | 2024-08-30 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 0
20240831 | 2024-08-31 | 2024 | 8 | August | Q3 | 2025 | FY2025 | 1
20240901 | 2024-09-01 | 2024 | 9 | September | Q3 | 2025 | FY2025 | 1
20240902 | 2024-09-02 | 2024 | 9 | September | Q3 | 2025 | FY2025 | 0
20240903 | 2024-09-03 | 2024 | 9 | September | Q3 | 2025 | FY2025 | 0
20240904 | 2024-09-04 | 2024 | 9 | September | Q3 | 2025 | FY2025 | 0
20240905 | 2024-09-05 | 2024 | 9 | September | Q3 | 2025 | FY2025 | 0
20240906 | 2024-09-06 | 2024 | 9 | September | Q3 | 2025 | FY2025 | 0
20240907 | 2024-09-07 | 2024 | 9 | September | Q3 | 2025 | FY2025 | 1
20240908 | 2024-09-08 | 2024 | 9 | September | Q3 | 2025 | FY2025 | 1
20240909 | 2024-09-09 | 2024 | 9 | September | Q3 | 2025 | FY2025 | 0
20240910 | 2024-09-10 | 2024 | 9 | September | Q3 | 2025 | FY2025 | 0
20240911 | 2024-09-11 | 2024 | 9 | September | Q3 | 2025 | FY2025 | 0
20240912 | 2024-09-12 | 2024 | 9 | September | Q3 | 2025 | FY2025 | 0
20240913 | 2024-09-13 | 2024 | 9 | September | Q3 | 2025 | FY2025 | 0
20240914 | 2024-09-14 | 2024 | 9 | September | Q3 | 2025 | FY2025 | 1
20240915 | 2024-09-15 | 2024 | 9 | September | Q3 | 2025 | FY2025 | 1
20240916 | 2024-09-16 | 2024 | 9 | September | Q3 | 2025 | FY2025 | 0
20240917 | 2024-09-17 | 2024 | 9 | September | Q3 | 2025 | FY2025 | 0
20240918 | 2024-09-18 | 2024 | 9 | September | Q3 | 2025 | FY2025 | 0
20240919 | 2024-09-19 | 2024 | 9 | September | Q3 | 2025 | FY2025 | 0
20240920 | 2024-09-20 | 2024 | 9 | September | Q3 | 2025 | FY2025 | 0
20240921 | 2024-09-21 | 2024 | 9 | September | Q3 | 2025 | FY2025 | 1
20240922 | 2024-09-22 | 2024 | 9 | September | Q3 | 2025 | FY2025 | 1
20240923 | 2024-09-23 | 2024 | 9 | September | Q3 | 2025 | FY2025 | 0
20240924 | 2024-09-24 | 2024 | 9 | September | Q3 | 2025 | FY2025 | 0
20240925 | 2024-09-25 | 2024 | 9 | September | Q3 | 2025 | FY2025 | 0
20240926 | 2024-09-26 | 2024 | 9 | September | Q3 | 2025 | FY2025 | 0
20240927 | 2024-09-27 | 2024 | 9 | September | Q3 | 2025 | FY2025 | 0
20240928 | 2024-09-28 | 2024 | 9 | September | Q3 | 2025 | FY2025 | 1
20240929 | 2024-09-29 | 2024 | 9 | September | Q3 | 2025 | FY2025 | 1
20240930 | 2024-09-30 | 2024 | 9 | September | Q3 | 2025 | FY2025 | 0
20241001 | 2024-10-01 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 0
20241002 | 2024-10-02 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 0
20241003 | 2024-10-03 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 0
20241004 | 2024-10-04 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 0
20241005 | 2024-10-05 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 1
20241006 | 2024-10-06 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 1
20241007 | 2024-10-07 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 0
20241008 | 2024-10-08 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 0
20241009 | 2024-10-09 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 0
20241010 | 2024-10-10 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 0
20241011 | 2024-10-11 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 0
20241012 | 2024-10-12 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 1
20241013 | 2024-10-13 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 1
20241014 | 2024-10-14 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 0
20241015 | 2024-10-15 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 0
20241016 | 2024-10-16 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 0
20241017 | 2024-10-17 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 0
20241018 | 2024-10-18 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 0
20241019 | 2024-10-19 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 1
20241020 | 2024-10-20 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 1
20241021 | 2024-10-21 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 0
20241022 | 2024-10-22 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 0
20241023 | 2024-10-23 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 0
20241024 | 2024-10-24 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 0
20241025 | 2024-10-25 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 0
20241026 | 2024-10-26 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 1
20241027 | 2024-10-27 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 1
20241028 | 2024-10-28 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 0
20241029 | 2024-10-29 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 0
20241030 | 2024-10-30 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 0
20241031 | 2024-10-31 | 2024 | 10 | October | Q4 | 2025 | FY2025 | 0
20241101 | 2024-11-01 | 2024 | 11 | November | Q4 | 2025 | FY2025 | 0
20241102 | 2024-11-02 | 2024 | 11 | November | Q4 | 2025 | FY2025 | 1
20241103 | 2024-11-03 | 2024 | 11 | November | Q4 | 2025 | FY2025 | 1
20241104 | 2024-11-04 | 2024 | 11 | November | Q4 | 2025 | FY2025 | 0
20241105 | 2024-11-05 | 2024 | 11 | November | Q4 | 2025 | FY2025 | 0
20241106 | 2024-11-06 | 2024 | 11 | November | Q4 | 2025 | FY2025 | 0
20241107 | 2024-11-07 | 2024 | 11 | November | Q4 | 2025 | FY2025 | 0
20241108 | 2024-11-08 | 2024 | 11 | November | Q4 | 2025 | FY2025 | 0
20241109 | 2024-11-09 | 2024 | 11 | November | Q4 | 2025 | FY2025 | 1
20241110 | 2024-11-10 | 2024 | 11 | November | Q4 | 2025 | FY2025 | 1
20241111 | 2024-11-11 | 2024 | 11 | November | Q4 | 2025 | FY2025 | 0
20241112 | 2024-11-12 | 2024 | 11 | November | Q4 | 2025 | FY2025 | 0
20241113 | 2024-11-13 | 2024 | 11 | November | Q4 | 2025 | FY2025 | 0
20241114 | 2024-11-14 | 2024 | 11 | November | Q4 | 2025 | FY2025 | 0
20241115 | 2024-11-15 | 2024 | 11 | November | Q4 | 2025 | FY2025 | 0
20241116 | 2024-11-16 | 2024 | 11 | November | Q4 | 2025 | FY2025 | 1
20241117 | 2024-11-17 | 2024 | 11 | November | Q4 | 2025 | FY2025 | 1
20241118 | 2024-11-18 | 2024 | 11 | November | Q4 | 2025 | FY2025 | 0
20241119 | 2024-11-19 | 2024 | 11 | November | Q4 | 2025 | FY2025 | 0
20241120 | 2024-11-20 | 2024 | 11 | November | Q4 | 2025 | FY2025 | 0
20241121 | 2024-11-21 | 2024 | 11 | November | Q4 | 2025 | FY2025 | 0
20241122 | 2024-11-22 | 2024 | 11 | November | Q4 | 2025 | FY2025 | 0
20241123 | 2024-11-23 | 2024 | 11 | November | Q4 | 2025 | FY2025 | 1
20241124 | 2024-11-24 | 2024 | 11 | November | Q4 | 2025 | FY2025 | 1
20241125 | 2024-11-25 | 2024 | 11 | November | Q4 | 2025 | FY2025 | 0
20241126 | 2024-11-26 | 2024 | 11 | November | Q4 | 2025 | FY2025 | 0
20241127 | 2024-11-27 | 2024 | 11 | November | Q4 | 2025 | FY2025 | 0
20241128 | 2024-11-28 | 2024 | 11 | November | Q4 | 2025 | FY2025 | 0
20241129 | 2024-11-29 | 2024 | 11 | November | Q4 | 2025 | FY2025 | 0
20241130 | 2024-11-30 | 2024 | 11 | November | Q4 | 2025 | FY2025 | 1
20241201 | 2024-12-01 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 1
20241202 | 2024-12-02 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 0
20241203 | 2024-12-03 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 0
20241204 | 2024-12-04 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 0
20241205 | 2024-12-05 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 0
20241206 | 2024-12-06 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 0
20241207 | 2024-12-07 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 1
20241208 | 2024-12-08 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 1
20241209 | 2024-12-09 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 0
20241210 | 2024-12-10 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 0
20241211 | 2024-12-11 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 0
20241212 | 2024-12-12 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 0
20241213 | 2024-12-13 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 0
20241214 | 2024-12-14 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 1
20241215 | 2024-12-15 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 1
20241216 | 2024-12-16 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 0
20241217 | 2024-12-17 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 0
20241218 | 2024-12-18 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 0
20241219 | 2024-12-19 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 0
20241220 | 2024-12-20 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 0
20241221 | 2024-12-21 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 1
20241222 | 2024-12-22 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 1
20241223 | 2024-12-23 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 0
20241224 | 2024-12-24 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 0
20241225 | 2024-12-25 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 0
20241226 | 2024-12-26 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 0
20241227 | 2024-12-27 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 0
20241228 | 2024-12-28 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 1
20241229 | 2024-12-29 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 1
20241230 | 2024-12-30 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 0
20241231 | 2024-12-31 | 2024 | 12 | December | Q4 | 2025 | FY2025 | 0
20250101 | 2025-01-01 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 0
20250102 | 2025-01-02 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 0
20250103 | 2025-01-03 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 0
20250104 | 2025-01-04 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 1
20250105 | 2025-01-05 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 1
20250106 | 2025-01-06 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 0
20250107 | 2025-01-07 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 0
20250108 | 2025-01-08 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 0
20250109 | 2025-01-09 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 0
20250110 | 2025-01-10 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 0
20250111 | 2025-01-11 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 1
20250112 | 2025-01-12 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 1
20250113 | 2025-01-13 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 0
20250114 | 2025-01-14 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 0
20250115 | 2025-01-15 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 0
20250116 | 2025-01-16 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 0
20250117 | 2025-01-17 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 0
20250118 | 2025-01-18 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 1
20250119 | 2025-01-19 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 1
20250120 | 2025-01-20 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 0
20250121 | 2025-01-21 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 0
20250122 | 2025-01-22 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 0
20250123 | 2025-01-23 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 0
20250124 | 2025-01-24 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 0
20250125 | 2025-01-25 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 1
20250126 | 2025-01-26 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 1
20250127 | 2025-01-27 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 0
20250128 | 2025-01-28 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 0
20250129 | 2025-01-29 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 0
20250130 | 2025-01-30 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 0
20250131 | 2025-01-31 | 2025 | 1 | January | Q1 | 2025 | FY2025 | 0
20250201 | 2025-02-01 | 2025 | 2 | February | Q1 | 2025 | FY2025 | 1
20250202 | 2025-02-02 | 2025 | 2 | February | Q1 | 2025 | FY2025 | 1
20250203 | 2025-02-03 | 2025 | 2 | February | Q1 | 2025 | FY2025 | 0
20250204 | 2025-02-04 | 2025 | 2 | February | Q1 | 2025 | FY2025 | 0
20250205 | 2025-02-05 | 2025 | 2 | February | Q1 | 2025 | FY2025 | 0
20250206 | 2025-02-06 | 2025 | 2 | February | Q1 | 2025 | FY2025 | 0
20250207 | 2025-02-07 | 2025 | 2 | February | Q1 | 2025 | FY2025 | 0
20250208 | 2025-02-08 | 2025 | 2 | February | Q1 | 2025 | FY2025 | 1
20250209 | 2025-02-09 | 2025 | 2 | February | Q1 | 2025 | FY2025 | 1
20250210 | 2025-02-10 | 2025 | 2 | February | Q1 | 2025 | FY2025 | 0
20250211 | 2025-02-11 | 2025 | 2 | February | Q1 | 2025 | FY2025 | 0
20250212 | 2025-02-12 | 2025 | 2 | February | Q1 | 2025 | FY2025 | 0
20250213 | 2025-02-13 | 2025 | 2 | February | Q1 | 2025 | FY2025 | 0
20250214 | 2025-02-14 | 2025 | 2 | February | Q1 | 2025 | FY2025 | 0
20250215 | 2025-02-15 | 2025 | 2 | February | Q1 | 2025 | FY2025 | 1
20250216 | 2025-02-16 | 2025 | 2 | February | Q1 | 2025 | FY2025 | 1
20250217 | 2025-02-17 | 2025 | 2 | February | Q1 | 2025 | FY2025 | 0
20250218 | 2025-02-18 | 2025 | 2 | February | Q1 | 2025 | FY2025 | 0
20250219 | 2025-02-19 | 2025 | 2 | February | Q1 | 2025 | FY2025 | 0
20250220 | 2025-02-20 | 2025 | 2 | February | Q1 | 2025 | FY2025 | 0
20250221 | 2025-02-21 | 2025 | 2 | February | Q1 | 2025 | FY2025 | 0
20250222 | 2025-02-22 | 2025 | 2 | February | Q1 | 2025 | FY2025 | 1
20250223 | 2025-02-23 | 2025 | 2 | February | Q1 | 2025 | FY2025 | 1
20250224 | 2025-02-24 | 2025 | 2 | February | Q1 | 2025 | FY2025 | 0
20250225 | 2025-02-25 | 2025 | 2 | February | Q1 | 2025 | FY2025 | 0
20250226 | 2025-02-26 | 2025 | 2 | February | Q1 | 2025 | FY2025 | 0
20250227 | 2025-02-27 | 2025 | 2 | February | Q1 | 2025 | FY2025 | 0
20250228 | 2025-02-28 | 2025 | 2 | February | Q1 | 2025 | FY2025 | 0
20250301 | 2025-03-01 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 1
20250302 | 2025-03-02 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 1
20250303 | 2025-03-03 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 0
20250304 | 2025-03-04 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 0
20250305 | 2025-03-05 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 0
20250306 | 2025-03-06 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 0
20250307 | 2025-03-07 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 0
20250308 | 2025-03-08 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 1
20250309 | 2025-03-09 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 1
20250310 | 2025-03-10 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 0
20250311 | 2025-03-11 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 0
20250312 | 2025-03-12 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 0
20250313 | 2025-03-13 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 0
20250314 | 2025-03-14 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 0
20250315 | 2025-03-15 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 1
20250316 | 2025-03-16 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 1
20250317 | 2025-03-17 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 0
20250318 | 2025-03-18 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 0
20250319 | 2025-03-19 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 0
20250320 | 2025-03-20 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 0
20250321 | 2025-03-21 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 0
20250322 | 2025-03-22 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 1
20250323 | 2025-03-23 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 1
20250324 | 2025-03-24 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 0
20250325 | 2025-03-25 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 0
20250326 | 2025-03-26 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 0
20250327 | 2025-03-27 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 0
20250328 | 2025-03-28 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 0
20250329 | 2025-03-29 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 1
20250330 | 2025-03-30 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 1
20250331 | 2025-03-31 | 2025 | 3 | March | Q1 | 2025 | FY2025 | 0
20250401 | 2025-04-01 | 2025 | 4 | April | Q2 | 2026 | FY2026 | 0
20250402 | 2025-04-02 | 2025 | 4 | April | Q2 | 2026 | FY2026 | 0
20250403 | 2025-04-03 | 2025 | 4 | April | Q2 | 2026 | FY2026 | 0
20250404 | 2025-04-04 | 2025 | 4 | April | Q2 | 2026 | FY2026 | 0
20250405 | 2025-04-05 | 2025 | 4 | April | Q2 | 2026 | FY2026 | 1
20250406 | 2025-04-06 | 2025 | 4 | April | Q2 | 2026 | FY2026 | 1
20250407 | 2025-04-07 | 2025 | 4 | April | Q2 | 2026 | FY2026 | 0
20250408 | 2025-04-08 | 2025 | 4 | April | Q2 | 2026 | FY2026 | 0
20250409 | 2025-04-09 | 2025 | 4 | April | Q2 | 2026 | FY2026 | 0
20250410 | 2025-04-10 | 2025 | 4 | April | Q2 | 2026 | FY2026 | 0
20250411 | 2025-04-11 | 2025 | 4 | April | Q2 | 2026 | FY2026 | 0
20250412 | 2025-04-12 | 2025 | 4 | April | Q2 | 2026 | FY2026 | 1
20250413 | 2025-04-13 | 2025 | 4 | April | Q2 | 2026 | FY2026 | 1
20250414 | 2025-04-14 | 2025 | 4 | April | Q2 | 2026 | FY2026 | 0
20250415 | 2025-04-15 | 2025 | 4 | April | Q2 | 2026 | FY2026 | 0
20250416 | 2025-04-16 | 2025 | 4 | April | Q2 | 2026 | FY2026 | 0
20250417 | 2025-04-17 | 2025 | 4 | April | Q2 | 2026 | FY2026 | 0
20250418 | 2025-04-18 | 2025 | 4 | April | Q2 | 2026 | FY2026 | 0
20250419 | 2025-04-19 | 2025 | 4 | April | Q2 | 2026 | FY2026 | 1
20250420 | 2025-04-20 | 2025 | 4 | April | Q2 | 2026 | FY2026 | 1
20250421 | 2025-04-21 | 2025 | 4 | April | Q2 | 2026 | FY2026 | 0
20250422 | 2025-04-22 | 2025 | 4 | April | Q2 | 2026 | FY2026 | 0
20250423 | 2025-04-23 | 2025 | 4 | April | Q2 | 2026 | FY2026 | 0
20250424 | 2025-04-24 | 2025 | 4 | April | Q2 | 2026 | FY2026 | 0
20250425 | 2025-04-25 | 2025 | 4 | April | Q2 | 2026 | FY2026 | 0
20250426 | 2025-04-26 | 2025 | 4 | April | Q2 | 2026 | FY2026 | 1
20250427 | 2025-04-27 | 2025 | 4 | April | Q2 | 2026 | FY2026 | 1
20250428 | 2025-04-28 | 2025 | 4 | April | Q2 | 2026 | FY2026 | 0
20250429 | 2025-04-29 | 2025 | 4 | April | Q2 | 2026 | FY2026 | 0
20250430 | 2025-04-30 | 2025 | 4 | April | Q2 | 2026 | FY2026 | 0
20250501 | 2025-05-01 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 0
20250502 | 2025-05-02 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 0
20250503 | 2025-05-03 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 1
20250504 | 2025-05-04 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 1
20250505 | 2025-05-05 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 0
20250506 | 2025-05-06 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 0
20250507 | 2025-05-07 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 0
20250508 | 2025-05-08 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 0
20250509 | 2025-05-09 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 0
20250510 | 2025-05-10 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 1
20250511 | 2025-05-11 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 1
20250512 | 2025-05-12 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 0
20250513 | 2025-05-13 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 0
20250514 | 2025-05-14 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 0
20250515 | 2025-05-15 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 0
20250516 | 2025-05-16 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 0
20250517 | 2025-05-17 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 1
20250518 | 2025-05-18 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 1
20250519 | 2025-05-19 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 0
20250520 | 2025-05-20 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 0
20250521 | 2025-05-21 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 0
20250522 | 2025-05-22 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 0
20250523 | 2025-05-23 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 0
20250524 | 2025-05-24 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 1
20250525 | 2025-05-25 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 1
20250526 | 2025-05-26 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 0
20250527 | 2025-05-27 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 0
20250528 | 2025-05-28 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 0
20250529 | 2025-05-29 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 0
20250530 | 2025-05-30 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 0
20250531 | 2025-05-31 | 2025 | 5 | May | Q2 | 2026 | FY2026 | 1
20250601 | 2025-06-01 | 2025 | 6 | June | Q2 | 2026 | FY2026 | 1
20250602 | 2025-06-02 | 2025 | 6 | June | Q2 | 2026 | FY2026 | 0
20250603 | 2025-06-03 | 2025 | 6 | June | Q2 | 2026 | FY2026 | 0
20250604 | 2025-06-04 | 2025 | 6 | June | Q2 | 2026 | FY2026 | 0
20250605 | 2025-06-05 | 2025 | 6 | June | Q2 | 2026 | FY2026 | 0
20250606 | 2025-06-06 | 2025 | 6 | June | Q2 | 2026 | FY2026 | 0
20250607 | 2025-06-07 | 2025 | 6 | June | Q2 | 2026 | FY2026 | 1
20250608 | 2025-06-08 | 2025 | 6 | June | Q2 | 2026 | FY2026 | 1
20250609 | 2025-06-09 | 2025 | 6 | June | Q2 | 2026 | FY2026 | 0
20250610 | 2025-06-10 | 2025 | 6 | June | Q2 | 2026 | FY2026 | 0
20250611 | 2025-06-11 | 2025 | 6 | June | Q2 | 2026 | FY2026 | 0
20250612 | 2025-06-12 | 2025 | 6 | June | Q2 | 2026 | FY2026 | 0
20250613 | 2025-06-13 | 2025 | 6 | June | Q2 | 2026 | FY2026 | 0
20250614 | 2025-06-14 | 2025 | 6 | June | Q2 | 2026 | FY2026 | 1
20250615 | 2025-06-15 | 2025 | 6 | June | Q2 | 2026 | FY2026 | 1
20250616 | 2025-06-16 | 2025 | 6 | June | Q2 | 2026 | FY2026 | 0
20250617 | 2025-06-17 | 2025 | 6 | June | Q2 | 2026 | FY2026 | 0
20250618 | 2025-06-18 | 2025 | 6 | June | Q2 | 2026 | FY2026 | 0
20250619 | 2025-06-19 | 2025 | 6 | June | Q2 | 2026 | FY2026 | 0
20250620 | 2025-06-20 | 2025 | 6 | June | Q2 | 2026 | FY2026 | 0
20250621 | 2025-06-21 | 2025 | 6 | June | Q2 | 2026 | FY2026 | 1
20250622 | 2025-06-22 | 2025 | 6 | June | Q2 | 2026 | FY2026 | 1
20250623 | 2025-06-23 | 2025 | 6 | June | Q2 | 2026 | FY2026 | 0
20250624 | 2025-06-24 | 2025 | 6 | June | Q2 | 2026 | FY2026 | 0
20250625 | 2025-06-25 | 2025 | 6 | June | Q2 | 2026 | FY2026 | 0
20250626 | 2025-06-26 | 2025 | 6 | June | Q2 | 2026 | FY2026 | 0
20250627 | 2025-06-27 | 2025 | 6 | June | Q2 | 2026 | FY2026 | 0
20250628 | 2025-06-28 | 2025 | 6 | June | Q2 | 2026 | FY2026 | 1
20250629 | 2025-06-29 | 2025 | 6 | June | Q2 | 2026 | FY2026 | 1
20250630 | 2025-06-30 | 2025 | 6 | June | Q2 | 2026 | FY2026 | 0
20250701 | 2025-07-01 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 0
20250702 | 2025-07-02 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 0
20250703 | 2025-07-03 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 0
20250704 | 2025-07-04 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 0
20250705 | 2025-07-05 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 1
20250706 | 2025-07-06 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 1
20250707 | 2025-07-07 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 0
20250708 | 2025-07-08 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 0
20250709 | 2025-07-09 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 0
20250710 | 2025-07-10 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 0
20250711 | 2025-07-11 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 0
20250712 | 2025-07-12 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 1
20250713 | 2025-07-13 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 1
20250714 | 2025-07-14 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 0
20250715 | 2025-07-15 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 0
20250716 | 2025-07-16 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 0
20250717 | 2025-07-17 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 0
20250718 | 2025-07-18 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 0
20250719 | 2025-07-19 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 1
20250720 | 2025-07-20 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 1
20250721 | 2025-07-21 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 0
20250722 | 2025-07-22 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 0
20250723 | 2025-07-23 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 0
20250724 | 2025-07-24 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 0
20250725 | 2025-07-25 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 0
20250726 | 2025-07-26 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 1
20250727 | 2025-07-27 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 1
20250728 | 2025-07-28 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 0
20250729 | 2025-07-29 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 0
20250730 | 2025-07-30 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 0
20250731 | 2025-07-31 | 2025 | 7 | July | Q3 | 2026 | FY2026 | 0
20250801 | 2025-08-01 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 0
20250802 | 2025-08-02 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 1
20250803 | 2025-08-03 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 1
20250804 | 2025-08-04 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 0
20250805 | 2025-08-05 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 0
20250806 | 2025-08-06 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 0
20250807 | 2025-08-07 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 0
20250808 | 2025-08-08 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 0
20250809 | 2025-08-09 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 1
20250810 | 2025-08-10 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 1
20250811 | 2025-08-11 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 0
20250812 | 2025-08-12 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 0
20250813 | 2025-08-13 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 0
20250814 | 2025-08-14 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 0
20250815 | 2025-08-15 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 0
20250816 | 2025-08-16 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 1
20250817 | 2025-08-17 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 1
20250818 | 2025-08-18 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 0
20250819 | 2025-08-19 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 0
20250820 | 2025-08-20 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 0
20250821 | 2025-08-21 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 0
20250822 | 2025-08-22 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 0
20250823 | 2025-08-23 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 1
20250824 | 2025-08-24 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 1
20250825 | 2025-08-25 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 0
20250826 | 2025-08-26 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 0
20250827 | 2025-08-27 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 0
20250828 | 2025-08-28 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 0
20250829 | 2025-08-29 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 0
20250830 | 2025-08-30 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 1
20250831 | 2025-08-31 | 2025 | 8 | August | Q3 | 2026 | FY2026 | 1
20250901 | 2025-09-01 | 2025 | 9 | September | Q3 | 2026 | FY2026 | 0
20250902 | 2025-09-02 | 2025 | 9 | September | Q3 | 2026 | FY2026 | 0
20250903 | 2025-09-03 | 2025 | 9 | September | Q3 | 2026 | FY2026 | 0
20250904 | 2025-09-04 | 2025 | 9 | September | Q3 | 2026 | FY2026 | 0
20250905 | 2025-09-05 | 2025 | 9 | September | Q3 | 2026 | FY2026 | 0
20250906 | 2025-09-06 | 2025 | 9 | September | Q3 | 2026 | FY2026 | 1
20250907 | 2025-09-07 | 2025 | 9 | September | Q3 | 2026 | FY2026 | 1
20250908 | 2025-09-08 | 2025 | 9 | September | Q3 | 2026 | FY2026 | 0
20250909 | 2025-09-09 | 2025 | 9 | September | Q3 | 2026 | FY2026 | 0
20250910 | 2025-09-10 | 2025 | 9 | September | Q3 | 2026 | FY2026 | 0
20250911 | 2025-09-11 | 2025 | 9 | September | Q3 | 2026 | FY2026 | 0
20250912 | 2025-09-12 | 2025 | 9 | September | Q3 | 2026 | FY2026 | 0
20250913 | 2025-09-13 | 2025 | 9 | September | Q3 | 2026 | FY2026 | 1
20250914 | 2025-09-14 | 2025 | 9 | September | Q3 | 2026 | FY2026 | 1
20250915 | 2025-09-15 | 2025 | 9 | September | Q3 | 2026 | FY2026 | 0
20250916 | 2025-09-16 | 2025 | 9 | September | Q3 | 2026 | FY2026 | 0
20250917 | 2025-09-17 | 2025 | 9 | September | Q3 | 2026 | FY2026 | 0
20250918 | 2025-09-18 | 2025 | 9 | September | Q3 | 2026 | FY2026 | 0
20250919 | 2025-09-19 | 2025 | 9 | September | Q3 | 2026 | FY2026 | 0
20250920 | 2025-09-20 | 2025 | 9 | September | Q3 | 2026 | FY2026 | 1
20250921 | 2025-09-21 | 2025 | 9 | September | Q3 | 2026 | FY2026 | 1
20250922 | 2025-09-22 | 2025 | 9 | September | Q3 | 2026 | FY2026 | 0
20250923 | 2025-09-23 | 2025 | 9 | September | Q3 | 2026 | FY2026 | 0
20250924 | 2025-09-24 | 2025 | 9 | September | Q3 | 2026 | FY2026 | 0
20250925 | 2025-09-25 | 2025 | 9 | September | Q3 | 2026 | FY2026 | 0
20250926 | 2025-09-26 | 2025 | 9 | September | Q3 | 2026 | FY2026 | 0
20250927 | 2025-09-27 | 2025 | 9 | September | Q3 | 2026 | FY2026 | 1
20250928 | 2025-09-28 | 2025 | 9 | September | Q3 | 2026 | FY2026 | 1
20250929 | 2025-09-29 | 2025 | 9 | September | Q3 | 2026 | FY2026 | 0
20250930 | 2025-09-30 | 2025 | 9 | September | Q3 | 2026 | FY2026 | 0
20251001 | 2025-10-01 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 0
20251002 | 2025-10-02 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 0
20251003 | 2025-10-03 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 0
20251004 | 2025-10-04 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 1
20251005 | 2025-10-05 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 1
20251006 | 2025-10-06 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 0
20251007 | 2025-10-07 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 0
20251008 | 2025-10-08 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 0
20251009 | 2025-10-09 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 0
20251010 | 2025-10-10 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 0
20251011 | 2025-10-11 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 1
20251012 | 2025-10-12 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 1
20251013 | 2025-10-13 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 0
20251014 | 2025-10-14 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 0
20251015 | 2025-10-15 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 0
20251016 | 2025-10-16 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 0
20251017 | 2025-10-17 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 0
20251018 | 2025-10-18 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 1
20251019 | 2025-10-19 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 1
20251020 | 2025-10-20 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 0
20251021 | 2025-10-21 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 0
20251022 | 2025-10-22 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 0
20251023 | 2025-10-23 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 0
20251024 | 2025-10-24 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 0
20251025 | 2025-10-25 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 1
20251026 | 2025-10-26 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 1
20251027 | 2025-10-27 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 0
20251028 | 2025-10-28 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 0
20251029 | 2025-10-29 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 0
20251030 | 2025-10-30 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 0
20251031 | 2025-10-31 | 2025 | 10 | October | Q4 | 2026 | FY2026 | 0
20251101 | 2025-11-01 | 2025 | 11 | November | Q4 | 2026 | FY2026 | 1
20251102 | 2025-11-02 | 2025 | 11 | November | Q4 | 2026 | FY2026 | 1
20251103 | 2025-11-03 | 2025 | 11 | November | Q4 | 2026 | FY2026 | 0
20251104 | 2025-11-04 | 2025 | 11 | November | Q4 | 2026 | FY2026 | 0
20251105 | 2025-11-05 | 2025 | 11 | November | Q4 | 2026 | FY2026 | 0
20251106 | 2025-11-06 | 2025 | 11 | November | Q4 | 2026 | FY2026 | 0
20251107 | 2025-11-07 | 2025 | 11 | November | Q4 | 2026 | FY2026 | 0
20251108 | 2025-11-08 | 2025 | 11 | November | Q4 | 2026 | FY2026 | 1
20251109 | 2025-11-09 | 2025 | 11 | November | Q4 | 2026 | FY2026 | 1
20251110 | 2025-11-10 | 2025 | 11 | November | Q4 | 2026 | FY2026 | 0
20251111 | 2025-11-11 | 2025 | 11 | November | Q4 | 2026 | FY2026 | 0
20251112 | 2025-11-12 | 2025 | 11 | November | Q4 | 2026 | FY2026 | 0
20251113 | 2025-11-13 | 2025 | 11 | November | Q4 | 2026 | FY2026 | 0
20251114 | 2025-11-14 | 2025 | 11 | November | Q4 | 2026 | FY2026 | 0
20251115 | 2025-11-15 | 2025 | 11 | November | Q4 | 2026 | FY2026 | 1
20251116 | 2025-11-16 | 2025 | 11 | November | Q4 | 2026 | FY2026 | 1
20251117 | 2025-11-17 | 2025 | 11 | November | Q4 | 2026 | FY2026 | 0
20251118 | 2025-11-18 | 2025 | 11 | November | Q4 | 2026 | FY2026 | 0
20251119 | 2025-11-19 | 2025 | 11 | November | Q4 | 2026 | FY2026 | 0
20251120 | 2025-11-20 | 2025 | 11 | November | Q4 | 2026 | FY2026 | 0
20251121 | 2025-11-21 | 2025 | 11 | November | Q4 | 2026 | FY2026 | 0
20251122 | 2025-11-22 | 2025 | 11 | November | Q4 | 2026 | FY2026 | 1
20251123 | 2025-11-23 | 2025 | 11 | November | Q4 | 2026 | FY2026 | 1
20251124 | 2025-11-24 | 2025 | 11 | November | Q4 | 2026 | FY2026 | 0
20251125 | 2025-11-25 | 2025 | 11 | November | Q4 | 2026 | FY2026 | 0
20251126 | 2025-11-26 | 2025 | 11 | November | Q4 | 2026 | FY2026 | 0
20251127 | 2025-11-27 | 2025 | 11 | November | Q4 | 2026 | FY2026 | 0
20251128 | 2025-11-28 | 2025 | 11 | November | Q4 | 2026 | FY2026 | 0
20251129 | 2025-11-29 | 2025 | 11 | November | Q4 | 2026 | FY2026 | 1
20251130 | 2025-11-30 | 2025 | 11 | November | Q4 | 2026 | FY2026 | 1
20251201 | 2025-12-01 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 0
20251202 | 2025-12-02 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 0
20251203 | 2025-12-03 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 0
20251204 | 2025-12-04 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 0
20251205 | 2025-12-05 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 0
20251206 | 2025-12-06 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 1
20251207 | 2025-12-07 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 1
20251208 | 2025-12-08 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 0
20251209 | 2025-12-09 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 0
20251210 | 2025-12-10 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 0
20251211 | 2025-12-11 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 0
20251212 | 2025-12-12 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 0
20251213 | 2025-12-13 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 1
20251214 | 2025-12-14 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 1
20251215 | 2025-12-15 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 0
20251216 | 2025-12-16 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 0
20251217 | 2025-12-17 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 0
20251218 | 2025-12-18 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 0
20251219 | 2025-12-19 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 0
20251220 | 2025-12-20 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 1
20251221 | 2025-12-21 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 1
20251222 | 2025-12-22 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 0
20251223 | 2025-12-23 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 0
20251224 | 2025-12-24 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 0
20251225 | 2025-12-25 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 0
20251226 | 2025-12-26 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 0
20251227 | 2025-12-27 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 1
20251228 | 2025-12-28 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 1
20251229 | 2025-12-29 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 0
20251230 | 2025-12-30 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 0
20251231 | 2025-12-31 | 2025 | 12 | December | Q4 | 2026 | FY2026 | 0
20260101 | 2026-01-01 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 0
20260102 | 2026-01-02 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 0
20260103 | 2026-01-03 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 1
20260104 | 2026-01-04 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 1
20260105 | 2026-01-05 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 0
20260106 | 2026-01-06 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 0
20260107 | 2026-01-07 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 0
20260108 | 2026-01-08 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 0
20260109 | 2026-01-09 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 0
20260110 | 2026-01-10 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 1
20260111 | 2026-01-11 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 1
20260112 | 2026-01-12 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 0
20260113 | 2026-01-13 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 0
20260114 | 2026-01-14 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 0
20260115 | 2026-01-15 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 0
20260116 | 2026-01-16 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 0
20260117 | 2026-01-17 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 1
20260118 | 2026-01-18 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 1
20260119 | 2026-01-19 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 0
20260120 | 2026-01-20 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 0
20260121 | 2026-01-21 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 0
20260122 | 2026-01-22 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 0
20260123 | 2026-01-23 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 0
20260124 | 2026-01-24 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 1
20260125 | 2026-01-25 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 1
20260126 | 2026-01-26 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 0
20260127 | 2026-01-27 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 0
20260128 | 2026-01-28 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 0
20260129 | 2026-01-29 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 0
20260130 | 2026-01-30 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 0
20260131 | 2026-01-31 | 2026 | 1 | January | Q1 | 2026 | FY2026 | 1
20260201 | 2026-02-01 | 2026 | 2 | February | Q1 | 2026 | FY2026 | 1
20260202 | 2026-02-02 | 2026 | 2 | February | Q1 | 2026 | FY2026 | 0
20260203 | 2026-02-03 | 2026 | 2 | February | Q1 | 2026 | FY2026 | 0
20260204 | 2026-02-04 | 2026 | 2 | February | Q1 | 2026 | FY2026 | 0
20260205 | 2026-02-05 | 2026 | 2 | February | Q1 | 2026 | FY2026 | 0
20260206 | 2026-02-06 | 2026 | 2 | February | Q1 | 2026 | FY2026 | 0
20260207 | 2026-02-07 | 2026 | 2 | February | Q1 | 2026 | FY2026 | 1
20260208 | 2026-02-08 | 2026 | 2 | February | Q1 | 2026 | FY2026 | 1
20260209 | 2026-02-09 | 2026 | 2 | February | Q1 | 2026 | FY2026 | 0
20260210 | 2026-02-10 | 2026 | 2 | February | Q1 | 2026 | FY2026 | 0
20260211 | 2026-02-11 | 2026 | 2 | February | Q1 | 2026 | FY2026 | 0
20260212 | 2026-02-12 | 2026 | 2 | February | Q1 | 2026 | FY2026 | 0
20260213 | 2026-02-13 | 2026 | 2 | February | Q1 | 2026 | FY2026 | 0
20260214 | 2026-02-14 | 2026 | 2 | February | Q1 | 2026 | FY2026 | 1
20260215 | 2026-02-15 | 2026 | 2 | February | Q1 | 2026 | FY2026 | 1
20260216 | 2026-02-16 | 2026 | 2 | February | Q1 | 2026 | FY2026 | 0
20260217 | 2026-02-17 | 2026 | 2 | February | Q1 | 2026 | FY2026 | 0
20260218 | 2026-02-18 | 2026 | 2 | February | Q1 | 2026 | FY2026 | 0
20260219 | 2026-02-19 | 2026 | 2 | February | Q1 | 2026 | FY2026 | 0
20260220 | 2026-02-20 | 2026 | 2 | February | Q1 | 2026 | FY2026 | 0
20260221 | 2026-02-21 | 2026 | 2 | February | Q1 | 2026 | FY2026 | 1
20260222 | 2026-02-22 | 2026 | 2 | February | Q1 | 2026 | FY2026 | 1
20260223 | 2026-02-23 | 2026 | 2 | February | Q1 | 2026 | FY2026 | 0
20260224 | 2026-02-24 | 2026 | 2 | February | Q1 | 2026 | FY2026 | 0
20260225 | 2026-02-25 | 2026 | 2 | February | Q1 | 2026 | FY2026 | 0
20260226 | 2026-02-26 | 2026 | 2 | February | Q1 | 2026 | FY2026 | 0
20260227 | 2026-02-27 | 2026 | 2 | February | Q1 | 2026 | FY2026 | 0
20260228 | 2026-02-28 | 2026 | 2 | February | Q1 | 2026 | FY2026 | 1
20260301 | 2026-03-01 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 1
20260302 | 2026-03-02 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 0
20260303 | 2026-03-03 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 0
20260304 | 2026-03-04 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 0
20260305 | 2026-03-05 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 0
20260306 | 2026-03-06 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 0
20260307 | 2026-03-07 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 1
20260308 | 2026-03-08 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 1
20260309 | 2026-03-09 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 0
20260310 | 2026-03-10 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 0
20260311 | 2026-03-11 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 0
20260312 | 2026-03-12 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 0
20260313 | 2026-03-13 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 0
20260314 | 2026-03-14 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 1
20260315 | 2026-03-15 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 1
20260316 | 2026-03-16 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 0
20260317 | 2026-03-17 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 0
20260318 | 2026-03-18 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 0
20260319 | 2026-03-19 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 0
20260320 | 2026-03-20 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 0
20260321 | 2026-03-21 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 1
20260322 | 2026-03-22 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 1
20260323 | 2026-03-23 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 0
20260324 | 2026-03-24 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 0
20260325 | 2026-03-25 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 0
20260326 | 2026-03-26 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 0
20260327 | 2026-03-27 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 0
20260328 | 2026-03-28 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 1
20260329 | 2026-03-29 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 1
20260330 | 2026-03-30 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 0
20260331 | 2026-03-31 | 2026 | 3 | March | Q1 | 2026 | FY2026 | 0
20260401 | 2026-04-01 | 2026 | 4 | April | Q2 | 2027 | FY2027 | 0
20260402 | 2026-04-02 | 2026 | 4 | April | Q2 | 2027 | FY2027 | 0
20260403 | 2026-04-03 | 2026 | 4 | April | Q2 | 2027 | FY2027 | 0
20260404 | 2026-04-04 | 2026 | 4 | April | Q2 | 2027 | FY2027 | 1
20260405 | 2026-04-05 | 2026 | 4 | April | Q2 | 2027 | FY2027 | 1
20260406 | 2026-04-06 | 2026 | 4 | April | Q2 | 2027 | FY2027 | 0
20260407 | 2026-04-07 | 2026 | 4 | April | Q2 | 2027 | FY2027 | 0
20260408 | 2026-04-08 | 2026 | 4 | April | Q2 | 2027 | FY2027 | 0
20260409 | 2026-04-09 | 2026 | 4 | April | Q2 | 2027 | FY2027 | 0
20260410 | 2026-04-10 | 2026 | 4 | April | Q2 | 2027 | FY2027 | 0
20260411 | 2026-04-11 | 2026 | 4 | April | Q2 | 2027 | FY2027 | 1
20260412 | 2026-04-12 | 2026 | 4 | April | Q2 | 2027 | FY2027 | 1
20260413 | 2026-04-13 | 2026 | 4 | April | Q2 | 2027 | FY2027 | 0
20260414 | 2026-04-14 | 2026 | 4 | April | Q2 | 2027 | FY2027 | 0
20260415 | 2026-04-15 | 2026 | 4 | April | Q2 | 2027 | FY2027 | 0
20260416 | 2026-04-16 | 2026 | 4 | April | Q2 | 2027 | FY2027 | 0
20260417 | 2026-04-17 | 2026 | 4 | April | Q2 | 2027 | FY2027 | 0
20260418 | 2026-04-18 | 2026 | 4 | April | Q2 | 2027 | FY2027 | 1
20260419 | 2026-04-19 | 2026 | 4 | April | Q2 | 2027 | FY2027 | 1
20260420 | 2026-04-20 | 2026 | 4 | April | Q2 | 2027 | FY2027 | 0
20260421 | 2026-04-21 | 2026 | 4 | April | Q2 | 2027 | FY2027 | 0
20260422 | 2026-04-22 | 2026 | 4 | April | Q2 | 2027 | FY2027 | 0
20260423 | 2026-04-23 | 2026 | 4 | April | Q2 | 2027 | FY2027 | 0
20260424 | 2026-04-24 | 2026 | 4 | April | Q2 | 2027 | FY2027 | 0
20260425 | 2026-04-25 | 2026 | 4 | April | Q2 | 2027 | FY2027 | 1
20260426 | 2026-04-26 | 2026 | 4 | April | Q2 | 2027 | FY2027 | 1
20260427 | 2026-04-27 | 2026 | 4 | April | Q2 | 2027 | FY2027 | 0
20260428 | 2026-04-28 | 2026 | 4 | April | Q2 | 2027 | FY2027 | 0
20260429 | 2026-04-29 | 2026 | 4 | April | Q2 | 2027 | FY2027 | 0
20260430 | 2026-04-30 | 2026 | 4 | April | Q2 | 2027 | FY2027 | 0
20260501 | 2026-05-01 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 0
20260502 | 2026-05-02 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 1
20260503 | 2026-05-03 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 1
20260504 | 2026-05-04 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 0
20260505 | 2026-05-05 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 0
20260506 | 2026-05-06 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 0
20260507 | 2026-05-07 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 0
20260508 | 2026-05-08 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 0
20260509 | 2026-05-09 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 1
20260510 | 2026-05-10 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 1
20260511 | 2026-05-11 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 0
20260512 | 2026-05-12 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 0
20260513 | 2026-05-13 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 0
20260514 | 2026-05-14 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 0
20260515 | 2026-05-15 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 0
20260516 | 2026-05-16 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 1
20260517 | 2026-05-17 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 1
20260518 | 2026-05-18 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 0
20260519 | 2026-05-19 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 0
20260520 | 2026-05-20 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 0
20260521 | 2026-05-21 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 0
20260522 | 2026-05-22 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 0
20260523 | 2026-05-23 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 1
20260524 | 2026-05-24 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 1
20260525 | 2026-05-25 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 0
20260526 | 2026-05-26 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 0
20260527 | 2026-05-27 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 0
20260528 | 2026-05-28 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 0
20260529 | 2026-05-29 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 0
20260530 | 2026-05-30 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 1
20260531 | 2026-05-31 | 2026 | 5 | May | Q2 | 2027 | FY2027 | 1
20260601 | 2026-06-01 | 2026 | 6 | June | Q2 | 2027 | FY2027 | 0
20260602 | 2026-06-02 | 2026 | 6 | June | Q2 | 2027 | FY2027 | 0
20260603 | 2026-06-03 | 2026 | 6 | June | Q2 | 2027 | FY2027 | 0
20260604 | 2026-06-04 | 2026 | 6 | June | Q2 | 2027 | FY2027 | 0
20260605 | 2026-06-05 | 2026 | 6 | June | Q2 | 2027 | FY2027 | 0
20260606 | 2026-06-06 | 2026 | 6 | June | Q2 | 2027 | FY2027 | 1
20260607 | 2026-06-07 | 2026 | 6 | June | Q2 | 2027 | FY2027 | 1
20260608 | 2026-06-08 | 2026 | 6 | June | Q2 | 2027 | FY2027 | 0
20260609 | 2026-06-09 | 2026 | 6 | June | Q2 | 2027 | FY2027 | 0
20260610 | 2026-06-10 | 2026 | 6 | June | Q2 | 2027 | FY2027 | 0
20260611 | 2026-06-11 | 2026 | 6 | June | Q2 | 2027 | FY2027 | 0
20260612 | 2026-06-12 | 2026 | 6 | June | Q2 | 2027 | FY2027 | 0
20260613 | 2026-06-13 | 2026 | 6 | June | Q2 | 2027 | FY2027 | 1
20260614 | 2026-06-14 | 2026 | 6 | June | Q2 | 2027 | FY2027 | 1
20260615 | 2026-06-15 | 2026 | 6 | June | Q2 | 2027 | FY2027 | 0
20260616 | 2026-06-16 | 2026 | 6 | June | Q2 | 2027 | FY2027 | 0
20260617 | 2026-06-17 | 2026 | 6 | June | Q2 | 2027 | FY2027 | 0
20260618 | 2026-06-18 | 2026 | 6 | June | Q2 | 2027 | FY2027 | 0
20260619 | 2026-06-19 | 2026 | 6 | June | Q2 | 2027 | FY2027 | 0
20260620 | 2026-06-20 | 2026 | 6 | June | Q2 | 2027 | FY2027 | 1
20260621 | 2026-06-21 | 2026 | 6 | June | Q2 | 2027 | FY2027 | 1
20260622 | 2026-06-22 | 2026 | 6 | June | Q2 | 2027 | FY2027 | 0
20260623 | 2026-06-23 | 2026 | 6 | June | Q2 | 2027 | FY2027 | 0
20260624 | 2026-06-24 | 2026 | 6 | June | Q2 | 2027 | FY2027 | 0
20260625 | 2026-06-25 | 2026 | 6 | June | Q2 | 2027 | FY2027 | 0
20260626 | 2026-06-26 | 2026 | 6 | June | Q2 | 2027 | FY2027 | 0
20260627 | 2026-06-27 | 2026 | 6 | June | Q2 | 2027 | FY2027 | 1
20260628 | 2026-06-28 | 2026 | 6 | June | Q2 | 2027 | FY2027 | 1
20260629 | 2026-06-29 | 2026 | 6 | June | Q2 | 2027 | FY2027 | 0
20260630 | 2026-06-30 | 2026 | 6 | June | Q2 | 2027 | FY2027 | 0
20260701 | 2026-07-01 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 0
20260702 | 2026-07-02 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 0
20260703 | 2026-07-03 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 0
20260704 | 2026-07-04 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 1
20260705 | 2026-07-05 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 1
20260706 | 2026-07-06 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 0
20260707 | 2026-07-07 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 0
20260708 | 2026-07-08 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 0
20260709 | 2026-07-09 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 0
20260710 | 2026-07-10 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 0
20260711 | 2026-07-11 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 1
20260712 | 2026-07-12 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 1
20260713 | 2026-07-13 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 0
20260714 | 2026-07-14 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 0
20260715 | 2026-07-15 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 0
20260716 | 2026-07-16 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 0
20260717 | 2026-07-17 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 0
20260718 | 2026-07-18 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 1
20260719 | 2026-07-19 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 1
20260720 | 2026-07-20 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 0
20260721 | 2026-07-21 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 0
20260722 | 2026-07-22 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 0
20260723 | 2026-07-23 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 0
20260724 | 2026-07-24 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 0
20260725 | 2026-07-25 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 1
20260726 | 2026-07-26 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 1
20260727 | 2026-07-27 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 0
20260728 | 2026-07-28 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 0
20260729 | 2026-07-29 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 0
20260730 | 2026-07-30 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 0
20260731 | 2026-07-31 | 2026 | 7 | July | Q3 | 2027 | FY2027 | 0
20260801 | 2026-08-01 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 1
20260802 | 2026-08-02 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 1
20260803 | 2026-08-03 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 0
20260804 | 2026-08-04 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 0
20260805 | 2026-08-05 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 0
20260806 | 2026-08-06 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 0
20260807 | 2026-08-07 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 0
20260808 | 2026-08-08 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 1
20260809 | 2026-08-09 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 1
20260810 | 2026-08-10 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 0
20260811 | 2026-08-11 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 0
20260812 | 2026-08-12 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 0
20260813 | 2026-08-13 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 0
20260814 | 2026-08-14 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 0
20260815 | 2026-08-15 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 1
20260816 | 2026-08-16 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 1
20260817 | 2026-08-17 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 0
20260818 | 2026-08-18 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 0
20260819 | 2026-08-19 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 0
20260820 | 2026-08-20 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 0
20260821 | 2026-08-21 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 0
20260822 | 2026-08-22 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 1
20260823 | 2026-08-23 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 1
20260824 | 2026-08-24 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 0
20260825 | 2026-08-25 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 0
20260826 | 2026-08-26 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 0
20260827 | 2026-08-27 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 0
20260828 | 2026-08-28 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 0
20260829 | 2026-08-29 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 1
20260830 | 2026-08-30 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 1
20260831 | 2026-08-31 | 2026 | 8 | August | Q3 | 2027 | FY2027 | 0
20260901 | 2026-09-01 | 2026 | 9 | September | Q3 | 2027 | FY2027 | 0
20260902 | 2026-09-02 | 2026 | 9 | September | Q3 | 2027 | FY2027 | 0
20260903 | 2026-09-03 | 2026 | 9 | September | Q3 | 2027 | FY2027 | 0
20260904 | 2026-09-04 | 2026 | 9 | September | Q3 | 2027 | FY2027 | 0
20260905 | 2026-09-05 | 2026 | 9 | September | Q3 | 2027 | FY2027 | 1
20260906 | 2026-09-06 | 2026 | 9 | September | Q3 | 2027 | FY2027 | 1
20260907 | 2026-09-07 | 2026 | 9 | September | Q3 | 2027 | FY2027 | 0
20260908 | 2026-09-08 | 2026 | 9 | September | Q3 | 2027 | FY2027 | 0
20260909 | 2026-09-09 | 2026 | 9 | September | Q3 | 2027 | FY2027 | 0
20260910 | 2026-09-10 | 2026 | 9 | September | Q3 | 2027 | FY2027 | 0
20260911 | 2026-09-11 | 2026 | 9 | September | Q3 | 2027 | FY2027 | 0
20260912 | 2026-09-12 | 2026 | 9 | September | Q3 | 2027 | FY2027 | 1
20260913 | 2026-09-13 | 2026 | 9 | September | Q3 | 2027 | FY2027 | 1
20260914 | 2026-09-14 | 2026 | 9 | September | Q3 | 2027 | FY2027 | 0
20260915 | 2026-09-15 | 2026 | 9 | September | Q3 | 2027 | FY2027 | 0
20260916 | 2026-09-16 | 2026 | 9 | September | Q3 | 2027 | FY2027 | 0
20260917 | 2026-09-17 | 2026 | 9 | September | Q3 | 2027 | FY2027 | 0
20260918 | 2026-09-18 | 2026 | 9 | September | Q3 | 2027 | FY2027 | 0
20260919 | 2026-09-19 | 2026 | 9 | September | Q3 | 2027 | FY2027 | 1
20260920 | 2026-09-20 | 2026 | 9 | September | Q3 | 2027 | FY2027 | 1
20260921 | 2026-09-21 | 2026 | 9 | September | Q3 | 2027 | FY2027 | 0
20260922 | 2026-09-22 | 2026 | 9 | September | Q3 | 2027 | FY2027 | 0
20260923 | 2026-09-23 | 2026 | 9 | September | Q3 | 2027 | FY2027 | 0
20260924 | 2026-09-24 | 2026 | 9 | September | Q3 | 2027 | FY2027 | 0
20260925 | 2026-09-25 | 2026 | 9 | September | Q3 | 2027 | FY2027 | 0
20260926 | 2026-09-26 | 2026 | 9 | September | Q3 | 2027 | FY2027 | 1
20260927 | 2026-09-27 | 2026 | 9 | September | Q3 | 2027 | FY2027 | 1
20260928 | 2026-09-28 | 2026 | 9 | September | Q3 | 2027 | FY2027 | 0
20260929 | 2026-09-29 | 2026 | 9 | September | Q3 | 2027 | FY2027 | 0
20260930 | 2026-09-30 | 2026 | 9 | September | Q3 | 2027 | FY2027 | 0

## DimProgramme
ProgrammeKey | ProgrammeName | PortfolioCategory | LeadBusinessUnitKey
1 | Customer Experience Renewal | Growth | 1
2 | Cloud and Core Modernisation | Technology | 4
3 | Finance Transformation | Efficiency | 2
4 | Operational Excellence | Efficiency | 3
5 | Cyber Resilience | Risk | 5
6 | Data and AI Enablement | Technology | 4
7 | Regulatory Readiness | Risk | 5
8 | Future Workforce | People | 6
9 | Sustainable Operations | ESG | 8
10 | Supply Network Renewal | Operations | 7

## DimBusinessUnit
BusinessUnitKey | BusinessUnitName | Division | PrimaryValueDriver
1 | Customer & Digital | Commercial | Revenue Growth
2 | Finance | Corporate Services | Efficiency
3 | Operations | Core Operations | Resilience
4 | Technology | Enterprise Technology | Modernisation
5 | Risk & Compliance | Corporate Services | Compliance
6 | People & Culture | Corporate Services | Workforce
7 | Supply Chain | Core Operations | Efficiency
8 | Sustainability | Strategy | ESG

## DimEmployee
EmployeeKey | EmployeeName | PortfolioRole | Seniority | HomeBusinessUnitKey
1 | Nora Bennett | Project Manager | Principal | 1
2 | Lena Costa | Project Manager | Lead | 2
3 | Daniel Silva | Project Manager | Director | 3
4 | Elena Clarke | Project Manager | Principal | 4
5 | Leo Navarro | Project Manager | Senior | 5
6 | Daniel Rossi | Project Manager | Lead | 6
7 | Grace Rossi | Project Manager | Senior | 7
8 | Nora Laurent | Project Manager | Senior | 8
9 | Laura Nowak | Project Manager | Director | 1
10 | Alex Bennett | Project Manager | Lead | 2
11 | Julia Bennett | Project Manager | Director | 3
12 | Ines Bennett | Project Manager | Senior | 4
13 | Elena Laurent | Project Manager | Director | 5
14 | Samuel Silva | Project Manager | Lead | 6
15 | Leo Petrov | Project Manager | Lead | 7
16 | Eva Martin | Project Manager | Director | 8
17 | Alice Silva | Project Manager | Senior | 1
18 | Felix Petrov | Project Manager | Senior | 2
19 | Sofia Weber | Project Manager | Principal | 3
20 | Sofia Martin | Project Manager | Lead | 4
21 | Lucas Murphy | Project Manager | Director | 5
22 | Samuel Dubois | Project Manager | Principal | 6
23 | Marco Morgan | Project Manager | Director | 7
24 | Marco Meyer | Project Manager | Director | 8
25 | Lucas Dubois | Executive Sponsor | Principal | 1
26 | Arthur Silva | Executive Sponsor | Director | 2
27 | Isla Murphy | Executive Sponsor | Director | 3
28 | Ines Bennett | Executive Sponsor | Principal | 4
29 | Clara Silva | Executive Sponsor | Senior | 5
30 | Grace Jansen | Executive Sponsor | Lead | 6
31 | Marco Laurent | Executive Sponsor | Principal | 7
32 | Amelia Rossi | Executive Sponsor | Principal | 8
33 | Nora Morgan | Executive Sponsor | Senior | 1
34 | Alex Dubois | Executive Sponsor | Director | 2
35 | Theo Nowak | Executive Sponsor | Lead | 3
36 | Grace Clarke | Executive Sponsor | Director | 4

## DimLocation
LocationKey | City | Country | Region | Latitude | Longitude
1 | London | United Kingdom | Northern Europe | 51.5074 | -0.1278
2 | Madrid | Spain | Southern Europe | 40.4168 | -3.7038
3 | Paris | France | Western Europe | 48.8566 | 2.3522
4 | Berlin | Germany | Central Europe | 52.52 | 13.405
5 | Riga | Latvia | Northern Europe | 56.9496 | 24.1052
6 | Milan | Italy | Southern Europe | 45.4642 | 9.19
7 | Amsterdam | Netherlands | Western Europe | 52.3676 | 4.9041
8 | Dublin | Ireland | Northern Europe | 53.3498 | -6.2603

## DimDelivery
DeliveryModelKey | DeliveryModel | GovernanceApproach
1 | Waterfall | Stage-gate governance
2 | Agile | Quarterly product governance
3 | Hybrid | Stage-gate with iterative delivery

## DimStrategic
StrategicThemeKey | StrategicTheme
1 | Revenue Growth
2 | Customer Experience
3 | Cost Efficiency
4 | Operational Resilience
5 | Technology Modernisation
6 | Risk and Compliance
7 | Workforce Capability
8 | Sustainability

## DataDictionary
Table | Field | DataType | Definition | PowerBIAggregationGuidance
FactProjectMonthly | SnapshotKey | Whole number | Monthly project snapshot attribute or measure | Do not aggregate
FactProjectMonthly | ReportingDateKey | Whole number | Month-end reporting date key | Do not aggregate
FactProjectMonthly | ProjectKey | Whole number | Project identifier for the snapshot | Do not aggregate
FactProjectMonthly | ProgrammeKey | Whole number | Monthly project snapshot attribute or measure | Do not aggregate
FactProjectMonthly | BusinessUnitKey | Whole number | Monthly project snapshot attribute or measure | Do not aggregate
FactProjectMonthly | ProjectManagerKey | Whole number | Monthly project snapshot attribute or measure | Do not aggregate
FactProjectMonthly | SponsorKey | Whole number | Monthly project snapshot attribute or measure | Do not aggregate
FactProjectMonthly | LocationKey | Whole number | Monthly project snapshot attribute or measure | Do not aggregate
FactProjectMonthly | DeliveryModelKey | Whole number | Monthly project snapshot attribute or measure | Do not aggregate
FactProjectMonthly | StrategicThemeKey | Whole number | Monthly project snapshot attribute or measure | Do not aggregate
FactProjectMonthly | ProjectStatus | Number / text | Status as at the reporting month | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | LifecycleStage | Number / text | Monthly project snapshot attribute or measure | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | RAGStatus | Number / text | Composite delivery health band | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | PlannedProgressPct | Decimal | Baseline expected completion percentage | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | ActualProgressPct | Decimal | Reported completion percentage | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | BaselineBudgetEUR | Number / text | Current approved baseline budget | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | PlannedCostToDateEUR | Number / text | Monthly project snapshot attribute or measure | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | ActualCostToDateEUR | Number / text | Cumulative actual cost | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | ForecastTotalCostEUR | Number / text | Latest estimate at completion | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | ScheduleVarianceEUR | Number / text | Monthly project snapshot attribute or measure | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | CostVarianceEUR | Number / text | Monthly project snapshot attribute or measure | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | SchedulePerformanceIndex | Decimal | Earned value divided by planned value | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | CostPerformanceIndex | Decimal | Earned value divided by actual cost | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | BaselineCompletionDateKey | Whole number | Monthly project snapshot attribute or measure | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | ForecastCompletionDateKey | Whole number | Monthly project snapshot attribute or measure | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | ForecastDelayDays | Number / text | Monthly project snapshot attribute or measure | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | TotalMilestones | Number / text | Monthly project snapshot attribute or measure | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | MilestonesDue | Number / text | Monthly project snapshot attribute or measure | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | MilestonesCompletedOnTime | Number / text | Monthly project snapshot attribute or measure | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | OverdueMilestones | Number / text | Monthly project snapshot attribute or measure | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | CriticalMilestonesOverdue | Number / text | Monthly project snapshot attribute or measure | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | PlannedResourceHours | Number / text | Monthly project snapshot attribute or measure | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | AvailableResourceHours | Number / text | Monthly project snapshot attribute or measure | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | ActualResourceHours | Number / text | Monthly project snapshot attribute or measure | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | ResourceCapacityGapHours | Number / text | Available less planned resource hours | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | OpenRisks | Number / text | Monthly project snapshot attribute or measure | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | CriticalRisks | Number / text | Monthly project snapshot attribute or measure | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | RiskExposureScore | Number / text | Weighted exposure from open and critical risks | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | OverdueMitigationActions | Number / text | Monthly project snapshot attribute or measure | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | PlannedBenefitEUR | Number / text | Monthly project snapshot attribute or measure | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | PlannedBenefitToDateEUR | Number / text | Monthly project snapshot attribute or measure | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | ForecastBenefitEUR | Number / text | Latest expected lifetime benefit | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | RealisedBenefitToDateEUR | Number / text | Monthly project snapshot attribute or measure | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | BenefitRealisationPct | Decimal | Realised benefit divided by planned benefit due to date | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | ApprovedScopeChanges | Number / text | Monthly project snapshot attribute or measure | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | ApprovedChangeValueEUR | Number / text | Monthly project snapshot attribute or measure | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | OpenQualityDefects | Number / text | Monthly project snapshot attribute or measure | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | StakeholderConfidenceScore | Number / text | Monthly project snapshot attribute or measure | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
FactProjectMonthly | PortfolioHealthScore | Decimal | Composite 0–100 delivery-health indicator | Use latest snapshot or appropriate measure; counts and monthly flows may be summed
DimProject | ScenarioArchetype | Text | Generation scenario included for transparency and optional analysis | Do not aggregate
DimDate | DateKey | Whole number | YYYYMMDD surrogate key | Do not aggregate
DimEmployee | PortfolioRole | Text | Project manager or executive sponsor role | Do not aggregate

## Validation
ValidationArea | Check | Result | Details
Structure | Fact grain is unique | PASS | 1,696 unique project-month rows
Keys | All project keys resolve | PASS | No orphan ProjectKey values
Keys | All date keys resolve | PASS | Reporting dates exist in DimDate
Keys | All dimension keys resolve | PASS | No orphan foreign keys across dimensions
Logic | Actual progress bounded | PASS | Values remain between 0% and 100%
Logic | Milestone counts reconcile | PASS | Completed and overdue do not exceed due milestones
Logic | Critical risks do not exceed open risks | PASS | All rows valid
Logic | Forecast cost covers actual cost | PASS | All rows valid
Logic | Variance calculations reconcile | PASS | Schedule and cost variances match earned-value inputs within rounding tolerance
Logic | Cumulative measures are non-decreasing | PASS | Actual progress and actual cost do not reverse within a project
Variation | All seven delivery archetypes represented | PASS | Stable through structural failure scenarios included
Variation | Multiple RAG states represented | PASS | Green, Red, Amber
Variation | Monthly measures change within projects | PASS | More than 90 projects have changing progress
Variation | Portfolio is not flat | PASS | Schedule delay, risk exposure and health score contain broad distributions
Model | One fact table only | PASS | FactProjectMonthly is the only fact table

## DimProject
ProjectKey | ProjectID | ProjectName | StartDate | BaselineCompletionDate | PlannedDurationMonths | Priority | Complexity | StrategicAlignmentScore | ScenarioArchetype
1 | PRJ-0001 | Identity Renewal 001 | 2025-04-01 | 2026-06-30 | 15 | Critical | Medium | 71 | stable
2 | PRJ-0002 | Regulatory Consolidation 002 | 2025-06-01 | 2027-05-31 | 24 | Medium | Medium | 90 | accelerating
3 | PRJ-0003 | Data Transformation 003 | 2022-12-01 | 2024-08-31 | 21 | Medium | Medium | 78 | resource constrained
4 | PRJ-0004 | Identity Automation 004 | 2025-03-01 | 2027-02-28 | 24 | Low | Low | 92 | recoverable
5 | PRJ-0005 | Cyber Modernisation 005 | 2022-09-01 | 2024-08-31 | 24 | Critical | High | 75 | benefit gap
6 | PRJ-0006 | Finance Migration 006 | 2024-06-01 | 2025-05-31 | 12 | Low | High | 47 | structural failure
7 | PRJ-0007 | Service Enablement 007 | 2022-12-01 | 2024-11-30 | 24 | Medium | High | 73 | volatile
8 | PRJ-0008 | Regulatory Automation 008 | 2023-03-01 | 2023-11-30 | 9 | Low | High | 79 | stable
9 | PRJ-0009 | Payments Integration 009 | 2025-02-01 | 2026-01-31 | 12 | Medium | High | 89 | accelerating
10 | PRJ-0010 | Cloud Modernisation 010 | 2025-06-01 | 2026-02-28 | 9 | Medium | Medium | 61 | resource constrained
11 | PRJ-0011 | Payments Automation 011 | 2024-08-01 | 2025-07-31 | 12 | Medium | Medium | 81 | recoverable
12 | PRJ-0012 | Identity Migration 012 | 2025-11-01 | 2027-07-31 | 21 | High | Low | 55 | benefit gap
13 | PRJ-0013 | Regulatory Controls 013 | 2025-10-01 | 2027-03-31 | 18 | Medium | Medium | 50 | structural failure
14 | PRJ-0014 | Workforce Transformation 014 | 2023-09-01 | 2024-08-31 | 12 | Critical | Very High | 98 | volatile
15 | PRJ-0015 | Commerce Migration 015 | 2025-08-01 | 2027-04-30 | 21 | High | Very High | 86 | stable
16 | PRJ-0016 | Digital Automation 016 | 2025-01-01 | 2026-12-31 | 24 | Critical | Very High | 67 | accelerating
17 | PRJ-0017 | Regulatory Automation 017 | 2023-11-01 | 2024-07-31 | 9 | Low | Very High | 50 | resource constrained
18 | PRJ-0018 | Cloud Analytics 018 | 2022-11-01 | 2024-10-31 | 24 | High | High | 48 | recoverable
19 | PRJ-0019 | Planning Enablement 019 | 2025-06-01 | 2027-11-30 | 30 | Medium | Medium | 57 | benefit gap
20 | PRJ-0020 | Customer Modernisation 020 | 2022-09-01 | 2024-08-31 | 24 | Low | Medium | 59 | structural failure
21 | PRJ-0021 | Payments Controls 021 | 2025-11-01 | 2027-10-31 | 24 | Medium | Low | 76 | volatile
22 | PRJ-0022 | Service Transformation 022 | 2022-09-01 | 2023-05-31 | 9 | Critical | Medium | 93 | stable
23 | PRJ-0023 | Regulatory Migration 023 | 2023-07-01 | 2025-06-30 | 24 | High | Medium | 93 | accelerating
24 | PRJ-0024 | Supply Optimisation 024 | 2024-05-01 | 2026-04-30 | 24 | High | Low | 74 | resource constrained
25 | PRJ-0025 | Planning Enablement 025 | 2023-03-01 | 2024-11-30 | 21 | High | Low | 57 | recoverable
26 | PRJ-0026 | Identity Consolidation 026 | 2025-12-01 | 2027-05-31 | 18 | Critical | High | 89 | benefit gap
27 | PRJ-0027 | Workforce Modernisation 027 | 2023-09-01 | 2025-02-28 | 18 | Critical | Medium | 68 | structural failure
28 | PRJ-0028 | Operations Controls 028 | 2025-05-01 | 2027-10-31 | 30 | Low | Medium | 70 | volatile
29 | PRJ-0029 | Planning Platform 029 | 2023-04-01 | 2025-09-30 | 30 | Medium | Low | 75 | stable
30 | PRJ-0030 | Cloud Analytics 030 | 2022-10-01 | 2025-03-31 | 30 | Critical | Medium | 91 | accelerating
31 | PRJ-0031 | Service Optimisation 031 | 2023-11-01 | 2024-10-31 | 12 | High | Medium | 91 | resource constrained
32 | PRJ-0032 | Planning Integration 032 | 2024-08-01 | 2025-10-31 | 15 | High | Low | 48 | recoverable
33 | PRJ-0033 | Workforce Modernisation 033 | 2023-11-01 | 2024-07-31 | 9 | Medium | High | 80 | benefit gap
34 | PRJ-0034 | Cyber Migration 034 | 2023-01-01 | 2024-09-30 | 21 | Medium | High | 86 | structural failure
35 | PRJ-0035 | Payments Modernisation 035 | 2025-11-01 | 2026-07-31 | 9 | Critical | High | 75 | volatile
36 | PRJ-0036 | Operations Renewal 036 | 2025-10-01 | 2027-03-31 | 18 | Low | Very High | 58 | stable
37 | PRJ-0037 | Customer Modernisation 037 | 2023-02-01 | 2024-01-31 | 12 | Medium | Very High | 74 | accelerating
38 | PRJ-0038 | Payments Optimisation 038 | 2024-07-01 | 2026-03-31 | 21 | Medium | High | 56 | resource constrained
39 | PRJ-0039 | Regulatory Optimisation 039 | 2023-04-01 | 2025-09-30 | 30 | Medium | Medium | 71 | recoverable
40 | PRJ-0040 | Finance Optimisation 040 | 2025-11-01 | 2028-04-30 | 30 | Medium | Medium | 69 | benefit gap
41 | PRJ-0041 | Finance Enablement 041 | 2025-04-01 | 2025-12-31 | 9 | Medium | Medium | 76 | structural failure
42 | PRJ-0042 | Cloud Consolidation 042 | 2025-12-01 | 2027-08-31 | 21 | Medium | High | 48 | volatile
43 | PRJ-0043 | Planning Automation 043 | 2024-07-01 | 2025-12-31 | 18 | Medium | Medium | 50 | stable
44 | PRJ-0044 | Cyber Renewal 044 | 2025-10-01 | 2027-09-30 | 24 | Medium | Very High | 53 | accelerating
45 | PRJ-0045 | Finance Consolidation 045 | 2023-07-01 | 2025-03-31 | 21 | Low | Very High | 46 | resource constrained
46 | PRJ-0046 | Payments Automation 046 | 2025-11-01 | 2027-01-31 | 15 | Medium | Low | 55 | recoverable
47 | PRJ-0047 | Payments Migration 047 | 2024-11-01 | 2026-07-31 | 21 | Medium | High | 89 | benefit gap
48 | PRJ-0048 | Payments Migration 048 | 2025-09-01 | 2026-11-30 | 15 | Medium | Low | 80 | structural failure
49 | PRJ-0049 | Planning Optimisation 049 | 2024-05-01 | 2026-01-31 | 21 | Medium | Low | 64 | volatile
50 | PRJ-0050 | Digital Automation 050 | 2023-04-01 | 2024-12-31 | 21 | High | Low | 67 | stable
51 | PRJ-0051 | Cloud Optimisation 051 | 2025-02-01 | 2027-07-31 | 30 | High | Low | 70 | accelerating
52 | PRJ-0052 | Sustainability Renewal 052 | 2023-04-01 | 2024-06-30 | 15 | High | Very High | 53 | resource constrained
53 | PRJ-0053 | Service Transformation 053 | 2024-03-01 | 2025-11-30 | 21 | Medium | Medium | 50 | recoverable
54 | PRJ-0054 | Digital Modernisation 054 | 2023-10-01 | 2024-06-30 | 9 | Medium | Medium | 75 | benefit gap
55 | PRJ-0055 | Cloud Enablement 055 | 2023-03-01 | 2023-11-30 | 9 | Medium | High | 79 | structural failure
56 | PRJ-0056 | Cyber Analytics 056 | 2023-05-01 | 2025-01-31 | 21 | Medium | Medium | 56 | volatile
57 | PRJ-0057 | Data Transformation 057 | 2025-07-01 | 2026-12-31 | 18 | Medium | Low | 68 | stable
58 | PRJ-0058 | Cloud Consolidation 058 | 2023-05-01 | 2024-07-31 | 15 | Critical | Low | 83 | accelerating
59 | PRJ-0059 | Planning Renewal 059 | 2024-06-01 | 2025-02-28 | 9 | Low | Low | 82 | resource constrained
60 | PRJ-0060 | Customer Renewal 060 | 2025-07-01 | 2027-06-30 | 24 | Medium | Medium | 51 | recoverable
61 | PRJ-0061 | Regulatory Consolidation 061 | 2025-03-01 | 2027-02-28 | 24 | Medium | Low | 89 | benefit gap
62 | PRJ-0062 | Commerce Renewal 062 | 2024-10-01 | 2026-09-30 | 24 | High | Medium | 47 | structural failure
63 | PRJ-0063 | Finance Integration 063 | 2024-10-01 | 2025-09-30 | 12 | Medium | Low | 82 | volatile
64 | PRJ-0064 | Planning Modernisation 064 | 2022-08-01 | 2023-04-30 | 9 | Critical | Low | 73 | stable
65 | PRJ-0065 | Workforce Migration 065 | 2023-02-01 | 2024-04-30 | 15 | Medium | Medium | 50 | accelerating
66 | PRJ-0066 | Data Integration 066 | 2025-10-01 | 2027-06-30 | 21 | High | Medium | 67 | resource constrained
67 | PRJ-0067 | Sustainability Integration 067 | 2024-06-01 | 2025-08-31 | 15 | High | Medium | 79 | recoverable
68 | PRJ-0068 | Planning Analytics 068 | 2023-06-01 | 2025-05-31 | 24 | High | High | 70 | benefit gap
69 | PRJ-0069 | Regulatory Consolidation 069 | 2022-08-01 | 2023-07-31 | 12 | Medium | Very High | 56 | structural failure
70 | PRJ-0070 | Identity Renewal 070 | 2024-09-01 | 2027-02-28 | 30 | Medium | Medium | 63 | volatile
71 | PRJ-0071 | Workforce Integration 071 | 2022-11-01 | 2025-04-30 | 30 | Low | High | 60 | stable
72 | PRJ-0072 | Payments Enablement 072 | 2024-06-01 | 2025-11-30 | 18 | High | High | 58 | accelerating
73 | PRJ-0073 | Service Platform 073 | 2025-06-01 | 2026-08-31 | 15 | Medium | Low | 50 | resource constrained
74 | PRJ-0074 | Operations Enablement 074 | 2025-11-01 | 2028-04-30 | 30 | Medium | High | 72 | recoverable
75 | PRJ-0075 | Service Analytics 075 | 2024-04-01 | 2026-03-31 | 24 | Medium | Low | 83 | benefit gap
76 | PRJ-0076 | Planning Analytics 076 | 2024-05-01 | 2026-04-30 | 24 | Medium | Medium | 82 | structural failure
77 | PRJ-0077 | Operations Migration 077 | 2024-09-01 | 2026-05-31 | 21 | High | Medium | 83 | volatile
78 | PRJ-0078 | Commerce Optimisation 078 | 2024-09-01 | 2025-08-31 | 12 | Medium | Low | 71 | stable
79 | PRJ-0079 | Regulatory Consolidation 079 | 2025-10-01 | 2026-12-31 | 15 | High | Very High | 82 | accelerating
80 | PRJ-0080 | Cloud Modernisation 080 | 2025-06-01 | 2027-11-30 | 30 | Critical | High | 87 | resource constrained
81 | PRJ-0081 | Planning Platform 081 | 2023-12-01 | 2026-05-31 | 30 | High | Low | 85 | recoverable
82 | PRJ-0082 | Sustainability Renewal 082 | 2023-02-01 | 2024-01-31 | 12 | Medium | High | 87 | benefit gap
83 | PRJ-0083 | Digital Analytics 083 | 2024-08-01 | 2026-01-31 | 18 | Critical | Medium | 71 | structural failure
84 | PRJ-0084 | Customer Modernisation 084 | 2024-12-01 | 2026-08-31 | 21 | Medium | High | 68 | volatile
85 | PRJ-0085 | Commerce Consolidation 085 | 2023-09-01 | 2025-05-31 | 21 | Low | Low | 64 | stable
86 | PRJ-0086 | Operations Consolidation 086 | 2024-01-01 | 2025-09-30 | 21 | Medium | Low | 73 | accelerating
87 | PRJ-0087 | Regulatory Consolidation 087 | 2025-04-01 | 2026-06-30 | 15 | High | High | 53 | resource constrained
88 | PRJ-0088 | Identity Migration 088 | 2022-10-01 | 2025-03-31 | 30 | Critical | Medium | 64 | recoverable
89 | PRJ-0089 | Payments Modernisation 089 | 2024-06-01 | 2026-02-28 | 21 | Medium | High | 45 | benefit gap
90 | PRJ-0090 | Identity Optimisation 090 | 2023-05-01 | 2024-07-31 | 15 | Medium | Very High | 93 | structural failure
91 | PRJ-0091 | Identity Automation 091 | 2023-07-01 | 2024-09-30 | 15 | Medium | Low | 86 | volatile
92 | PRJ-0092 | Finance Renewal 092 | 2025-05-01 | 2026-07-31 | 15 | High | Medium | 64 | stable
93 | PRJ-0093 | Data Automation 093 | 2023-06-01 | 2024-02-29 | 9 | Medium | Low | 54 | accelerating
94 | PRJ-0094 | Cloud Automation 094 | 2023-09-01 | 2025-05-31 | 21 | Low | Medium | 49 | resource constrained
95 | PRJ-0095 | Identity Transformation 095 | 2024-11-01 | 2026-01-31 | 15 | Medium | High | 46 | recoverable
96 | PRJ-0096 | Sustainability Analytics 096 | 2024-08-01 | 2025-04-30 | 9 | Critical | Medium | 98 | benefit gap
97 | PRJ-0097 | Cyber Consolidation 097 | 2023-08-01 | 2025-01-31 | 18 | Critical | Medium | 91 | structural failure
98 | PRJ-0098 | Identity Optimisation 098 | 2025-12-01 | 2028-05-31 | 30 | Low | Very High | 92 | volatile
99 | PRJ-0099 | Regulatory Optimisation 099 | 2024-09-01 | 2026-05-31 | 21 | Critical | Low | 83 | stable
100 | PRJ-0100 | Customer Modernisation 100 | 2025-03-01 | 2026-05-31 | 15 | Low | Low | 58 | accelerating